## Exported from SC
Punchlist Category (Name) | Punchlist Type (Name) | Discipline (Name) | Systemization - System (Summary) | Systemization - Subsystem (Summary) | Scheduling - Due Date | Workflow - Originated Date | Workflow - Rejected Date | Workflow - Closing By | Workflow - Closing Date | Workflow - Status | Punchlist ID | Asset (Summary) | Work Breakdown - Phase (Summary) | Scheduling - Action Required | Priority (Summary)
A |  | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 20:27 |  |  |  | Originated | PL-00972 | 3331-TA-4002 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | Leak test to be confirmed
A | Incorrect Labels | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-01-24 04:24 | 2021-01-24 05:10 |  |  | Rejected | PL-00286 | 3331-AG-4001-M1 - Motor for CONCENTRATE STORAGE TANK 1 AGITATOR | S2 - Stage 2 Pre Commissioning | Local and Remote selector is backwards.
A | Incorrect Labels | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-05 - Marshalling boxes Utilities | 2021-03-03 02:51 | 2021-03-01 02:51 |  |  |  | Originated | PL-00985 | 3334-MB-4084 - Newcrest Marshalling Box Type 3 | S1 - Stage 1 Construction Completion | Incorrect Label | 1: A-High
A | Item Damaged | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-03-21 02:10 | 2021-03-19 02:09 |  | Fuller, Lachlan | 2021-03-26 20:55 | Closed | PL-01262 | 3331-FV-0005 - COPPER CONCENTRATE TO BLAYNEY PLANT | S1 - Stage 1 Construction Completion | Motor windings are down to earth due to Moisture inside top part of valve. | 1: A-High
A | Item Damaged | ELEC | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-11 23:42 | 2021-04-09 23:38 |  |  |  | Originated | PL-01506 | 3332-OP-4114 - Fail safe Cabinet for 3332-FB-4014 | S1 - Stage 1 Construction Completion | Replace damaged door and Air selector valve on door | 1: A-High
A | Item Damaged | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-02-10 00:23 | 2021-02-08 00:22 |  | Muell, Thomas | 2021-03-18 21:54 | Closed | PL-00561 | 3331-FV-1005 - PROCESS WATER TO COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Terminal box needs remounting to valve. | 1: A-High
A | Item Damaged | INST | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers | 2021-03-12 21:40 | 2021-03-10 21:39 |  |  |  | Originated | PL-01130 | 3332-FV-0604 - INLET ROUGHER DOWNCOMER PUMP | S1 - Stage 1 Construction Completion | Broken inductive proximity limit switch requires replacing | 1: A-High
A | Item Damaged | INST | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-12 06:57 | 2021-04-10 06:56 |  |  |  | Accepted | PL-01509 | 3332-FV-0316 - SECOND CLEANER FLOTATION CELL 3 DRAIN | S1 - Stage 1 Construction Completion | 3332ZSO0316-C1 limit switch is broken | 1: A-High
A | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 20:19 |  | Lanser, Richard | 2021-03-15 21:53 | Closed | PL-00970 | 3331-TA-4002 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | EWP and Ladder need to be removed from inside the tank
A | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) | 2021-03-02 06:10 | 2021-02-28 06:56 |  | Lanser, Richard | 2021-03-15 21:51 | Closed | PL-00966 | 3331-AG-4002 - CONCENTRATE STORAGE TANK 2 AGITATOR | S1 - Stage 1 Construction Completion | Scissor lift and ladder still in tank. May contact blades.... remove these items. | 1: A-High
A | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-02 06:26 |  | Lanser, Richard | 2021-04-06 17:28 | Closed | PL-01416 | 3332-HP-4001 - SECOND CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Internal inspection needed
A | Item Incomplete | CABL | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-03 06:15 | 2021-03-01 06:15 |  |  |  | Originated | PL-00991 | 3332OP4028-C1 - FROM DCS TO 3332-OP-4028 | S1 - Stage 1 Construction Completion | Spare core terminals need to be replaced from knife terminals and spares need to be earthed @ DCS | 1: A-High
A | Item Incomplete | CABL | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-03-03 05:50 | 2021-03-01 05:49 |  |  |  | Originated | PL-00990 | 3332OP4033-C1 - FROM DCS TO 3332-OP-4033 | S1 - Stage 1 Construction Completion | Spares require bridging as earthing @ DCS | 1: A-High
A | Item Incomplete | CABL | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-03-02 01:50 | 2021-02-28 01:49 |  |  |  | Originated | PL-00955 | 3332MB4026-J3 - FROM DCS TO 3332-MB-4026 | S1 - Stage 1 Construction Completion | Spare cores are to be earthed at DCS. Terminals needs to be replaced from knife terminals, and 1.5mm earth installed with bridges | 1: A-High
A | Item Incomplete | CABL | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-03-10 06:16 | 2021-03-08 06:11 |  |  |  | Originated | PL-01085 | 3332MB4033-J2 - FROM DCS TO 3332-MB-4033 | S1 - Stage 1 Construction Completion | Spares cores in DCS panel in substation are not bridge to earth. A 2.5mm bridging comb is required. | 1: A-High
A | Item Incomplete | CABL | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-04-03 01:49 | 2021-04-01 01:48 |  |  |  | Originated | PL-01404 | 3332MB4030-J1 - FROM DCS TO 3332-MB-4030 | S1 - Stage 1 Construction Completion | Spare cores require terminals to be swapped out from knife terminals and bridges required to be installed to allow for earthing of spares @DCS | 1: A-High
A | Item Incomplete | CABL | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-13 22:51 | 2021-02-11 22:49 |  | Muell, Thomas | 2021-02-18 22:49 | Closed | PL-00568 | 3335OP4203-C1 - DCS TO FIRE WATER PUMP CONTROL PANEL | S1 - Stage 1 Construction Completion | Cable is terminated in DCS cabinet - terminals have no label and no internal wiring from terminals to PLC. No drawings for this as it has been an add on. | 1: A-High
A | Item Incomplete | CABL | CS14 - NaHS Preparation & Distribution | CS14-03 - NaHS Ring Main & Storage Tanks | 2021-03-02 06:49 | 2021-02-28 06:49 |  |  |  | Originated | PL-00964 | 3334ZS0683-C1 - FROM 3334-OP-4081 TO 3334-ZS-0683 | S1 - Stage 1 Construction Completion | Spare core requires earthing at panel | 1: A-High
A | Item Incomplete | CABL | CS14 - NaHS Preparation & Distribution | CS14-03 - NaHS Ring Main & Storage Tanks | 2021-03-03 00:18 | 2021-03-01 00:17 |  |  |  | Originated | PL-00983 | 3334OP4081-C1 - FROM DCS TO 3334-OP-4081 | S1 - Stage 1 Construction Completion | Spares cores in DCS panel in substation are not bridge to earth. A 2.5mm bridging comb is required. | 1: A-High
A | Item Incomplete | CABL | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-03-29 21:28 | 2021-03-27 21:28 |  |  |  | Originated | PL-01386 | 3331OP4206-C1 - 3331-SA-4001 - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER TO PRIMARY SAMPLER (TBJ1) | S1 - Stage 1 Construction Completion | Earth terminals not installed in panel and earth not laid down/terminated | 1: A-High
A | Item Incomplete | CABL | CSEC - Power Factor Correction / Harmonic Filters | CSEC-01 - Power Factor Correction / Harmonic Filters | 2021-03-01 04:57 | 2021-02-27 04:56 |  | Fontana, Chris | 2021-03-20 00:23 | Closed | PL-00949 | 3338PF4002-P1A - POWER FACTOR CORRECTION PANEL | S1 - Stage 1 Construction Completion | Glands require earthing | 1: A-High
A | Item Incomplete | CABL | CSEC - Power Factor Correction / Harmonic Filters | CSEC-01 - Power Factor Correction / Harmonic Filters | 2021-03-01 04:58 | 2021-02-27 04:57 |  | Fontana, Chris | 2021-03-20 00:24 | Closed | PL-00950 | 3338PF4002-P1B - POWER FACTOR CORRECTION PANEL | S1 - Stage 1 Construction Completion | Glands require earthing | 1: A-High
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-25 23:16 | 2021-04-23 23:14 |  | Polkinghorne, Scott | 2021-04-24 12:28 | Closed | PL-01649 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Install tank earthing for 3332-TA-4004 and 3332-TA-4005 per 730-332-ME-VDA-M107-D01-0001 and 730-332-ME-VDA-M107-D01-0002 | 1: A-High
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:02 |  | Fontana, Chris | 2021-02-25 00:16 | Closed | PL-00822 | 3332-FB-4004 - ROUGHER SCAVENGER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:06 |  | Fontana, Chris | 2021-02-25 00:16 | Closed | PL-00824 | 3332-FB-4002 - ROUGHER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:10 |  | Fontana, Chris | 2021-02-25 00:16 | Closed | PL-00826 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 06:07 |  | Fontana, Chris | 2021-02-25 00:17 | Closed | PL-00859 | 3332-FB-4005 - ROUGHER SCAVENGER FLOTATION CELL 5 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-24 02:59 | 2021-02-22 02:58 |  | Fontana, Chris | 2021-02-25 | Closed | PL-00820 | 3332-FB-4003 - ROUGHER SCAVENGER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Earths need to be fitted | 1: A-High
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-18 02:31 |  |  |  | Accepted | PL-00626 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:26 |  |  |  | Accepted | PL-00653 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:31 |  |  |  | Accepted | PL-00656 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 04:37 |  |  |  | Accepted | PL-00659 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-09 04:44 | 2021-03-07 01:40 |  |  |  | Originated | PL-01048 | 3332-OP-4029 - OP Instrument Air for 3332-FV-0204 3332-FV-0205 3332-FV-1032 3332-FV-1037 | S1 - Stage 1 Construction Completion | Airlines not terminated at field or board | 1: A-High
A | Item Incomplete | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 01:43 | 2021-03-07 01:42 | 2021-03-07 03:42 |  |  | Rejected | PL-01049 | 3332-OP-4029 - OP Instrument Air for 3332-FV-0204 3332-FV-0205 3332-FV-1032 3332-FV-1037 | S1 - Stage 1 Construction Completion | Require completion or movement of boundary/isolation for valves 1035 & 1037 prior to board energisation. | 2: B-Low
A | Item Incomplete | ELEC | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:21 |  |  |  | Accepted | PL-00674 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:35 |  |  |  | Accepted | PL-00677 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 22:00 |  |  |  | Accepted | PL-00680 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-20 00:21 |  |  |  | Accepted | PL-00687 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 04:43 |  |  |  | Accepted | PL-00662 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 21:10 |  |  |  | Accepted | PL-00671 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Earths need to be fitted
A | Item Incomplete | ELEC | CS09 - Concentrate Dryer & Scrubber | CS09-01 - Concentrate Dryer | 2021-02-27 22:41 | 2021-02-25 22:41 |  | Loparev, Roman | 2021-03-16 05:41 | Closed | PL-00925 | 3333-DY-4001 - CONCENTRATE DRYER MOTOR REQUIRES FORCED VENTILATION | S1 - Stage 1 Construction Completion | Missing Contactor, Overload and re-set module | 1: A-High
A | Item Incomplete | ELEC | CS09 - Concentrate Dryer & Scrubber | CS09-01 - Concentrate Dryer | 2021-02-27 22:43 | 2021-02-25 22:42 |  | Loparev, Roman | 2021-03-16 05:41 | Closed | PL-00926 | 3333-DY-4001 - CONCENTRATE DRYER MOTOR REQUIRES FORCED VENTILATION | S1 - Stage 1 Construction Completion | Not installed | 1: A-High
A | Item Incomplete | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-05 - Marshalling boxes Utilities | 2021-03-03 02:52 | 2021-03-01 02:52 |  |  |  | Originated | PL-00986 | 3334-MB-4084 - Newcrest Marshalling Box Type 3 | S1 - Stage 1 Construction Completion | Requires bungs in panel | 1: A-High
A | Item Incomplete | ELEC | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-01-20 23:39 | 2021-01-18 23:38 |  | Fuller, Lachlan | 2021-01-20 05:15 | Closed | PL-00195 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Thickener 1)Install and terminate running 120mm earth in cable ladder (north side) - A. Conc Storage Tanks 1)Install and terminate running 120mm earth in vertical cable ladders - A. | 1: A-High
A | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Loparev, Roman | 2021-02-04 02:30 | Closed | PL-00067 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Certificate issue
A | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2021-01-06 | 2020-12-11 02:22 |  | Van Der Veen, Roger | 2020-12-20 | Closed | PL-00066 | 3338-SS-4001 - Substation 33kVA
A | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-02 00:54 | Closed | PL-01363 | 3331DB4007-R61 - STORAGE AREA LIGHT AND POWER BOARD TO COPPER CONCENTRATE THICKENER TOP WALKWAY 15A OUTLET | S1 - Stage 1 Construction Completion | Install bung
A | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-02 00:54 | Closed | PL-01364 | 3331DB4007-R1 - STORAGE AREA LIGHT AND POWER BOARD TO CONCENTRATE HANDLING AREA WEST 3-PHASE OUTLET | S1 - Stage 1 Construction Completion | Install bung
A | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation |  | 2021-03-11 21:06 |  | Muell, Thomas | 2021-03-18 00:01 | Closed | PL-01132 | 3332-DB-4008 - Flotation East Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Danger 240VAC labels to be installed and tighten/torque all luminaire bolts as some are loose
A | Item Incomplete | INST | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-04-24 03:55 | 2021-04-22 03:54 |  |  |  | Originated | PL-01629 | 3332-AIT-0584 - SRUBBER ORP | S1 - Stage 1 Construction Completion | Lines not connected yet | 1: A-High
A | Item Incomplete | INST | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-04-24 05:02 | 2021-04-22 05:01 |  |  |  | Originated | PL-01636 | 3332-AIT-0585 - FLOTATION SCRUBBER | S1 - Stage 1 Construction Completion | Lines not connected to OP panel | 1: A-High
A | Item Incomplete | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-24 04:14 |  | Fontana, Chris | 2021-02-25 00:17 | Closed | PL-00877 | 3331-OP-4006 - OP Instrument Air for 3331-FV-0051 3331-FV-0052 3331-FV-1012 | S1 - Stage 1 Construction Completion | Install Solenoid and label in OP box
A | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 03:46 |  | Lanser, Richard | 2021-04-19 07:12 | Closed | PL-00726 | 3331-TA-4001 - CONCENTRATE STORAGE TANK 1 | S1 - Stage 1 Construction Completion | Leak test to be confirmed
A | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-03-08 | 2021-02-21 03:00 |  | Irvine, Darren | 2021-03-09 01:13 | Closed | PL-00724 | 3331-PU-4011 - CONCENTRATE STORAGE SUMP PUMP | S1 - Stage 1 Construction Completion | Keyless drive shaft needs to be confirmed for taperlock fitment
A | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 11:42 | 2021-03-08 14:40 |  | Lanser, Richard | 2021-04-16 21:11 | Closed | PL-01093 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
A | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:12 |  | Lanser, Richard | 2021-04-16 20:52 | Closed | PL-01374 | 3332-CY-4001 - ROUGHER JAMESON CELL | S1 - Stage 1 Construction Completion | Bolts missing from downcomer feed valve. 4 off M16 x 140mm long S/S bolt with Double wash and nuts
A | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:24 |  | Lanser, Richard | 2021-04-16 21:04 | Closed | PL-01375 | 3332-CY-4001 - ROUGHER JAMESON CELL | S1 - Stage 1 Construction Completion | Dart valve shafts need connecting to actuator. Pipe hangers need adjustment to level s/steel piping.
A | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-03 03:22 | 2021-02-01 03:21 |  | Gayler, Randal | 2021-03-04 23:10 | Closed | PL-00513 | 3332-AG-4105 - ROUGHER SCAVENGER FLOTATION CELL 5 AGITATOR | S1 - Stage 1 Construction Completion | Re-instate guard after new taper lock is installed | 1: A-High
A | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-18 03:10 |  |  |  | Submitted | PL-01562 | 3332-ML-4001 - REGRIND MILL | S1 - Stage 1 Construction Completion | All guarding and covers to be fitted
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump | 2021-04-25 05:50 | 2021-04-23 05:50 |  | Lanser, Richard | 2021-04-25 22:03 | Closed | PL-01644 | 3332-LIT-0452 - CLEANER AREA SUMP 1 | S1 - Stage 1 Construction Completion | Flange requires bolts and to be torqued up. | 1: A-High
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-18 03:51 |  |  |  | Submitted | PL-01566 | 3332-CY-4016 - FOURTH CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Pipe work not complete
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-18 03:54 |  |  |  | Submitted | PL-01568 | 3332-CY-4016 - FOURTH CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Valves to be installed
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-18 03:55 |  |  |  | Submitted | PL-01569 | 3332-CY-4016 - FOURTH CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Instruments not fitted
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-18 03:57 |  |  |  | Submitted | PL-01570 | 3332-CY-4016 - FOURTH CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | hand valves incomplete
A | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-18 03:45 |  |  |  | Originated | PL-01564 | 3332-CY-4015 - THIRD CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion
A | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-17 02:06 | 2021-01-15 02:18 |  | Nutt, Richard | 2021-02-27 06:05 | Closed | PL-00157 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | FLANGE MANAGEMENT REQUIRED TO BE COMPLETED ON ALL FLANGES | 1: A-High
A | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-17 02:08 | 2021-01-15 02:18 |  | Gayler, Randal | 2021-03-04 23:51 | Closed | PL-00158 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | FLANGE MANAGEMENT REQUIRED TO BE COMPLETED ON ALL FLANGES | 1: A-High
A | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-01-28 20:48 | 2021-01-26 20:47 |  | Lanser, Richard | 2021-03-09 05:57 | Closed | PL-00325 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 00:51 |  |  |  | Submitted | PL-01593 | 3331-SN-4001 - CONCENTRATE THICKENER FEED SCREEN | S1 - Stage 1 Construction Completion | Bolts to be fitted
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 00:53 |  |  |  | Submitted | PL-01594 | 3331-SN-4001 - CONCENTRATE THICKENER FEED SCREEN | S1 - Stage 1 Construction Completion | Bolts missing
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 00:54 |  |  |  | Submitted | PL-01595 | 3331-SN-4001 - CONCENTRATE THICKENER FEED SCREEN | S1 - Stage 1 Construction Completion | Packers to be fitted
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-01-25 06:45 | 2021-01-23 20:59 |  | Lanser, Richard | 2021-03-29 02:42 | Closed | PL-00276 | 3331-PU-4009 - COPPER CONCENTRATE THICKENER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Drive pulley assembly not complete- attach drive pulley, confirm alignment and install V belts | 1: A-High
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-01-25 06:49 | 2021-01-23 20:59 |  | Lanser, Richard | 2021-03-29 02:43 | Closed | PL-00277 | 3331-PU-4009 - COPPER CONCENTRATE THICKENER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Connecting discharge pipe needs flange management | 1: A-High
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-01-25 06:55 | 2021-01-23 20:59 |  | Lanser, Richard | 2021-03-29 02:44 | Closed | PL-00278 | 3331-PU-4009 - COPPER CONCENTRATE THICKENER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Ensure pump has been lubricated | 1: A-High
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-01-25 06:57 | 2021-01-23 20:59 |  | Lanser, Richard | 2021-03-29 02:44 | Closed | PL-00279 | 3331-PU-4009 - COPPER CONCENTRATE THICKENER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Confirm drive alignment | 1: A-High
A | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-01-25 06:58 | 2021-01-23 20:59 |  | Lanser, Richard | 2021-03-29 02:45 | Closed | PL-00280 | 3331-PU-4009 - COPPER CONCENTRATE THICKENER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Complete drive alignment | 1: A-High
A | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-01-21 06:43 | 2021-01-19 06:43 |  | Lanser, Richard | 2021-03-14 20:33 | Closed | PL-00205 | 3331-160-CSL-0010-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete flange management | 1: A-High
A | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-01-21 06:44 | 2021-01-19 06:44 |  | Lanser, Richard | 2021-03-14 20:34 | Closed | PL-00206 | 3331-160-CSL-0010-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete flange management | 1: A-High
A | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:22 |  | Liang, Dennis | 2021-03-18 00:15 | Closed | PL-00740 | 3331-150-CSL-0062-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Transition spool missing
A | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-03-15 05:26 | 2021-03-13 05:26 |  | Fuller, Lachlan | 2021-03-27 22:24 | Closed | PL-01198 | 3331-90-PD-0059-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Flange Management | 1: A-High
A | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-04-14 22:20 | 2021-03-08 03:36 |  | Lanser, Richard | 2021-04-17 21:01 | Closed | PL-01079 | 3331-90-PD-0061-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required. | 1: A-High
A | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-03-21 04:17 |  | Nutt, Richard | 2021-04-23 03:45 | Closed | PL-01337 | 3332-200-MCS-0006-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Re-design and supply
A | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-03-21 04:19 |  | Lanser, Richard | 2021-04-16 07:39 | Closed | PL-01338 | 3332-110-VGN-0003-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Missing Pipe Material
A | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:44 |  |  |  | Submitted | PL-01377 | 3332-400-MCS-0112-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Test Electric Actuator Valve
A | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-25 00:43 |  | Lanser, Richard | 2021-04-19 07:12 | Closed | PL-00906 | 3332-160-PD-0010-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Spool Install
A | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-03-24 02:38 |  | Lanser, Richard | 2021-04-24 09:26 | Closed | PL-01369 | 3332-63-MCS-0289-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-06 23:35 | 2021-04-05 03:23 |  |  | Rejected | PL-01046 | 3332-25-PWL-0176-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | requires final design to complete line
A | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-10 11:02 | 2021-03-07 14:00 |  |  |  | Submitted | PL-01065 | 3332-90-VGN-0029-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Item # 4 - 80mm spec blind not installed | 1: A-High
A | Item Incomplete | PIPE | CS09 - Concentrate Dryer & Scrubber | CS09-01 - Concentrate Dryer |  | 2021-03-22 23:39 |  |  |  | Submitted | PL-01345 | 3333-15-NG-0043-C4 - NG Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-21 03:34 |  |  |  | Submitted | PL-01335 | 3332-50-IA-0020-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-21 23:00 |  | Lanser, Richard | 2021-04-05 19:11 | Closed | PL-00788 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | flange managment required
A | Item Incomplete | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution | 2021-03-22 02:44 | 2021-03-19 05:43 |  |  |  | Submitted | PL-01265 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | INSTALL ITEMS- 3335-SP-4309, 150MM BUTERFLY VALVE, 3335-SP-4039, 3335-SP-4305 | 1: A-High
A | Item Incomplete | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution | 2021-03-22 02:53 | 2021-03-19 05:52 |  |  |  | Submitted | PL-01267 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | install all SP items | 1: A-High
A | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-03-21 04:12 |  |  |  | Submitted | PL-01336 | 3332-50-PWH-0210-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Correct Design / Pipe Support
A | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-03-22 01:04 |  |  |  | Submitted | PL-01342 | 3332-50-PWH-0151-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | flanges not torqued
A | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-02-17 06:21 | 2021-02-15 06:21 |  |  |  | Submitted | PL-00602 | 3332-100-PWH-0030-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Blanking flange to be installed and flange managed 3332-PWH-0030-C6-05. | 1: A-High
A | Item Incomplete | PIPE | CS0M - Gland Water | CS0M-02 - Gland Seal Water Charging Pumps |  | 2021-03-24 02:41 |  | Lanser, Richard | 2021-04-05 19:16 | Closed | PL-01370 | 3332-25-RWA-0257-C5-TI - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks |  | 2021-03-23 01:05 |  |  |  | Submitted | PL-01346 | 3332-110-PD-0218-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks |  | 2021-03-23 01:08 |  |  |  | Submitted | PL-01347 | 3332-110-PD-0217-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Design
A | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-14 21:39 | 2021-03-12 21:38 |  | Fuller, Lachlan | 2021-03-29 18:23 | Closed | PL-01193 | 3331-63-MCS-0305-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
A | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 23:45 |  | Fuller, Lachlan | 2021-03-29 18:21 | Closed | PL-01157 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
A | Item not secured | INST | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-04-24 04:59 | 2021-04-22 04:59 |  |  |  | Originated | PL-01635 | 3332-AIT-0585 - FLOTATION SCRUBBER | S1 - Stage 1 Construction Completion | Probe not bolted to flange - needs flange management | 1: A-High
A | Item not secured | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-06 02:25 |  |  |  | Submitted | PL-01485 | 3332-PU-4110 - ROUGHER DOWNCOMER PUMP | S1 - Stage 1 Construction Completion | Hold down bolts not fitted
A | Item not secured | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-06 02:43 |  |  |  | Submitted | PL-01486 | 3332-PU-4110 - ROUGHER DOWNCOMER PUMP | S1 - Stage 1 Construction Completion | Bolts not fitted
A | Item not secured | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-04 04:18 | 2021-03-02 04:17 |  |  |  | Originated | PL-01006 | 3332-LIT-0414 - REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | Transmitter needs flange management - not bolted or torqued | 1: A-High
A | Item not secured | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-04 04:44 | 2021-03-02 04:41 |  |  |  | Originated | PL-01007 | 3332-PIT-0419 - OUTLET REGRIND MILL DISCHARGE PUMP | S1 - Stage 1 Construction Completion | Device requires flange management- not torqued | 1: A-High
A | Item not secured | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid |  | 2021-02-19 02:06 |  | Clark, Connor | 2021-02-19 02:12 | Closed | PL-00650 | 3335-PU-4094 - FIRE WATER JOCKEY PUMP | S1 - Stage 1 Construction Completion | Turn Motor Guard
A | Item not secured | MECH | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-04-24 03:39 | 2021-04-22 03:39 |  |  |  | Originated | PL-01627 | 3332-AIT-0584 - SRUBBER ORP | S1 - Stage 1 Construction Completion | Flange bolts for probe missing- needs flange management | 1: A-High
A | Item not secured | MECH | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-02 - Caustic Dosing and Distribution | 2021-04-21 05:02 | 2021-04-19 05:01 |  |  |  | Originated | PL-01579 | 3334-PU-4119-M1 - Motor for SODIUM HYDROXIDE (CAUSTIC) DOSING PUMP | S1 - Stage 1 Construction Completion | Motor needs to be bolted down to plinth | 1: A-High
A | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:10 |  | Polkinghorne, Scott | 2020-11-05 | Closed | PL-00030 | 3338DB4001-R2 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Emergency LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
A | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:15 |  | Polkinghorne, Scott | 2020-11-05 | Closed | PL-00031 | 3338DB4001-R26 - SUBSTATION LIGHT AND POWER BOARD TO Substation External LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
A | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:17 |  | Polkinghorne, Scott | 2020-11-05 | Closed | PL-00032 | 3338DB4001-W4 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Emergency LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
A | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:17 |  | Polkinghorne, Scott | 2020-11-05 | Closed | PL-00033 | 3338DB4001-W28 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Flood Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
A | Missing Labels | ELEC | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:14 |  |  |  | Submitted | PL-01640 | 3332-PU-4012-M1 - Motor for ROUGHER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | install label on LSC
A | Missing Labels | ELEC | CSEC - Power Factor Correction / Harmonic Filters | CSEC-01 - Power Factor Correction / Harmonic Filters |  | 2021-04-05 20:02 |  | Polkinghorne, Scott | 2021-04-19 18:36 | Closed | PL-01479 | 3338-PF-4001 - Power Factor Correction | S1 - Stage 1 Construction Completion | Labels not provided by vendor - Use SI-125 to label Power factor correction A) Cable ferrule inside cabinets 18&19. B) Label on front of MCC panel C) discharge label 1 minute before opening panel. D) Tag label on PFC panels (3338-PF-4001 and 3338-PF-4002)
A | Missing Labels | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-03 05:08 | Closed | PL-01360 | 3331-DB-4007 - Concentrate Handling Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Add 240V labels
A | Missing Labels | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-02 00:55 | Closed | PL-01361 | 3331-DB-4007 - Concentrate Handling Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Install arc flash sticker
A | Missing Labels | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-02 00:55 | Closed | PL-01362 | 3331-DB-4007 - Concentrate Handling Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Trefalit label on gpo & outlet
A | Missing Labels | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling |  | 2021-03-23 06:09 |  | Loparev, Roman | 2021-04-02 00:55 | Closed | PL-01365 | 3331-DB-4007 - Concentrate Handling Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Install 415V sticker
A | Missing Parts | CABL | CS0A - Process Control - Network and DCS panels | CS0A-05 - Marshalling boxes Utilities | 2021-03-03 00:40 | 2021-03-01 00:38 |  |  |  | Originated | PL-00984 | 3334MB4081-C1 - FROM DCS TO 3334-MB-4081 | S1 - Stage 1 Construction Completion | Bridging links required for terminals in 3332-MB-4081 ( terminals 40, 42, 44, 46 and terminals 48, 50) Cores 13-20 need internal wiring installed in DCS as they are used in the field.( Refer to termination schedule for 3334MB4081-C1) | 1: A-High
A | Missing Parts | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-03-10 03:59 | 2021-03-08 03:58 |  |  |  | Originated | PL-01080 | 3332MB4033-J1 - FROM DCS TO 3332-MB-4033 | S1 - Stage 1 Construction Completion | Terminals need swapping out and bridging link installed to earth spares in DCS cabinet | 1: A-High
A | Missing Parts | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-03-10 04:10 | 2021-03-08 04:10 |  |  |  | Originated | PL-01081 | 3332MB4033-J2 - FROM DCS TO 3332-MB-4033 | S1 - Stage 1 Construction Completion | Terminals require bridging links installed to earth spares in DCS | 1: A-High
A | Missing Parts | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-03 - Marshalling boxes Molybdenum Floatation | 2021-03-10 04:24 | 2021-03-08 04:19 |  |  |  | Originated | PL-01082 | 3332MB4033-C1 - FROM DCS TO 3332-MB-4033 | S1 - Stage 1 Construction Completion | Terminals require bridging links to earth spares in DCS | 1: A-High
A | Missing Parts | ELEC | CS14 - NaHS Preparation & Distribution | CS14-03 - NaHS Ring Main & Storage Tanks | 2021-03-02 22:23 | 2021-02-28 22:23 |  |  |  | Originated | PL-00974 | 3334-PU-4041-M1 - Motor for NaHS TRANSFER PUMP | S1 - Stage 1 Construction Completion | Requires bung | 1: A-High
A | Missing Parts | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) | 2021-02-08 21:32 | 2021-02-06 21:32 |  | Muell, Thomas | 2021-03-18 21:51 | Closed | PL-00546 | 3331-FV-0070 - OUTLET COPPER CONCENTRATE CHARGING PUMP | S1 - Stage 1 Construction Completion | Missing 4x screws for terminal box | 1: A-High
A | Missing Parts | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) | 2021-02-08 22:16 | 2021-02-06 22:16 |  | Muell, Thomas | 2021-03-18 21:52 | Closed | PL-00547 | 3331-FV-0075 - INLET COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Missing 4x screws in terminal box cover | 1: A-High
A | Missing Parts | INST | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-15 06:31 | 2021-03-01 06:26 |  |  |  | Originated | PL-00993 | 3332-FV-0415 - OUTLET REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | Fit 20mm Bung to terminal box | 2: B-Low
A | Missing Parts | INST | CS0M - Gland Water | CS0M-02 - Gland Seal Water Charging Pumps | 2021-04-26 06:28 | 2021-04-24 06:27 |  |  |  | Originated | PL-01667 | 3331-FV-1025 - GLAND WATER TO COPPER CONC. CHARGING PUMP | S1 - Stage 1 Construction Completion | Limit switch has been taken. Lachlan Fuller has indicated this with an information tag showing that he is aware of this. | 1: A-High
A | Missing Parts | INST | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-03-10 05:07 | 2021-03-08 05:07 |  |  |  | Submitted | PL-01084 | 3331OP4205-C1 - DCS TO 3331-SA-4001 - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Design to be completed and cabling to be installed | 1: A-High
A | Missing Parts | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid |  | 2021-02-19 02:03 |  | Clark, Connor | 2021-02-19 02:09 | Closed | PL-00649 | 3335-PU-4093 - FIRE WATER PUMP | S1 - Stage 1 Construction Completion | Replace/install motor guard
A | Missing Parts | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-01-24 22:34 | 2021-01-22 22:34 |  | Clark, Connor | 2021-02-18 23:49 | Closed | PL-00262 | 3335-PU-4092 - FIRE WATER DIESEL PUMP | S1 - Stage 1 Construction Completion | Connect suction and discharge piping to fire water skid | 1: A-High
A | Missing Parts | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-01-24 22:59 | 2021-01-22 22:59 |  | Clark, Connor | 2021-02-18 23:49 | Closed | PL-00264 | 3335-PU-4093 - FIRE WATER PUMP | S1 - Stage 1 Construction Completion | Install suction and discharge lines to skid | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-01-21 06:20 |  | Gayler, Randal | 2021-03-15 04:03 | Closed | PL-00223 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install blind flange
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-02-07 05:02 |  | Gayler, Randal | 2021-03-04 23:19 | Closed | PL-00554 | 3335-50-IA-0044-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing blind flange at end of line
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-02-07 05:02 |  | Gayler, Randal | 2021-03-04 23:20 | Closed | PL-00555 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing ball valves on 3335-50-IA-0038-C4-01, 02 and 03. (3 valves)
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-23 23:20 | 2021-01-21 23:13 |  | Gayler, Randal | 2021-03-04 23:40 | Closed | PL-00230 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install 3 missing 20mm x 75mm long seamless nipples Install 3 missing 20mm ball valves | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 03:04 | 2021-02-07 05:02 |  | Gayler, Randal | 2021-03-04 23:41 | Closed | PL-00552 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install blinds x3 | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 03:06 | 2021-02-07 05:02 |  | Gayler, Randal | 2021-03-04 23:43 | Closed | PL-00553 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing blind. | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 04:50 | 2021-02-07 05:03 |  | Gayler, Randal | 2021-03-15 03:59 | Closed | PL-00557 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing blind at end of line | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 04:54 | 2021-02-07 05:03 |  | Gayler, Randal | 2021-03-15 04:00 | Closed | PL-00558 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing 20mm ball valve | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 06:40 | 2021-02-07 06:40 |  | Gayler, Randal | 2021-03-15 04:01 | Closed | PL-00559 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing blind at end of line. | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-09 06:44 | 2021-02-07 06:44 |  | Gayler, Randal | 2021-03-15 04:02 | Closed | PL-00560 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing 20mm ball valve. | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-21 04:59 | 2021-02-07 05:02 |  | Gayler, Randal | 2021-03-04 23:47 | Closed | PL-00556 | 3335-50-IA-0044-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing U-bolts. | 2: B-Low
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-01-25 03:02 | 2021-01-23 03:02 |  | Lanser, Richard | 2021-04-05 19:19 | Closed | PL-00265 | 3332-50-IA-0083-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install missing valve- 3332VV0635 and 25mm nipple | 1: A-High
A | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 21:40 | 2021-01-22 02:16 |  | Liang, Dennis | 2021-03-18 19:47 | Closed | PL-00242 | 3332-50-IA-0112-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete line- install 20mm pipe and 20mm ball valve to go with it | 2: B-Low
A | Not to Contract Spec | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-01-24 04:27 | 2021-01-24 05:09 |  |  | Rejected | PL-00287 | 3331-AG-4001-M1 - Motor for CONCENTRATE STORAGE TANK 1 AGITATOR | S2 - Stage 2 Pre Commissioning | Local and Remote selector is backwards.
A | Not to Contract Spec | ELEC | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-04-20 21:33 | 2021-04-18 21:32 |  |  |  | Submitted | PL-01573 | 3335-PU-4155 - FLUSH CHARGE PUMP | S2 - Stage 2 Pre Commissioning | Installed Circuit breaker in MCC is 20A As per Worley protection setting report circuit breaker should be a Terasaki S125-GJ 100A. Start up current is 68A | 1: A-High
A | Not to Contract Spec | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-23 03:30 | 2021-03-20 06:30 |  | Lanser, Richard | 2021-04-16 05:44 | Closed | PL-01286 | 3332-110-VGN-0091-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flange managment required | 1: A-High
A | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-03-23 22:36 | 2021-03-21 01:35 |  | Lanser, Richard | 2021-04-05 18:25 | Closed | PL-01326 | 3332-90-VGN-0098-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | complete flange management | 1: A-High
A | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-23 20:31 | 2021-01-21 20:31 |  | Gayler, Randal | 2021-03-04 23:13 | Closed | PL-00227 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Incorrect flange installed. Replace RF for table E FF flange and install same spec blind flange. | 1: A-High
A | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-08 05:27 |  | Nutt, Richard | 2021-02-25 20:24 | Closed | PL-00565 | 3331-50-PWH-0042-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required.
A | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-10 02:02 | 2021-02-08 05:26 |  | Nutt, Richard | 2021-02-27 06:51 | Closed | PL-00564 | 3331-50-PWH-0040-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required. | 1: A-High
A | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-03 22:41 | 2021-03-20 01:44 |  | Lanser, Richard | 2021-04-05 19:20 | Closed | PL-01275 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | fix F2 clashing on other pipe work. also fix same pipe laying on top of others in the rack. | 2: B-Low
A | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-20 04:48 | 2021-03-21 01:59 |  | Lanser, Richard | 2021-04-18 04:49 | Closed | PL-01332 | 3331-90-PD-0011-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Modification to poly pipe currently sitting too high | 1: A-High
A | Not to Drawings | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-03 - Flocculant area sump |  | 2021-03-22 00:45 |  | Lanser, Richard | 2021-04-27 07:36 | Closed | PL-01340 | 3334-90-PD-0002-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment to be completed
A | Not to Drawings | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-03 - Flocculant area sump |  | 2021-03-22 00:46 |  |  |  | Originated | PL-01341 | 3334-80-PD-0001-R5 - PD Process Line | S1 - Stage 1 Construction Completion
A | Not to Drawings | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-21 02:04 |  | Lanser, Richard | 2021-04-18 04:49 | Closed | PL-01333 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe Clash
A | Not to Equipment Specs | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-01-24 04:58 | 2021-01-24 05:11 |  |  | Rejected | PL-00288 | 3331-AG-4001-M1 - Motor for CONCENTRATE STORAGE TANK 1 AGITATOR | S2 - Stage 2 Pre Commissioning | Run command not working, instant trip
A | Not to Equipment Specs | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-21 20:30 |  | Lanser, Richard | 2021-04-19 21:35 | Closed | PL-01339 | 3332-SA-4008 - ROUGHER JAMESON TAILS LSA | S1 - Stage 1 Construction Completion | Modify Flange to suit (ASME #150)
A | Not to Equipment Specs | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-25 00:06 |  | Lanser, Richard | 2021-04-16 20:52 | Closed | PL-01371 | 3332-LD-4006 - Rougher Jamerson Concentrate Launder | S1 - Stage 1 Construction Completion | FLANGE TO 3332-CY-4001 NEED MODIFICATION
A | Other | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-03-16 05:08 |  | Muell, Thomas | 2021-03-16 05:58 | Closed | PL-01226 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Earth to be installed
A | Other | ELEC | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-01-24 | 2021-01-18 22:23 |  | Muell, Thomas | 2021-02-17 22:07 | Closed | PL-00190 | 3335-PU-4092 - FIRE WATER DIESEL PUMP | S1 - Stage 1 Construction Completion | SI-110 for non-compliance repairs for Elect items 1.Control Panel seal nut / bolt holes as required 2.Modify to reduce to ELV Square D pressure switches 3.provide covering over exposed terminals 4.Supply and install traffolyte identification labels on 3 x panels Jockey (3335-OP-4205), Diesel (3335-OP-4204) and Electric (3335-OP-4092). | 1: A-High
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00081 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Label required to identify equipment number and description of 2 x earth bars (eg 3338-EB-4001, 3338-EB-4002)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00082 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Additional 120mm sq earth cable to be installed between 3338-RU-4001 RMU Earth Bar and the additional compound earth bar
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00086 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : 2 x 120mm sq earth cables to be installed between compound earth bar and main earth bar within 33kV RMU switchboard
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00087 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : 33kV RMU cable box to STSF outgoing circuit : multiple bolts loose
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00088 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Traffolite labels to be installed adjacent to outgoing 33kV cable boxes to identify circuit number / description
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00090 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : 33kV cable glands to be tightened - multiple glands found to be loose
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00091 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Penetration in wall to TF4002 compound to be sealed with 2hr fire rated mortar (temporary fire pillows permitted in interim)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00092 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Stairs to RMU deck to be earthed
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00093 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Timber packing to be removed from within 3338-RU-4001 metering panel
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00094 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Timber packing to be removed from within 3338-RU-4001 feeder to 3338-TF-4001 - supporting CTs
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00095 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Timber packing to be removed from within 3338-RU-4001 feeder to 3338-TF-4001 - supporting CTs
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00101 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Equipotential earth connection to RMU loose (connection to IP56 external enclosure on switchroom side)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00105 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Label required to identify equipment number and description of earth bars (eg 3338-EB-40xx)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00116 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Label required to identify equipment number and description of earth bars (eg 3338-EB-40xx)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00127 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : external earth grid to be completed - multiple earth connections not installed
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00129 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Scaffolding to be relocated to allow N/E door to be usable and facilitate egress from switchroom
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00139 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Label required to identify equipment number and description of earth bars (eg 3338-EB-40xx)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Loparev, Roman | 2021-02-04 02:27 | Closed | PL-00130 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | 3338-SS-4001 Substation : All doors to be closed and door hardware completed (eg door closers, crash bars, door locks, weather seals etc)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00079 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : RMU compound warning and safety signage to be installed : eg Authorised Personnel Only, Danger 33,000 V
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00080 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : RMU compound area : fire extinguisher and fire signage to be installed
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00103 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Transformer compound warning and safety signage to be installed : eg Authorised Personnel Only, Danger 33,000 V
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00104 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Transformer compound area : fire extinguisher and fire signage to be installed
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00112 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Penetration in wall to switchroom to be sealed with 2hr fire rated mortar (temporary fire pillows permitted in interim)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00114 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Transformer compound warning and safety signage to be installed : eg Authorised Personnel Only, Danger 33,000 V
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00115 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Transformer compound area : fire extinguisher and fire signage to be installed
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00122 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : 33kV cable tray : Danger 33,000V sticker to be attached
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00123 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Penetration in wall to switchroom to be sealed with 2hr fire rated mortar (temporary fire pillows permitted in interim)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-16 | Closed | PL-00068 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Mechanical protection required over 33kV cable and fibre at cable tray to underground conduit transition
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-16 | Closed | PL-00069 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Mechanical protection required over buried conduits between cable tray and first pit (eg concrete slab)
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-16 | Closed | PL-00100 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Caps to be attached to all elbow connections on incoming / outgoing 33kV cables in RMU
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-17 | Closed | PL-00070 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Water to be removed from main 33kV pit on western side of access road
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-17 | Closed | PL-00136 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Resuscitation signs to be installed within switchroom
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-17 | Closed | PL-00137 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Low voltage rescue kits to be installed within switchroom
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-18 | Closed | PL-00071 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : 33kV cabling and fibre optic cable to be supported within main 33kV pit on western side of access road
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-18 | Closed | PL-00074 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Danger 33,000V stickers to be attached to 33 kV tray lid
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00097 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Electrical lock to be attached to RMU metering cubicle to prevent unauthorised access
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00099 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Surge arrestors to be fitted to all incoming / outgoing 33kV cable circuits in RMU
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00102 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Transformer compound fence and gates to be installed and earthed with gates locked
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00113 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Transformer compound fence and gates to be installed and earthed with gates locked
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00131 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Signage to be attached to external wall to identify switchroom number and description
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00135 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Fire extinguishers and signage to be installed within switchroom
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00141 | 3338-MC-4001 - Motor Control Centre No 1 |  | 3338-MC-4001 : Danger 415V stickers to be attached to all modules
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00143 | 3338-MC-4001 - Motor Control Centre No 1 |  | 3338-MC-4001 : Incoming 415V ACB to be locked to prevent energisation of the busbar
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00144 | 3338-MC-4001 - Motor Control Centre No 1 |  | 3338-MC-4001 : Spare modules : busbar connections are not IP2X rated - can touch busbars with finger
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00145 | 3338-MC-4002 - Motor Control Centre No 2 |  | 3338-MC-4002 : Danger 415V stickers to be attached to all modules
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00147 | 3338-MC-4002 - Motor Control Centre No 2 |  | 3338-MC-4002 : Incoming 415V ACB to be locked to prevent energisation of the busbar
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00148 | 3338-MC-4002 - Motor Control Centre No 2 |  | 3338-MC-4002 : Spare modules : busbar connections are not IP2X rated - can touch busbars with finger
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-06 - Switch room General |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00125 | 3338-GE-4001 - Emergency Diesel Generator |  | 3338-GE-4001 compound : Compound earthing and earth bar to be completed to complete the 120mmsq earth ring for the substation
A | Other | ELEC | CSED - Switch Room & MCCs | CSED-06 - Switch room General |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00126 | 3338-GE-4001 - Emergency Diesel Generator |  | 3338-GE-4001 compound : Label required to identify equipment number and description of earth bars (eg 3338-EB-40xx)
A | Other | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-03 02:59 |  |  |  | Submitted | PL-01434 | 3332-HT-4001 - REGRIND MILL HOIST 1 | S1 - Stage 1 Construction Completion | Earths need to be confirmed
A | Other | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-03 03:10 |  |  |  | Submitted | PL-01443 | 3332-HT-4002 - REGRIND MILL HOIST 2 | S1 - Stage 1 Construction Completion | Earths need to be confirmed
A | Other | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-01-20 22:40 | 2021-01-18 22:39 |  | Lanser, Richard | 2021-02-17 22:25 | Closed | PL-00192 | 3335-PU-4092 - FIRE WATER DIESEL PUMP | S1 - Stage 1 Construction Completion | Engage Awcon / M2P diesel fitter to inspect Diesel pump (first fills etc) prior to starting | 1: A-High
B |  | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-05-01 07:55 | 2021-04-17 07:55 | 2021-04-21 04:03 |  |  | Rejected | PL-01553 | 3335-FV-0845 - OUTLET PROCESS WATER PUMP | S2 - Stage 2 Pre Commissioning | 4:adjust valve limits | 2: B-Low
B |  | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:19 |  |  |  | Originated | PL-01650 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | 3332-50-PWH-0324-C6 missing spec blind
B |  | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump | 2021-04-23 22:07 | 2021-04-09 22:07 |  |  |  | Originated | PL-01499 | 3332-110-VGN-0103-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B |  | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:23 |  |  |  | Originated | PL-01182 | 3332-100-PD-0050-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B |  | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:14 |  |  |  | Originated | PL-01240 | 3335-50-IA-0061-C4 - IA Process Line | S1 - Stage 1 Construction Completion | U-Bolts to be installed
B | Incorrect Labels | ELEC | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-10 21:06 | 2021-02-08 21:06 |  | Loparev, Roman | 2021-02-19 02:44 | Closed | PL-00566 | 3335-PU-4093-M1 - Motor for FIRE WATER PUMP | S1 - Stage 1 Construction Completion | Incorrectly labelled. Labelled as 3335-PU-4093 but should be labelled as 3335-PU-4092.Both fire water skid diesel and electric motors need labels fixed up. | 1: A-High
B | Incorrect Labels | ELEC | CSED - Switch Room & MCCs | CSED-05 - Switch room Air-conditioning | 2021-02-27 06:38 | 2021-02-25 06:37 |  |  |  | Originated | PL-00916 | 3338-AC-4002 - Substation Air Conditioning | S1 - Stage 1 Construction Completion | New label, needs information updated from 25A to 32A | 1: A-High
B | Incorrect Labels | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-01-22 03:42 |  |  |  | Submitted | PL-00246 | 3331-AIT-0085 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | Free issued equipment to supplied with instrument tag.
B | Incorrect Labels | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-02-26 00:09 | 2021-02-08 02:24 |  |  |  | Originated | PL-00562 | 3332-LCV-0190B - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Vendor ID Tag incorrect Current ID tag = 3332-LCV-0189B Correct ID tag = 3332-LCV-0190B | 1: A-High
B | Incorrect Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:04 |  |  |  | Submitted | PL-01439 | 3332-25-PWH-0253-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Incorrect Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:32 | 2021-01-18 02:32 |  |  |  | Originated | PL-00166 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all U-bolts | 2: B-Low
B | Item Damaged | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-03-21 00:12 | 2021-03-19 00:12 |  | Fuller, Lachlan | 2021-03-26 21:41 | Closed | PL-01261 | 3331-FV-0009 - BULK Cu-Mo CONCENTRATE DRAIN | S1 - Stage 1 Construction Completion | The selector switch, local control plate is broken off. | 1: A-High
B | Item Damaged | ELEC | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 20:27 |  |  |  | Originated | PL-00444 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S1 - Stage 1 Construction Completion | 1/ Teraski TemBreak isolator to be replaced. Isolator Switch has been broken internally. Can now open panel when isolator ON. 2/ 240v and 415v stickers to be added to internal panel covers. 3/ Need to provide a traffolyte identification label to both panels. I will see what tag number / descriptor supplier has used to identified panels.
B | Item Damaged | INST | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener | 2021-03-19 05:24 | 2021-03-05 05:22 |  |  |  | Originated | PL-01019 | 3332-FV-0433 - Mo SLURRY TO REGRIND MILL | S1 - Stage 1 Construction Completion | New exhaust filter require - 1/8” NPT | 2: B-Low
B | Item Damaged | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-06 22:49 | 2021-02-20 22:49 |  |  |  | Originated | PL-00693 | 3331-FV-1020 - COPPER CONCENTRATE TO COPPER CONC. THICK. FEED BOX | S1 - Stage 1 Construction Completion | Damaged proxy | 2: B-Low
B | Item Damaged | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 04:36 |  | Lanser, Richard | 2021-04-05 22:52 | Closed | PL-00657 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Damaged | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells | 2021-04-16 07:32 | 2021-04-02 06:31 |  |  |  | Originated | PL-01417 | 3332-AG-4118-M1 - Motor for CLEANER SCAVENGER FLOTATION CELL 2 AGITATOR | S1 - Stage 1 Construction Completion | Motor needs painting - paint has peeled off motor frame and is back to bare metal | 2: B-Low
B | Item Damaged | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:30 | 2021-01-31 03:30 |  | Lanser, Richard | 2021-04-19 22:07 | Closed | PL-00482 | 3332-25-PWH-0248-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Valve 3332-FB-4005 Locking mechanisam bent and need to be repaired. | 1: A-High
B | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 06:56 |  | Lanser, Richard | 2021-04-22 10:15 | Closed | PL-00967 | 3331-AG-4002 - CONCENTRATE STORAGE TANK 2 AGITATOR | S1 - Stage 1 Construction Completion | Clean debris from tank.
B | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 01:52 |  | Lanser, Richard | 2021-04-19 07:11 | Closed | PL-00712 | 3331-AG-4001 - CONCENTRATE STORAGE TANK 1 AGITATOR | S1 - Stage 1 Construction Completion | Clean tank internal at completion of scope
B | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-02-21 02:50 |  | Lanser, Richard | 2021-04-16 07:35 | Closed | PL-00723 | 3331-PU-4011 - CONCENTRATE STORAGE SUMP PUMP | S1 - Stage 1 Construction Completion | Sumps to be cleaned prior to pump start up
B | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 13:10 | 2021-03-08 16:09 |  |  |  | Submitted | PL-01106 | 3332-DI-4001 - CONDITIONING TANK FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Internals need cleaning | 1: A-High
B | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 05:42 | 2021-02-01 05:39 |  | Lanser, Richard | 2021-04-05 23:17 | Closed | PL-00519 | 3332-FB-4004 - ROUGHER SCAVENGER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | House keeping required | 2: B-Low
B | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 07:09 | 2021-02-01 07:07 |  | Lanser, Richard | 2021-04-05 23:17 | Closed | PL-00522 | 3332-FB-4003 - ROUGHER SCAVENGER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | House keeping required | 2: B-Low
B | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-25 00:43 | 2021-02-22 03:42 |  | Lanser, Richard | 2021-04-18 00:01 | Closed | PL-00830 | 3332-LD-4007 - ROUGHER SCAVENGER LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | INTERNAL CLEAN UP | 1: A-High
B | Item Dirty | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-04-06 01:54 |  | Lanser, Richard | 2021-04-19 21:35 | Closed | PL-01484 | 3332-TH-4002 - INTERMEDIATE THICKENER | S1 - Stage 1 Construction Completion | House keeping required
B | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 04:10 |  | Lanser, Richard | 2021-04-05 23:16 | Closed | PL-01401 | 3332-LD-4005 - SECOND CLEANER CONCENTRATE LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | Visual inspection
B | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 04:12 |  | Lanser, Richard | 2021-04-05 23:16 | Closed | PL-01402 | 3332-LD-4003 - SECOND CLEANER CONCENTRATE LAUNDER | S1 - Stage 1 Construction Completion | Visual inspection
B | Item Dirty | MECH | CS08 - Molybdenum Thickener and Concentrate Filter | CS08-01 - Molybdenum Concentrate Thickener |  | 2021-04-26 06:51 |  |  |  | Submitted | PL-01672 | 3332-TH-4003 - MOLYBDENUM CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Needs internal clean
B | Item Dirty | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 04:29 |  | Nutt, Richard | 2021-04-14 03:27 | Closed | PL-00744 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Clean tank internal at completion of scope
B | Item Dirty | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:32 |  | Lanser, Richard | 2021-04-16 20:51 | Closed | PL-01350 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Clean top of hopper
B | Item Dirty | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-07 04:24 | 2021-02-21 04:23 |  | Lanser, Richard | 2021-04-16 21:11 | Closed | PL-00741 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Clean hopper prior to first fill | 2: B-Low
B | Item Dirty | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:27 | 2021-04-23 01:09 |  |  | Rejected | PL-01376 | 3332-250-MCS-0113-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:50 | 2021-04-23 01:09 |  |  | Rejected | PL-01379 | 3332-400-MCS-0112-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-03-26 05:22 |  | Lanser, Richard | 2021-04-05 19:18 | Closed | PL-01385 | 3332-110-MCS-0135-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:08 | 2021-04-23 01:09 |  |  | Rejected | PL-01239 | 3335-50-IA-0055-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:15 | 2021-04-23 01:09 |  |  | Rejected | PL-01242 | 3335-50-IA-0061-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:24 | 2021-04-23 01:09 |  |  | Rejected | PL-01247 | 3332-50-IA-0013-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:33 | 2021-04-23 01:09 |  |  | Rejected | PL-01252 | 3332-50-IA-0006-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Incomplete | CABL | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-07 06:48 | 2021-02-21 06:48 |  |  |  | Accepted | PL-00777 | 3332ZS0114-C1 - FROM 3332-OP-4022 TO 3332-ZS-0114 | S1 - Stage 1 Construction Completion | Spare cores require earthing at Operations Panel | 2: B-Low
B | Item Incomplete | CABL | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-07 06:50 | 2021-02-21 06:50 |  |  |  | Accepted | PL-00778 | 3332ZS0116-C1 - FROM 3332-OP-4022 TO 3332-ZS-0116 | S1 - Stage 1 Construction Completion | Spare cores require earthing at Operations Panel | 2: B-Low
B | Item Incomplete | CABL | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-07 06:51 | 2021-02-21 06:51 |  |  |  | Accepted | PL-00779 | 3332ZS1023-C1 - FROM 3332-OP-4022 TO 3332-ZS-1023 | S1 - Stage 1 Construction Completion | Spare cores require earthing at Operations Panel | 2: B-Low
B | Item Incomplete | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation | 2021-03-09 03:57 | 2021-02-23 03:57 |  | Muell, Thomas | 2021-03-15 21:58 | Closed | PL-00867 | 3332DB4008-W10 - FLOATATION AREA LIGHT AND POWER BOARD TO FLOATATION BUILDING (4TH FLOOR) EMERGENCY LIGHTING | S1 - Stage 1 Construction Completion | Light to be installed and terminated. Back bone cables terminated in JB and spare entry closed with bung to allow completion of circuit. | 2: B-Low
B | Item Incomplete | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation | 2021-03-09 04:11 | 2021-02-23 04:11 |  | Muell, Thomas | 2021-03-17 23:43 | Closed | PL-00868 | 3332DB4008-W46 - FLOATATION AREA LIGHT AND POWER BOARD TO FLOATATION BUILDING AREA LIGHTING | S1 - Stage 1 Construction Completion | Light to be installed and terminated. Back bone cable terminated in JB with a bung in spare entry to allow completion of the circuit. | 2: B-Low
B | Item Incomplete | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation | 2021-03-09 04:19 | 2021-02-23 04:19 |  | Muell, Thomas | 2021-03-17 23:51 | Closed | PL-00869 | 3332DB4008-B48 - FLOATATION AREA LIGHT AND POWER BOARD TO STORAGE TANK FLOOD LIGHTING | S1 - Stage 1 Construction Completion | L124 and L122 (flood lights) to be installed and terminated into JB. Feed cable has been terminated in JB and spare entries made safe with bung. | 2: B-Low
B | Item Incomplete | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation | 2021-03-09 23:49 | 2021-02-23 23:49 |  | Muell, Thomas | 2021-03-17 23:55 | Closed | PL-00897 | 3332DB4008-R2 - FLOATATION AREA LIGHT AND POWER BOARD TO FLOATATION BUILDING GROUND FLOOR EMERGENCY LIGHTING | S1 - Stage 1 Construction Completion | L022 needs to be installed and terminated. Feed cable has been terminated and tested at JB. Bungs have been applied to spare entries on JB. | 2: B-Low
B | Item Incomplete | CIVIL | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 01:52 |  | Nutt, Richard | 2021-04-27 05:22 | Closed | PL-00713 | 3331-AG-4001 - CONCENTRATE STORAGE TANK 1 AGITATOR | S1 - Stage 1 Construction Completion | Concrete to internal floor of tank and fit shaft stabilizing ring.
B | Item Incomplete | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-01-24 05:11 |  |  |  | Submitted | PL-00291 | 3331-AG-4001-M1 - Motor for CONCENTRATE STORAGE TANK 1 AGITATOR | S2 - Stage 2 Pre Commissioning | Hook UP the Motor
B | Item Incomplete | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-07 02:27 | 2021-02-21 02:27 |  | Polkinghorne, Scott | 2021-04-13 13:28 | Closed | PL-00717 | 3331-OP-4201 - PM001 - Concentrate Transfer Piston Diaphragm Pumps | S1 - Stage 1 Construction Completion | Vendor supplied panel missing components | 2: B-Low
B | Item Incomplete | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane |  | 2021-03-11 21:41 |  | Muell, Thomas | 2021-03-14 01:03 | Closed | PL-01150 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Install pendant on crane. Neutral not required - earth redundant conductor
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:27 |  |  |  | Originated | PL-01653 | 3332-LIT-0106 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | 3332-LIT-0106 and 3332-LIT-0111 not bolted and spec blinds missing
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:15 | 2021-02-21 00:15 |  |  |  | Originated | PL-00696 | 3332-OP-4101 - Fail safe Cabinet for 3332-FB-4001 | S1 - Stage 1 Construction Completion | 20mm bungs required for spare cable entries | 2: B-Low
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:19 | 2021-02-21 00:18 |  |  |  | Originated | PL-00698 | 3332-OP-4102 - Fail safe Cabinet for 3332-FB-4002 | S1 - Stage 1 Construction Completion | 20mm bungs required for spare cable entries | 2: B-Low
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:21 | 2021-02-21 00:21 |  |  |  | Originated | PL-00700 | 3332-OP-4103 - Fail safe Cabinet for 3332-FB-4003 | S1 - Stage 1 Construction Completion | 20mm bungs required for spare cable entries | 2: B-Low
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:25 | 2021-02-21 00:25 |  |  |  | Originated | PL-00702 | 3332-OP-4104 - Fail safe Cabinet for 3332-FB-4004 | S1 - Stage 1 Construction Completion | 20mm bungs required for spare cable entries | 2: B-Low
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:29 | 2021-02-21 00:29 |  |  |  | Originated | PL-00704 | 3332-OP-4105 - Fail safe Cabinet for 3332-FB-4005 | S1 - Stage 1 Construction Completion | 20mm bungs required for spare cable entries | 2: B-Low
B | Item Incomplete | ELEC | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:31 |  |  |  | Submitted | PL-01643 | 3332-PU-4012 - ROUGHER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Install Barrier strips, PCV cables ties & Cable tray lid
B | Item Incomplete | ELEC | CS09 - Concentrate Dryer & Scrubber | CS09-01 - Concentrate Dryer | 2021-03-11 22:43 | 2021-02-25 22:43 |  |  |  | Originated | PL-00927 | 3333-DY-4001 - CONCENTRATE DRYER MOTOR REQUIRES FORCED VENTILATION | S1 - Stage 1 Construction Completion | Missing equipment in bucket | 2: B-Low
B | Item Incomplete | ELEC | CS0A - Process Control - Network and DCS panels | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | 2021-03-21 21:09 | 2021-03-06 23:45 |  |  |  | Originated | PL-01047 | 3331MB4011-C2 - GHEO PUMP CONTROL PANEL TO GHEO PUMP MARSHALLING BOX | S1 - Stage 1 Construction Completion | Spare cores need to be earthed in 3331-OP-4201 | 2: B-Low
B | Item Incomplete | ELEC | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-02 00:27 | 2021-01-19 00:27 |  |  |  | Originated | PL-00198 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Install painted kickplate (around cable entry) through platework at base of OP panel in first thickener area | 2: B-Low
B | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation |  | 2021-03-11 21:09 |  |  |  | Originated | PL-01133 | 3332-DB-4008 - Flotation East Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | W4 (west) – rubber not installed under handrail “U” mounting bracket + No Emerg light W4 (face N) – readjust and bolt swivel when scaffold removed W10 – no light R26 – tighten 4 x swivel bolts hen scaffold removed R26 (NE) paint stand / install galv stand R44 – remove scaffold clip from handrail (mech) B48 – no floodlights installed (x2) 3332-W/O-4007 – prep and paint stand footing / baseplate 3332-GPO-4020 (upper level) - prep and paint stand footing / baseplate L105 To be fixed once scaffold is complete
B | Item Incomplete | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-01-22 03:39 |  |  |  | Submitted | PL-00245 | 3331-AIT-0085 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | Pneumatic lines to be completed
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | 2021-03-07 00:42 | 2021-02-21 00:42 |  |  |  | Originated | PL-00709 | 3332-OP-4226 - Sampler 3332-SA-4009 | S1 - Stage 1 Construction Completion | Air lines to be installed and fitted | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 00:40 |  |  |  | Originated | PL-00946 | 3332-AIT-0166 - ROUGHER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Install flushing plugs on 3332-AIT-0142/0166 and install silencers on OP boxes
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:16 | 2021-02-21 00:16 |  |  |  | Originated | PL-00697 | 3332-OP-4101 - Fail safe Cabinet for 3332-FB-4001 | S1 - Stage 1 Construction Completion | Air lines to be run in and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:19 | 2021-02-21 00:19 |  |  |  | Submitted | PL-00699 | 3332-OP-4102 - Fail safe Cabinet for 3332-FB-4002 | S1 - Stage 1 Construction Completion | Air lines to be run and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:22 | 2021-02-21 00:22 |  |  |  | Originated | PL-00701 | 3332-OP-4103 - Fail safe Cabinet for 3332-FB-4003 | S1 - Stage 1 Construction Completion | Air lines to be run and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:25 | 2021-02-21 00:25 |  |  |  | Originated | PL-00703 | 3332-OP-4104 - Fail safe Cabinet for 3332-FB-4004 | S1 - Stage 1 Construction Completion | Air lines to be run and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:30 | 2021-02-21 00:30 |  |  |  | Originated | PL-00705 | 3332-OP-4105 - Fail safe Cabinet for 3332-FB-4005 | S1 - Stage 1 Construction Completion | Air lines to be run and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:39 | 2021-02-21 00:38 |  |  |  | Originated | PL-00707 | 3332-OP-4542 - OP Instrument Air for 3332-AV-0142 | S1 - Stage 1 Construction Completion | Air lines to be installed and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-07 00:40 | 2021-02-21 00:40 |  |  |  | Originated | PL-00708 | 3332-OP-4543 - OP Instrument Air for 3332-AV-0166 | S1 - Stage 1 Construction Completion | Air lines to be installed and fitted - No Design | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-20 22:24 | 2021-03-06 22:24 |  |  |  | Originated | PL-01042 | 3332-FV-0202 - FIRST CLEANER FLOTATION CELL 1 DRAIN | S1 - Stage 1 Construction Completion | Airlines not present or connected to actuator | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-20 22:29 | 2021-03-06 22:28 |  |  |  | Originated | PL-01043 | 3332-FV-0203 - FIRST CLEANER FLOTATION CELL 2 DRAIN | S1 - Stage 1 Construction Completion | No airlines at device/airlines not connected | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-20 22:32 | 2021-03-06 22:31 |  |  |  | Originated | PL-01044 | 3332-FV-0204 - FIRST CLEANER FLOTATION CELL 4 DRAIN | S1 - Stage 1 Construction Completion | No airlines supplied to device/airlines not connected | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-20 22:37 | 2021-03-06 22:36 |  |  |  | Originated | PL-01045 | 3332-FV-0205 - FIRST CLEANER FLOTATION CELL 4 DRAIN | S1 - Stage 1 Construction Completion | No airlines to device/airlines not connected. | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 01:48 | 2021-03-07 01:47 |  |  |  | Originated | PL-01050 | 3332-OP-4028 - OP Instrument Air for 3332-FV-0202 3332-FV-0203 3332-FV-1035 | S1 - Stage 1 Construction Completion | Airlines not completed/installed at field or board ends | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 22:28 | 2021-03-07 22:27 |  |  |  | Originated | PL-01077 | 3332-OP-4544 - OP Instrument Air for 3332-AV-0196 | S1 - Stage 1 Construction Completion | Air lines to be run in and fitted | 2: B-Low
B | Item Incomplete | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-24 05:07 | 2021-03-10 05:06 |  |  |  | Originated | PL-01127 | 3332-FV-0203 - FIRST CLEANER FLOTATION CELL 2 DRAIN | S1 - Stage 1 Construction Completion | Install/terminate airlines | 2: B-Low
B | Item Incomplete | INST | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-03-15 02:56 | 2021-03-01 02:56 |  |  |  | Originated | PL-00987 | 3332-OP-4033 - OP Instrument Air for 3332-FV-0350 3332-FV-0352 | S1 - Stage 1 Construction Completion | Air lines to be installed | 2: B-Low
B | Item Incomplete | INST | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-24 17:13 |  |  |  | Submitted | PL-00871 | 3335-LIT-0856 - RAW WATER TANK | S1 - Stage 1 Construction Completion | install earthing cable
B | Item Incomplete | INST | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:16 |  |  |  | Submitted | PL-00901 | 3335-AIT-0868 - OUTLET INLINE SODIUM HYDROXIDE MIXER | S2 - Stage 2 Pre Commissioning | Install pH probe flushing caps
B | Item Incomplete | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:19 |  |  |  | Submitted | PL-00889 | 3335-PDIT-0852 - INLET PROCESS WATER PUMP (STAND-BY) | S1 - Stage 1 Construction Completion | Install NPT plugs on the PDIT
B | Item Incomplete | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:28 |  |  |  | Submitted | PL-00890 | 3335-PDIT-0853 - INLET PROCESS WATER PUMP | S1 - Stage 1 Construction Completion | Install NPT plugs on the PDIT
B | Item Incomplete | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-05-02 07:40 | 2021-04-18 07:39 |  |  |  | Submitted | PL-01572 | 3335-AIT-0854 - PROCESS WATER TANK | S2 - Stage 2 Pre Commissioning | Change from ORP to PH in DCS system | 2: B-Low
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 20:23 |  | Lanser, Richard | 2021-04-22 10:15 | Closed | PL-00971 | 3331-TA-4002 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | Pipe supports not installed
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 20:29 |  | Lanser, Richard | 2021-04-05 19:15 | Closed | PL-00973 | 3331-TA-4002 - CONCENTRATE STORAGE TANK 2 | S1 - Stage 1 Construction Completion | flanges not torqued
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 02:02 |  | Lanser, Richard | 2021-04-19 07:11 | Closed | PL-00714 | 3331-TA-4001 - CONCENTRATE STORAGE TANK 1 | S1 - Stage 1 Construction Completion | Clean tank internal at completion of scope
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 02:28 |  | Lanser, Richard | 2021-04-19 07:11 | Closed | PL-00719 | 3331-DI-4005 - CONCENTRATE STORAGE DIVERTER BOX | S1 - Stage 1 Construction Completion | Clean tank internal at completion of scope
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 04:03 |  | Davies, Jesse | 2021-03-19 23:11 | Closed | PL-00731 | 3331-DI-4005 - CONCENTRATE STORAGE DIVERTER BOX | S1 - Stage 1 Construction Completion | Flange management to piping
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-24 00:57 | 2021-02-21 03:56 |  | Lanser, Richard | 2021-04-27 03:41 | Closed | PL-00728 | 3331-TA-4001 - CONCENTRATE STORAGE TANK 1 | S1 - Stage 1 Construction Completion | Pipe supports not installed | 1: A-High
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-24 00:58 | 2021-02-21 03:57 |  |  |  | Submitted | PL-00729 | 3331-TA-4001 - CONCENTRATE STORAGE TANK 1 | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-13 21:52 | 2021-03-11 00:51 |  | Nutt, Richard | 2021-04-13 22:01 | Closed | PL-01134 | 3331-VE-4002 - DISCHARGE PULSATION DAMPENER | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-13 23:57 | 2021-03-11 02:55 |  | Nutt, Richard | 2021-04-13 22:02 | Closed | PL-01137 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Base plate bolts to be tightened when grout cures. | 1: A-High
B | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane | 2021-03-14 02:26 | 2021-03-11 05:25 |  | Lanser, Richard | 2021-04-21 11:50 | Closed | PL-01140 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Pendant not installed | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-01 - Rougher Conditioning Metallurgical Sampler |  | 2021-04-21 01:44 |  |  |  | Submitted | PL-01599 | 3332-SA-4002A - ROUGHER FLOTATION FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Piping incomplete
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-01 - Rougher Conditioning Metallurgical Sampler |  | 2021-04-21 01:50 |  |  |  | Submitted | PL-01600 | 3332-SA-4002C - ROUGHER FLOTATION FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | needs completion
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:30 |  | Lanser, Richard | 2021-04-27 03:40 | Closed | PL-01655 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Tank vents to be installed on 3332-TA-4004 and 3332-TA-4005
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-01 00:18 | 2021-02-27 00:18 |  |  |  | Submitted | PL-00934 | 3332-AIT-0110 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Requires bolting up to tank | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 11:01 | 2021-03-08 14:00 |  |  |  | Submitted | PL-01091 | 3332-PU-4010 - ROUGHER FEED PUMP | S1 - Stage 1 Construction Completion | Gland water piping not connected | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 11:49 | 2021-03-08 14:48 |  | Lanser, Richard | 2021-04-18 00:02 | Closed | PL-01095 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Not all valves are installed | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 12:00 | 2021-03-08 14:59 |  | Lanser, Richard | 2021-04-18 00:02 | Closed | PL-01102 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Not all valves are installed | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 12:01 | 2021-03-08 15:00 |  | Lanser, Richard | 2021-04-18 00:02 | Closed | PL-01103 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Overflow not installed | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:05 |  |  |  | Submitted | PL-01373 | 3332-CY-4001 - ROUGHER JAMESON CELL | S1 - Stage 1 Construction Completion | Frame covers need fitting
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-18 02:39 |  |  |  | Submitted | PL-01558 | 3332-SA-4008 - ROUGHER JAMESON TAILS LSA | S1 - Stage 1 Construction Completion | Valves to be installed
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-18 02:40 |  |  |  | Submitted | PL-01559 | 3332-SA-4008 - ROUGHER JAMESON TAILS LSA | S1 - Stage 1 Construction Completion | All flange connection need completing
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 00:29 |  | Lanser, Richard | 2021-04-17 23:59 | Closed | PL-00792 | 3332-LD-4007 - ROUGHER SCAVENGER LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | RANDON CHECK 10% OF ALL BOLTS
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 02:24 |  | Lanser, Richard | 2021-04-18 | Closed | PL-00796 | 3332-VE-4001 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4001 | S1 - Stage 1 Construction Completion | Feed/Relief Conneciton
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 02:38 |  | Lanser, Richard | 2021-04-18 | Closed | PL-00804 | 3332-VE-4005 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4005 | S1 - Stage 1 Construction Completion | Feed/Relief Conneciton
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 02:39 |  | Lanser, Richard | 2021-04-18 | Closed | PL-00807 | 3332-VE-4002 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4002 | S1 - Stage 1 Construction Completion | Feed/Relief Conneciton
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 02:41 |  | Lanser, Richard | 2021-04-18 | Closed | PL-00809 | 3332-VE-4004 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4004 | S1 - Stage 1 Construction Completion | Feed/Relief Conneciton
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 02:56 |  | Lanser, Richard | 2021-04-05 23:09 | Closed | PL-00819 | 3332-FB-4003 - ROUGHER SCAVENGER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:01 |  | Lanser, Richard | 2021-04-05 23:09 | Closed | PL-00821 | 3332-FB-4004 - ROUGHER SCAVENGER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:05 |  | Lanser, Richard | 2021-04-05 23:09 | Closed | PL-00823 | 3332-FB-4002 - ROUGHER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 03:09 |  | Lanser, Richard | 2021-04-05 23:10 | Closed | PL-00825 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 06:10 |  | Lanser, Richard | 2021-04-05 23:15 | Closed | PL-00861 | 3332-FB-4005 - ROUGHER SCAVENGER FLOTATION CELL 5 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 01:50 |  |  |  | Submitted | PL-00948 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Flange Management on vendor blinds, PD-0008-H14 not installed, Tighten up all manholes, Missing bolts on top of all rougher flotation cells, All 5 nitrogen valves not torqued
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 03:46 | 2021-02-01 03:46 |  | Lanser, Richard | 2021-04-05 23:16 | Closed | PL-00516 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Install burst disc | 2: B-Low
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 03:48 | 2021-02-01 03:48 |  | Lanser, Richard | 2021-04-05 23:16 | Closed | PL-00517 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | House keeping required | 2: B-Low
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 07:20 | 2021-02-01 07:19 |  | Lanser, Richard | 2021-04-05 23:17 | Closed | PL-00524 | 3332-FB-4003 - ROUGHER SCAVENGER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Install burst disc | 2: B-Low
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-25 00:10 | 2021-02-22 00:25 |  | Lanser, Richard | 2021-04-18 00:01 | Closed | PL-00791 | 3332-LD-4007 - ROUGHER SCAVENGER LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | SENSOR FLANGE CONNECTION | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-25 18:00 | 2021-02-22 02:35 |  | Lanser, Richard | 2021-04-18 00:01 | Closed | PL-00803 | 3332-VE-4003 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4003 | S1 - Stage 1 Construction Completion | Feed/Relief Conneciton | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-02-02 12:52 | 2021-01-31 12:51 |  | Lanser, Richard | 2021-04-16 21:09 | Closed | PL-00486 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Hold down bolts loose and not grouted | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-02-02 12:56 | 2021-01-31 12:56 |  | Lanser, Richard | 2021-04-16 21:10 | Closed | PL-00488 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Base plate anchor loose | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:09 | 2021-03-08 17:08 |  | Lanser, Richard | 2021-04-16 21:12 | Closed | PL-01108 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:14 | 2021-03-08 17:13 |  | Lanser, Richard | 2021-04-18 00:03 | Closed | PL-01110 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | Platform brace not installed | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:16 | 2021-03-08 17:15 |  | Lanser, Richard | 2021-04-17 06:38 | Closed | PL-01112 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:19 | 2021-03-08 17:18 |  | Lanser, Richard | 2021-04-16 21:12 | Closed | PL-01113 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 | 2021-04-13 02:07 | 2021-03-30 01:07 |  | Lanser, Richard | 2021-04-17 06:39 | Closed | PL-01391 | 3332-LIT-0146 - ROUGHER AREA SUMP 1 | S1 - Stage 1 Construction Completion | Transmitter requires mounted to flange prior to calibration and stage 3 commissioning. | 2: B-Low
B | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump | 2021-04-13 02:12 | 2021-03-30 01:11 |  | Lanser, Richard | 2021-04-17 06:39 | Closed | PL-01392 | 3332-LIT-0173 - ROUGHER AREA SUMP 2 | S1 - Stage 1 Construction Completion | Transmitter requires mounting to flange prior to stage 3 commissioning and calibrating | 2: B-Low
B | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-04-19 02:51 |  |  |  | Submitted | PL-01578 | 3332-DI-4009 - INTERMEDIATE THICKENER FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Bolts missing from lid
B | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-03 00:31 |  | Lanser, Richard | 2021-04-27 03:38 | Closed | PL-01419 | 3332-HP-4005 - REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | Leak test to be confirmed
B | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-03 00:44 |  | Lanser, Richard | 2021-04-27 03:39 | Closed | PL-01420 | 3332-HP-4005 - REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | feet need grouting
B | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-07 02:31 |  |  |  | Submitted | PL-01487 | 3332-SN-4003 - REGRIND MILL MEDIA SCREEN | S1 - Stage 1 Construction Completion | Install Guard
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-18 02:26 |  | Lanser, Richard | 2021-04-05 22:40 | Closed | PL-00625 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:19 |  | Lanser, Richard | 2021-04-05 22:45 | Closed | PL-00651 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:30 |  | Lanser, Richard | 2021-04-05 22:51 | Closed | PL-00654 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-21 06:31 |  | Lanser, Richard | 2021-04-05 22:58 | Closed | PL-00776 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 01:50 |  | Lanser, Richard | 2021-04-05 22:58 | Closed | PL-00794 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:21 |  | Lanser, Richard | 2021-04-05 22:58 | Closed | PL-00795 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:25 |  | Lanser, Richard | 2021-04-05 22:59 | Closed | PL-00797 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:27 |  | Lanser, Richard | 2021-04-05 22:59 | Closed | PL-00798 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:28 |  | Lanser, Richard | 2021-04-05 23:01 | Closed | PL-00799 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:32 |  | Lanser, Richard | 2021-04-05 23:01 | Closed | PL-00800 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 02:34 |  | Lanser, Richard | 2021-04-05 23:01 | Closed | PL-00801 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-19 05:09 |  | Lanser, Richard | 2021-04-27 03:39 | Closed | PL-01581 | 3332-LD-4008 - FIRST CLEANER CONCENTRATE LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | Blinds need fitting
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:21 |  | Lanser, Richard | 2021-04-05 22:54 | Closed | PL-00672 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:35 |  | Lanser, Richard | 2021-04-05 22:55 | Closed | PL-00675 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:59 |  | Lanser, Richard | 2021-04-05 22:56 | Closed | PL-00678 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-20 00:21 |  | Lanser, Richard | 2021-04-05 22:57 | Closed | PL-00685 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:38 |  | Lanser, Richard | 2021-04-05 23:02 | Closed | PL-00805 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:39 |  | Lanser, Richard | 2021-04-05 23:02 | Closed | PL-00806 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:40 |  | Lanser, Richard | 2021-04-05 23:02 | Closed | PL-00808 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:41 |  | Lanser, Richard | 2021-04-05 23:03 | Closed | PL-00810 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:43 |  | Lanser, Richard | 2021-04-05 23:03 | Closed | PL-00811 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:46 |  | Lanser, Richard | 2021-04-05 23:04 | Closed | PL-00812 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:48 |  | Lanser, Richard | 2021-04-05 23:04 | Closed | PL-00813 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 02:49 |  | Lanser, Richard | 2021-04-05 23:04 | Closed | PL-00814 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 04:43 |  | Lanser, Richard | 2021-04-05 22:52 | Closed | PL-00660 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 21:10 |  | Lanser, Richard | 2021-04-05 22:53 | Closed | PL-00669 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Burst disc to be installed prior to wet commissioning
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 02:50 |  | Lanser, Richard | 2021-04-05 23:05 | Closed | PL-00815 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 02:51 |  | Lanser, Richard | 2021-04-05 23:05 | Closed | PL-00816 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 02:52 |  | Lanser, Richard | 2021-04-05 23:06 | Closed | PL-00817 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Grease to all points
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 02:53 |  | Lanser, Richard | 2021-04-05 23:07 | Closed | PL-00818 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Launders need inspection
B | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells | 2021-04-16 03:37 | 2021-04-02 02:37 |  |  |  | Originated | PL-01414 | 3332-LIT-0508 - CLEANER SCAV. CONC.TO THIRD CLEANER FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | LIT requires flange to be mounted prior to wet commissioning | 2: B-Low
B | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-24 05:35 |  |  |  | Submitted | PL-01665 | 3332-PU-4028 - CLEANER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Needs completing
B | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:22 |  |  |  | Submitted | PL-01612 | 3332-DI-4005 - THIRD CLEANER DISTRIBUTOR | S1 - Stage 1 Construction Completion | Needs completing
B | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:32 |  |  |  | Submitted | PL-01615 | 3332-HP-4006 - THIRD CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | works incomplete
B | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-02-02 14:14 | 2021-01-31 14:13 |  | Lanser, Richard | 2021-04-21 11:48 | Closed | PL-00495 | 3332-PU-4024 - THIRD CLEANER FEED PUMP | S1 - Stage 1 Construction Completion | Base plate anchor loose | 1: A-High
B | Item Incomplete | MECH | CS0C - Raw Water | CS0C-02 - Raw Water Tank | 2021-03-10 23:53 | 2021-02-07 03:59 |  | Lanser, Richard | 2021-04-17 01:24 | Closed | PL-00551 | 3335-LIT-0856 - RAW WATER TANK | S1 - Stage 1 Construction Completion | Needs to be bolted to flange on tank. | 2: B-Low
B | Item Incomplete | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-14 00:44 | 2021-02-12 00:43 |  | Lanser, Richard | 2021-02-17 21:08 | Closed | PL-00569 | 3335-PK-4012 - FIRE WATER PUMP VENDOR PACKAGE | S1 - Stage 1 Construction Completion | Complete bolt up of pipe work | 1: A-High
B | Item Incomplete | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:39 |  | Lanser, Richard | 2021-04-18 01:37 | Closed | PL-00892 | 3335-150-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Attach a blank & valve to ASC tie in points
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-04-15 02:49 |  |  |  | Submitted | PL-01548 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S2 - Stage 2 Pre Commissioning | Install Vendor supplied calibration cylinders to suction of each pump (5 items)
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-01-29 20:31 | 2021-01-27 20:29 |  | Nutt, Richard | 2021-04-14 03:19 | Closed | PL-00358 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S1 - Stage 1 Construction Completion | Powder transfer tube not installed needs to be re-worked | 1: A-High
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-09 22:46 | 2021-01-26 22:45 |  | Nutt, Richard | 2021-04-14 03:21 | Closed | PL-00341 | 3334-MX-4002 - FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Drawings & Schedules to be completed. | 2: B-Low
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-09 22:52 | 2021-01-26 22:52 |  | Nutt, Richard | 2021-04-14 03:22 | Closed | PL-00342 | 3334-MX-4003 - FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Drawings & Schedules to be completed. | 2: B-Low
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-09 22:57 | 2021-01-26 22:57 |  | Nutt, Richard | 2021-04-14 03:22 | Closed | PL-00343 | 3334-MX-4004 - FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Drawings & Schedules to be completed. | 2: B-Low
B | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-03 - Flocculant area sump |  | 2021-04-22 04:10 |  | Lanser, Richard | 2021-04-27 03:39 | Closed | PL-01630 | 3334-PU-4056 - FLOCCULANT AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Pump to be installed on C channel
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-29 11:29 |  | Lanser, Richard | 2021-04-17 06:37 | Closed | PL-00362 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Install pipe or blind flange to Hopper Box
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-02-21 02:47 |  | Lanser, Richard | 2021-04-17 06:37 | Closed | PL-00722 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | leak test not complete
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-01-31 10:07 | 2021-01-29 10:06 |  | Lanser, Richard | 2021-04-16 21:08 | Closed | PL-00360 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Complete pipe work to under flow cone | 1: A-High
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 00:42 |  | Lanser, Richard | 2021-04-21 11:14 | Closed | PL-01592 | 3331-SA-4001A - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | check outlets
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 01:17 |  |  |  | Submitted | PL-01596 | 3331-SA-4001C - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | lines not complete
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 01:21 |  |  |  | Submitted | PL-01597 | 3331-SA-4001A - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Needs flange management
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 03:00 |  |  |  | Submitted | PL-01607 | 3331-CH-4009 - CONCENTRATE THICKENER SCREEN UNDERPAN | S1 - Stage 1 Construction Completion | Bolts missing
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 04:20 |  | Lanser, Richard | 2021-04-05 18:53 | Closed | PL-00739 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Needs flange management and H14 frother outlet needs fitting
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 04:25 |  | Lanser, Richard | 2021-03-09 09:34 | Closed | PL-00743 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | To be confirmed at wet commissioning
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 05:44 |  | Lanser, Richard | 2021-03-05 18:15 | Closed | PL-00769 | 3331-PU-4154 - CONCENTRATE THICKENER FROTH OVERFLOW PUMP | S1 - Stage 1 Construction Completion | Grout to be completed
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 05:54 |  | Lanser, Richard | 2021-04-16 07:35 | Closed | PL-00770 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Grout to be completed
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 05:57 |  | Lanser, Richard | 2021-04-16 07:35 | Closed | PL-00771 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Access platform not installed
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-28 06:55 |  | Lanser, Richard | 2021-04-16 07:36 | Closed | PL-00965 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Bolt out and seal lid
B | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-02-23 05:36 | 2021-02-21 05:34 |  | Lanser, Richard | 2021-04-16 21:10 | Closed | PL-00765 | 3331-PU-4154 - CONCENTRATE THICKENER FROTH OVERFLOW PUMP | S1 - Stage 1 Construction Completion | Alignment tags need removing before pump rotation | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-27 03:47 |  | Liang, Dennis | 2021-03-18 01:45 | Closed | PL-00940 | 3331-160-PD-0002-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe installation / inlet block due to water leak test feed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-03-23 01:42 |  |  |  | Submitted | PL-01356 | 3331-PU-4005 - COPPER CONCENTRATE CHARGING PUMP | S1 - Stage 1 Construction Completion | Install gland water piping to pump
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 02:17 |  | Davies, Jesse | 2021-03-18 03:13 | Closed | PL-00715 | 3331-280-PD-0007-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 02:17 |  | Davies, Jesse | 2021-03-18 02:19 | Closed | PL-00716 | 3331-280-PD-0007-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 04:02 |  |  |  | Submitted | PL-00730 | 3331-80-CSL-0060-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe supports / hangers / flange supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 04:03 |  | Davies, Jesse | 2021-03-18 02:16 | Closed | PL-00732 | 3331-80-CSL-0060-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-21 04:36 |  | Davies, Jesse | 2021-03-18 04:00 | Closed | PL-00746 | 3331-150-CSL-0030-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-28 04:15 |  | Liang, Dennis | 2021-03-18 00:05 | Closed | PL-00959 | 3331-160-PD-0006-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install Knife Valve
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-01-21 06:30 | 2021-01-19 06:29 |  | Lanser, Richard | 2021-03-15 21:32 | Closed | PL-00201 | 3331-160-CSL-0011-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Flange manage F1 & F2 | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-01-21 06:32 | 2021-01-19 06:32 |  |  |  | Submitted | PL-00202 | 3331-160-CSL-0011-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install supports S8,S9 & S11 | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-01-21 06:52 | 2021-01-19 06:52 |  | Lanser, Richard | 2021-03-15 21:32 | Closed | PL-00209 | 3331-160-CSL-0011-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete flange management | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-02 06:46 | 2021-01-19 06:45 |  |  |  | Originated | PL-00207 | 3331-160-CSL-0010-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install supports- S9 & S10 | 2: B-Low
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 02:27 |  | Liang, Dennis | 2021-03-18 00:08 | Closed | PL-00718 | 3331-100-CSL-0021-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:12 |  | Liang, Dennis | 2021-03-18 00:07 | Closed | PL-00736 | 3331-150-PWL-0019-H14 - PWL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:13 |  | Liang, Dennis | 2021-03-18 00:07 | Closed | PL-00737 | 3331-150-PWL-0019-H14 - PWL Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:30 |  | Liang, Dennis | 2021-03-18 00:16 | Closed | PL-00745 | 3331-150-CSL-0062-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | flange management required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:56 |  | Liang, Dennis | 2021-03-18 00:13 | Closed | PL-00750 | 3331-160-CSL-0063-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:57 |  |  |  | Submitted | PL-00751 | 3331-160-CSL-0063-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-28 03:28 |  |  |  | Submitted | PL-00956 | 3331-110-CSL-0050-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install U-bolts / Pipe Hangers / Flange Supports and pipe alignment
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-28 04:13 |  |  |  | Originated | PL-00958 |  | S1 - Stage 1 Construction Completion | Install spool (currently block by construction scaffolding)
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-02-20 03:49 | 2021-02-18 03:48 |  | Liang, Dennis | 2021-03-18 00:16 | Closed | PL-00636 | 3331-150-CSL-0062-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Dummy leg not installed. Pipe support to be installed. Ubolts to be installed. | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 05:35 | 2021-01-26 05:33 |  | Lanser, Richard | 2021-03-28 16:47 | Closed | PL-00306 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Pulsation clamps S12 not installed | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 06:05 | 2021-01-26 06:05 |  | Fuller, Lachlan | 2021-03-29 00:54 | Closed | PL-00313 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Actuated valves not tested yet | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 20:20 | 2021-01-26 20:20 |  | Fuller, Lachlan | 2021-03-29 00:55 | Closed | PL-00322 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Actuated valves not tested yet | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 21:59 | 2021-01-26 21:58 |  | Lanser, Richard | 2021-03-28 17:15 | Closed | PL-00331 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Drain and knock pot not installed | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:01 | 2021-01-26 22:01 |  | Fuller, Lachlan | 2021-03-18 23:33 | Closed | PL-00333 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Drain and knock pot not installed | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:02 | 2021-01-26 22:02 |  | Fuller, Lachlan | 2021-03-29 00:55 | Closed | PL-00334 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Actuated valves not tested yet | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:04 | 2021-01-26 22:03 |  | Lanser, Richard | 2021-03-28 03:10 | Closed | PL-00335 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Drain not installed F1 to be torqued up | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:06 | 2021-01-26 22:05 |  | Fuller, Lachlan | 2021-03-26 21:10 | Closed | PL-00336 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Drain and knock pot not installed | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:12 | 2021-01-26 22:06 |  | Fuller, Lachlan | 2021-03-26 21:10 | Closed | PL-00337 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Drain and knock pot not installed or supports and u-bolts | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 22:59 | 2021-01-26 22:58 |  | Fuller, Lachlan | 2021-03-29 00:56 | Closed | PL-00345 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Actuated valves not tested yet | 1: A-High
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-03-16 04:58 |  | Nutt, Richard | 2021-04-13 22:58 | Closed | PL-01225 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Install tubing support clamp on pulsation dampener
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-03-16 04:58 |  | Polkinghorne, Scott | 2021-04-13 12:58 | Closed | PL-01225 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Install tubing support clamp on pulsation dampener
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-02-28 23:42 |  | Lanser, Richard | 2021-04-05 19:15 | Closed | PL-00977 | 3331-80-PD-0056-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Install Pipe Supports and U-bolts
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 21:13 |  | Lanser, Richard | 2021-04-16 07:36 | Closed | PL-00995 | 3331-80-PD-0056-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Install Drain Valve / MINSUP
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 21:18 |  | Lanser, Richard | 2021-04-16 07:36 | Closed | PL-00996 | 3331-80-PD-0058-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Install Drain Valve / MINSUP
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 21:19 |  | Lanser, Richard | 2021-04-16 07:36 | Closed | PL-00997 | 3331-80-PD-0060-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Install Drain Valve / MINSUP
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-08 03:34 |  | Lanser, Richard | 2021-04-17 06:52 | Closed | PL-01078 | 3331-90-PD-0061-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-03-15 05:28 | 2021-03-13 05:27 |  | Lanser, Richard | 2021-04-23 12:34 | Closed | PL-01199 | 3331-90-PD-0059-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install U-bolts / Install Flange Supports and pipe alignment | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-01 - Rougher Conditioning Metallurgical Sampler |  | 2021-04-04 01:56 |  |  |  | Submitted | PL-01455 | 3332-90-CSL-0104-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe Hanger
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-01 - Rougher Conditioning Metallurgical Sampler |  | 2021-04-21 01:39 |  |  |  | Submitted | PL-01598 | 3332-SA-4002B - ROUGHER FLOTATION FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Piping incomplete
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-02-22 04:26 |  |  |  | Submitted | PL-00842 | 3332-50-PWH-0054-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | PIPE SUPPORT INSTALL
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-02-28 23:02 |  |  |  | Submitted | PL-00975 | 3332-350-MCS-0003-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Install Pipe Support and U-bolts
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-03-01 04:08 |  |  |  | Submitted | PL-00988 | 3332-150-MCS-0004-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Install Pipe Supports and U-bolts
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-03-02 00:48 |  |  |  | Submitted | PL-00999 | 3332-160-MCS-0111-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Install Pipe Hangers
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:10 |  |  |  | Originated | PL-01648 | 3332-400-PD-0003-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed on overflow pipe 3332-400-PD-0003-H14
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:22 |  |  |  | Originated | PL-01651 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | 3332-50-PWH-0037-C6 missing spec blind
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:28 |  |  |  | Originated | PL-01654 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:31 |  |  |  | Originated | PL-01656 | 3332-200-MCS-0006-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | 3332-200-MCS-0006-H14 (interconnecting pipe between tanks) has some bolts with insufficient threads exposed and require replacing
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:34 |  |  |  | Originated | PL-01658 | 3332-150-MCS-0004-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Pipe hangers to be installed on 3332-150-MCS-0004-R5
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:37 |  |  |  | Originated | PL-01661 | 3332-150-MCS-0004-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | 3332-150-MCS-0004-R5 - support on horizontal line to Jameson Cell to be fitted with 300mm cable ladder. Refer WOR-MOLY-GCOR-012483
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-03 02:34 |  |  |  | Submitted | PL-01421 | 3332-90-MCS-0258-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-01-30 22:27 |  | Lanser, Richard | 2021-04-19 07:05 | Closed | PL-00459 | 3332-25-PWH-0007-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Supports not installed
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-01-31 02:48 |  | Lanser, Richard | 2021-04-06 18:46 | Closed | PL-00468 | 3332-25-PWH-0244-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-01-31 03:16 |  | Lanser, Richard | 2021-04-06 18:53 | Closed | PL-00479 | 3332-25-PWH-0247-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-20 04:52 |  | Liang, Dennis | 2021-02-25 21:31 | Closed | PL-00690 | 3332-110-VGN-0096-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-23 20:45 |  | Nutt, Richard | 2021-02-27 05:54 | Closed | PL-00878 | 3332-110-VGN-0096-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Spectacle Blind and Valve need to swap around (incorrect location)
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-25 00:38 |  | Lanser, Richard | 2021-04-19 07:12 | Closed | PL-00905 | 3332-160-PD-0010-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Spool Install
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-03-04 02:43 |  | Lanser, Richard | 2021-04-19 07:23 | Closed | PL-01008 | 3332-160-PD-0010-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Flange managment required
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-03-04 02:44 |  | Lanser, Richard | 2021-04-19 07:25 | Closed | PL-01009 | 3332-160-PD-0010-H14 - PD Process Line | S1 - Stage 1 Construction Completion | pipe supports required
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 16:09 | 2021-01-30 16:08 |  | Lanser, Richard | 2021-04-19 21:37 | Closed | PL-00415 | 3332-80-NG-0029-C4 - NG Process Line | S1 - Stage 1 Construction Completion | DN25 threaded spool not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 16:21 | 2021-01-30 16:21 |  | Lanser, Richard | 2021-04-19 21:37 | Closed | PL-00417 | 3332-80-NG-0030-C4 - NG Process Line | S1 - Stage 1 Construction Completion | DN25 threaded spool not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 16:30 | 2021-01-30 16:29 |  | Lanser, Richard | 2021-04-19 22:01 | Closed | PL-00419 | 3332-80-NG-0030-C4 - NG Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 16:45 | 2021-01-30 16:45 |  | Lanser, Richard | 2021-04-19 22:01 | Closed | PL-00421 | 3332-160-PD-0006-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:07 | 2021-01-30 17:07 | 2021-04-18 22:57 |  |  | Rejected | PL-00423 | 3332-160-PD-0007-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:08 | 2021-01-30 17:08 |  |  |  | Submitted | PL-00424 | 3332-160-PD-0007-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:13 | 2021-01-30 17:12 |  |  |  | Submitted | PL-00425 | 3332-160-PD-0009-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:13 | 2021-01-30 17:13 |  |  |  | Submitted | PL-00426 | 3332-160-PD-0009-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:43 | 2021-01-30 17:43 |  |  |  | Submitted | PL-00428 | 3332-160-PD-0008-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:44 | 2021-01-30 17:44 |  |  |  | Submitted | PL-00429 | 3332-160-PD-0008-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:54 | 2021-01-30 17:54 |  | Lanser, Richard | 2021-04-19 22:02 | Closed | PL-00430 | 3332-110-VGN-0005-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 17:57 | 2021-01-30 17:57 |  | Lanser, Richard | 2021-04-19 22:02 | Closed | PL-00431 | 3332-110-VGN-0006-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 18:02 | 2021-01-30 18:02 |  | Lanser, Richard | 2021-04-19 22:02 | Closed | PL-00433 | 3332-110-VGN-0007-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 18:07 | 2021-01-30 18:07 |  | Lanser, Richard | 2021-04-19 22:03 | Closed | PL-00434 | 3332-110-VGN-0008-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 18:11 | 2021-01-30 18:10 |  | Lanser, Richard | 2021-04-19 22:03 | Closed | PL-00435 | 3332-110-VGN-0009-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 18:41 | 2021-01-30 18:41 |  | Lanser, Richard | 2021-04-19 22:03 | Closed | PL-00441 | 3332-25-PWH-0006-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 21:19 | 2021-01-30 21:19 |  | Lanser, Richard | 2021-04-16 21:08 | Closed | PL-00446 | 3332-80-NG-0026-C4 - NG Process Line | S1 - Stage 1 Construction Completion | DN25 Threaded spool not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 21:35 | 2021-01-30 21:34 |  | Lanser, Richard | 2021-04-19 22:03 | Closed | PL-00448 | 3332-80-NG-0026-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 21:46 | 2021-01-30 21:45 |  | Lanser, Richard | 2021-04-16 21:09 | Closed | PL-00450 | 3332-80-NG-0027-C4 - NG Process Line | S1 - Stage 1 Construction Completion | DN25 Threaded spool not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 21:49 | 2021-01-30 21:48 |  | Lanser, Richard | 2021-04-19 22:04 | Closed | PL-00452 | 3332-80-NG-0027-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 21:59 | 2021-01-30 21:58 |  | Lanser, Richard | 2021-04-16 21:09 | Closed | PL-00454 | 3332-80-NG-0028-C4 - NG Process Line | S1 - Stage 1 Construction Completion | DN25 Threaded spool not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 22:04 | 2021-01-30 22:03 |  | Lanser, Richard | 2021-04-19 22:04 | Closed | PL-00456 | 3332-80-NG-0028-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 02:34 | 2021-01-31 02:34 |  | Lanser, Richard | 2021-04-19 22:05 | Closed | PL-00464 | 3332-25-PWH-0116-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 02:36 | 2021-01-31 02:36 |  | Lanser, Richard | 2021-04-19 22:05 | Closed | PL-00465 | 3332-25-PWH-0116-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 02:56 | 2021-01-31 02:55 |  | Lanser, Richard | 2021-04-19 22:06 | Closed | PL-00471 | 3332-25-PWH-0245-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:03 | 2021-01-31 03:02 |  | Lanser, Richard | 2021-04-19 22:06 | Closed | PL-00474 | 3332-25-PWH-0246-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:05 | 2021-01-31 03:03 |  | Lanser, Richard | 2021-04-19 22:06 | Closed | PL-00475 | 3332-25-PWH-0246-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:15 | 2021-01-31 03:14 |  | Lanser, Richard | 2021-04-19 22:06 | Closed | PL-00478 | 3332-25-PWH-0247-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:31 | 2021-01-31 03:31 |  | Lanser, Richard | 2021-04-19 22:07 | Closed | PL-00483 | 3332-25-PWH-0248-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 03:32 | 2021-01-31 03:32 |  | Lanser, Richard | 2021-04-19 22:07 | Closed | PL-00484 | 3332-25-PWH-0248-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-11 18:40 | 2021-01-30 16:05 |  | Lanser, Richard | 2021-04-19 22:08 | Closed | PL-00414 | 3332-80-NG-0029-C4 - NG Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 2: B-Low
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-03-26 05:20 |  | Lanser, Richard | 2021-04-05 19:16 | Closed | PL-01382 | 3332-110-MCS-0135-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Install Minsup
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-03-26 05:20 |  | Lanser, Richard | 2021-04-05 19:17 | Closed | PL-01383 | 3332-110-MCS-0135-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-04-24 04:39 |  |  |  | Submitted | PL-01662 | 3332-110-VGN-0100-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Spec blind and flange managmant
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:07 |  |  |  | Submitted | PL-01637 | 3332-80-PD-0054-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Install fittings to connect flexi pip
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 | 2021-04-11 21:56 | 2021-03-11 20:52 |  |  |  | Submitted | PL-01142 | 3332-80-PD-0054-R5 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required | 1: A-High
B | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump |  | 2021-04-11 05:09 |  |  |  | Submitted | PL-01519 | 3334-25-NAHS-0048-S6 - NAHS Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:12 |  |  |  | Submitted | PL-01161 | 3332-50-MCS-0073-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:20 |  | Lanser, Richard | 2021-04-15 22:49 | Closed | PL-01163 | 3332-50-MCS-0074-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:26 |  |  |  | Submitted | PL-01165 | 3332-63-MCS-0145-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:35 |  |  |  | Submitted | PL-01169 | 3332-63-MCS-0148-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:41 |  |  |  | Submitted | PL-01171 | 3332-50-MCS-0262-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:51 |  |  |  | Submitted | PL-01172 | 3332-63-MCS-0266-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:05 |  |  |  | Submitted | PL-01174 | 3332-63-MCS-0267-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:10 |  |  |  | Submitted | PL-01176 | 3332-63-MCS-0271-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:15 |  |  |  | Submitted | PL-01178 | 3332-50-MCS-0279-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:23 |  |  |  | Submitted | PL-01181 | 3332-100-PD-0050-R5 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:35 |  |  |  | Submitted | PL-01184 | 3332-50-PWH-0008-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:41 |  |  |  | Submitted | PL-01187 | 3332-25-PWH-0081-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:47 |  | Lanser, Richard | 2021-04-03 21:28 | Closed | PL-01189 | 3332-25-PWH-0083-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:48 |  | Lanser, Richard | 2021-04-03 21:28 | Closed | PL-01190 | 3332-25-PWH-0083-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:54 |  |  |  | Submitted | PL-01192 | 3332-200-PWL-0026-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-04-19 02:36 |  |  |  | Submitted | PL-01575 | 3332-DI-4009 - INTERMEDIATE THICKENER FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | pipe work needs connecting
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-04-19 02:44 |  |  |  | Submitted | PL-01576 | 3332-DI-4009 - INTERMEDIATE THICKENER FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Pipe missing
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-05 04:51 |  | Lanser, Richard | 2021-03-10 10:57 | Closed | PL-01013 | 3332-100-PWL-0009-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-05 04:56 |  | Lanser, Richard | 2021-04-16 07:37 | Closed | PL-01015 | 3332-80-PWL-0013-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-05 04:57 |  | Lanser, Richard | 2021-04-16 07:37 | Closed | PL-01016 | 3332-80-PWL-0013-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Pipe supports/ubolts to be installed
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-04 06:49 |  |  |  | Submitted | PL-01474 | 3332-50-PWH-0042-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | 1" CAP
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-09 13:37 | 2021-03-06 16:36 |  |  |  | Submitted | PL-01036 | 3332-50-MCS-0280-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-09 15:20 | 2021-03-06 18:19 |  |  |  | Submitted | PL-01041 | 3332-160-MCS-0032-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 05:46 |  |  |  | Submitted | PL-01523 | 3332-160-PD-0014-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 05:59 |  |  |  | Submitted | PL-01525 | 3332-160-PD-0015-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install U-bolts / Pipe Hangers
B | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-26 05:22 |  |  |  | Submitted | PL-01670 | 3332-160-PD-0013-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed
B | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 22:43 |  |  |  | Submitted | PL-01413 | 3332-90-VGN-0021-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | change studs out for correct length stud
B | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:36 |  |  |  | Submitted | PL-01395 | 3332-90-VGN-0018-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flange managment to be completed
B | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:46 |  |  |  | Submitted | PL-01397 | 3332-90-VGN-0017-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flange managment to be completed
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-13 01:01 |  |  |  | Submitted | PL-01535 | 3332-90-PD-0146-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe support and hanger installation
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:13 |  |  |  | Submitted | PL-01674 | 3332-80-PD-0022-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Barb flange to be installed (awaiting delivery)
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:17 |  |  |  | Submitted | PL-01675 | 3332-PU-4028 - CLEANER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Misup couplings to be replaced with gal type
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:18 |  |  |  | Submitted | PL-01676 | 3332-PU-4028 - CLEANER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Sump to be cleaned and guarding to be installed
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:18 |  |  |  | Submitted | PL-01677 | 3332-110-VGN-0104-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Vent line 3332-110-VGN-0104-H14 has plastice plug installed after isolation valve. To be replaced with CS plug.
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:19 |  |  |  | Submitted | PL-01678 | 3332-80-PD-0022-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Vent line has sections of transport material (carpet , etc) on line. To be removed.
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:20 |  |  |  | Submitted | PL-01679 | 3332-80-PD-0022-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Line 3332-80-PD-0022-R5 HDPE section is touching another pipe and rubbing against cable ladder. To be rectified.
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-27 05:20 |  |  |  | Submitted | PL-01680 | 3332-80-PD-0022-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Line 3332-80-PD-0022-R5 HDPE section pipe supprots to be installed.)
B | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 02:28 |  |  |  | Submitted | PL-01626 | 3332-SA-4004 - CLEANER IN-STREAM ANALYSER | S1 - Stage 1 Construction Completion | Piping incomplete
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:21 | 2021-01-29 16:20 |  | Gayler, Randal | 2021-03-16 01:08 | Closed | PL-00373 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Blind flange not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:22 | 2021-01-29 16:22 |  | Gayler, Randal | 2021-03-16 01:09 | Closed | PL-00374 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Studs not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:24 | 2021-01-29 16:24 |  | Gayler, Randal | 2021-03-16 01:10 | Closed | PL-00375 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Blind flange not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:25 | 2021-01-29 16:25 |  | Gayler, Randal | 2021-03-16 01:10 | Closed | PL-00376 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Studs not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:49 | 2021-01-29 16:48 |  | Gayler, Randal | 2021-03-03 17:33 | Closed | PL-00377 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | 20mm ball valve not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:50 | 2021-01-29 16:49 |  | Gayler, Randal | 2021-03-03 17:34 | Closed | PL-00378 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Blind flange not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-31 16:51 | 2021-01-29 16:50 |  | Gayler, Randal | 2021-03-16 01:11 | Closed | PL-00379 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Studs not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 04:33 | 2021-01-18 04:33 |  | Gayler, Randal | 2021-03-15 05:46 | Closed | PL-00176 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install blind after blow out is complete | 2: B-Low
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 07:22 | 2021-01-30 07:22 |  | Gayler, Randal | 2021-03-16 01:11 | Closed | PL-00406 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Blind flange not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 07:23 | 2021-01-30 07:23 |  | Gayler, Randal | 2021-03-16 01:12 | Closed | PL-00407 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Studs not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 08:39 | 2021-01-30 08:39 |  |  |  | Submitted | PL-00410 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | 20mm ball valve not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 08:41 | 2021-01-30 08:40 |  | Liang, Dennis | 2021-03-18 00:55 | Closed | PL-00411 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Blind flange not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 08:42 | 2021-01-30 08:41 |  | Liang, Dennis | 2021-03-18 00:56 | Closed | PL-00412 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Studs not installed | 1: A-High
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:05 |  | Lanser, Richard | 2021-03-30 22:55 | Closed | PL-01237 | 3335-50-IA-0055-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:30 | 2021-01-18 02:29 |  |  |  | Originated | PL-00165 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all U-bolts | 2: B-Low
B | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:12 | 2021-01-27 09:12 |  |  |  | Submitted | PL-00353 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all supports and U-bolts as per design | 2: B-Low
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-21 22:53 |  |  |  | Submitted | PL-00784 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Spool 3335-RWA-0001-C5-01 cannont be installed due to temp water line being attached to 3335-RWU-0021-H15-01
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-21 22:57 |  | Lanser, Richard | 2021-04-05 19:10 | Closed | PL-00786 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-24 17:51 |  | Lanser, Richard | 2021-04-05 19:11 | Closed | PL-00882 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install Drain and valve
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-24 17:58 |  | Lanser, Richard | 2021-04-05 19:13 | Closed | PL-00886 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Complete Flange management on subsystem
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed | 2021-03-10 23:54 | 2021-02-20 21:23 |  |  |  | Submitted | PL-00692 | 3335-160-RWU-0021-H15 - RWA Process Line | S1 - Stage 1 Construction Completion | Temporary line to be removed | 2: B-Low
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 00:46 |  | Lanser, Richard | 2021-04-06 20:30 | Closed | PL-00710 | 3335-200-FWA-0001-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 00:47 |  | Lanser, Richard | 2021-04-06 20:42 | Closed | PL-00711 | 3335-200-FWA-0001-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 21:23 |  | Liang, Dennis | 2021-03-19 19:15 | Closed | PL-00781 | 3335-100-FWA-0003-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 21:24 |  | Lanser, Richard | 2021-04-17 01:23 | Closed | PL-00782 | 3335-100-FWA-0003-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-23 02:17 |  |  |  | Submitted | PL-00865 | 3335-150-FWA-0004-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | Booster pipe to be fabricated and installed
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 04:25 |  | Lanser, Richard | 2021-04-05 19:00 | Closed | PL-00742 | 3335-50-RWA-0024-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Flange Management Required
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 04:58 |  |  |  | Submitted | PL-00752 | 3335-100-RWA-0010-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Flange Management Required F3
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 04:59 |  | Lanser, Richard | 2021-04-05 19:01 | Closed | PL-00753 | 3335-100-RWA-0010-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:11 |  | Lanser, Richard | 2021-04-05 19:01 | Closed | PL-00758 | 3335-100-RWA-0004-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Flange Management Required
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:26 |  | Lanser, Richard | 2021-04-05 19:02 | Closed | PL-00762 | 3335-100-RWA-0005-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:35 |  | Lanser, Richard | 2021-04-05 19:02 | Closed | PL-00766 | 3335-100-RWA-0006-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:41 |  | Lanser, Richard | 2021-04-05 19:03 | Closed | PL-00768 | 3335-100-RWA-0006-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Spool 3335-RWA-0006-C5-02 Incomplete Missing Valve
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 06:01 |  | Lanser, Richard | 2021-04-05 19:10 | Closed | PL-00773 | 3335-100-RWA-0007-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:06 |  | Lanser, Richard | 2021-04-05 19:14 | Closed | PL-00898 | 3335-100-RWA-0004-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install Drain valves in subsystem
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:20 |  | Lanser, Richard | 2021-04-05 19:14 | Closed | PL-00902 | 3335-100-RWA-0010-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install missing pipe work
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-03-28 22:47 |  | Lanser, Richard | 2021-04-05 19:18 | Closed | PL-01389 | 3335-100-RWA-0257-C5 - Raw water header | S1 - Stage 1 Construction Completion | flange managment to be completed
B | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header | 2021-02-14 15:43 | 2021-02-13 02:42 |  | Gayler, Randal | 2021-02-13 10:35 | Closed | PL-00572 | 3335-100-RWA-0008-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Flange managment required | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-19 20:52 |  | Lanser, Richard | 2021-04-06 19:20 | Closed | PL-00666 | 3335-25-ASC-0002-C6 - ASC Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-23 02:20 |  | Lanser, Richard | 2021-04-18 03:33 | Closed | PL-00866 | 3335-100-PWL-0008-C5 - PWL Process Line | S2 - Stage 2 Pre Commissioning | Install Drain and valve
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-20 04:48 | 2021-02-18 04:47 |  | Lanser, Richard | 2021-04-18 03:34 | Closed | PL-00641 | 3335-25-PWH-0341-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:25 |  | Davies, Jesse | 2021-03-08 23:23 | Closed | PL-00907 | 3332-50-PWH-0001-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:29 |  |  |  | Submitted | PL-00909 | 3332-50-PWH-0001-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Install blind F6
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:31 | 2021-04-23 01:09 |  |  | Rejected | PL-00910 | 3332-50-PWH-0001-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:44 |  |  |  | Submitted | PL-00911 | 3332-80-PWH-0031-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Install U-bolts and check for pipe support clash in grid mesh floor penetration
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:46 |  |  |  | Submitted | PL-00912 | 3332-80-PWH-0031-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:47 | 2021-04-23 01:09 |  |  | Rejected | PL-00913 | 3332-80-PWH-0031-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 06:00 | 2021-04-23 01:09 |  |  | Rejected | PL-00915 | 3332-25-PWH-0356-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 19:55 |  |  |  | Submitted | PL-00917 | 3332-50-PWH-0215-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange Management
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 20:13 |  |  |  | Submitted | PL-00920 | 3332-25-PWH-0319-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | SP ITEM 4
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 21:35 |  |  |  | Submitted | PL-00923 | 3332-50-PWH-0324-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 07:15 | 2021-03-06 10:13 |  |  |  | Submitted | PL-01023 | 3332-50-PWH-0037-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Item #7 on Iso not installed. Spec blind. | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 07:16 | 2021-03-06 10:15 |  |  |  | Submitted | PL-01024 | 3332-50-PWH-0037-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 08:01 | 2021-03-06 11:00 |  |  |  | Submitted | PL-01027 | 3332-50-PWH-0038-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 08:02 | 2021-03-06 11:01 |  | Davies, Jesse | 2021-03-08 23:23 | Closed | PL-01028 | 3332-50-PWH-0038-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-02-23 02:15 |  |  |  | Submitted | PL-00864 | 3331-25-PWH-0353-C6-TI-ET - PWH Process Line | S2 - Stage 2 Pre Commissioning | Additional Scope
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:20 |  |  |  | Submitted | PL-01219 | 3332-80-PWH-0373-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Flange Management
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-02-19 22:53 |  | Lanser, Richard | 2021-04-16 07:34 | Closed | PL-00683 |  | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-04-14 05:09 |  |  |  | Submitted | PL-01543 | 3335-25-PWH-0310-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe Supports Required
B | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-02-20 03:14 | 2021-02-18 03:13 |  |  |  | Submitted | PL-00631 | 3332-100-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | U-bolt not installed | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 03:52 |  | Lanser, Richard | 2021-04-06 18:20 | Closed | PL-00393 | 3334-15-FLOC-0044-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 04:30 |  | Lanser, Richard | 2021-04-06 18:20 | Closed | PL-00400 | 3334-15-FLOC-0042-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-01 00:50 | 2021-01-30 00:49 |  | Lanser, Richard | 2021-03-09 06:19 | Closed | PL-00381 | 3334-50-FLOC-0046-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-01 00:51 | 2021-01-30 00:51 |  | Lanser, Richard | 2021-03-09 06:23 | Closed | PL-00382 | 3334-50-FLOC-0046-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-01 01:00 | 2021-01-30 01:00 |  | Lanser, Richard | 2021-03-09 06:17 | Closed | PL-00384 | 3334-50-FLOC-0047-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-01 01:31 | 2021-01-30 01:31 |  | Lanser, Richard | 2021-03-09 06:16 | Closed | PL-00385 | 3334-50-FLOC-0047-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-01 04:17 | 2021-01-30 04:16 |  | Lanser, Richard | 2021-03-09 06:24 | Closed | PL-00395 | 3334-15-FLOC-0045-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-05 22:59 | 2021-02-03 22:59 |  | Lanser, Richard | 2021-03-09 06:14 | Closed | PL-00526 | 3334-50-FLOC-0002-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 00:34 | 2021-02-04 00:34 |  | Lanser, Richard | 2021-03-09 06:25 | Closed | PL-00531 | 3334-25-FLOC-0003-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 01:48 | 2021-02-04 01:47 |  | Lanser, Richard | 2021-03-09 06:18 | Closed | PL-00539 | 3334-40-FLOC-0048-C3 - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-03-04 21:58 |  | Lanser, Richard | 2021-04-16 07:37 | Closed | PL-01010 | 3331-250-PD-0199-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-16 05:59 | 2021-02-14 05:59 |  | Liang, Dennis | 2021-03-21 18:36 | Closed | PL-00584 | 3331-100-PWH-0013-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Handle on valve to be installed | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-16 21:34 | 2021-02-14 21:33 |  | Irvine, Darren | 2021-02-18 00:24 | Closed | PL-00586 | 3331-300-PWL-0001-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 04:15 |  | Davies, Jesse | 2021-03-19 22:19 | Closed | PL-00839 | 3331-150-CSL-0032-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 05:30 |  | Liang, Dennis | 2021-03-18 01:21 | Closed | PL-00849 | 3331-160-CSL-0064-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 05:33 |  | Lanser, Richard | 2021-04-23 12:34 | Closed | PL-00850 | 3331-160-CSL-0064-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed and hangers
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-28 05:36 |  | Lanser, Richard | 2021-04-23 12:34 | Closed | PL-00962 | 3331-160-CSL-0059-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install Pipe Hangers
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-02 16:44 | 2021-01-31 16:42 |  | Lanser, Richard | 2021-02-17 03:23 | Closed | PL-00503 | 3331-150-CSL-0001-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Some valves not installed 3331-FV-0047, 3331-FV-0048 and 50mm knife gate. | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-02 16:47 | 2021-01-31 16:45 |  | Liang, Dennis | 2021-03-18 01:23 | Closed | PL-00504 | 3331-150-CSL-0001-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | bolts missing not all flanges torqued up | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-02 17:37 | 2021-01-31 17:36 |  | Lanser, Richard | 2021-02-17 03:45 | Closed | PL-00507 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Some valves not installed 3331-FV-0051, 3331-FV-0052 and 50mm knife gate. | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-02 17:39 | 2021-01-31 17:39 |  | Lanser, Richard | 2021-04-16 21:10 | Closed | PL-00508 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | bolts missing not all flanges torqued up | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-03 02:10 | 2021-02-01 02:10 |  | Irvine, Darren | 2021-02-14 04:03 | Closed | PL-00511 | 3331-150-CSL-0003-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-11 05:02 |  |  |  | Submitted | PL-01517 | 3331-110-CSL-0031-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 02:53 |  |  |  | Submitted | PL-01605 | 3331-SA-4001B - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Pipe work not complete
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-04-28 22:58 | 2021-04-05 03:23 |  | Lanser, Richard | 2021-04-27 03:42 | Closed | PL-01481 | 3331-225-MCS-0283-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | flanges not torqued | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-10 10:11 | 2021-03-08 10:10 |  | Lanser, Richard | 2021-04-23 12:34 | Closed | PL-01087 | 3331-160-PD-0198-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install pipe hanger | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-14 21:41 | 2021-03-12 21:40 |  | Lanser, Richard | 2021-04-16 21:13 | Closed | PL-01194 | 3331-63-MCS-0305-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:31 |  | Davies, Jesse | 2021-03-18 23:13 | Closed | PL-01145 | 3331-90-PD-0011-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:39 |  | Davies, Jesse | 2021-03-18 23:14 | Closed | PL-01148 | 3331-80-PD-0062-R5 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:59 |  | Lanser, Richard | 2021-03-28 19:26 | Closed | PL-01153 | 3331-80-PD-0063-R5 - PD Process Line | S1 - Stage 1 Construction Completion | flange management required on 80mm knife gate valve.
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 22:08 |  | Davies, Jesse | 2021-03-18 23:17 | Closed | PL-01155 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required
B | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-03-23 01:22 | 2021-03-11 23:56 |  | Lanser, Richard | 2021-04-15 03:38 | Closed | PL-01159 | 3331-80-PD-0026-R5 - PD Process Line | S1 - Stage 1 Construction Completion | flange managment required | 1: A-High
B | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-21 23:51 |  |  |  | Submitted | PL-00235 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Ladder base to be completed at mid platform
B | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-02-23 21:38 | 2021-02-21 00:37 |  |  |  | Submitted | PL-00706 | Filter Building Steel & Stair Tower - Filter Building Steel and Structure | S1 - Stage 1 Construction Completion | Cladding incomplete | 1: A-High
B | Item Incomplete | STRU | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:33 |  |  |  | Submitted | PL-01351 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Grout base of stairs
B | Item not secured | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-03-21 02:31 | 2021-03-19 02:31 |  | Fuller, Lachlan | 2021-03-28 17:28 | Closed | PL-01263 | 3331-FV-0081 - OUTLET COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | The valve must be installed | 1: A-High
B | Item not secured | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-08 03:39 | 2021-01-25 03:38 |  |  |  | Submitted | PL-00296 | 3335-AIT-0854 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Instrument not bolted to flange. | 2: B-Low
B | Item not secured | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-05-02 03:53 | 2021-04-18 03:52 |  |  |  | Originated | PL-01567 | 3335-LIT-0840 - PROCESS WATER TANK | S2 - Stage 2 Pre Commissioning | Secure in place | 2: B-Low
B | Item not secured | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-07 01:15 | 2021-01-22 05:36 |  |  |  | Accepted | PL-00251 | 3331-PIT-2104 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Mount Correctly | 2: B-Low
B | Item not secured | INST | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 21:45 |  |  |  | Submitted | PL-01348 | 3331-FV-1109 - OUTLET CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Terminal Box needs Sikaflex and refast wiring
B | Item not secured | INST | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-02 06:56 | 2021-03-19 06:55 |  | Polkinghorne, Scott | 2021-04-21 21:29 | Closed | PL-01271 | 3331-LIT-0039 - COPPER CONCENTRATE THICKENER AREA SUMP | S1 - Stage 1 Construction Completion | Device mounted correctly | 2: B-Low
B | Item not secured | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-04-20 07:37 |  |  |  | Originated | PL-01588 | 3332-160-PD-0017-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Check if 3 ubolts are required
B | Item not secured | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-04-20 07:37 |  |  |  | Originated | PL-01589 | 3332-TA-4031 - THICKENER OVERFLOW TANK | S1 - Stage 1 Construction Completion | Install and drill
B | Item not secured | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:09 | 2021-01-15 02:18 |  | Gayler, Randal | 2021-03-16 01:05 | Closed | PL-00181 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete all supports and install all U-bolts as per isometric drawings | 2: B-Low
B | Item not secured | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-26 00:47 | 2021-02-12 00:46 |  | Wojcik, David | 2021-04-15 05:31 | Closed | PL-00570 | 3335-PK-4012 - FIRE WATER PUMP VENDOR PACKAGE | S1 - Stage 1 Construction Completion | re-instate guard for electric pump coupling after bump test | 2: B-Low
B | Item not secured | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:41 |  | Lanser, Richard | 2021-04-18 01:39 | Closed | PL-00893 | 3335-TA-4022 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Fix tank ladder to concrete base
B | Item not secured | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-03-11 02:49 |  |  |  | Submitted | PL-01128 | 3334-LIT-2109 - Level Indicating Transmitter | S1 - Stage 1 Construction Completion | Weld PUP piece for LIT refer WOR-MOLY-RTRFI-000333
B | Item not secured | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-07 01:15 | 2021-01-21 23:53 |  | Davies, Jesse | 2021-03-19 20:04 | Closed | PL-00236 | 3331-PIT-2104 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Install MIssing Bolts | 2: B-Low
B | Item not secured | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-03-27 23:37 | 2021-02-07 02:52 |  | Davies, Jesse | 2021-03-19 23:51 | Closed | PL-00550 | 3331-LIT-2147 - TA4041 DEARATION TANK FROTH LEVEL | S1 - Stage 1 Construction Completion | Transmitter requires to be bolted to flange | 2: B-Low
B | Item not secured | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:34 |  | Lanser, Richard | 2021-04-16 20:51 | Closed | PL-01352 | 3331-PU-4154 - CONCENTRATE THICKENER FROTH OVERFLOW PUMP | S1 - Stage 1 Construction Completion | Ensure bolts are installed and cut
B | Item not secured | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 22:24 |  | Lanser, Richard | 2021-04-16 20:50 | Closed | PL-01349 | 3331-LIT-1110 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Tighten bolts + Anti Seize
B | Item not secured | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 00:05 |  | Lanser, Richard | 2021-04-18 | Closed | PL-00979 | 3331-90-PD-0057-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install pipe vertical clamp
B | Item not secured | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-04-26 21:51 | 2021-04-12 21:50 |  | Lanser, Richard | 2021-04-21 11:51 | Closed | PL-01534 | 3331-90-PD-0061-H14 - PD Process Line | S1 - Stage 1 Construction Completion | 3331-PD-0059-H14-01 remove temporary support wood in cable tray. | 2: B-Low
B | Item not secured | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-03-02 00:58 |  |  |  | Submitted | PL-01001 | 3332-110-PD-0168-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install Pipe Hangers
B | Item not secured | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 | 2021-04-23 20:51 | 2021-04-09 20:50 |  |  |  | Originated | PL-01497 | 3332-90-PD-0055-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install missing supports, change vertical u bolt from guide to clamp. | 2: B-Low
B | Item not secured | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump | 2021-04-23 22:09 | 2021-04-09 22:09 |  |  |  | Originated | PL-01500 | 3332-110-VGN-0103-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Install missing support | 2: B-Low
B | Item not secured | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-10 10:00 | 2021-03-07 12:59 |  |  |  | Submitted | PL-01062 | 3332-225-MCS-0009-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
B | Item not secured | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-04-04 03:26 | 2021-03-20 06:26 |  |  |  | Submitted | PL-01284 | 3332-110-VGN-0091-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install missing support and u bolts | 2: B-Low
B | Item not secured | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 23:15 |  |  |  | Originated | PL-01299 | 3332-25-PWH-0256-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install u-bolts
B | Item not secured | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:21 |  |  |  | Originated | PL-01321 | 3332-25-PWH-0258-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install u-bolts
B | Item not secured | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 19:38 | 2021-03-20 22:38 |  |  |  | Submitted | PL-01289 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install u-bolts | 2: B-Low
B | Item not secured | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 21:42 | 2021-03-21 00:42 |  |  |  | Originated | PL-01308 | 3332-25-PWH-0257-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install u-bolts | 2: B-Low
B | Item not secured | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:26 |  |  |  | Submitted | PL-01243 | 3335-50-IA-0023-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item not secured | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:30 |  |  |  | Submitted | PL-01231 | 3332-50-IA-0089-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item not secured | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:52 |  |  |  | Submitted | PL-01235 | 3332-50-IA-0028-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
B | Item not secured | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution |  | 2021-03-19 06:26 |  | Lanser, Richard | 2021-04-16 07:38 | Closed | PL-01270 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | install missing u-bolt guide
B | Item not secured | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:15 |  | Lanser, Richard | 2021-04-18 01:38 | Closed | PL-00888 | 3335-TA-4022 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Install blanks on tank nozzles
B | Item not secured | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:47 |  |  |  | Submitted | PL-00895 | 3335-AIT-0854 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | management to be completed on AIT
B | Item not secured | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | 2021-04-01 19:54 | 2021-03-18 19:54 |  |  |  | Originated | PL-01258 | 3335-80-PWH-0006-C6-TI - PWH Process Line | S1 - Stage 1 Construction Completion | Install missing U-bolts on 3335-PWH-0006-C6-02 & change one from clamp to guide. | 2: B-Low
B | Item not secured | PIPE | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-03 - Flotation Scrubber Vent Network | 2021-04-23 22:50 | 2021-04-09 22:50 |  |  |  | Originated | PL-01504 | 3332-100-VGN-0202-C3 - VGN Process Line | S1 - Stage 1 Construction Completion | install vertical u-bolt guide on 3332-vgn-0202-c3-02 | 2: B-Low
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-24 17:38 |  | Davies, Jesse | 2021-03-19 22:21 | Closed | PL-00875 | 3331-110-CSL-0061-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete Flange management for CS25-02 Subsystem
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:40 |  | Lanser, Richard | 2021-04-16 20:52 | Closed | PL-01355 | 3331-63-MCS-0305-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Install supports and complete flange management
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-20 02:44 |  | Lanser, Richard | 2021-04-18 04:05 | Closed | PL-01277 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | remove temp. support rope.
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-03 22:39 | 2021-03-20 01:37 |  | Lanser, Richard | 2021-04-21 11:50 | Closed | PL-01274 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install missing cable ladder. (under north west corner of flotation- supports 2152mm section of pipe) | 2: B-Low
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-04 | 2021-03-20 02:59 |  | Lanser, Richard | 2021-04-18 04:05 | Closed | PL-01278 | 3331-90-PD-0011-H14 - PD Process Line | S1 - Stage 1 Construction Completion | remove temp. support rope. | 2: B-Low
B | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-04 02:42 | 2021-03-20 05:42 |  | Lanser, Richard | 2021-04-18 04:06 | Closed | PL-01280 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install all missing u-bolts, supports and cable ladder | 2: B-Low
B | Missing Labels | CABL | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 21:44 |  |  |  | Submitted | PL-00904 | 3335AV0854-C1 - FROM 3335-MB-4091 TO 3335-AV-0854 | S1 - Stage 1 Construction Completion | Install labels in 3338-XE-4013
B | Missing Labels | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-13 04:32 | 2021-02-27 04:32 |  |  |  | Originated | PL-00943 | 3332-AG-4110-M1 - Motor for FIRST CLEANER FLOTATION CELL 4 AGITATOR | S1 - Stage 1 Construction Completion | Equipment ID label to be attached | 2: B-Low
B | Missing Labels | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-13 04:35 | 2021-02-27 04:35 |  |  |  | Originated | PL-00944 | 3332-AG-4109-M1 - Motor for FIRST CLEANER FLOTATION CELL 3 AGITATOR | S1 - Stage 1 Construction Completion | Equipment ID label to be attached | 2: B-Low
B | Missing Labels | ELEC | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-13 04:37 | 2021-02-27 04:37 |  |  |  | Originated | PL-00945 | 3332-AG-4108-M1 - Motor for FIRST CLEANER FLOTATION CELL 2 AGITATOR | S1 - Stage 1 Construction Completion | Equipment ID label to be attached | 2: B-Low
B | Missing Labels | ELEC | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-02 - Caustic Dosing and Distribution | 2021-05-03 05:10 | 2021-04-19 05:09 |  |  |  | Originated | PL-01580 | 3334-PU-4119-M1 - Motor for SODIUM HYDROXIDE (CAUSTIC) DOSING PUMP | S1 - Stage 1 Construction Completion | Motor has no ID tag. Identified by cable label only. | 2: B-Low
B | Missing Labels | ELEC | CSEC - Power Factor Correction / Harmonic Filters | CSEC-01 - Power Factor Correction / Harmonic Filters | 2021-04-01 21:43 | 2021-03-18 21:43 |  | Khatib, Jordan | 2021-04-21 23:57 | Closed | PL-01260 | 3338-PF-4002 - Power Factor Correction | S1 - Stage 1 Construction Completion | Module labels required for both PFC cabinets - 3338-PF-4002. Warning label re capacitor discharge before entry also. | 2: B-Low
B | Missing Labels | ELEC | CSEC - Power Factor Correction / Harmonic Filters | CSEC-01 - Power Factor Correction / Harmonic Filters | 2021-04-03 00:28 | 2021-03-20 00:28 |  | Khatib, Jordan | 2021-04-21 23:57 | Closed | PL-01273 | 3338-PF-4001 - Power Factor Correction | S1 - Stage 1 Construction Completion | Module labels required for both PFC cabinets - 3338-PF-4001. Warning label re capacitor discharge before entry also. | 2: B-Low
B | Missing Labels | INST | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells | 2021-04-24 06:37 | 2021-04-10 06:36 |  |  |  | Originated | PL-01507 | 3332-FV-0495 - CLEANER SCAVENGER FLOTATION CELL 1 DRAIN | S1 - Stage 1 Construction Completion | Vendor labels to be supplied for this device | 2: B-Low
B | Missing Labels | INST | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-03-12 00:31 | 2021-02-07 00:31 |  |  |  | Accepted | PL-00548 | 3335-LCV-0840 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Requires ID tag on device Cable at device labelled. | 2: B-Low
B | Missing Labels | INST | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-05-06 03:51 | 2021-04-22 03:50 |  |  |  | Originated | PL-01628 | 3332-AIT-0584 - SRUBBER ORP | S1 - Stage 1 Construction Completion | Device is missing ID Tag | 2: B-Low
B | Missing Labels | INST | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | 2021-05-06 04:58 | 2021-04-22 04:58 |  |  |  | Originated | PL-01634 | 3332-AIT-0585 - FLOTATION SCRUBBER | S1 - Stage 1 Construction Completion | Device missing ID tag | 2: B-Low
B | Missing Labels | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-09 02:52 | 2021-02-07 02:51 |  |  |  | Originated | PL-00549 | 3331-LIT-2147 - TA4041 DEARATION TANK FROTH LEVEL | S1 - Stage 1 Construction Completion | Requires ID tag - Free issue vendor equipment. | 1: A-High
B | Missing Labels | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-07 02:34 |  |  |  | Submitted | PL-01489 | 3332-HE-4007A - Regrind Mill Heater 1 | S1 - Stage 1 Construction Completion | Tag no been supply
B | Missing Labels | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-04-28 05:28 | 2021-04-14 05:27 |  |  |  | Originated | PL-01547 | 3332-LCV-0449 - THIRD CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Missing valve ID tag | 2: B-Low
B | Missing Labels | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:10 | 2021-01-15 02:18 |  |  |  | Originated | PL-00182 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all valves tags as per P&ID | 2: B-Low
B | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-27 03:55 |  |  |  | Submitted | PL-00941 | 3331-280-PD-0003-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-02-28 19:19 |  |  |  | Submitted | PL-00969 | 3331-160-PD-0002-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-02 06:47 | 2021-01-19 06:47 | 2021-01-20 03:14 |  |  | Rejected | PL-00208 | 3331-160-CSL-0010-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install permanent valve tag | 2: B-Low
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-01 - Rougher Conditioning Metallurgical Sampler |  | 2021-04-04 01:57 |  |  |  | Submitted | PL-01456 | 3332-90-CSL-0104-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-25 23:56 |  |  |  | Submitted | PL-01372 | 3332-250-MCS-0113-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 00:45 |  |  |  | Submitted | PL-01378 | 3332-400-MCS-0112-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 01:04 |  |  |  | Submitted | PL-01380 | 3332-280-MCS-0114-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-03-26 01:13 |  |  |  | Submitted | PL-01381 | 3332-250-MCS-0313-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-03-26 05:22 |  |  |  | Submitted | PL-01384 | 3332-110-MCS-0135-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-04-04 05:46 |  |  |  | Submitted | PL-01470 | 3332-400-PD-0202-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler |  | 2021-04-04 05:48 |  |  |  | Submitted | PL-01471 | 3332-110-PD-0203-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 | 2021-04-23 20:48 | 2021-04-09 20:48 |  |  |  | Originated | PL-01496 | 3332-90-PD-0055-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump |  | 2021-04-11 05:10 |  |  |  | Submitted | PL-01520 | 3334-25-NAHS-0048-S6 - NAHS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-04-25 22:55 | 2021-04-11 22:54 |  |  |  | Originated | PL-01530 | 3332-80-PWL-0013-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-04-25 22:56 | 2021-04-11 22:56 |  |  |  | Submitted | PL-01531 | 3332-80-PWL-0013-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | install valve ID tags. | 2: B-Low
B | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-04 06:50 |  |  |  | Submitted | PL-01475 | 3332-50-PWH-0042-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-11 06:09 |  |  |  | Submitted | PL-01527 | 3332-63-PD-0212-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:41 |  |  |  | Submitted | PL-01425 | 3332-25-PWH-0251-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:47 |  |  |  | Submitted | PL-01429 | 3332-25-PWH-0010-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:57 |  |  |  | Submitted | PL-01432 | 3332-25-PWH-0252-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:00 |  |  |  | Submitted | PL-01436 | 3332-25-PWH-0011-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:10 |  |  |  | Submitted | PL-01442 | 3332-160-PD-0012-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:14 |  |  |  | Submitted | PL-01446 | 3332-25-PWH-0254-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:48 |  |  |  | Submitted | PL-01449 | 3332-25-PWH-0012-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 04:03 |  |  |  | Submitted | PL-01452 | 3332-25-PWH-0013-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 00:02 |  |  |  | Submitted | PL-01511 | 3332-110-VGN-0011-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 00:33 |  |  |  | Submitted | PL-01512 | 3332-110-VGN-0012-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 00:37 |  |  |  | Submitted | PL-01513 | 3332-110-VGN-0013-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 00:43 |  |  |  | Submitted | PL-01514 | 3332-110-VGN-0014-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 05:46 |  |  |  | Submitted | PL-01524 | 3332-160-PD-0014-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-11 06:00 |  |  |  | Submitted | PL-01526 | 3332-160-PD-0015-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 22:39 |  |  |  | Submitted | PL-01290 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 22:53 |  |  |  | Submitted | PL-01293 | 3332-25-PWH-0014-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels.
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 23:07 |  |  |  | Originated | PL-01295 | 3332-25-PWH-0014-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 23:16 |  |  |  | Originated | PL-01300 | 3332-25-PWH-0256-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:43 |  |  |  | Originated | PL-01309 | 3332-25-PWH-0257-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:50 |  |  |  | Originated | PL-01311 | 3332-160-PD-0019-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install line labels
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:53 |  |  |  | Originated | PL-01313 | 3332-160-PD-0019-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install valve ID tags
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:19 |  |  |  | Originated | PL-01319 | 3332-25-PWH-0258-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:22 |  |  |  | Originated | PL-01322 | 3332-25-PWH-0258-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:37 |  |  |  | Originated | PL-01327 | 3332-90-VGN-0098-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install valve ID tag
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 20:14 | 2021-03-20 23:13 |  |  |  | Originated | PL-01297 | 3332-25-PWH-0256-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 21:33 | 2021-03-21 00:33 |  |  |  | Originated | PL-01302 | 3332-25-PWH-0018-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 21:36 | 2021-03-21 00:35 |  |  |  | Originated | PL-01304 | 3332-25-PWH-0018-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 21:40 | 2021-03-21 00:40 |  |  |  | Originated | PL-01306 | 3332-25-PWH-0257-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 22:13 | 2021-03-21 01:12 |  |  |  | Originated | PL-01315 | 3332-25-PWH-0017-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 22:16 | 2021-03-21 01:15 |  |  |  | Originated | PL-01317 | 3332-25-PWH-0017-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install valve ID tags | 2: B-Low
B | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 22:34 | 2021-03-21 01:34 |  |  |  | Originated | PL-01325 | 3332-90-VGN-0098-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Labels | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:02 |  |  |  | Submitted | PL-01458 | 3332-25-PWH-0249-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:07 |  |  |  | Submitted | PL-01461 | 3332-50-PWH-0188-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:11 |  |  |  | Submitted | PL-01464 | 3332-25-PWH-0020-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:15 |  |  |  | Submitted | PL-01468 | 3332-25-PWH-0250-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-13 01:02 |  |  |  | Submitted | PL-01536 | 3332-90-PD-0146-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-13 01:11 |  |  |  | Submitted | PL-01537 | 3332-110-VGN-0104-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-11 05:14 |  |  |  | Submitted | PL-01521 | 3332-80-MCS-0052-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-11 05:36 |  |  |  | Submitted | PL-01522 | 3332-150-MCS-0064-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:06 |  |  |  | Submitted | PL-01238 | 3335-50-IA-0055-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:14 |  |  |  | Submitted | PL-01241 | 3335-50-IA-0061-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:34 |  |  |  | Submitted | PL-01244 | 3335-50-IA-0023-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-23 21:42 |  |  |  | Submitted | PL-01367 | 3332-50-IA-0020-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:22 |  | Liang, Dennis | 2021-03-18 19:27 | Closed | PL-01227 | 3332-25-IA-0115-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:25 |  |  |  | Submitted | PL-01229 | 3332-25-IA-0115-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Label Tag
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:31 |  |  |  | Submitted | PL-01232 | 3332-50-IA-0089-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:53 |  |  |  | Submitted | PL-01236 | 3332-50-IA-0028-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:23 |  |  |  | Submitted | PL-01246 | 3332-50-IA-0013-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:28 |  |  |  | Submitted | PL-01248 | 3332-50-IA-0080-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:32 |  |  |  | Submitted | PL-01251 | 3332-50-IA-0006-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:57 |  |  |  | Submitted | PL-00914 | 3332-25-PWH-0356-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 19:56 |  |  |  | Submitted | PL-00918 | 3332-50-PWH-0215-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 21:09 |  |  |  | Submitted | PL-00921 | 3332-25-PWH-0319-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-03-22 01:05 |  |  |  | Originated | PL-01343 | 3332-50-PWH-0151-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:13 |  |  |  | Submitted | PL-01218 | 3332-50-PWH-0134-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:25 |  |  |  | Submitted | PL-01220 | 3332-80-PWH-0033-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:33 |  |  |  | Submitted | PL-01222 | 3332-50-PWH-0360-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area |  | 2021-04-04 06:11 |  |  |  | Submitted | PL-01473 | 3335-50-PWH-0005-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
B | Missing Labels | PIPE | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-03 - Flotation Scrubber Vent Network |  | 2021-04-09 22:41 |  |  |  | Originated | PL-01503 | 3332-100-VGN-0202-C3 - VGN Process Line | S1 - Stage 1 Construction Completion | install valve ID tag
B | Missing Labels | PIPE | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | CS11-03 - Flotation Scrubber Vent Network | 2021-04-23 22:40 | 2021-04-09 22:40 |  |  |  | Originated | PL-01502 | 3332-100-VGN-0202-C3 - VGN Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
B | Missing Parts | CIVIL | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) | 2021-03-02 06:21 | 2021-02-28 06:56 |  |  |  | Submitted | PL-00968 | 3331-AG-4002 - CONCENTRATE STORAGE TANK 2 AGITATOR | S1 - Stage 1 Construction Completion | Concrete internal stabiliser ring inside tank | 1: A-High
B | Missing Parts | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-04-22 03:47 | 2021-04-08 03:47 |  |  |  | Submitted | PL-01492 | 3331-FV-0019 - PROCESS WATER TO CONCENTRATE STORAGE TANK 1 OUTLET | S2 - Stage 2 Pre Commissioning | Install M20 bung | 2: B-Low
B | Missing Parts | INST | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-21 20:19 | 2021-03-06 06:50 |  |  |  | Accepted | PL-01020 | 3332ZS0120-C1 - FROM 3332-OP-4021 TO 3332-ZS-0120 | S1 - Stage 1 Construction Completion | Needs spare nylon gland swapped out for 20mm bung Screws missing from terminal box cover | 2: B-Low
B | Missing Parts | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-08 03:42 | 2021-01-25 03:41 |  |  |  | Originated | PL-00297 | 3335-AIT-0854 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Tubing not installed | 2: B-Low
B | Missing Parts | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 05:43 | 2021-01-24 05:43 |  |  |  | Originated | PL-00293 | 3334-LIT-2101 - Level Indicating Transmitter | S1 - Stage 1 Construction Completion | Incorrect mount/e | 2: B-Low
B | Missing Parts | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-24 17:44 |  |  |  | Submitted | PL-00879 | 3331-PU-4004 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP (STAND-BY) | S1 - Stage 1 Construction Completion | Install level switches on 3338MB4002-C1 panel XE4010
B | Missing Parts | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-03-23 01:44 |  | Lanser, Richard | 2021-04-22 10:15 | Closed | PL-01357 | 3331-PU-4005 - COPPER CONCENTRATE CHARGING PUMP | S1 - Stage 1 Construction Completion | Instal lubrication reservoir to pump
B | Missing Parts | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-04-20 07:37 |  |  |  | Originated | PL-01587 | 3332-LIT-0600 - THICKENER OVERFLOW TANK | S1 - Stage 1 Construction Completion | Install mounting
B | Missing Parts | MECH | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-24 17:54 |  | Lanser, Richard | 2021-04-20 06:15 | Closed | PL-00884 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install Isolation handle on strainer
B | Missing Parts | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-21 22:38 | 2021-02-19 22:37 |  | Lanser, Richard | 2021-04-16 21:10 | Closed | PL-00682 | 3335-TA-4022 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | BF1 100mm valve not available to install drain | 1: A-High
B | Missing Parts | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 05:18 |  | Lanser, Richard | 2021-03-09 11:04 | Closed | PL-00761 | 3331-PU-4154 - CONCENTRATE THICKENER FROTH OVERFLOW PUMP | S1 - Stage 1 Construction Completion | Discharge line not fitted, incorrect flange bolts
B | Missing Parts | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 13:33 | 2021-03-09 13:32 |  |  |  | Submitted | PL-01118 | 3332-50-PWH-0200-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe supports missing | 1: A-High
B | Missing Parts | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-04-20 07:37 |  |  |  | Originated | PL-01590 | 3332-100-PWL-0009-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Tighten hangers
B | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-05 01:33 | 2021-01-22 01:32 |  |  |  | Originated | PL-00241 | 3332-80-IA-0001-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all U-bolts throughout system and remaining T-post supports | 2: B-Low
B | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-06 03:07 | 2021-01-23 03:06 |  |  |  | Submitted | PL-00267 | 3332-50-IA-0083-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install additional pipe support at south end of line | 2: B-Low
B | Missing Parts | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-05 21:03 | 2021-02-19 20:59 |  | Lanser, Richard | 2021-04-16 21:11 | Closed | PL-00668 | 3335-100-PWL-0008-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | 100mm BF1 valve not available to install drain on tank | 2: B-Low
B | Missing Parts | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-23 05:58 | 2021-03-09 06:19 |  | Davies, Jesse | 2021-03-17 23:59 | Closed | PL-01116 | 3331-110-PD-0066-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install missing pipe support | 2: B-Low
B | Missing Parts | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-23 06:13 | 2021-03-09 06:18 |  | Davies, Jesse | 2021-03-17 02:41 | Closed | PL-01115 | 3331-110-PD-0065-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install pipe support | 2: B-Low
B | Not to Contract Spec | ELEC | CS0E - Process Water Distribution | CS0E-12 - Containment Pond |  | 2021-02-20 22:53 |  |  |  | Submitted | PL-00694 | 3335PU4097-T1 - CONCENTRATE STORAGE SUMP PUMP | S1 - Stage 1 Construction Completion | Modification required to motor for thermistor and earth continuity pilot wire
B | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 02:23 | 2021-01-31 02:22 |  | Lanser, Richard | 2021-04-19 22:05 | Closed | PL-00462 | 3332-25-PWH-0007-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Flange management required | 1: A-High
B | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 | 2021-04-23 23:10 | 2021-04-09 23:07 |  |  |  | Originated | PL-01505 | 3332-90-PD-0170-H14 - PD Process Line | S1 - Stage 1 Construction Completion | change vertical u-bolt from guide to clamp | 2: B-Low
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 22:34 |  |  |  | Submitted | PL-01288 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:41 |  |  |  | Originated | PL-01307 | 3332-25-PWH-0257-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:51 |  |  |  | Originated | PL-01312 | 3332-160-PD-0019-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install lagging
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:14 |  |  |  | Originated | PL-01316 | 3332-25-PWH-0017-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:20 |  |  |  | Originated | PL-01320 | 3332-25-PWH-0258-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 19:43 | 2021-03-20 22:42 |  |  |  | Submitted | PL-01291 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | remove rust | 2: B-Low
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 19:45 | 2021-03-20 22:44 | 2021-04-23 01:09 |  |  | Rejected | PL-01292 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line | 2: B-Low
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 20:05 | 2021-03-20 23:04 |  |  |  | Submitted | PL-01294 | 3332-25-PWH-0014-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging | 2: B-Low
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 20:15 | 2021-03-20 23:14 |  |  |  | Originated | PL-01298 | 3332-25-PWH-0256-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging | 2: B-Low
B | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 21:34 | 2021-03-21 00:34 |  |  |  | Originated | PL-01303 | 3332-25-PWH-0018-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install lagging | 2: B-Low
B | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-04-03 01:36 | 2021-03-19 04:36 |  |  |  | Submitted | PL-01264 | 3332-50-IA-0083-C4 - IA Process Line | S1 - Stage 1 Construction Completion | change u-bolts from clamps to guides | 2: B-Low
B | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-02-15 01:25 |  |  |  | Submitted | PL-00589 | 3331-80-PWH-0035-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Valve handle clashes with poly pipe on 3335-PWH-0002-C6-02 end of spool
B | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 05:28 |  | Lanser, Richard | 2021-04-06 18:28 | Closed | PL-00403 | 3334-25-FLOC-0020-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required
B | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-03-16 05:38 | 2021-01-20 05:19 |  | Davies, Jesse | 2021-03-18 23:02 | Closed | PL-00215 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Confirm flange faces are clean and free of damage, torque bolts in sequence and attach flange tag | 1: A-High
B | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-20 05:49 |  | Lanser, Richard | 2021-04-16 07:38 | Closed | PL-01281 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Change U-bolt guides to clamps on vertical section - west side of stair tower. + install missing flange support.
B | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-20 05:52 |  | Lanser, Richard | 2021-04-16 07:38 | Closed | PL-01282 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | fix F4 clashing on support.
B | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-03-22 23:43 | 2021-03-20 02:41 |  | Lanser, Richard | 2021-04-16 21:13 | Closed | PL-01276 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Replace top 2 gaskets. - gylon installed instead of garlock. | 1: A-High
B | Not to Drawings | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 05:28 | 2021-01-18 05:43 |  |  |  | Originated | PL-00187 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line mark up P&ID | 2: B-Low
B | Not to Drawings | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 05:34 | 2021-01-18 05:43 |  |  |  | Originated | PL-00188 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line mark up P&ID | 2: B-Low
B | Not to Drawings | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 05:36 | 2021-01-18 05:43 |  | Gayler, Randal | 2021-03-16 01:07 | Closed | PL-00189 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Attach weld map | 2: B-Low
B | Not to Drawings | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-10 11:04 | 2021-03-07 14:02 |  |  |  | Submitted | PL-01066 | 3332-90-VGN-0029-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Incorrect Iso number on flange tags | 1: A-High
B | Not to Drawings | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-03-23 22:31 | 2021-03-21 01:30 |  | Lanser, Richard | 2021-04-05 18:25 | Closed | PL-01324 | 3332-90-VGN-0098-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | spectacle blind tail facing wrong direction. turn to the north. | 1: A-High
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 04:36 | 2021-01-18 04:34 |  |  |  | Originated | PL-00177 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line P&ID as per as built | 2: B-Low
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 04:39 | 2021-01-18 04:38 |  |  |  | Originated | PL-00178 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line P&ID as per as built | 2: B-Low
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 04:40 | 2021-01-18 04:39 |  | Gayler, Randal | 2021-03-16 01:06 | Closed | PL-00179 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Attach weld maps | 2: B-Low
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 08:35 | 2021-01-30 08:32 |  | Liang, Dennis | 2021-03-18 00:54 | Closed | PL-00408 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | P&ID will need to be revised | 1: A-High
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-01 08:38 | 2021-01-30 08:37 |  | Liang, Dennis | 2021-03-18 00:55 | Closed | PL-00409 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | ISO will need to be revised to reflect what has been site run in the field. | 1: A-High
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 04:01 | 2021-01-18 04:00 |  |  |  | Originated | PL-00174 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line P&ID as per as built | 2: B-Low
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-02 00:09 | 2021-01-19 00:09 |  |  |  | Originated | PL-00196 | 3332-80-IA-0001-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line mark up P&ID | 2: B-Low
B | Not to Drawings | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-02 00:17 | 2021-01-19 00:10 |  |  |  | Originated | PL-00197 | 3332-80-IA-0001-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Red line mark up P&ID’s | 2: B-Low
B | Not to Equipment Specs | MECH | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-24 17:52 |  | Lanser, Richard | 2021-04-05 19:12 | Closed | PL-00883 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Replace zinc bolts on strainer
B | Not to Equipment Specs | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-02 02:19 | 2021-01-31 02:18 |  | Lanser, Richard | 2021-04-19 22:04 | Closed | PL-00461 | 3332-25-PWH-0007-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Valve 3332-FB-4006 Locking mechanisam bent and need to be repaired. | 1: A-High
B | Not to Equipment Specs | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:19 |  |  |  | Submitted | PL-01641 | 3332-80-PD-0054-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Minsups to be HDG
B | Not to Equipment Specs | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:43 |  |  |  | Submitted | PL-00894 | 3335-200-PWL-0001-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Ensure valves can reach last notch for full isolation on process water subsystem
B | Not to Equipment Specs | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:49 |  |  |  | Submitted | PL-00896 | 3335-LIT-0840 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Replace Table D Flange with ANSI
B | Not to Equipment Specs | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-03-04 21:59 |  |  |  | Submitted | PL-01011 | 3331-250-PD-0199-H14 - PD Process Line | S1 - Stage 1 Construction Completion | pipe clashing with steel, supports need to be modified
B | Other | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-04-20 07:17 | 2021-04-20 07:20 |  |  | Rejected | PL-01586 | 3331-PU-4007-M1 - Motor for COPPER CONCENTRATE TRANSFER PUMP | S2 - Stage 2 Pre Commissioning | Connect Drive
B | Other | ELEC | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-01 22:32 | 2021-01-18 22:32 |  | Muell, Thomas | 2021-02-17 22:07 | Closed | PL-00191 | 3335-PU-4094 - FIRE WATER JOCKEY PUMP | S1 - Stage 1 Construction Completion | 1.Battery enclosure lids loose (secure). 2.Fire water valve position feedback cores (x4). Cut cores back inside Valve box, insulate and seal (bung) valve cable entries. 3.Fire water Pump PU-4093 and Diesel Pump PU 4092 have back the front S/S tag numbers on nameplates. Supply and install 2 x S/S tags and glue onto nameplate in respective locations. 4.Missing barrier strip on Cable ladder bend (UCA – C). | 2: B-Low
B | Other | ELEC | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-30 20:43 |  |  |  | Originated | PL-00445 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | 1) Bed level probe to calibrated. ( ELE ) 2)Rake height indicator to be calibrated ( ELE ) 3)Turbodil VSD to be connected and direction tested ( ELE ) 4)Deaeration tank dart valve. Air supply to be installed and Dart valve stroked ( ELE )
B | Other | INST | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header | 2021-04-06 05:48 | 2021-04-04 05:44 |  |  |  | Submitted | PL-01469 | 3335-AIT-0868 - OUTLET INLINE SODIUM HYDROXIDE MIXER | S2 - Stage 2 Pre Commissioning | 1. The retractable probe proximity sensor 3335ZSO0868, 3335ZSC0868 indications are not reliable and there are situations that both sensor are at "ON" position. We found the proximity switch behaviours are not different from clean contacts of mechanical switch. For mechnical switch with clean contact, the sensor's output to DCS input should be either OV, or 24V, some close value. However the output of the proximity sensor (blue color sensor wire in this type of sensor) could be something between 24V and 0V (for example we observed 11.5V at one time). 2. The action direction of the retractable probe is "solenoid valve coil energized to INSERT the probe at measurement position", while the action of the probe 3331AY0085 is solenoid coil energized to RETRACT the probe out of measurement position. The action direction of solenoid need to be reviewed and confirmed. | 1: A-High
B | Other | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-01-27 23:53 | 2021-01-25 23:44 |  |  |  | Originated | PL-00301 | 3334-FIT-2119 - Flow Indicating Transmitter | S2 - Stage 2 Pre Commissioning | Instrument not configured and must be configured according to data sheets. | 1: A-High
B | Other | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-04-07 04:18 | 2021-04-07 04:22 |  |  | Rejected | PL-01491 | 3331-ZIT-2146 - TH4001 Rake Height Transmitter | S2 - Stage 2 Pre Commissioning | do the thing
B | Other | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-03-16 02:50 |  | Nutt, Richard | 2021-04-13 23:49 | Closed | PL-01224 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | fix grout under geho
B | Other | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-21 01:43 |  | Lanser, Richard | 2021-04-17 06:38 | Closed | PL-01329 | 3331-LIT-0034 - CONCENTRATE STORAGE SUMP | S1 - Stage 1 Construction Completion | Lit to be flangers managed
B | Other | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:23 |  | Lanser, Richard | 2021-04-27 03:40 | Closed | PL-01642 | 3332-HT-4003 - ROUGHER AREA SUMP PUMP 1 DAVIT | S1 - Stage 1 Construction Completion | Rotate Winch
B | Other | MECH | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-24 17:56 |  | Lanser, Richard | 2021-04-05 19:12 | Closed | PL-00885 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Preservation on carbon steel components
B | Other | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-01 22:43 | 2021-01-18 22:42 |  | Wojcik, David | 2021-04-15 05:29 | Closed | PL-00193 | 3335-PU-4092 - FIRE WATER DIESEL PUMP | S1 - Stage 1 Construction Completion | 1.Connect suction, discharge and bypass lines 2.Provide & fit S/S tags for valving identification 3.Blow out concrete base (under skid) and grout 4.Denso tape pump jacking bolts 5.Provide & fit direction “firewater’ flow stickers as per AS. | 2: B-Low
B | Other | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 05:30 | 2021-01-26 05:29 |  | Fuller, Lachlan | 2021-03-29 00:54 | Closed | PL-00305 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Actuated valves not tested yet | 1: A-High
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 23:09 | 2021-04-23 01:08 |  |  | Rejected | PL-01296 | 3332-25-PWH-0014-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-20 23:18 | 2021-04-23 01:08 |  |  | Rejected | PL-01301 | 3332-25-PWH-0256-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:36 | 2021-04-23 01:08 |  |  | Rejected | PL-01305 | 3332-25-PWH-0018-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:47 | 2021-04-23 01:08 |  |  | Rejected | PL-01310 | 3332-25-PWH-0257-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 00:54 | 2021-04-23 01:08 |  |  | Rejected | PL-01314 | 3332-160-PD-0019-H14 - PD Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:16 | 2021-04-23 01:08 |  |  | Rejected | PL-01318 | 3332-25-PWH-0017-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-21 01:24 | 2021-04-23 01:08 |  |  | Rejected | PL-01323 | 3332-25-PWH-0258-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | paint line
B | Other | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 04:12 | 2021-01-18 04:11 |  |  |  | Originated | PL-00175 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Attach weld maps | 2: B-Low
C |  | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-17 23:54 |  |  |  | Originated | PL-01554 | 3332-PU-4012 - ROUGHER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Sumps to be cleaned prior to pump start up
C | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 06:09 | 2021-01-22 20:09 |  |  |  | Accepted | PL-00255 | 3334-FIT-2111 - Flow Indicating Transmitter | S1 - Stage 1 Construction Completion | Vendor Supplied Device Label Missing | 2: B-Low
C | Incorrect Labels | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-01-22 00:50 | 2021-01-08 00:48 |  |  |  | Originated | PL-00153 | 3331-PT-2104 - TH4001 BED MASS | S1 - Stage 1 Construction Completion | Current SS tag Vendor supplied is 3332-TH-4001-PT04 need to be 3331-PT-2104 | 2: B-Low
C | Incorrect Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 03:54 | 2021-01-18 03:52 |  |  |  | Originated | PL-00171 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install pipe identification lables | 2: B-Low
C | Incorrect Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:11 | 2021-01-27 09:10 |  |  |  | Submitted | PL-00352 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install pipe identification lables | 2: B-Low
C | Item Damaged | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | 2021-04-23 21:34 | 2021-04-09 21:28 |  |  |  | Submitted | PL-01498 | 3331DB4007-W28 - STORAGE AREA LIGHT AND POWER BOARD TO CONCENTRATE STORAGE TANKS BRIDGE LIGHTING | S2 - Stage 2 Pre Commissioning | Light requires replacement. Water damaged. Light has been removed from Posi box and bagged and tagged. | 2: B-Low
C | Item Damaged | INST | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-05 05:18 |  |  |  | Rejected | PL-01018 | 3332-FV-0428 - Mo SLURRY TO REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | fix
C | Item Damaged | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:00 |  |  |  | Submitted | PL-01435 | 3332-25-PWH-0011-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-14 00:08 | 2021-03-11 03:07 |  | Lanser, Richard | 2021-04-16 21:12 | Closed | PL-01138 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Clean up area. | 1: A-High
C | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump |  | 2021-04-18 02:48 |  |  |  | Submitted | PL-01560 | 3332-PU-4013 - ROUGHER AREA SUMP PUMP 2 | S1 - Stage 1 Construction Completion | Sumps to be cleaned prior to pump start up
C | Item Dirty | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-06 - Cleaner area sump |  | 2021-04-24 05:42 |  |  |  | Submitted | PL-01666 | 3332-PU-4028 - CLEANER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Sump to be cleaned
C | Item Dirty | MECH | CS08 - Molybdenum Thickener and Concentrate Filter | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains |  | 2021-04-24 05:31 |  |  |  | Submitted | PL-01664 | 3333-PU-4040 - FILTER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Sumps need cleaning
C | Item Dirty | MECH | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-05 22:57 | 2021-01-22 22:56 |  | Davies, Jesse | 2021-03-18 00:06 | Closed | PL-00263 | 3335-PU-4093 - FIRE WATER PUMP | S1 - Stage 1 Construction Completion | Removal of spare bolts and parts not associated with fire water skid. | 2: B-Low
C | Item Dirty | MECH | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-02-06 06:32 | 2021-01-23 21:00 |  | Lanser, Richard | 2021-03-29 02:46 | Closed | PL-00281 | 3331-SU-4009 - SUMP | S1 - Stage 1 Construction Completion | Clean sump | 2: B-Low
C | Item Dirty | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-04 06:51 | 2021-04-23 01:09 |  |  | Rejected | PL-01476 | 3332-50-PWH-0042-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:41 | 2021-04-23 01:09 |  |  | Rejected | PL-01426 | 3332-25-PWH-0251-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:43 | 2021-04-23 01:09 |  |  | Rejected | PL-01427 | 3332-160-PD-0013-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:48 | 2021-04-23 01:09 |  |  | Rejected | PL-01430 | 3332-25-PWH-0010-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:57 | 2021-04-23 01:09 |  |  | Rejected | PL-01433 | 3332-25-PWH-0252-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:01 | 2021-04-23 01:09 |  |  | Rejected | PL-01437 | 3332-25-PWH-0011-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:05 | 2021-04-23 01:09 |  |  | Rejected | PL-01440 | 3332-25-PWH-0253-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:11 | 2021-04-23 01:09 |  |  | Rejected | PL-01444 | 3332-160-PD-0012-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:15 | 2021-04-23 01:09 |  |  | Rejected | PL-01447 | 3332-25-PWH-0254-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:49 | 2021-04-23 01:09 |  |  | Rejected | PL-01450 | 3332-25-PWH-0012-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 04:04 | 2021-04-23 01:09 |  |  | Rejected | PL-01453 | 3332-25-PWH-0013-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:04 | 2021-04-23 01:09 |  |  | Rejected | PL-01459 | 3332-25-PWH-0249-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:08 | 2021-04-23 01:09 |  |  | Rejected | PL-01462 | 3332-50-PWH-0188-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:12 | 2021-04-23 01:09 |  |  | Rejected | PL-01465 | 3332-25-PWH-0020-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:15 | 2021-04-23 01:09 |  |  | Rejected | PL-01467 | 3332-25-PWH-0250-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-23 21:44 | 2021-04-23 01:09 |  |  | Rejected | PL-01368 | 3332-50-IA-0020-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:23 | 2021-04-23 01:09 |  |  | Rejected | PL-01228 | 3332-25-IA-0115-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-18 01:29 | 2021-04-23 01:09 |  |  | Rejected | PL-01249 | 3332-50-IA-0080-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Dirty | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-03-22 01:06 | 2021-04-23 01:09 |  |  | Rejected | PL-01344 | 3332-50-PWH-0151-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | CIVIL | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:36 |  |  |  | Originated | PL-01660 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | 3332-TA-4004 and 3332-TA-4005 floor penetrations to be fixed
C | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-14 04:41 |  |  |  | Originated | PL-00056 | 3338-MC-4002 - Motor Control Centre No 2 | S1 - Stage 1 Construction Completion | MCC does not match GA. General arrangement drawing to be As Built
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:24 |  |  |  | Originated | PL-01652 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | 3332-TA-4004 grid mesh gaps to be rectified. Refer WOR-MOLY-RESTECHQ-000346 / SI-079
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 10:40 | 2021-03-08 13:39 |  | Lanser, Richard | 2021-04-18 00:02 | Closed | PL-01090 | 3332-PU-4010 - ROUGHER FEED PUMP | S1 - Stage 1 Construction Completion | grouting not done | 1: A-High
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 11:47 | 2021-03-08 14:46 |  |  |  | Submitted | PL-01094 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | U bolt needed for overflow | 1: A-High
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 11:58 | 2021-03-08 14:57 |  |  |  | Submitted | PL-01100 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 13:12 | 2021-03-08 16:11 |  |  |  | Submitted | PL-01107 | 3332-DI-4001 - CONDITIONING TANK FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Pipe work not complete | 1: A-High
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 11:50 | 2021-03-08 14:49 |  | Lanser, Richard | 2021-04-27 03:42 | Closed | PL-01096 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Anchor bolts not installed | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 11:55 | 2021-03-08 14:54 |  | Lanser, Richard | 2021-04-24 09:27 | Closed | PL-01098 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Edge sealing not completed. | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 11:56 | 2021-03-08 14:55 |  | Lanser, Richard | 2021-04-27 03:42 | Closed | PL-01099 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Anchor bolts not installed | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 00:20 |  |  |  | Submitted | PL-00790 | 3332-LD-4001 - ROUGHER SCAVENGER FLOTATION LAUNDER | S1 - Stage 1 Construction Completion | LEAK TEST
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 00:30 |  |  |  | Submitted | PL-00793 | 3332-LD-4007 - ROUGHER SCAVENGER LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | NIL
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 03:13 |  | Lanser, Richard | 2021-04-27 03:38 | Closed | PL-00954 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Connect flushing port to level transmitter on all rougher flotation cell
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-18 09:41 | 2021-02-04 09:40 |  | Lanser, Richard | 2021-04-05 23:17 | Closed | PL-00543 | 3332-FB-4002 - ROUGHER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Install burst disc | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-18 09:43 | 2021-02-04 09:43 |  | Lanser, Richard | 2021-04-05 23:18 | Closed | PL-00544 | 3332-FB-4004 - ROUGHER SCAVENGER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Install burst disc | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-02-14 13:36 | 2021-01-31 13:36 |  | Lanser, Richard | 2021-04-17 06:38 | Closed | PL-00489 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:15 | 2021-03-08 17:14 |  | Lanser, Richard | 2021-04-16 21:12 | Closed | PL-01111 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | grouting not done | 1: A-High
C | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:21 | 2021-03-08 17:20 |  | Lanser, Richard | 2021-04-16 21:12 | Closed | PL-01114 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | grouting not done | 1: A-High
C | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener | 2021-03-14 22:26 | 2021-03-12 22:24 |  | Lanser, Richard | 2021-04-19 22:08 | Closed | PL-01195 | 3332-PU-4030 - INTERMEDIATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | grouting not done and hold down bolts need to be cut off. | 1: A-High
C | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-03-12 11:41 | 2021-03-09 14:40 |  | Lanser, Richard | 2021-04-19 22:08 | Closed | PL-01123 | 3332-PU-4120 - THICKENER OVERFLOW PUMP | S1 - Stage 1 Construction Completion | grouting not done | 1: A-High
C | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-03 00:29 |  |  |  | Submitted | PL-01418 | 3332-HP-4005 - REGRIND MILL DISCHARGE HOPPER | S1 - Stage 1 Construction Completion | Lables need install
C | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:25 |  | Lanser, Richard | 2021-04-05 22:45 | Closed | PL-00652 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 02:31 |  | Lanser, Richard | 2021-04-05 22:51 | Closed | PL-00655 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-19 04:37 |  | Lanser, Richard | 2021-04-05 22:52 | Closed | PL-00658 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-02-14 14:24 | 2021-01-31 14:23 |  | Lanser, Richard | 2021-04-27 03:41 | Closed | PL-00496 | 3332-PU-4014 - SECOND CLEANER TAILINGS PUMP | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:21 |  | Lanser, Richard | 2021-04-05 22:55 | Closed | PL-00673 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:35 |  | Lanser, Richard | 2021-04-05 22:55 | Closed | PL-00676 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-19 21:59 |  | Lanser, Richard | 2021-04-05 22:56 | Closed | PL-00679 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-20 00:21 |  | Lanser, Richard | 2021-04-05 22:57 | Closed | PL-00686 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 04:43 |  | Lanser, Richard | 2021-04-05 22:53 | Closed | PL-00661 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-19 21:10 |  | Lanser, Richard | 2021-04-05 22:54 | Closed | PL-00670 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Touch up paint
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:35 |  |  |  | Submitted | PL-01618 | 3332-HP-4007 - FOURTH CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Breather needs install
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:36 |  |  |  | Submitted | PL-01619 | 3332-HP-4007 - FOURTH CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Needs to be installed
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:47 |  |  |  | Submitted | PL-01622 | 3332-HP-4008 - THIRD CLEANER / FOURTH CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | needs completion
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:49 |  |  |  | Submitted | PL-01623 | 3332-HP-4008 - THIRD CLEANER / FOURTH CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Install breather
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:55 |  |  |  | Submitted | PL-01625 | 3332-HP-4008 - THIRD CLEANER / FOURTH CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Needs fitting
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-02-14 14:04 | 2021-01-31 14:04 |  | Lanser, Richard | 2021-04-27 03:41 | Closed | PL-00491 | 3332-PU-4024 - THIRD CLEANER FEED PUMP | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-02-14 14:11 | 2021-01-31 14:11 |  | Lanser, Richard | 2021-04-21 11:47 | Closed | PL-00493 | 3332-PU-4024 - THIRD CLEANER FEED PUMP | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS08 - Molybdenum Thickener and Concentrate Filter | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains |  | 2021-04-24 05:29 |  |  |  | Submitted | PL-01663 | 3333-PU-4040 - FILTER AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Piping incomplete
C | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:12 | 2021-01-15 02:18 | 2021-04-23 01:14 |  |  | Rejected | PL-00183 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up painting as required | 2: B-Low
C | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:13 | 2021-01-15 02:18 | 2021-04-23 01:14 |  |  | Rejected | PL-00184 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up painting as required | 2: B-Low
C | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:14 | 2021-01-15 02:18 | 2021-04-23 01:14 |  |  | Rejected | PL-00185 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up painting as required | 2: B-Low
C | Item Incomplete | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:14 | 2021-01-15 02:18 | 2021-04-23 01:14 |  |  | Rejected | PL-00186 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up painting as required | 2: B-Low
C | Item Incomplete | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-21 05:29 | 2021-02-19 05:28 |  | Lanser, Richard | 2021-04-18 01:37 | Closed | PL-00663 | 3335-PU-4155 - FLUSH CHARGE PUMP | S1 - Stage 1 Construction Completion | Anchor bolts not tight | 1: A-High
C | Item Incomplete | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-21 05:47 | 2021-02-19 05:46 |  | Lanser, Richard | 2021-04-18 01:38 | Closed | PL-00664 | 3335-PU-4095 - PROCESS WATER PUMP | S1 - Stage 1 Construction Completion | Anchor bolts not tight | 1: A-High
C | Item Incomplete | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-21 05:49 | 2021-02-19 05:48 |  | Lanser, Richard | 2021-04-18 01:38 | Closed | PL-00665 | 3335-PU-4096 - PROCESS WATER PUMP (STANDBY) | S1 - Stage 1 Construction Completion | Anchor bolts not tight | 1: A-High
C | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-03 - Flocculant area sump |  | 2021-04-22 04:17 |  | Lanser, Richard | 2021-04-27 03:40 | Closed | PL-01632 | 3334-PU-4056 - FLOCCULANT AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Grout to be completed
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-02 14:48 | 2021-01-31 14:48 |  | Davies, Jesse | 2021-03-17 02:19 | Closed | PL-00498 | 3331-PU-4003 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | grouting not done | 1: A-High
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 14:55 | 2021-01-31 14:55 |  | Nutt, Richard | 2021-02-27 05:59 | Closed | PL-00499 | 3331-PU-4003 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 15:00 | 2021-01-31 14:58 |  | Davies, Jesse | 2021-03-17 02:21 | Closed | PL-00500 | 3331-PU-4004 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP (STAND-BY) | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 15:02 | 2021-01-31 15:01 |  | Lanser, Richard | 2021-02-22 23:22 | Closed | PL-00501 | 3331-PU-4004 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP (STAND-BY) | S1 - Stage 1 Construction Completion | grouting not done | 2: B-Low
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 02:57 |  |  |  | Submitted | PL-01606 | 3331-CH-4009 - CONCENTRATE THICKENER SCREEN UNDERPAN | S1 - Stage 1 Construction Completion | Curtains to be installed at commissioning
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 03:04 |  |  |  | Submitted | PL-01608 | 3331-CH-4007 - CONCENTRATE THICKENER SCREEN FEED BOX | S1 - Stage 1 Construction Completion | Curtains to be installed at commissioning
C | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 03:14 |  |  |  | Submitted | PL-01609 | 3331-CH-4008 - CONCENTRATE THICKENER SCREEN DISCHARGE CHUTE | S1 - Stage 1 Construction Completion | Curtains to be installed at commissioning
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-25 23:16 | 2021-04-23 01:21 |  |  | Rejected | PL-00930 | 3331-80-PWH-0084-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-27 02:38 | 2021-04-23 01:20 |  |  | Rejected | PL-00937 | 3331-150-CSL-0007-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:11 |  |  |  | Submitted | PL-00735 | 3331-150-PWL-0019-H14 - PWL Process Line | S1 - Stage 1 Construction Completion | Labels
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 04:55 |  |  |  | Submitted | PL-00748 | 3331-160-CSL-0063-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Labels
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-04 04:44 | 2021-02-18 04:43 |  | Liang, Dennis | 2021-03-18 00:09 | Closed | PL-00638 | 3331-100-CSL-0021-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed. Grouting of pipe stands. | 2: B-Low
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 06:08 | 2021-01-26 06:07 |  | Lanser, Richard | 2021-03-28 03:08 | Closed | PL-00314 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Install pipe rest and knock out pot | 1: A-High
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-01-28 20:23 | 2021-01-26 20:23 |  | Lanser, Richard | 2021-03-28 17:12 | Closed | PL-00323 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Pulsation clamps S16 and S9 not installed | 1: A-High
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 22:23 | 2021-01-26 22:22 |  | Nutt, Richard | 2021-03-28 03:39 | Closed | PL-00340 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | P&ID not marked up | 2: B-Low
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 23:03 | 2021-01-26 23:02 |  | Lanser, Richard | 2021-03-28 03:11 | Closed | PL-00346 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Pipe rest not installed | 2: B-Low
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-10 03:04 | 2021-01-27 03:03 |  | Lanser, Richard | 2021-03-28 17:21 | Closed | PL-00350 | 3331-150-CSH-0002-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-10 03:05 | 2021-01-27 03:04 |  | Nutt, Richard | 2021-03-28 03:40 | Closed | PL-00351 | 3331-150-CSH-0002-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | P&ID not marked up | 2: B-Low
C | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 00:17 |  |  |  | Submitted | PL-00982 | 3331-80-PD-0060-R5 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-02-22 04:29 | 2021-04-23 01:09 |  |  | Rejected | PL-00844 | 3332-50-PWH-0054-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:32 |  |  |  | Originated | PL-01657 | 3332-350-MCS-0003-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Minsup couplings missing on 3332-350-MCS-0003-R5 & 3332-150-MCS-0004-R5 and require to be installed
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:26 | 2021-03-02 01:28 | 2021-04-23 01:09 |  |  | Rejected | PL-01004 | 3332-50-MCS-0008-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up | 2: B-Low
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-01 16:47 | 2021-01-30 16:46 |  | Lanser, Richard | 2021-04-19 22:02 | Closed | PL-00422 | 3332-160-PD-0006-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-03-11 20:53 |  | Lanser, Richard | 2021-04-16 07:38 | Closed | PL-01143 | 3332-80-PD-0054-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
C | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump |  | 2021-04-22 04:29 |  |  |  | Submitted | PL-01633 | 3334-PU-4045 - NaHS AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Piping incomplete
C | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:36 |  |  |  | Submitted | PL-01185 | 3332-50-PWH-0008-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
C | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-03-12 12:14 | 2021-03-09 15:13 |  |  |  | Submitted | PL-01126 | 3332-160-PD-0017-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
C | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-09 11:31 | 2021-03-06 14:30 |  |  |  | Submitted | PL-01033 | 3332-50-MCS-0247-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
C | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-09 14:19 | 2021-03-06 17:18 |  |  |  | Submitted | PL-01038 | 3332-110-PD-0028-H14 - PD Process Line | S1 - Stage 1 Construction Completion | supports not installed | 1: A-High
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:34 |  |  |  | Submitted | PL-01422 | 3332-160-PD-0013-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:37 | 2021-04-23 01:09 |  |  | Rejected | PL-01423 | 3332-160-PD-0013-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:40 |  |  |  | Submitted | PL-01424 | 3332-25-PWH-0251-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:46 |  |  |  | Submitted | PL-01428 | 3332-25-PWH-0010-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 02:56 |  |  |  | Submitted | PL-01431 | 3332-25-PWH-0252-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:03 |  |  |  | Submitted | PL-01438 | 3332-25-PWH-0253-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:09 |  | Lanser, Richard | 2021-04-26 06:37 | Closed | PL-01441 | 3332-160-PD-0012-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:13 |  |  |  | Submitted | PL-01445 | 3332-25-PWH-0254-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 03:48 |  |  |  | Submitted | PL-01448 | 3332-25-PWH-0012-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-03 04:02 |  |  |  | Submitted | PL-01451 | 3332-25-PWH-0013-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-19 05:22 |  |  |  | Submitted | PL-01584 | 3332-LD-4002 - FIRST CLEANER CONCENTRATE LAUNDER | S1 - Stage 1 Construction Completion | Defoaming lines not in
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-03-03 21:45 | 2021-02-17 21:44 |  |  |  | Submitted | PL-00615 | 3332-50-PWH-0323-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | supports not installed | 2: B-Low
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:32 |  |  |  | Submitted | PL-01393 | 3332-90-VGN-0020-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | flange managment to be completed
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:33 |  |  |  | Submitted | PL-01394 | 3332-90-VGN-0020-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:37 |  |  |  | Submitted | PL-01396 | 3332-90-VGN-0018-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 01:46 |  |  |  | Submitted | PL-01398 | 3332-90-VGN-0017-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Pipe support to be installed
C | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 03:17 |  |  |  | Submitted | PL-01399 | 3332-LD-4003 - SECOND CLEANER CONCENTRATE LAUNDER | S1 - Stage 1 Construction Completion | DEF lines to be fitted to launder
C | Item Incomplete | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:02 |  |  |  | Submitted | PL-01457 | 3332-25-PWH-0249-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:06 |  |  |  | Submitted | PL-01460 | 3332-50-PWH-0188-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:10 |  |  |  | Submitted | PL-01463 | 3332-25-PWH-0020-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-04 02:13 |  |  |  | Submitted | PL-01466 | 3332-25-PWH-0250-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-26 22:26 |  |  |  | Submitted | PL-01673 | 3332-200-MCS-0273-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Blind Flange not installed
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-12 15:48 | 2021-01-29 15:47 |  | Gayler, Randal | 2021-03-04 23:08 | Closed | PL-00371 | 3335-50-IA-0044-C4 - IA Process Line | S1 - Stage 1 Construction Completion | S11 u-bolt guide not installed. | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 01:53 | 2021-03-15 01:52 |  |  |  | Submitted | PL-01203 | 3335-OP-4573-IA - INSTRUMENT AIR HEADER TO 3335-OP-4573 ISOLATION VALVE 3335VV1922 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 01:57 | 2021-03-15 01:56 |  |  |  | Submitted | PL-01204 | 3334-OP-4084-IA - INSTRUMENT AIR HEADER TO 3334-OP-4084 ISOLATION VALVE 3335VV1931 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:01 | 2021-03-15 02:00 |  |  |  | Submitted | PL-01205 | 3331-OP-4002-IA - INSTRUMENT AIR HEADER TO 3331-OP-4002 ISOLATION VALVE 3335VV0200 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:04 | 2021-03-15 02:03 |  |  |  | Submitted | PL-01206 | 3335-OP-4571-IA - INSTRUMENT AIR HEADER TO 3335-OP-4571 ISOLATION VALVE 3335VV1700 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:06 | 2021-03-15 02:05 |  |  |  | Submitted | PL-01207 | 3335-OP-4574-IA - INSTRUMENT AIR HEADER TO 3335-OP-4574 ISOLATION VALVE 3335VV196 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:34 | 2021-03-15 02:07 |  |  |  | Submitted | PL-01208 | 3335-OP-4093-IA - INSTRUMENT AIR HEADER TO 3335-OP-4093 ISOLATION VALVE 3335VV1918 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:37 | 2021-03-15 02:36 |  |  |  | Submitted | PL-01209 | 3331-OP-4010-IA - INSTRUMENT AIR HEADER TO 3331-OP-4010 ISOLATION VALVE 3335VV0198 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:40 | 2021-03-15 02:39 |  |  |  | Submitted | PL-01210 | 3335-OP-4572-IA - INSTRUMENT AIR HEADER TO 3335-OP-4572 ISOLATION VALVE 3335VV1923 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:42 | 2021-03-15 02:41 |  |  |  | Submitted | PL-01211 | 3331-OP-4001-IA - INSTRUMENT AIR HEADER TO 3331-OP-4001 ISOLATION VALVE 3335VV1933 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:44 | 2021-03-15 02:43 |  |  |  | Submitted | PL-01212 | 3331-OP-4008-IA - INSTRUMENT AIR HEADER TO 3331-OP-4008 ISOLATION VALVE 3335VV1921 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:45 | 2021-03-15 02:45 |  |  |  | Submitted | PL-01213 | 3331-OP-4009-IA - INSTRUMENT AIR HEADER TO 3331-OP-4009 ISOLATION VALVE 3335VV1916 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 02:49 | 2021-03-15 02:48 |  |  |  | Submitted | PL-01214 | 3331-OP-4004-IA - INSTRUMENT AIR HEADER TO 3331-OP-4004 ISOLATION VALVE 3335VV1920 | S1 - Stage 1 Construction Completion | U-Bolts to be installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-03-18 00:35 | 2021-04-23 01:09 |  |  | Rejected | PL-01245 | 3335-50-IA-0023-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:33 | 2021-01-18 02:33 |  |  |  | Originated | PL-00167 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete touch up as per site spec | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:35 | 2021-01-18 02:34 |  |  |  | Originated | PL-00168 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete touch up as per site spec | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:35 | 2021-01-18 02:35 |  |  |  | Originated | PL-00169 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete touch up as per site spec | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B | 2021-02-01 02:36 | 2021-01-18 02:36 |  |  |  | Originated | PL-00170 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete touch up as per site spec | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:26 | 2021-04-23 01:09 |  |  | Rejected | PL-01230 | 3332-25-IA-0115-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:32 | 2021-04-23 01:09 |  |  | Rejected | PL-01233 | 3332-50-IA-0089-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header |  | 2021-03-17 22:51 | 2021-04-23 01:09 |  |  | Rejected | PL-01234 | 3332-50-IA-0028-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-01-31 14:32 | 2021-01-29 14:32 |  | Liang, Dennis | 2021-03-18 22:38 | Closed | PL-00366 | 3332-50-IA-0016-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Pipe supports not installed | 1: A-High
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:14 | 2021-01-27 09:14 | 2021-04-23 01:09 |  |  | Rejected | PL-00354 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up paint as required | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:16 | 2021-01-27 09:15 | 2021-04-23 01:09 |  |  | Rejected | PL-00355 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up paint as required | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:17 | 2021-01-27 09:16 |  |  |  | Originated | PL-00356 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion |  | 2: B-Low
C | Item Incomplete | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-10 09:18 | 2021-01-27 09:17 | 2021-04-23 01:09 |  |  | Rejected | PL-00357 | 3332-50-IA-0025-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Touch up paint as required | 2: B-Low
C | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-24 17:08 |  | Lanser, Richard | 2021-04-17 01:23 | Closed | PL-00870 | 3335-TA-4021 - RAW WATER TANK | S1 - Stage 1 Construction Completion | install piping U bolts
C | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank | 2021-02-26 15:50 | 2021-02-13 02:50 |  | Lanser, Richard | 2021-04-17 01:24 | Closed | PL-00575 | 3335-400-RWA-0002-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Ubolt required | 2: B-Low
C | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-03-28 22:48 |  | Lanser, Richard | 2021-04-05 19:19 | Closed | PL-01390 | 3335-100-RWA-0257-C5 - Raw water header | S1 - Stage 1 Construction Completion | ubolts to be installed
C | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header | 2021-02-26 15:44 | 2021-02-13 02:43 |  | Lanser, Richard | 2021-04-05 19:20 | Closed | PL-00573 | 3335-100-RWA-0008-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Ubolts required | 2: B-Low
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-01 03:19 | 2021-02-15 03:18 |  | Lanser, Richard | 2021-04-19 22:07 | Closed | PL-00593 | 3335-25-PWH-0335-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Supports & Ubolts not installed | 2: B-Low
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-02 19:21 | 2021-02-16 19:17 |  | Lanser, Richard | 2021-04-19 22:07 | Closed | PL-00605 | 3332-50-PWH-0207-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Grouting required under pipe supports | 2: B-Low
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-02 - Process Water to Concentrate Feed Pumps | 2021-03-04 05:00 | 2021-02-18 05:00 |  |  |  | Submitted | PL-00645 | 3331-50-PWH-0105-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | U-bolt not installed | 2: B-Low
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 05:26 |  |  |  | Submitted | PL-00908 | 3332-50-PWH-0001-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 20:02 | 2021-04-23 01:09 |  |  | Rejected | PL-00919 | 3332-50-PWH-0215-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 21:27 | 2021-04-23 01:09 |  |  | Rejected | PL-00922 | 3332-25-PWH-0319-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-25 21:37 | 2021-04-23 01:09 |  |  | Rejected | PL-00924 | 3332-50-PWH-0324-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-01 06:16 | 2021-02-15 06:15 |  |  |  | Submitted | PL-00601 | 3332-100-PWH-0030-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe supports & Ubolts to be installed. | 2: B-Low
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 07:13 | 2021-03-06 10:12 |  |  |  | Submitted | PL-01022 | 3332-50-PWH-0037-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Valve handles need to be turned | 1: A-High
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:27 | 2021-04-23 01:09 |  |  | Rejected | PL-01221 | 3332-80-PWH-0033-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner |  | 2021-03-16 04:36 | 2021-04-23 01:09 |  |  | Rejected | PL-01223 | 3332-50-PWH-0360-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area |  | 2021-04-04 06:10 |  |  |  | Submitted | PL-01472 | 3335-50-PWH-0005-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Lagging
C | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-01 01:29 | 2021-02-15 01:28 |  | Lanser, Richard | 2021-04-18 06:49 | Closed | PL-00590 | 3331-80-PWH-0035-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Pipe support S16 to be installed | 2: B-Low
C | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-17 23:06 | 2021-02-03 23:06 |  | Lanser, Richard | 2021-03-09 06:15 | Closed | PL-00529 | 3334-50-FLOC-0002-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed | 2: B-Low
C | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 00:59 | 2021-02-04 00:59 |  | Lanser, Richard | 2021-03-09 06:25 | Closed | PL-00533 | 3334-25-FLOC-0003-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed | 2: B-Low
C | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:05 | 2021-02-04 01:04 |  | Lanser, Richard | 2021-04-06 22:47 | Closed | PL-00535 | 3334-25-FLOC-0004-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Flange management required | 2: B-Low
C | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:06 | 2021-02-04 01:05 |  | Lanser, Richard | 2021-04-06 22:58 | Closed | PL-00536 | 3334-25-FLOC-0004-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed | 2: B-Low
C | Item Incomplete | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-03 - Flocculant area sump |  | 2021-04-22 04:14 |  |  |  | Submitted | PL-01631 | 3334-PU-4056 - FLOCCULANT AREA SUMP PUMP | S1 - Stage 1 Construction Completion | Piping incomplete
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-02-18 22:27 |  |  |  | Submitted | PL-00647 | 3331-110-VGN-0016-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 05:52 | 2021-02-14 05:52 |  |  |  | Originated | PL-00582 | 3331-100-PWH-0013-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed | 2: B-Low
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 04:16 |  | Davies, Jesse | 2021-03-19 22:20 | Closed | PL-00840 | 3331-150-CSL-0032-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Pipe supports need to be installed
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-24 17:40 |  |  |  | Submitted | PL-00876 | 3331-PU-4003 - COPPER CONCENTRATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | First fill Nitrogen Gas on Pulsation Dampeners
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-28 05:48 |  |  |  | Submitted | PL-00963 | 3331-110-CSL-0061-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-05 19:54 |  | Lanser, Richard | 2021-04-16 21:05 | Closed | PL-01478 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Install Minsup connection and clean up under thickener
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:35 |  | Lanser, Richard | 2021-04-16 20:51 | Closed | PL-01353 | 3331-63-MCS-0305-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Install mnsups
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:32 |  | Lanser, Richard | 2021-04-18 04:05 | Closed | PL-01146 | 3331-90-PD-0011-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install all missing u-bolts, supports and cable ladder
C | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 23:41 |  |  |  | Submitted | PL-01156 | 3331-90-PD-0001-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
C | Item Incomplete | STRU | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-04-23 23:35 |  |  |  | Originated | PL-01659 | 3332-150-MCS-0004-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | 3332-150-MCS-0004-R5 - floor penetrations to be fixed
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-21 23:42 |  |  |  | Submitted | PL-00233 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Handrail to be completed easten end
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-21 23:47 |  |  |  | Submitted | PL-00234 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Install stairtread on small stairway above regring mill
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 00:02 |  |  |  | Submitted | PL-00238 | Steel Phase 3 - Phase three (3) Steel Structure | S1 - Stage 1 Construction Completion | Handrail & kickrails not complete. Boltholes to be drilled & bolted, kickrails to be installed
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-02-22 05:26 |  |  |  | Submitted | PL-00846 | Steel Phase 3 - Phase three (3) Steel Structure | S1 - Stage 1 Construction Completion | Structural bolts & cross bracing to be tightened and X marked
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2020-12-30 04:05 | 2020-12-16 04:04 |  |  |  | Originated | PL-00058 | Con. Tank Access Structure - Bulk Concentrate Handling Facility | S1 - Stage 1 Construction Completion | Handrail to be reinstated on first floor | 2: B-Low
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-02-25 02:22 | 2021-02-22 05:19 |  |  |  | Submitted | PL-00845 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Structural bolts & cross bracing to be tightened and X marked | 1: A-High
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:28 | 2021-02-22 05:28 |  |  |  | Submitted | PL-00847 | Steel Phase 4 - Phase four (4) Steel Structure | S1 - Stage 1 Construction Completion | Structural bolts & cross bracing to be tightened and X marked | 2: B-Low
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:33 | 2021-02-22 05:33 |  |  |  | Submitted | PL-00851 | Steel Phase 5 - Phase five (5) Steel Structure | S1 - Stage 1 Construction Completion | Structural bolts & cross bracing to be tightened and X marked | 2: B-Low
C | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:59 | 2021-02-22 05:59 |  |  |  | Submitted | PL-00856 | Steel Phase 6 - Phase six (6) Steel Structure | S1 - Stage 1 Construction Completion | Structural bolts & cross bracing to be tightened and X marked | 2: B-Low
C | Item not secured | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-20 05:30 |  | Davies, Jesse | 2021-03-19 23:21 | Closed | PL-00217 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Remove remaining ropes and slings
C | Missing Labels | ELEC | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 00:24 | 2021-01-05 17:49 |  |  |  | Originated | PL-00151 | 3334-AG-4013-M1 - Motor for FLOCCULANT PREPARATION TANK AGITATOR | S1 - Stage 1 Construction Completion | UGCA-RFI-000133 | 2: B-Low
C | Missing Labels | ELEC | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 05:54 | 2021-01-05 17:01 |  |  |  | Originated | PL-00149 | 3334-AT-4001-M1 - Motor for BIN FILTER ACTIVATOR | S1 - Stage 1 Construction Completion | UGCA-RFI-000133 | 2: B-Low
C | Missing Labels | ELEC | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 05:54 | 2021-01-05 17:15 |  |  |  | Originated | PL-00150 | 3334-VI-4001-M1 - Motor for BIN VIBRATOR | S1 - Stage 1 Construction Completion | UGCA-RFI-000133 | 2: B-Low
C | Missing Labels | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-03-09 22:55 | 2021-02-23 01:54 |  | Lanser, Richard | 2021-03-28 17:23 | Closed | PL-00863 | 3331-PSV-0079 - OUTLET COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
C | Missing Labels | MECH | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-01-29 02:02 | 2021-01-15 02:18 |  |  |  | Originated | PL-00180 | 3335-80-IA-0071-C4 - IA Process Line | S1 - Stage 1 Construction Completion | INSTALL CORRECT PERMANENT LINE LABELS AND CORRECTLY FITTED & VISIBLE | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-25 23:04 |  |  |  | Submitted | PL-00928 | 3331-90-CSL-0101-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-25 23:14 |  |  |  | Submitted | PL-00929 | 3331-80-PWH-0084-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-27 02:33 |  |  |  | Submitted | PL-00936 | 3331-150-CSL-0007-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-27 03:25 |  |  |  | Submitted | PL-00938 | 3331-150-CSL-0006-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-27 03:41 |  |  |  | Submitted | PL-00939 | 3331-90-CSL-0100-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-02-27 04:02 |  |  |  | Submitted | PL-00942 | 3331-80-PWH-0011-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-02-28 04:17 |  |  |  | Submitted | PL-00960 | 3331-160-PD-0006-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-02 06:20 | 2021-01-19 06:19 |  |  |  | Originated | PL-00200 | 3331-160-CSL-0011-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Attach line labels | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-02 06:42 | 2021-01-19 06:41 |  |  |  | Originated | PL-00204 | 3331-160-CSL-0010-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | Install labels | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-28 03:30 |  |  |  | Submitted | PL-00957 | 3331-110-CSL-0050-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-04 03:47 | 2021-02-18 03:46 |  |  |  | Submitted | PL-00635 | 3331-150-CSL-0062-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-04 04:47 | 2021-02-18 04:46 |  |  |  | Submitted | PL-00640 | 3331-100-CSL-0021-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) |  | 2021-01-26 20:19 |  | Lanser, Richard | 2021-03-28 16:57 | Closed | PL-00321 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 05:27 | 2021-01-26 05:26 |  | Lanser, Richard | 2021-03-28 16:47 | Closed | PL-00304 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 05:37 | 2021-01-26 05:36 |  | Lanser, Richard | 2021-03-28 16:48 | Closed | PL-00307 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Pipe labels not applied | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 22:58 | 2021-01-26 22:57 |  | Lanser, Richard | 2021-03-28 17:19 | Closed | PL-00344 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-02-28 23:43 |  |  |  | Submitted | PL-00978 | 3331-80-PD-0056-R5 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 00:06 |  |  |  | Submitted | PL-00980 | 3331-90-PD-0057-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-01 00:14 |  |  |  | Submitted | PL-00981 | 3331-80-PD-0058-R5 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-04-26 21:48 | 2021-04-12 21:48 |  |  |  | Originated | PL-01533 | 3331-90-PD-0061-H14 - PD Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:23 | 2021-02-28 23:07 |  |  |  | Originated | PL-00976 | 3332-350-MCS-0003-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:23 | 2021-03-01 04:09 |  |  |  | Submitted | PL-00989 | 3332-150-MCS-0004-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:24 | 2021-03-01 06:25 |  |  |  | Submitted | PL-00992 | 3332-110-PD-0002-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:24 | 2021-03-01 06:30 |  |  |  | Submitted | PL-00994 | 3332-110-PD-0004-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:24 | 2021-03-02 00:40 |  |  |  | Submitted | PL-00998 | 3332-110-VGN-0002-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:25 | 2021-03-02 00:49 |  |  |  | Submitted | PL-01000 | 3332-160-MCS-0111-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:25 | 2021-03-02 01:17 |  |  |  | Submitted | PL-01002 | 3332-110-PD-0168-H14 - PD Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:25 | 2021-03-02 01:25 |  |  |  | Submitted | PL-01003 | 3332-50-MCS-0008-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-04-28 03:26 | 2021-03-02 02:28 |  |  |  | Submitted | PL-01005 | 3332-350-MCS-0202-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
C | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-21 - Rougher Area Sump 2 & NaHS Sump | 2021-04-23 22:11 | 2021-04-09 22:11 |  |  |  | Originated | PL-01501 | 3332-110-VGN-0103-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install valve ID tag | 2: B-Low
C | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-03-20 06:23 |  |  |  | Submitted | PL-01283 | 3332-110-VGN-0091-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install permanent line labels
C | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-04-04 03:28 | 2021-03-20 06:27 |  |  |  | Submitted | PL-01285 | 3332-110-VGN-0091-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | install permanent valve ID tag | 2: B-Low
C | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-04-04 19:33 | 2021-03-20 22:29 |  |  |  | Submitted | PL-01287 | 3332-25-PWH-0255-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air |  |  | 2021-01-21 06:32 |  |  |  | Originated | PL-00225 |  | S1 - Stage 1 Construction Completion | Attach permanent labels to pipe
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-01-21 06:18 |  |  |  | Originated | PL-00222 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Fit permanent labels to pipe
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-04 20:35 | 2021-01-21 20:34 |  |  |  | Originated | PL-00228 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-04 23:21 | 2021-01-21 23:21 |  |  |  | Originated | PL-00231 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Fit permanent line labels to pipe | 2: B-Low
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-05 01:31 | 2021-01-22 01:30 |  |  |  | Originated | PL-00240 | 3332-80-IA-0001-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-05 02:18 | 2021-01-22 02:18 |  |  |  | Originated | PL-00243 | 3332-50-IA-0112-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-06 03:05 | 2021-01-23 03:05 |  |  |  | Originated | PL-00266 | 3332-50-IA-0083-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution |  | 2021-03-19 05:54 |  |  |  | Submitted | PL-01268 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | install permanent line labels
C | Missing Labels | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution | 2021-04-03 02:50 | 2021-03-19 05:49 |  |  |  | Submitted | PL-01266 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | install line labels | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-15 03:17 |  | Lanser, Richard | 2021-04-19 07:07 | Closed | PL-00592 | 3335-25-PWH-0335-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-01 03:32 | 2021-02-15 03:31 |  |  |  | Submitted | PL-00595 | 3335-100-PWL-0012-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-01 03:45 | 2021-02-15 03:44 |  |  |  | Submitted | PL-00597 | 3335-50-PWL-0019-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-02 19:16 | 2021-02-16 19:15 |  |  |  | Submitted | PL-00604 | 3332-50-PWH-0207-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-02 19:46 | 2021-02-16 19:45 |  |  |  | Submitted | PL-00607 | 3332-50-PWH-0063-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-02 21:22 | 2021-02-16 21:22 |  |  |  | Submitted | PL-00609 | 3332-50-PWH-0207-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to valves & fittings | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-02 21:52 | 2021-02-16 21:52 |  |  |  | Submitted | PL-00610 | 3332-50-PWH-0063-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to valves | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-01 06:13 | 2021-02-15 06:12 |  |  |  | Submitted | PL-00599 | 3332-100-PWH-0030-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-01 06:14 | 2021-02-15 06:14 |  |  |  | Submitted | PL-00600 | 3332-100-PWH-0030-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | 2021-04-01 05:58 | 2021-03-18 05:58 |  |  |  | Originated | PL-01254 |  | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | 2021-04-01 06:03 | 2021-03-18 06:03 |  |  |  | Originated | PL-01255 | 3332-50-PWH-0039-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | 2021-04-01 19:50 | 2021-03-18 19:49 |  |  |  | Originated | PL-01257 | 3335-80-PWH-0006-C6-TI - PWH Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-01 01:24 | 2021-02-15 01:24 |  |  |  | Originated | PL-00588 | 3331-80-PWH-0035-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 04:29 |  |  |  | Submitted | PL-00399 | 3334-15-FLOC-0042-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to valves & fittings
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 04:31 |  |  |  | Submitted | PL-00401 | 3334-15-FLOC-0042-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 05:29 |  |  |  | Submitted | PL-00404 | 3334-25-FLOC-0020-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to valves & fittings
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 00:57 | 2021-01-30 00:57 |  |  |  | Submitted | PL-00383 | 3334-50-FLOC-0047-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Install permanent line labels | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 02:51 | 2021-01-30 02:50 |  |  |  | Submitted | PL-00386 | 3334-50-FLOC-0046-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 02:57 | 2021-01-30 02:57 |  |  |  | Submitted | PL-00388 | 3334-50-FLOC-0047-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 03:41 | 2021-01-30 03:40 |  |  |  | Submitted | PL-00390 | 3334-15-FLOC-0044-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 03:45 | 2021-01-30 03:44 |  |  |  | Submitted | PL-00391 | 3334-15-FLOC-0044-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 04:15 | 2021-01-30 04:15 |  |  |  | Submitted | PL-00394 | 3334-15-FLOC-0045-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 04:19 | 2021-01-30 04:18 |  |  |  | Submitted | PL-00396 | 3334-15-FLOC-0045-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to valves & fittings | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 05:27 | 2021-01-30 05:26 |  |  |  | Submitted | PL-00402 | 3334-25-FLOC-0020-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-17 22:57 | 2021-02-03 22:57 |  |  |  | Submitted | PL-00525 | 3334-50-FLOC-0002-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-17 23:05 | 2021-02-03 23:05 |  |  |  | Submitted | PL-00528 | 3334-50-FLOC-0002-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 00:33 | 2021-02-04 00:32 |  |  |  | Submitted | PL-00530 | 3334-25-FLOC-0003-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:03 | 2021-02-04 01:03 |  |  |  | Submitted | PL-00534 | 3334-25-FLOC-0004-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:46 | 2021-02-04 01:46 |  |  |  | Submitted | PL-00538 | 3334-40-FLOC-0048-C3 - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-20 20:28 |  |  |  | Originated | PL-00220 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Attach valve ID tags
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 05:51 | 2021-02-14 05:50 |  |  |  | Originated | PL-00581 | 3331-100-PWH-0013-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 21:32 | 2021-02-14 21:32 |  |  |  | Originated | PL-00585 | 3331-300-PWL-0001-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-03-03 23:33 | 2021-02-17 23:32 |  |  |  | Submitted | PL-00619 |  | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-04 01:51 |  |  |  | Submitted | PL-01454 | 3331-90-VGN-0212-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-11 05:02 |  |  |  | Submitted | PL-01518 | 3331-110-CSL-0031-H14 - CSL Process Line | S1 - Stage 1 Construction Completion | ISO Label
C | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump | 2021-04-04 02:27 | 2021-03-20 05:26 |  |  |  | Submitted | PL-01279 | 3331-80-PD-0063-R5 - PD Process Line | S1 - Stage 1 Construction Completion | install permanent valve ID tags | 2: B-Low
C | Missing Parts | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-01 23:28 | 2021-01-18 23:27 |  |  |  | Originated | PL-00194 | 3331-LT-2103 - TH4001 BED LEVEL | S1 - Stage 1 Construction Completion | Install top “U” bolt on 3331-LT-2103 probe conduit | 2: B-Low
C | Missing Parts | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-05 02:20 | 2021-01-22 02:19 |  |  |  | Originated | PL-00244 | 3332-50-IA-0112-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Install all U Bolts to line | 2: B-Low
C | Missing Parts | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks |  | 2021-02-26 09:39 |  |  |  | Originated | PL-00931 | 3332-50-PWH-0215-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Electrical tracing and thermal insulation to be applied to pipe, when available.
C | Missing Parts | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-13 06:56 | 2021-02-26 09:56 |  |  |  | Originated | PL-00932 | 3332-25-PWH-0319-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Electrical tracing and thermal insulation to be applied to pipe, when available. | 2: B-Low
C | Missing Parts | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-13 06:57 | 2021-02-26 09:57 |  |  |  | Originated | PL-00933 | 3332-25-PWH-0356-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Electrical tracing and thermal insulation to be applied to pipe, when available. | 2: B-Low
C | Missing Parts | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-23 22:00 | 2021-02-09 22:00 |  |  |  | Originated | PL-00567 | 3331-160-PD-0008-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Install u-bolt support. | 2: B-Low
C | Missing Parts | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 21:44 | 2021-01-20 05:26 |  |  |  | Submitted | PL-00216 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | U-Bolts etc to be installed | 2: B-Low
C | Not to Contract Spec | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump |  | 2021-03-19 01:49 |  | Fuller, Lachlan | 2021-04-25 05:54 | Closed | PL-01253 | 3331-VS-4004 - VSD for 3331-PU-4007 | S2 - Stage 2 Pre Commissioning | Increase acceleration and deacceleration times from 20 to 40 sec.
C | Not to Contract Spec | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 03:42 | 2021-02-01 03:42 |  |  |  | Originated | PL-00515 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Handrail not as per AS | 2: B-Low
C | Not to Contract Spec | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 06:56 | 2021-02-01 06:55 |  |  |  | Originated | PL-00520 | 3332-FB-4005 - ROUGHER SCAVENGER FLOTATION CELL 5 | S1 - Stage 1 Construction Completion | Handrail not as per Australian Standard | 2: B-Low
C | Not to Contract Spec | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-15 07:11 | 2021-02-01 07:11 |  |  |  | Originated | PL-00523 | 3332-FB-4003 - ROUGHER SCAVENGER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Handrail not as per Australian Standard | 2: B-Low
C | Not to Contract Spec | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-18 09:44 | 2021-02-04 09:44 |  |  |  | Originated | PL-00545 | 3332-FB-4004 - ROUGHER SCAVENGER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | Handrail not as per Australian Standard | 2: B-Low
C | Not to Contract Spec | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-04 02:23 | 2021-02-18 02:22 |  | Lanser, Richard | 2021-04-05 23:18 | Closed | PL-00624 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Toch up paint | 2: B-Low
C | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-02-21 05:06 | 2021-04-23 01:22 |  |  | Rejected | PL-00755 | 3331-150-CSL-0020-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
C | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-04 03:51 | 2021-02-18 03:50 | 2021-04-23 01:17 |  |  | Rejected | PL-00637 | 3331-150-CSL-0062-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-04 04:48 | 2021-02-18 04:47 | 2021-04-23 01:17 |  |  | Rejected | PL-00642 | 3331-100-CSL-0021-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air |  |  | 2021-01-21 06:41 | 2021-04-23 01:25 |  |  | Rejected | PL-00226 |  | S1 - Stage 1 Construction Completion | Paint bare sections of pipe
C | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-01-21 06:25 | 2021-04-23 01:15 |  |  | Rejected | PL-00224 | 3335-50-IA-0032-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Pipe requires some sections of paint
C | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-01-21 20:37 |  |  |  | Originated | PL-00229 | 3335-50-IA-0047-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Sections of paint removed for pipe threading need to be painted
C | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-01-21 23:23 |  |  |  | Originated | PL-00232 | 3335-50-IA-0038-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Pipe needs sections of removed paint taken off for threading to be redone
C | Not to Contract Spec | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header | 2021-02-26 15:47 | 2021-02-13 02:46 | 2021-04-23 01:13 |  |  | Rejected | PL-00574 | 3335-100-RWA-0008-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up painting required | 2: B-Low
C | Not to Contract Spec | PIPE | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-02-27 09:50 | 2021-02-13 20:50 | 2021-04-23 01:19 |  |  | Rejected | PL-00577 | 3335-100-RWA-0016-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up painting required | 2: B-Low
C | Not to Contract Spec | PIPE | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-02-27 09:58 | 2021-02-13 20:58 | 2021-04-23 01:13 |  |  | Rejected | PL-00578 | 3335-100-RWA-0017-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up painting required | 2: B-Low
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-15 03:20 | 2021-04-23 01:25 |  |  | Rejected | PL-00594 | 3335-25-PWH-0335-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-16 19:23 | 2021-04-23 01:24 |  |  | Rejected | PL-00606 | 3332-50-PWH-0207-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-16 19:47 | 2021-04-23 01:24 |  |  | Rejected | PL-00608 | 3332-50-PWH-0063-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-01 03:33 | 2021-02-15 03:33 | 2021-04-23 01:19 |  |  | Rejected | PL-00596 | 3335-100-PWL-0012-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-01 03:47 | 2021-02-15 03:46 | 2021-04-23 01:18 |  |  | Rejected | PL-00598 | 3335-50-PWL-0019-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-02 - Process Water to Concentrate Feed Pumps | 2021-02-27 10:13 | 2021-02-13 21:13 | 2021-04-23 01:19 |  |  | Rejected | PL-00579 | 3335-100-PWH-0013-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | painting required | 2: B-Low
C | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-01 06:26 | 2021-02-15 06:25 | 2021-04-23 01:09 |  |  | Rejected | PL-00603 | 3332-100-PWH-0030-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 02:53 |  | Lanser, Richard | 2021-04-06 22:36 | Closed | PL-00387 | 3334-50-FLOC-0046-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sectionsof paint removed for pipe threading need to painted
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 03:46 |  | Lanser, Richard | 2021-04-06 22:37 | Closed | PL-00392 | 3334-15-FLOC-0044-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sections of paint removed for pipe threading need to painted
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 04:21 |  | Lanser, Richard | 2021-04-06 22:38 | Closed | PL-00397 | 3334-15-FLOC-0045-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sections of paint removed for pipe threading need to painted
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 04:26 |  | Lanser, Richard | 2021-04-06 22:39 | Closed | PL-00398 | 3334-15-FLOC-0042-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sections of paint removed for pipe threading need to painted
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-30 05:31 |  | Lanser, Richard | 2021-04-06 22:39 | Closed | PL-00405 | 3334-25-FLOC-0020-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sections of paint removed for pipe threading need to painted
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-13 02:59 | 2021-01-30 02:59 |  | Lanser, Richard | 2021-04-06 22:41 | Closed | PL-00389 | 3334-50-FLOC-0047-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Sectionsof paint removed for pipe threading need to painted | 2: B-Low
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 00:42 | 2021-02-04 00:42 |  | Lanser, Richard | 2021-04-06 22:42 | Closed | PL-00532 | 3334-25-FLOC-0003-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:07 | 2021-02-04 01:07 |  | Lanser, Richard | 2021-04-06 23:02 | Closed | PL-00537 | 3334-25-FLOC-0004-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-18 01:56 | 2021-02-04 01:56 |  | Lanser, Richard | 2021-04-06 23:02 | Closed | PL-00541 | 3334-40-FLOC-0048-C3 - FLOC Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-20 05:49 |  | Lanser, Richard | 2021-04-06 23:08 | Closed | PL-00218 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | 3 field welds require painting
C | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-02-14 05:53 | 2021-04-23 01:14 |  |  | Rejected | PL-00583 | 3331-100-PWH-0013-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting
C | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 21:36 | 2021-02-14 21:36 | 2021-04-23 01:13 |  |  | Rejected | PL-00587 | 3331-300-PWL-0001-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-03-03 23:35 | 2021-02-17 23:34 | 2021-04-23 01:18 |  |  | Rejected | PL-00620 |  | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-15 02:12 | 2021-02-01 02:12 | 2021-04-23 01:19 |  |  | Rejected | PL-00512 | 3331-150-CSL-0003-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
C | Not to Equipment Specs | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-04-03 18:23 | 2021-03-19 21:23 | 2021-04-05 03:25 |  |  | Rejected | PL-01272 | 3332-25-PWL-0176-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Touch up paint | 2: B-Low
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00072 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Lid to be installed onto main 33kV pit on western side of access road
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00073 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Earthworks to be finalised around 33kV pit on western side of access road to direct surface drainage water away
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00075 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Permanent buried cable marker post to be installed on Molyplant side of access road (temp sign currently installed)
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00077 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Buried cable markers to be installed within moly plant to identify buried 33kV cable route
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00098 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Permanent arc flash labelling to be attached to RMU (temporary labelling has been installed)
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00106 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Final earth works in front of compound to be completed
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00108 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Transformer touch up paint to be applied to address multiple paint chips
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00117 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Final earth works in front of compound to be completed
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00119 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Transformer touch up paint to be applied to address multiple paint chips
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00124 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Cable tray lids to be installed
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00128 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : External earth pit and lids to be installed c/w labelling on lids to identify electrode
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00132 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Switchroom floor to be sealed and painted
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00133 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Ablative coating to be applied to all internal cabling within switchroom
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00134 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Authorised entry only and Danger 415V signage to be attached to the access door to switchroom
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  |  |  | Originated | PL-00140 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : External door 2hr fire rating compliance plates missing from door and frame
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00083 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Earthing drawing 730-338-EL-DDL-4237 to be updated to show new RMU compound earth bar and earth bar numbering
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00084 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Multiple earth cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00085 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : 33kV conduits to be sealed
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00089 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : 33kV cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00110 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Multiple earth cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00111 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : 33kV conduit to be sealed
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Hemmings, Sam | 2020-12-16 | Closed | PL-00121 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Multiple earth cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00096 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : Control cable to RMU heater circuit missing label - URC side of RMU cubicle
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00107 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : Discharge end of the compound bund drain pipe to be accessible
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00109 | 3338-TF-4001 - Distribution Transformer 1 |  | 3338-TF-4001 compound : 33kV cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00118 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : Discharge end of the compound bund drain pipe to be accessible
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00120 | 3338-TF-4002 - Distribution Transformer 2 |  | 3338-TF-4002 compound : 33kV cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Muell, Thomas | 2020-12-18 | Closed | PL-00138 | 3338-SS-4001 - Substation 33kVA |  | 3338-SS-4001 Substation : Multiple earth cable numbers missing
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-18 | Closed | PL-00076 | 3338RU4001-P1 - 33 kV Ring Main Unit |  | 33kV Cable Route : Conduits to be sealed within main 33kV pit on western side of access road
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00078 | 3338-RU-4001 - HV Ring Main Unit |  | 3338-RU-4001 compound : RMU compound fence and gates to be installed and earthed with gates locked
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00142 | 3338-MC-4001 - Motor Control Centre No 1 |  | 3338-MC-4001 : Permanent arc flash stickers to be attached to front of switchboard
C | Other | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC |  | 2020-12-11 02:22 |  | Polkinghorne, Scott | 2020-12-23 | Closed | PL-00146 | 3338-MC-4002 - Motor Control Centre No 2 |  | 3338-MC-4002 : Permanent arc flash stickers to be attached to front of switchboard
C | Other | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-19 05:12 |  |  |  | Submitted | PL-01582 | 3332-LD-4008 - FIRST CLEANER CONCENTRATE LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | Leak test at completion of scope
C | Other | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-04-19 05:20 |  |  |  | Submitted | PL-01583 | 3332-LD-4002 - FIRST CLEANER CONCENTRATE LAUNDER | S1 - Stage 1 Construction Completion | Leak test to be performed at completion of scope
C | Other | MECH | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-02 06:23 |  | Lanser, Richard | 2021-04-16 21:04 | Closed | PL-01415 | 3332-HP-4001 - SECOND CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Visual inspection for leaks during wet commissioning
C | Other | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 03:50 |  |  |  | Submitted | PL-01400 | 3332-LD-4005 - SECOND CLEANER CONCENTRATE LAUNDER EXTENSION | S1 - Stage 1 Construction Completion | Visual inspection when first wet commissioned
C | Other | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-03-30 04:14 |  |  |  | Submitted | PL-01403 | 3332-LD-4003 - SECOND CLEANER CONCENTRATE LAUNDER | S1 - Stage 1 Construction Completion | To be confirmed on wet commissioning
C | Other | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-04-05 02:05 |  |  |  | Submitted | PL-01480 | 3332-LD-4004 - CLEANER SCAVENGER LAUNDER | S1 - Stage 1 Construction Completion | Visual inspection when first wet commissioned
C | Other | MULTI | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-24 17:15 |  |  |  | Submitted | PL-00872 | 3335-TA-4021 - RAW WATER TANK | S1 - Stage 1 Construction Completion | Move sign
C | Other | PIPE | CS0E - Process Water Distribution | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | 2021-04-01 20:02 | 2021-03-18 20:02 | 2021-04-23 01:08 |  |  | Rejected | PL-01259 | 3335-80-PWH-0006-C6-TI - PWH Process Line | S1 - Stage 1 Construction Completion | Painting | 2: B-Low
D |  | ELEC | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 01:46 |  |  |  | Originated | PL-00947 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Install cable ties on vertical risers, remove unnessessary unistrut on all rougher flotation cells and install cover on top of marshalling box 3332-MB-4022 cable management
D |  | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-18 02:26 |  |  |  | Originated | PL-01557 | 3332-SA-4008 - ROUGHER JAMESON TAILS LSA | S1 - Stage 1 Construction Completion | Labels to be applied
D |  | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-19 22:33 |  |  |  | Originated | PL-00681 | 3335-TA-4022 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Clean tank
D |  | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02B - Instrument air header B |  | 2021-01-18 03:59 |  |  |  | Originated | PL-00173 | 3335-80-IA-0065-C4 - IA Process Line | S1 - Stage 1 Construction Completion
D | Incorrect Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers | 2021-03-21 04:23 | 2021-03-07 04:22 |  |  |  | Originated | PL-01052 | 3332-FIT-0658 - WASH WATER TO ROUGHER JAMESON CELL | S1 - Stage 1 Construction Completion | No stainless instrument tag attached to device | 2: B-Low
D | Incorrect Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | 2021-04-27 07:31 | 2021-04-13 07:30 |  |  |  | Accepted | PL-01541 | 3332-ME-4013 - CAMERA | S1 - Stage 1 Construction Completion | INSTALL LABEL ON EXTERIOR OF CAMERA HOUSING | 2: B-Low
D | Incorrect Labels | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 05:59 | 2021-03-07 05:59 |  |  |  | Originated | PL-01053 | 3332-PI-0183 - NITROGEN TO FIRST CLEANER FLOTATION CELL 1 AGITATOR | S1 - Stage 1 Construction Completion | Stainless instrument ID tag needed | 2: B-Low
D | Incorrect Labels | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 06:04 | 2021-03-07 06:04 |  |  |  | Originated | PL-01054 | 3332-PI-0188 - NITROGEN TO FIRST CLEANER FLOTATION CELL 2 AGITATOR | S1 - Stage 1 Construction Completion | No stainless instrument ID label attached | 2: B-Low
D | Incorrect Labels | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 06:07 | 2021-03-07 06:07 |  |  |  | Originated | PL-01055 | 3332-PI-0192 - NITROGEN TO FIRST CLEANER FLOTATION CELL 3 AGITATOR | S1 - Stage 1 Construction Completion | No stainless instrument ID tag attached | 2: B-Low
D | Incorrect Labels | INST | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells | 2021-03-21 06:10 | 2021-03-07 06:10 |  |  |  | Originated | PL-01056 | 3332-PI-0197 - NITROGEN TO FIRST CLEANER FLOTATION CELL 4 AGITATOR | S1 - Stage 1 Construction Completion | Requires stainless instrument ID tag fitted | 2: B-Low
D | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-26 00:05 |  |  |  | Submitted | PL-00303 | 3334-FIT-2111 - Flow Indicating Transmitter | S2 - Stage 2 Pre Commissioning | IO List indicates wrong mixer
D | Incorrect Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-03-23 02:02 |  |  |  | Submitted | PL-01359 | 3331-PU-4005 - COPPER CONCENTRATE CHARGING PUMP | S1 - Stage 1 Construction Completion | Install tag on 3331-SP-4491 & 3331-SP-4494
D | Incorrect Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 00:42 | 2021-03-07 11:38 |  |  |  | Submitted | PL-01059 | 3334-25-RWA-0007-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Incorrect Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 01:57 | 2021-03-07 12:57 |  |  |  | Submitted | PL-01061 | 3334-25-RWA-0004-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Item Damaged | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:10 |  |  |  | Submitted | PL-01638 | 3332-PU-4012 - ROUGHER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | Clear sump and replace covers
D | Item Damaged | MECH | CS29 - Bio sewage Treatment | CS29-02 - Permanent Building | 2021-01-22 01:05 | 2021-01-08 01:10 |  |  |  | Originated | PL-00154 | 3338-BG-4003 - ABLUTION BLOCK | S1 - Stage 1 Construction Completion | Purchase and replace Lock | 2: B-Low
D | Item Dirty |  | CS0D - Fire Water | CS0D-03 - Fire Water Skid | 2021-02-25 14:39 | 2021-02-12 01:38 |  |  |  | Originated | PL-00571 | 3335-PU-4093 - FIRE WATER PUMP | S1 - Stage 1 Construction Completion | Debris need to be removed from area | 2: B-Low
D | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) | 2021-03-06 03:34 | 2021-02-20 03:33 |  | Lanser, Richard | 2021-04-22 10:16 | Closed | PL-00689 | 3331-PU-4005 - COPPER CONCENTRATE CHARGING PUMP | S1 - Stage 1 Construction Completion | pump needs cleaning | 2: B-Low
D | Item Dirty | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | 2021-03-06 03:24 | 2021-02-20 03:23 |  | Lanser, Richard | 2021-04-20 06:15 | Closed | PL-00688 | 3331-PU-4001 - CONCENTRATE FEED PUMP | S1 - Stage 1 Construction Completion | pump needs cleaning | 2: B-Low
D | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 11:53 | 2021-03-08 14:52 |  | Lanser, Richard | 2021-04-18 00:03 | Closed | PL-01097 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Clean up tank | 2: B-Low
D | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 12:02 | 2021-03-08 15:01 |  | Lanser, Richard | 2021-04-18 00:03 | Closed | PL-01104 | 3332-TA-4004 - ROUGHER CONDITIONING TANK 1 | S1 - Stage 1 Construction Completion | Clean up tank | 2: B-Low
D | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 06:08 |  | Lanser, Richard | 2021-04-05 23:15 | Closed | PL-00860 | 3332-FB-4005 - ROUGHER SCAVENGER FLOTATION CELL 5 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-02-14 13:38 | 2021-01-31 13:37 |  | Lanser, Richard | 2021-04-17 06:38 | Closed | PL-00490 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Pump not clean | 2: B-Low
D | Item Dirty | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener | 2021-03-26 22:27 | 2021-03-12 22:26 |  | Lanser, Richard | 2021-04-16 21:13 | Closed | PL-01196 | 3332-PU-4030 - INTERMEDIATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | needs cleaning | 2: B-Low
D | Item Dirty | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-27 21:28 | 2021-03-13 21:27 |  |  |  | Submitted | PL-01200 | 3332-SN-4003 - REGRIND MILL MEDIA SCREEN | S1 - Stage 1 Construction Completion | Clean up area. | 2: B-Low
D | Item Dirty | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 03:30 |  | Lanser, Richard | 2021-04-05 23:10 | Closed | PL-00827 | 3332-FB-4009 - FIRST CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | Housekeeping
D | Item Dirty | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 03:34 |  | Lanser, Richard | 2021-04-05 23:11 | Closed | PL-00828 | 3332-FB-4007 - FIRST CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Housekeeping
D | Item Dirty | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 03:40 |  | Lanser, Richard | 2021-04-05 23:11 | Closed | PL-00829 | 3332-FB-4008 - FIRST CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | Housekeeping
D | Item Dirty | MECH | CS04 - 1st Cleaner Flotation | CS04-01 - First Cleaner Flotation Cells |  | 2021-02-22 03:46 |  | Lanser, Richard | 2021-04-05 23:11 | Closed | PL-00831 | 3332-FB-4010 - FIRST CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-02-14 14:25 | 2021-01-31 14:24 |  | Lanser, Richard | 2021-04-27 03:41 | Closed | PL-00497 | 3332-PU-4014 - SECOND CLEANER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Pump not clean | 2: B-Low
D | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 03:58 |  | Lanser, Richard | 2021-04-05 23:14 | Closed | PL-00834 | 3332-FB-4011 - SECOND CLEANER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 04:00 |  | Lanser, Richard | 2021-04-05 23:14 | Closed | PL-00835 | 3332-FB-4012 - SECOND CLEANER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 04:03 |  | Lanser, Richard | 2021-04-05 23:15 | Closed | PL-00836 | 3332-FB-4013 - SECOND CLEANER FLOTATION CELL 3 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells |  | 2021-02-22 04:06 |  | Lanser, Richard | 2021-04-05 23:15 | Closed | PL-00837 | 3332-FB-4014 - SECOND CLEANER FLOTATION CELL 4 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 03:52 |  | Lanser, Richard | 2021-04-05 23:11 | Closed | PL-00832 | 3332-FB-4017 - CLEANER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS06 - Cleaner Scavenger Flotation | CS06-01 - Cleaner Flotation Cells |  | 2021-02-22 03:56 |  | Lanser, Richard | 2021-04-05 23:14 | Closed | PL-00833 | 3332-FB-4018 - CLEANER SCAVENGER FLOTATION CELL 2 | S1 - Stage 1 Construction Completion | House keeping required
D | Item Dirty | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-02-14 14:05 | 2021-01-31 14:05 |  |  |  | Submitted | PL-00492 | 3332-PU-4024 - THIRD CLEANER FEED PUMP | S1 - Stage 1 Construction Completion | Pump not clean | 2: B-Low
D | Item Dirty | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) |  | 2021-01-26 05:51 |  | Lanser, Richard | 2021-03-28 16:49 | Closed | PL-00311 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Area needs to be cleaned
D | Item Dirty | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:22 | 2021-01-26 06:21 |  | Lanser, Richard | 2021-03-28 16:53 | Closed | PL-00318 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Area not cleaned up | 2: B-Low
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 00:05 |  |  |  | Originated | PL-00239 | Steel Phase 3 - Phase three (3) Steel Structure | S1 - Stage 1 Construction Completion | Phase 3 to be cleaned
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 22:06 |  |  |  | Submitted | PL-00259 | Filter Building Steel & Stair Tower - Filter Building Steel and Structure | S1 - Stage 1 Construction Completion | Structure to be cleaned
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 22:13 |  |  |  | Submitted | PL-00261 | Steel Phase 4 - Phase four (4) Steel Structure | S1 - Stage 1 Construction Completion | Structure to be cleaned
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2020-12-30 04:23 | 2020-12-16 04:18 |  |  |  | Originated | PL-00060 | Con. Tank Access Structure - Bulk Concentrate Handling Facility | S1 - Stage 1 Construction Completion |  | 2: B-Low
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:35 | 2021-02-22 05:35 |  |  |  | Submitted | PL-00853 | Steel Phase 5 - Phase five (5) Steel Structure | S1 - Stage 1 Construction Completion | Clean up required on all phases | 2: B-Low
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:57 | 2021-02-22 05:57 |  |  |  | Submitted | PL-00854 | Steel Phase 6 - Phase six (6) Steel Structure | S1 - Stage 1 Construction Completion | Structure to be cleaned | 2: B-Low
D | Item Dirty | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 03:02 | 2021-02-22 06:02 |  |  |  | Submitted | PL-00858 | Steel Phase 7 - Phase seven (7) Steel Structure | S1 - Stage 1 Construction Completion | Structure to be cleaned | 2: B-Low
D | Item Incomplete | CABL | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane | 2021-03-25 02:04 | 2021-03-11 02:03 |  | Muell, Thomas | 2021-03-11 06:30 | Closed | PL-01135 | 3331CN4002-P1 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Stainless cable label on field end required | 2: B-Low
D | Item Incomplete | CABL | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-02-24 17:26 |  |  |  | Submitted | PL-00874 | 3331-TH-4001 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Install barrier strip
D | Item Incomplete | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane | 2021-03-25 21:40 | 2021-03-11 21:39 |  |  |  | Originated | PL-01149 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Cutt off bolts on tray support. Add SS cable ties to verticle risers. | 2: B-Low
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed |  | 2020-12-15 02:41 |  |  |  | Originated | PL-00057 | Cadia Molybdenum Plant Earthing System - Cadia Molybdenum Plant Earth Grid System | S1 - Stage 1 Construction Completion | Earth pits for additional earth stakes added to design required to be installed
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2020-12-24 02:17 | 2020-12-22 02:16 |  |  |  | Originated | PL-00061 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Fire system not installed | 1: A-High
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2020-12-24 02:18 | 2020-12-22 02:18 |  |  |  | Originated | PL-00062 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Fire system not complete | 1: A-High
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2020-12-24 02:20 | 2020-12-22 02:19 |  |  |  | Originated | PL-00063 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Air conditioning not installed | 1: A-High
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2020-12-24 02:21 | 2020-12-22 02:21 |  |  |  | Originated | PL-00064 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Fire pillows to be replaced my fire mortar | 1: A-High
D | Item Incomplete | ELEC | CSED - Switch Room & MCCs | CSED-01 - RMU, Transformers and HV Feed | 2020-12-24 02:22 | 2020-12-22 02:22 |  |  |  | Originated | PL-00065 | 3338-SS-4001 - Substation 33kVA | S1 - Stage 1 Construction Completion | Handrails not complete | 1: A-High
D | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-05 - Lighting and Small Power Molybdenum Floatation |  | 2021-03-11 21:01 |  |  |  | Originated | PL-01131 | 3332-DB-4008 - Flotation East Area, Outdoor Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Permanent Ark Flash stickers to be installed on DB. Emergency lights for safety showers to be connected when installed. SS cable ties to be installed on vertical risers. Cable tie ends to be trimmed back. Cable ladder lids to be installed.
D | Item Incomplete | ELEC | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2021-03-15 20:18 |  |  |  | Submitted | PL-01217 | 3338-DB-4001 - Substation Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Remove construction tape on all circuits. Treffolite labels on GPOs
D | Item Incomplete | ELEC | CSEF - Permanent Buildings | CSEF-01 - Admin & Permanent Buildings |  | 2021-03-14 05:25 |  |  |  | Originated | PL-01201 | 3338-DB-4004 - Admin Building Light and Power Distribution Board | S1 - Stage 1 Construction Completion | Add LV/ELV segregation in cable ladder. Foam Fill Conduits. Cable tray lid and grind back cable tray welds and gal paint. Remove earth stake.
D | Item Incomplete | INST | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A |  | 2021-03-15 04:50 |  |  |  | Originated | PL-01216 | 3335-PIT-0903 - INSTRUMENT AIR HEADER | S1 - Stage 1 Construction Completion | DCS Cross Marshall PIT to DCS
D | Item Incomplete | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-11 01:11 |  |  |  | Accepted | PL-01515 | 3331-FV-0050 - COPPER CONCENTRATE TO CONCENTRATE STORAGE TANK 2 | S2 - Stage 2 Pre Commissioning | Mount termination box correctly
D | Item Incomplete | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-11 01:26 |  |  |  | Accepted | PL-01516 | 3331-FV-0054 - COPPER CONCENTRATE TO CONCENTRATE STORAGE TANK 2 | S2 - Stage 2 Pre Commissioning | Replace screws
D | Item Incomplete | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-11 06:32 | 2021-04-21 00:24 |  |  | Rejected | PL-01528 | 3331-FV-1020 - COPPER CONCENTRATE TO COPPER CONC. THICK. FEED BOX | S2 - Stage 2 Pre Commissioning | Mount terminal box on valve
D | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane |  | 2021-03-11 21:43 |  |  |  | Submitted | PL-01151 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Working load limit to be on crane
D | Item Incomplete | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane | 2021-03-26 02:25 | 2021-03-11 05:22 |  | Lanser, Richard | 2021-04-19 22:09 | Closed | PL-01139 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | Jib radius not clearly marked | 2: B-Low
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-11 13:09 | 2021-03-08 16:08 |  |  |  | Submitted | PL-01105 | 3332-DI-4001 - CONDITIONING TANK FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Name plate not installed | 1: A-High
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 | 2021-03-23 11:40 | 2021-03-08 14:39 |  | Lanser, Richard | 2021-04-24 09:26 | Closed | PL-01092 | 3332-TA-4005 - ROUGHER CONDITIONING TANK 2 | S1 - Stage 1 Construction Completion | Edge sealing not completed. | 2: B-Low
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-17 05:52 |  |  |  | Submitted | PL-01551 | 3332-SA-4003 - ROUGHER JAMESON CELL ISA | S1 - Stage 1 Construction Completion | plate not attached
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-17 05:54 |  | Lanser, Richard | 2021-04-17 21:01 | Closed | PL-01552 | 3332-SA-4003 - ROUGHER JAMESON CELL ISA | S1 - Stage 1 Construction Completion | Label not attached
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-05 - Rougher Jameson Cell & ISA Samplers |  | 2021-04-18 02:25 |  |  |  | Submitted | PL-01556 | 3332-SA-4008 - ROUGHER JAMESON TAILS LSA | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-22 00:19 |  | Lanser, Richard | 2021-04-17 23:58 | Closed | PL-00789 | 3332-LD-4001 - ROUGHER SCAVENGER FLOTATION LAUNDER | S1 - Stage 1 Construction Completion | 10% BOLT CHECK
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-02-14 12:55 | 2021-01-31 12:55 | 2021-04-23 01:09 |  |  | Rejected | PL-00487 | 3332-PU-4121 - ROUGHER SCAVENGER TAILINGS PUMP | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | MECH | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-11 14:12 | 2021-03-08 17:11 |  |  |  | Submitted | PL-01109 | 3332-HP-4009 - ROUGHER SCAVENGER TAILING HOPPER | S1 - Stage 1 Construction Completion | Name plate not installed | 1: A-High
D | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-03-24 11:47 | 2021-03-09 14:46 |  |  |  | Submitted | PL-01124 | 3332-TA-4031 - THICKENER OVERFLOW TANK | S1 - Stage 1 Construction Completion | Anchor bolts not installed | 2: B-Low
D | Item Incomplete | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-18 03:09 |  |  |  | Submitted | PL-01561 | 3332-ML-4001 - REGRIND MILL | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-05 06:49 |  |  |  | Submitted | PL-01482 | 3332-HP-4001 - SECOND CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:19 |  |  |  | Submitted | PL-01610 | 3332-DI-4005 - THIRD CLEANER DISTRIBUTOR | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:20 |  |  |  | Submitted | PL-01611 | 3332-DI-4005 - THIRD CLEANER DISTRIBUTOR | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:28 |  |  |  | Submitted | PL-01613 | 3332-HP-4006 - THIRD CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-21 03:29 |  |  |  | Submitted | PL-01614 | 3332-HP-4006 - THIRD CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | 2021-02-14 14:13 | 2021-01-31 14:12 |  | Lanser, Richard | 2021-04-21 11:47 | Closed | PL-00494 | 3332-PU-4024 - THIRD CLEANER FEED PUMP | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | MECH | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-24 17:18 |  | Lanser, Richard | 2021-04-21 11:50 | Closed | PL-00873 | 3335-TA-4021 - RAW WATER TANK | S1 - Stage 1 Construction Completion | Patch/fill weep holes
D | Item Incomplete | MECH | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:15 |  | Lanser, Richard | 2021-04-27 03:38 | Closed | PL-00900 | 3335-100-RWA-0004-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Grouting for all supports
D | Item Incomplete | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-26 21:32 |  | Lanser, Richard | 2021-03-09 06:28 | Closed | PL-00326 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S1 - Stage 1 Construction Completion | Drawings & Schedules to be completed.
D | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 02:51 |  |  |  | Submitted | PL-01603 | 3331-SA-4001B - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Name plate needs install
D | Item Incomplete | MECH | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler |  | 2021-04-21 02:52 |  |  |  | Submitted | PL-01604 | 3331-SA-4001B - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 21:36 | 2021-01-26 21:35 |  | Fuller, Lachlan | 2021-03-26 21:09 | Closed | PL-00327 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 21:38 | 2021-01-26 21:37 |  | Lanser, Richard | 2021-03-28 17:14 | Closed | PL-00328 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | P&ID not marked up | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 21:39 | 2021-01-26 21:39 |  | Lanser, Richard | 2021-03-28 17:14 | Closed | PL-00329 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Area needs to be cleaned | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 21:57 | 2021-01-26 21:55 |  | Liang, Dennis | 2021-03-17 22:32 | Closed | PL-00330 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 22:22 | 2021-01-26 22:20 |  | Lanser, Richard | 2021-03-28 17:18 | Closed | PL-00339 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 23:05 | 2021-01-26 23:04 |  | Lanser, Richard | 2021-03-28 17:20 | Closed | PL-00347 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | touch up paint required. | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 23:09 | 2021-01-26 23:09 |  | Lanser, Richard | 2021-03-28 17:20 | Closed | PL-00348 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Item Incomplete | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 23:10 | 2021-01-26 23:10 |  | Nutt, Richard | 2021-03-28 03:40 | Closed | PL-00349 | 3331-50-CSH-0102-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | P&ID not marked up | 2: B-Low
D | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-03-11 20:51 |  |  |  | Submitted | PL-01141 | 3332-80-PD-0054-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-05 22:37 |  |  |  | Submitted | PL-01483 | 3332-80-PD-0169-R5 - PD Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:11 |  |  |  | Submitted | PL-01160 | 3332-50-MCS-0073-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:19 |  |  |  | Submitted | PL-01162 | 3332-50-MCS-0074-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:24 |  |  |  | Submitted | PL-01164 | 3332-63-MCS-0145-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:30 |  |  |  | Submitted | PL-01166 | 3332-63-MCS-0147-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:33 |  |  |  | Submitted | PL-01168 | 3332-63-MCS-0148-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 00:39 |  |  |  | Submitted | PL-01170 | 3332-50-MCS-0262-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:04 |  |  |  | Submitted | PL-01173 | 3332-63-MCS-0267-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:09 |  |  |  | Submitted | PL-01175 | 3332-63-MCS-0271-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:14 |  |  |  | Submitted | PL-01177 | 3332-50-MCS-0279-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:21 |  |  |  | Submitted | PL-01180 | 3332-100-PD-0050-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:33 |  |  |  | Submitted | PL-01183 | 3332-50-PWH-0008-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:39 |  |  |  | Submitted | PL-01186 | 3332-25-PWH-0081-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:46 |  |  |  | Submitted | PL-01188 | 3332-25-PWH-0083-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-03-12 03:52 |  |  |  | Submitted | PL-01191 | 3332-200-PWL-0026-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-05 04:52 | 2021-04-23 01:09 |  |  | Rejected | PL-01014 | 3332-100-PWL-0009-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank |  | 2021-03-05 04:58 | 2021-04-23 01:09 |  |  | Rejected | PL-01017 | 3332-80-PWL-0013-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 11:33 | 2021-03-06 14:32 | 2021-04-23 01:09 |  |  | Rejected | PL-01034 | 3332-50-MCS-0247-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 13:38 | 2021-03-06 16:37 | 2021-04-23 01:09 |  |  | Rejected | PL-01037 | 3332-50-MCS-0280-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 14:32 | 2021-03-06 17:31 | 2021-04-23 01:09 |  |  | Rejected | PL-01040 | 3332-80-MCS-0033-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 20:55 |  |  |  | Submitted | PL-01405 | 3332-80-MCS-0270-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 21:04 |  |  |  | Submitted | PL-01406 | 3332-150-MCS-0023-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 21:35 |  |  |  | Submitted | PL-01407 | 3332-50-MCS-0024-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 21:48 |  |  |  | Submitted | PL-01408 | 3332-63-MCS-0025-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 21:55 |  |  |  | Submitted | PL-01409 | 3332-90-MCS-0208-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 22:02 |  |  |  | Submitted | PL-01410 | 3332-63-PD-0211-H14 - PD Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 22:14 |  |  |  | Submitted | PL-01411 | 3332-110-PD-0025-H14 - PD Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper |  | 2021-04-01 22:42 |  |  |  | Submitted | PL-01412 | 3332-90-VGN-0021-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-21 22:56 |  |  |  | Submitted | PL-00785 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-01 - Raw Water Feed |  | 2021-02-21 22:59 | 2021-04-23 01:21 |  |  | Rejected | PL-00787 | 3335-150-RWA-0001-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 21:21 |  |  |  | Submitted | PL-00780 | 3335-100-FWA-0003-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 03:46 | 2021-04-23 01:23 |  |  | Rejected | PL-00727 | 3335-50-RWA-0024-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 04:16 |  | Lanser, Richard | 2021-04-05 18:53 | Closed | PL-00738 | 3335-50-RWA-0024-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Install U-bolts
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 04:56 |  |  |  | Submitted | PL-00749 | 3335-100-RWA-0010-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Label
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:01 | 2021-04-23 01:22 |  |  | Rejected | PL-00754 | 3335-100-RWA-0010-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:09 |  |  |  | Submitted | PL-00756 | 3335-100-RWA-0004-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Label
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:12 | 2021-04-23 01:22 |  |  | Rejected | PL-00760 | 3335-100-RWA-0004-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:27 | 2021-04-23 01:22 |  |  | Rejected | PL-00763 | 3335-100-RWA-0005-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:30 |  |  |  | Submitted | PL-00764 | 3335-100-RWA-0005-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Label
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 05:37 | 2021-04-23 01:22 |  |  | Rejected | PL-00767 | 3335-100-RWA-0006-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 06:02 |  |  |  | Submitted | PL-00774 | 3335-100-RWA-0007-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Label
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-21 06:05 | 2021-04-23 01:21 |  |  | Rejected | PL-00775 | 3335-100-RWA-0007-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Paint Touch Up
D | Item Incomplete | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-03-28 22:45 |  |  |  | Submitted | PL-01388 | 3335-100-RWA-0257-C5 - Raw water header | S1 - Stage 1 Construction Completion | labels to be installed
D | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-09 07:18 | 2021-03-06 10:17 | 2021-04-23 01:09 |  |  | Rejected | PL-01025 | 3332-50-PWH-0037-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 1: A-High
D | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-21 08:03 | 2021-03-06 11:02 | 2021-04-23 01:09 |  |  | Rejected | PL-01029 | 3332-50-PWH-0038-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-21 09:40 | 2021-03-06 12:39 | 2021-04-23 01:09 |  |  | Rejected | PL-01031 | 3332-50-PWH-0187-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 04:14 |  |  |  | Submitted | PL-00838 | 3331-150-CSL-0032-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:30 |  |  |  | Submitted | PL-01144 | 3331-90-PD-0011-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:37 |  |  |  | Submitted | PL-01147 | 3331-80-PD-0062-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 21:54 |  |  |  | Submitted | PL-01152 | 3331-80-PD-0063-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 22:04 |  |  |  | Submitted | PL-01154 | 3331-90-PD-0064-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | PIPE | CS25 - Copper Concentrate Thickener | CS25-09 - Copper Concentrate Thickener Area Sump |  | 2021-03-11 23:54 |  |  |  | Submitted | PL-01158 | 3331-80-PD-0026-R5 - PD Process Line | S1 - Stage 1 Construction Completion | Labels
D | Item Incomplete | STRU |  |  | 2020-12-28 01:58 | 2020-12-14 01:57 | 2021-04-23 01:25 |  |  | Rejected | PL-00055 |  | S1 - Stage 1 Construction Completion | Touch up paint | 2: B-Low
D | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2020-12-14 21:16 | 2020-11-30 21:16 |  | Nutt, Richard | 2021-02-25 17:18 | Closed | PL-00048 | Steel Phase 1 - Phase one (1) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:30 | 2021-02-22 05:29 |  |  |  | Submitted | PL-00848 | Steel Phase 4 - Phase four (4) Steel Structure | S1 - Stage 1 Construction Completion | Handrail to be completed throughout building | 2: B-Low
D | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:35 | 2021-02-22 05:34 |  |  |  | Submitted | PL-00852 | Steel Phase 5 - Phase five (5) Steel Structure | S1 - Stage 1 Construction Completion | Handrail to be completed throughout building | 2: B-Low
D | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 02:58 | 2021-02-22 05:58 |  |  |  | Submitted | PL-00855 | Steel Phase 6 - Phase six (6) Steel Structure | S1 - Stage 1 Construction Completion | Handrail to be completed throughout building | 2: B-Low
D | Item Incomplete | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 03:01 | 2021-02-22 06:01 |  |  |  | Submitted | PL-00857 | Steel Phase 7 - Phase seven (7) Steel Structure | S1 - Stage 1 Construction Completion | Handrail to be completed throughout building | 2: B-Low
D | Item not secured | CABL | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-03-23 01:38 |  |  |  | Submitted | PL-01354 | 3331-OP-4003 - OP Instrument Air for 3331-FV-1109 | S1 - Stage 1 Construction Completion | Install cable ladder barrier strip
D | Item not secured | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 19:02 |  |  |  | Submitted | PL-00887 | 3335-100-RWA-0006-C5 - RWA Process Line | S2 - Stage 2 Pre Commissioning | Replace Carbon steel packing under pipe
D | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:18 |  | Muell, Thomas | 2021-03-15 22:40 | Closed | PL-00034 | 3338DB4001-R2 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Emergency LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
D | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:20 |  | Muell, Thomas | 2021-03-15 22:41 | Closed | PL-00035 | 3338DB4001-R26 - SUBSTATION LIGHT AND POWER BOARD TO Substation External LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
D | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:21 |  | Muell, Thomas | 2021-03-15 22:41 | Closed | PL-00036 | 3338DB4001-W28 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Flood Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
D | Missing Labels | CABL | CSEE - Lighting and General Purpose Outlets | CSEE-09 - Lighting and Small Power Plant Infrastructure |  | 2020-11-05 03:21 |  | Muell, Thomas | 2021-03-15 22:42 | Closed | PL-00037 | 3338DB4001-W4 - SUBSTATION LIGHT AND POWER BOARD TO Substation External Emergency LED Bulkhead Lighting | S1 - Stage 1 Construction Completion | Supply and install all missing S/S labels
D | Missing Labels | ELEC | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener | 2021-04-04 03:44 | 2021-03-21 02:43 |  |  |  | Originated | PL-01334 | 3332-PU-4030-M1 - Motor for INTERMEDIATE THICKENER UNDERFLOW PUMP | S1 - Stage 1 Construction Completion | Equipment ID not installed | 2: B-Low
D | Missing Labels | ELEC | CSEF - Permanent Buildings | CSEF-01 - Admin & Permanent Buildings | 2020-11-20 04:55 | 2020-11-06 05:14 |  | Fuller, Lachlan | 2021-03-15 05:48 | Closed | PL-00040 | 3338-DB-1396 - Office Sub Board | S1 - Stage 1 Construction Completion | Temporary labels attached, permanent label to be installed | 2: B-Low
D | Missing Labels | ELEC | CSEF - Permanent Buildings | CSEF-01 - Admin & Permanent Buildings | 2020-11-20 05:02 | 2020-11-06 05:14 |  |  |  | Closed | PL-00039 | 3338-DB-1385 - Ablution Sub Board | S1 - Stage 1 Construction Completion | Temporary label attached, permanent label to be installed | 2: B-Low
D | Missing Labels | ELEC | CSEF - Permanent Buildings | CSEF-01 - Admin & Permanent Buildings | 2020-11-20 05:02 | 2020-11-06 05:14 |  | Fuller, Lachlan | 2021-03-15 05:48 | Closed | PL-00039 | 3338-DB-1385 - Ablution Sub Board | S1 - Stage 1 Construction Completion | Temporary label attached, permanent label to be installed | 2: B-Low
D | Missing Labels | ELEC | CSEF - Permanent Buildings | CSEF-01 - Admin & Permanent Buildings | 2020-11-20 05:10 | 2020-11-06 05:14 |  | Fuller, Lachlan | 2021-03-15 05:47 | Closed | PL-00041 | 3338-DB-1377 - First Aid Sub Board | S1 - Stage 1 Construction Completion | Temporary label attached, permanent label to be installed
D | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | 2021-04-27 07:39 | 2021-04-13 07:39 |  |  |  | Accepted | PL-01542 | 3332-ME-4012 - CAMERA | S1 - Stage 1 Construction Completion | INSTALL LABEL ON EXTERIOR OF CAMERA HOUSING | 2: B-Low
D | Missing Labels | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-05 05:34 | 2021-01-22 05:34 |  |  |  | Submitted | PL-00250 | 3331-PIT-2104 - COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Attach Label | 2: B-Low
D | Missing Labels | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-03-07 04:06 | 2021-02-21 04:06 |  |  |  | Submitted | PL-00733 | 3331-DI-4005 - CONCENTRATE STORAGE DIVERTER BOX | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
D | Missing Labels | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-03-07 04:08 | 2021-02-21 04:07 |  |  |  | Submitted | PL-00734 | 3331-DI-4005 - CONCENTRATE STORAGE DIVERTER BOX | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
D | Missing Labels | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-09 - Copper concentrate Jib Crane | 2021-03-08 01:38 | 2021-02-21 04:37 |  |  |  | Originated | PL-00747 | 3331-CN-4002 - COPPER CONCENTRATE TRANSFER PUMP JIB CRANE | S1 - Stage 1 Construction Completion | No safety signs | 2: B-Low
D | Missing Labels | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-01 - Intermediate Thickener |  | 2021-04-19 02:48 |  |  |  | Submitted | PL-01577 | 3332-DI-4009 - INTERMEDIATE THICKENER FEED DISTRIBUTOR | S1 - Stage 1 Construction Completion | Name plate needs install
D | Missing Labels | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-21 23:52 |  |  |  | Submitted | PL-01616 | 3332-HP-4007 - FOURTH CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Missing Labels | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-21 23:53 |  |  |  | Submitted | PL-01617 | 3332-HP-4007 - FOURTH CLEANER FEED HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Missing Labels | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:45 |  |  |  | Submitted | PL-01620 | 3332-HP-4008 - THIRD CLEANER / FOURTH CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Missing Labels | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-22 01:46 |  |  |  | Submitted | PL-01621 | 3332-HP-4008 - THIRD CLEANER / FOURTH CLEANER TAILINGS HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Missing Labels | MECH | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-03-04 01:19 | 2021-02-18 01:19 |  |  |  | Submitted | PL-00623 | 3331-TA-4041 - DEAERATION TANK 1 | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
D | Missing Labels | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-02-21 05:59 |  |  |  | Submitted | PL-00772 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied
D | Missing Labels | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-07 05:11 | 2021-02-21 05:10 |  |  |  | Submitted | PL-00757 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
D | Missing Labels | MECH | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-07 05:12 | 2021-02-21 05:11 |  |  |  | Submitted | PL-00759 | 3331-HP-4011 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S1 - Stage 1 Construction Completion | Labels to be applied | 2: B-Low
D | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:03 | 2021-01-26 06:03 |  | Lanser, Richard | 2021-03-28 16:50 | Closed | PL-00312 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:34 | 2021-01-26 06:33 |  | Lanser, Richard | 2021-03-28 16:54 | Closed | PL-00319 | 3331-150-CSH-0002-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 22:00 | 2021-01-26 21:59 |  | Lanser, Richard | 2021-03-28 17:16 | Closed | PL-00332 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump | 2021-03-27 05:22 | 2021-03-13 05:21 |  |  |  | Submitted | PL-01197 | 3331-90-PD-0059-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-02 - Rougher Conditioning Tanks 1 & 2 |  | 2021-02-22 04:27 |  |  |  | Submitted | PL-00843 | 3332-50-PWH-0054-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | ISO Label
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 15:57 | 2021-01-30 15:56 |  |  |  | Submitted | PL-00413 | 3332-80-NG-0029-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 16:22 | 2021-01-30 16:22 |  |  |  | Submitted | PL-00418 | 3332-80-NG-0030-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 17:42 | 2021-01-30 17:42 |  |  |  | Submitted | PL-00427 | 3332-160-PD-0008-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:21 | 2021-01-30 18:21 |  |  |  | Submitted | PL-00436 | 3332-25-PWH-0003-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:31 | 2021-01-30 18:31 |  |  |  | Submitted | PL-00438 | 3332-25-PWH-0004-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:40 | 2021-01-30 18:40 |  |  |  | Submitted | PL-00440 | 3332-25-PWH-0006-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 21:33 | 2021-01-30 21:21 |  |  |  | Submitted | PL-00447 | 3332-80-NG-0026-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 21:47 | 2021-01-30 21:47 |  |  |  | Submitted | PL-00451 | 3332-80-NG-0027-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 22:01 | 2021-01-30 22:00 |  |  |  | Submitted | PL-00455 | 3332-80-NG-0028-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 22:24 | 2021-01-30 22:24 |  |  |  | Submitted | PL-00458 | 3332-25-PWH-0007-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:27 | 2021-01-31 02:27 |  |  |  | Submitted | PL-00463 | 3332-25-PWH-0116-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:47 | 2021-01-31 02:46 |  |  |  | Submitted | PL-00467 | 3332-25-PWH-0244-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:54 | 2021-01-31 02:54 |  |  |  | Submitted | PL-00470 | 3332-25-PWH-0245-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:01 | 2021-01-31 03:00 |  |  |  | Submitted | PL-00473 | 3332-25-PWH-0246-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:13 | 2021-01-31 03:12 |  |  |  | Submitted | PL-00477 | 3332-25-PWH-0247-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:29 | 2021-01-31 03:29 |  |  |  | Submitted | PL-00481 | 3332-25-PWH-0248-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-22 14:58 | 2021-03-08 14:57 |  |  |  | Submitted | PL-01101 | 3332-200-MCS-0133-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-23 13:30 | 2021-03-09 13:30 |  |  |  | Submitted | PL-01117 | 3332-50-PWH-0200-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-23 13:55 | 2021-03-09 13:54 |  |  |  | Submitted | PL-01120 | 3332-63-MCS-0261-H14 - MCS Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-23 14:05 | 2021-03-09 14:04 |  |  |  | Submitted | PL-01121 | 3332-100-MCS-0134-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-04 - Intermediate & Moly Thickener Overflow Tank | 2021-03-24 12:03 | 2021-03-09 15:02 |  |  |  | Submitted | PL-01125 | 3332-160-PD-0017-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 11:30 | 2021-03-06 14:29 |  |  |  | Submitted | PL-01032 | 3332-50-MCS-0247-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 13:35 | 2021-03-06 16:34 |  |  |  | Submitted | PL-01035 | 3332-50-MCS-0280-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-21 14:30 | 2021-03-06 17:29 |  |  |  | Submitted | PL-01039 | 3332-80-MCS-0033-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-22 08:22 | 2021-03-07 11:21 |  |  |  | Submitted | PL-01057 | 3332-80-MCS-0035-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-22 10:38 | 2021-03-07 13:37 |  |  |  | Submitted | PL-01064 | 3332-90-VGN-0029-H14 - VGN Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-03-03 21:43 | 2021-02-17 21:42 |  |  |  | Submitted | PL-00614 | 3332-50-PWH-0323-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-12 15:46 | 2021-01-29 15:46 |  |  |  | Submitted | PL-00370 | 3335-50-IA-0044-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-03-17 01:48 | 2021-03-15 01:47 |  |  |  | Submitted | PL-01202 | 3334-50-IA-0117-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 1: A-High
D | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-12 14:15 | 2021-01-29 14:15 |  |  |  | Submitted | PL-00363 | 3332-50-IA-0019-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-12 14:31 | 2021-01-29 14:31 |  |  |  | Submitted | PL-00365 | 3332-50-IA-0016-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header | 2021-03-08 01:15 | 2021-02-21 03:42 |  |  |  | Submitted | PL-00725 | 3335-50-RWA-0024-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | ISO Label | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-18 01:10 |  |  |  | Submitted | PL-00621 | 3335-150-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-03 23:19 | 2021-02-17 23:19 |  |  |  | Submitted | PL-00617 | 3335-200-PWL-0007-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-04 04:45 | 2021-02-18 04:45 |  |  |  | Submitted | PL-00639 | 3335-25-PWH-0341-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-02 - Process Water to Concentrate Feed Pumps | 2021-03-04 04:59 | 2021-02-18 04:59 |  |  |  | Submitted | PL-00644 | 3331-50-PWH-0105-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-21 07:12 | 2021-03-06 10:11 |  |  |  | Submitted | PL-01021 | 3332-50-PWH-0037-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-21 07:59 | 2021-03-06 10:59 |  |  |  | Submitted | PL-01026 | 3332-50-PWH-0038-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | 2021-03-21 09:35 | 2021-03-06 12:34 |  |  |  | Submitted | PL-01030 | 3332-50-PWH-0187-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-04-14 05:24 |  |  |  | Submitted | PL-01544 | 3335-25-PWH-0310-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Line labels to be installed
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-04-14 05:25 |  |  |  | Submitted | PL-01545 | 3335-25-PWH-0310-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Valve Tags to Be installed
D | Missing Labels | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-04 03:12 | 2021-02-18 03:11 |  |  |  | Submitted | PL-00630 | 3332-100-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-11 00:45 | 2021-01-28 00:39 |  |  |  | Submitted | PL-00359 | 3334-50-FLOC-0046-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 03:03 | 2021-03-07 14:02 |  |  |  | Submitted | PL-01067 | 3334-50-RWA-0002-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 03:21 | 2021-03-07 14:21 |  |  |  | Submitted | PL-01069 | 3334-50-RWA-0001-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 04:18 | 2021-03-07 15:18 |  |  |  | Submitted | PL-01070 | 3334-25-RWA-0006-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 04:42 | 2021-03-07 15:41 |  |  |  | Submitted | PL-01073 | 3334-50-RWA-0003-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 04:49 | 2021-03-07 15:48 |  |  |  | Submitted | PL-01074 |  | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-03 05:17 | 2021-01-20 05:16 |  |  |  | Originated | PL-00214 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Attach labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 16:41 | 2021-01-31 16:41 |  |  |  | Submitted | PL-00502 | 3331-150-CSL-0001-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 17:35 | 2021-01-31 17:35 |  |  |  | Submitted | PL-00506 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-15 02:08 | 2021-02-01 02:08 |  |  |  | Submitted | PL-00510 | 3331-150-CSL-0003-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Labels to be applied to line | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-03 05:11 | 2021-02-17 05:11 |  |  |  | Submitted | PL-00611 | 3331-150-CSL-0004-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-03 05:14 | 2021-02-17 05:13 |  |  |  | Submitted | PL-00612 | 3331-150-CSL-0004-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Valve tags not attached | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-22 10:07 | 2021-03-08 10:07 |  |  |  | Submitted | PL-01086 | 3331-160-PD-0198-H14 - PD Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-22 11:47 | 2021-03-08 11:47 |  |  |  | Submitted | PL-01088 | 3331-50-PWH-0313-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Missing labels | 2: B-Low
D | Missing Labels | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-22 14:23 | 2021-03-07 17:22 |  |  |  | Submitted | PL-01075 | 3331-150-MCS-0304-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Apply labels to pipe | 2: B-Low
D | Missing Parts | ELEC | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-07 02:30 | 2021-02-21 02:30 |  |  |  | Originated | PL-00720 | 3331-OP-4201 - PM001 - Concentrate Transfer Piston Diaphragm Pumps | S1 - Stage 1 Construction Completion | Missing 40mm duct lid | 2: B-Low
D | Not to Contract Spec | MECH | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-07 - GEHO Pump | 2021-03-25 23:55 | 2021-03-11 02:54 | 2021-04-23 01:15 |  |  | Rejected | PL-01136 | 3331-PU-4007 - COPPER CONCENTRATE TRANSFER PUMP | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) |  | 2021-01-26 05:49 |  | Nutt, Richard | 2021-03-28 03:41 | Closed | PL-00310 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Mark up P&ID's
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 05:39 | 2021-01-26 05:39 |  | Lanser, Richard | 2021-03-28 03:44 | Closed | PL-00308 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 05:49 | 2021-01-26 05:48 |  | Lanser, Richard | 2021-03-28 03:43 | Closed | PL-00309 | 3331-150-CSH-0004-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:12 | 2021-01-26 06:12 |  | Lanser, Richard | 2021-03-28 16:51 | Closed | PL-00315 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:19 | 2021-01-26 06:18 |  | Lanser, Richard | 2021-03-28 16:52 | Closed | PL-00316 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | As built not completed | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 06:20 | 2021-01-26 06:20 |  | Nutt, Richard | 2021-03-28 03:38 | Closed | PL-00317 | 3331-50-CSH-0110-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | P&ID's not marked up yet | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 20:25 | 2021-01-26 20:25 |  | Lanser, Richard | 2021-03-28 17:13 | Closed | PL-00324 | 3331-150-CSH-0001-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-05 - Blayney Feed & Bypass (C11) | 2021-02-09 22:16 | 2021-01-26 22:15 |  | Lanser, Richard | 2021-03-28 17:17 | Closed | PL-00338 | 3331-50-CSH-0111-C11 - CSH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-01-30 22:30 |  | Lanser, Richard | 2021-04-06 23:12 | Closed | PL-00460 | 3332-25-PWH-0007-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 16:11 | 2021-01-30 16:10 | 2021-04-23 01:09 |  |  | Rejected | PL-00416 | 3332-80-NG-0029-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 16:31 | 2021-01-30 16:31 | 2021-04-23 01:09 |  |  | Rejected | PL-00420 | 3332-80-NG-0030-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:23 | 2021-01-30 18:22 | 2021-04-23 01:09 |  |  | Rejected | PL-00437 | 3332-25-PWH-0003-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:33 | 2021-01-30 18:32 | 2021-04-23 01:09 |  |  | Rejected | PL-00439 | 3332-25-PWH-0004-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 18:42 | 2021-01-30 18:42 | 2021-04-23 01:09 |  |  | Rejected | PL-00442 | 3332-25-PWH-0006-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 21:37 | 2021-01-30 21:37 | 2021-04-23 01:09 |  |  | Rejected | PL-00449 | 3332-80-NG-0026-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 21:51 | 2021-01-30 21:50 | 2021-04-23 01:09 |  |  | Rejected | PL-00453 | 3332-80-NG-0027-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-13 22:06 | 2021-01-30 22:05 | 2021-04-23 01:09 |  |  | Rejected | PL-00457 | 3332-80-NG-0028-C4 - NG Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:42 | 2021-01-31 02:42 | 2021-04-23 01:09 |  |  | Rejected | PL-00466 | 3332-25-PWH-0116-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:50 | 2021-01-31 02:50 | 2021-04-23 01:09 |  |  | Rejected | PL-00469 | 3332-25-PWH-0244-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 02:57 | 2021-01-31 02:57 | 2021-04-23 01:09 |  |  | Rejected | PL-00472 | 3332-25-PWH-0245-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:08 | 2021-01-31 03:06 | 2021-04-23 01:09 |  |  | Rejected | PL-00476 | 3332-25-PWH-0246-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:24 | 2021-01-31 03:24 | 2021-04-23 01:09 |  |  | Rejected | PL-00480 | 3332-25-PWH-0247-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-02-14 03:34 | 2021-01-31 03:33 | 2021-04-23 01:09 |  |  | Rejected | PL-00485 | 3332-25-PWH-0248-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-23 13:41 | 2021-03-09 13:41 | 2021-04-23 01:09 |  |  | Rejected | PL-01119 | 3332-50-PWH-0200-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS02 - Rougher & Scavenger Cells | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | 2021-03-23 14:13 | 2021-03-09 14:13 |  |  |  | Submitted | PL-01122 | 3332-100-MCS-0134-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Install pipe hanger | 2: B-Low
D | Not to Contract Spec | PIPE | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-03-22 08:23 | 2021-03-07 11:23 | 2021-04-23 01:09 |  |  | Rejected | PL-01058 | 3332-80-MCS-0035-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS05 - 2nd Cleaner Flotation | CS05-03 - Second Cleaner Tailings Hopper | 2021-03-03 21:46 | 2021-02-17 21:46 | 2021-04-23 01:09 |  |  | Rejected | PL-00616 | 3332-50-PWH-0323-C6-TI-ET - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-12 15:33 | 2021-01-29 15:33 |  | Liang, Dennis | 2021-03-18 00:56 | Closed | PL-00369 | 3335-50-IA-0041-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-12 15:49 | 2021-01-29 15:49 | 2021-04-23 01:20 |  |  | Rejected | PL-00372 | 3335-50-IA-0044-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-02A - Instrument air header A | 2021-02-12 16:53 | 2021-01-29 16:52 | 2021-04-23 01:20 |  |  | Rejected | PL-00380 | 3335-50-IA-0050-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-12 14:19 | 2021-01-29 14:18 | 2021-04-23 01:09 |  |  | Rejected | PL-00364 | 3332-50-IA-0019-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Pipe and supports need painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS0B - Plant Air / Instrument Air | CS0B-03 - Flotation Instrument Air Header | 2021-02-12 14:34 | 2021-01-29 14:34 | 2021-04-23 01:09 |  |  | Rejected | PL-00367 | 3332-50-IA-0016-C4 - IA Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank |  | 2021-02-21 21:25 | 2021-04-23 01:21 |  |  | Rejected | PL-00783 | 3335-100-FWA-0003-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Not to Contract Spec | PIPE | CS0C - Raw Water | CS0C-02 - Raw Water Tank | 2021-02-26 15:51 | 2021-02-13 02:51 | 2021-04-23 01:13 |  |  | Rejected | PL-00576 | 3335-400-RWA-0002-C5 - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up painting required | 2: B-Low
D | Not to Contract Spec | PIPE | CS0D - Fire Water | CS0D-01 - Fire Water Ring Main & Distribution | 2021-04-03 02:57 | 2021-03-19 05:57 | 2021-04-23 01:09 |  |  | Rejected | PL-01269 | 3335-200-FWA-0002-C9 - FWA Process Line | S1 - Stage 1 Construction Completion | paint touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-20 23:36 | 2021-04-23 01:23 |  |  | Rejected | PL-00695 | 3335-25-PWH-0352-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-03 23:22 | 2021-02-17 23:21 | 2021-04-23 01:18 |  |  | Rejected | PL-00618 | 3335-200-PWL-0007-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-04 01:13 | 2021-02-18 01:13 | 2021-04-23 01:18 |  |  | Rejected | PL-00622 | 3335-150-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-03-04 04:49 | 2021-02-18 04:49 | 2021-04-23 01:17 |  |  | Rejected | PL-00643 | 3335-25-PWH-0341-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-02 - Process Water to Concentrate Feed Pumps | 2021-03-04 05:02 | 2021-02-18 05:01 | 2021-04-23 01:17 |  |  | Rejected | PL-00646 | 3331-50-PWH-0105-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area |  | 2021-04-14 05:26 | 2021-04-23 01:20 |  |  | Rejected | PL-01546 | 3335-25-PWH-0310-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-01 01:30 | 2021-02-15 01:30 | 2021-04-23 01:13 |  |  | Rejected | PL-00591 | 3331-80-PWH-0035-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-04 03:15 | 2021-02-18 03:15 | 2021-04-23 01:17 |  |  | Rejected | PL-00632 | 3332-100-PWH-0002-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS0E - Process Water Distribution | CS0E-14 - Process Water to Copper Thickener Area | 2021-03-05 22:55 | 2021-02-19 22:55 |  | Lanser, Richard | 2021-04-18 04:22 | Closed | PL-00684 |  | S1 - Stage 1 Construction Completion | painting needs to be completed | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-17 23:01 | 2021-02-03 23:01 |  | Lanser, Richard | 2021-04-06 22:42 | Closed | PL-00527 | 3334-50-FLOC-0002-C3-TI-ET - FLOC Process Line | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 00:45 | 2021-03-07 11:45 | 2021-04-23 01:16 |  |  | Rejected | PL-01060 | 3334-25-RWA-0007-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 02:02 | 2021-03-07 13:01 | 2021-04-23 01:16 |  |  | Rejected | PL-01063 | 3334-25-RWA-0004-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 03:05 | 2021-03-07 14:05 | 2021-04-23 01:16 |  |  | Rejected | PL-01068 | 3334-50-RWA-0002-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 04:20 | 2021-03-07 15:20 | 2021-04-23 01:16 |  |  | Rejected | PL-01071 | 3334-25-RWA-0006-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-03-21 04:36 | 2021-03-07 15:36 | 2021-04-23 01:16 |  |  | Rejected | PL-01072 | 3334-25-RWA-0005-C5-TI-ET - RWA Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-03-04 22:43 | 2021-04-23 01:20 |  |  | Rejected | PL-01012 | 3331-100-VGN-0017-C3 - VGN Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) | 2021-02-28 21:49 | 2021-02-13 23:56 | 2021-04-23 01:19 |  |  | Rejected | PL-00580 | 3331-80-PWH-0012-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | painting required | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-02-22 04:18 | 2021-04-23 01:21 |  |  | Rejected | PL-00841 | 3331-150-CSL-0032-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 16:49 | 2021-01-31 16:49 | 2021-04-23 01:19 |  |  | Rejected | PL-00505 | 3331-150-CSL-0001-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-02-14 17:41 | 2021-01-31 17:41 | 2021-04-23 01:19 |  |  | Rejected | PL-00509 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) | 2021-03-03 05:16 | 2021-02-17 05:15 | 2021-04-23 01:18 |  |  | Rejected | PL-00613 | 3331-150-CSL-0004-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-22 11:49 | 2021-03-08 11:49 | 2021-04-23 01:16 |  |  | Rejected | PL-01089 | 3331-50-PWH-0313-C6 - PWH Process Line | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Contract Spec | PIPE | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper | 2021-03-22 14:25 | 2021-03-07 17:24 | 2021-04-23 01:15 |  |  | Rejected | PL-01076 | 3331-150-MCS-0304-R5 - MCS Process Line | S1 - Stage 1 Construction Completion | Complete painting and touch ups | 2: B-Low
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-20 19:23 | 2021-04-23 01:09 |  |  | Rejected | PL-00219 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-21 03:22 | 2021-04-23 01:09 |  |  | Rejected | PL-00221 | Steel Phase 3 - Phase three (3) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 21:41 | 2021-04-23 01:09 |  |  | Rejected | PL-00257 | Filter Building Steel & Stair Tower - Filter Building Steel and Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 22:12 | 2021-04-23 01:09 |  |  | Rejected | PL-00260 | Steel Phase 4 - Phase four (4) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-23 05:37 | 2021-04-23 01:09 |  |  | Rejected | PL-00268 | Steel Phase 5 - Phase five (5) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-23 06:36 | 2021-04-23 01:09 |  |  | Rejected | PL-00272 | Steel Phase 7 - Phase seven (7) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-23 06:39 | 2021-04-23 01:09 |  |  | Rejected | PL-00273 | Steel Phase 6 - Phase six (6) Steel Structure | S1 - Stage 1 Construction Completion | Complete touchup painting
D | Not to Contract Spec | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2021-03-09 03:19 | 2021-02-22 06:19 | 2021-04-23 01:09 |  |  | Rejected | PL-00862 | 331 East West Pipe Rack - D03-0021 Plan @ RL.5790.650 TOS | S1 - Stage 1 Construction Completion | Touch up paint required | 2: B-Low
D | Not to Drawings | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-22 22:02 |  |  |  | Submitted | PL-00258 | Filter Building Steel & Stair Tower - Filter Building Steel and Structure | S1 - Stage 1 Construction Completion | Handrail to be completed throughout building
D | Not to Equipment Specs | INST | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-04-20 23:13 |  |  |  | Submitted | PL-01591 | 3331-LIT-1110 - CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S2 - Stage 2 Pre Commissioning | Data sheet has calibrated range to be set at 2.1m needs to be updated to 0-1.3m and blanking distance 0.250m
D | Not to Equipment Specs | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-19 20:53 | 2021-04-23 01:24 |  |  | Rejected | PL-00667 | 3335-25-ASC-0002-C6 - ASC Process Line | S1 - Stage 1 Construction Completion | painting needs to be completed
D | Other | INST | CS0M - Gland Water | CS0M-02 - Gland Seal Water Charging Pumps | 2021-05-09 18:33 | 2021-04-25 18:31 |  |  |  | Submitted | PL-01668 | 3331-FV-1025 - GLAND WATER TO COPPER CONC. CHARGING PUMP | S1 - Stage 1 Construction Completion | Replace existing model number on instrument data sheet to DFS063-DA-M-P | 2: B-Low
D | Other | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 01:59 |  |  |  | Originated | PL-00951 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | Touch up paint required on alot of areas within rougher flotation area, remove packing lists on Rflotation cells and fix handrail on top level RHS 3332-FB-4001
D | Other | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-09 18:36 | 2021-02-22 02:35 | 2021-02-23 18:37 |  |  | Rejected | PL-00802 | 3332-VE-4003 - FAIL SAFE DART VALVES ACCUMULATOR FOR 3332-FB-4003 | S1 - Stage 1 Construction Completion | Nil | 2: B-Low
D | Other | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-18 00:05 | 2021-04-23 01:08 |  |  | Rejected | PL-01555 | 3332-HT-4003 - ROUGHER AREA SUMP PUMP 1 DAVIT | S1 - Stage 1 Construction Completion | Touch up paint
D | Other | MECH | CS02 - Rougher & Scavenger Cells | CS02-12 - Rougher Area Sump 1 |  | 2021-04-23 00:12 |  |  |  | Submitted | PL-01639 | 3332-PU-4012 - ROUGHER AREA SUMP PUMP 1 | S1 - Stage 1 Construction Completion | HD stud bolts to be cut
D | Other | MECH | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill |  | 2021-04-18 03:17 | 2021-04-23 01:09 |  |  | Rejected | PL-01563 | 3332-PU-4022 - REGRIND MILL DISCHARGE PUMP | S1 - Stage 1 Construction Completion | Touch up paint
D | Other | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper |  | 2021-04-18 03:58 | 2021-04-23 01:09 |  |  | Rejected | PL-01571 | 3332-CY-4016 - FOURTH CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Touch up paint
D | Other | MECH | CS07 - 3rd & 4th Cleaner Jameson Cells | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper |  | 2021-04-18 03:47 | 2021-04-23 01:09 |  |  | Rejected | PL-01565 | 3332-CY-4015 - THIRD CLEANER JAMESON CELL | S1 - Stage 1 Construction Completion | Touch up paint
D | Other | MECH | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 17:49 |  | Lanser, Richard | 2021-04-18 01:37 | Closed | PL-00881 | 3335-PU-4155 - FLUSH CHARGE PUMP | S2 - Stage 2 Pre Commissioning | Cut pump studs
D | Other | MECH | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution |  | 2021-01-24 00:46 | 2021-04-23 01:25 |  |  | Rejected | PL-00282 | 3334-PK-4008 - FLOCCULANT STORAGE PACKAGE | S1 - Stage 1 Construction Completion | Complete painting and touch ups
D | Other | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:13 |  |  |  | Submitted | PL-00899 | 3335-PU-4090 - RAW WATER PUMP | S1 - Stage 1 Construction Completion | Trim Hold down bots on pumps
D | Other | PIPE | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header |  | 2021-02-24 19:36 |  |  |  | Submitted | PL-00891 | 3335-200-PWL-0001-C5 - PWL Process Line | S1 - Stage 1 Construction Completion | Check requirement to rotate Y Strainer
D | Other | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel |  | 2021-01-21 23:55 |  |  |  | Submitted | PL-00237 | Steel Phase 2 - Phase two (2) Steel Structure | S1 - Stage 1 Construction Completion | Clean up required on all of phase 2
D | Other | STRU | CS0S - Structrual Steel | CS0S-01 - Structural Steel | 2020-12-30 04:17 | 2020-12-16 04:08 | 2021-04-23 01:08 |  |  | Rejected | PL-00059 | Con. Tank Access Structure - Bulk Concentrate Handling Facility | S1 - Stage 1 Construction Completion | Complete touchup painting | 2: B-Low
D | Value Add | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01A - Concentrate Storage Tank 2 (PART A) |  | 2021-04-08 07:03 |  |  |  | Submitted | PL-01494 | 3331-LIT-0063 - CONCENTRATE STORAGE TANK 2 | S2 - Stage 2 Pre Commissioning | Data sheet needs to be updated calibrated range 0-10m
E | Incorrect Labels | ELEC | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-04-27 05:52 | 2021-04-13 05:51 |  |  |  | Originated | PL-01538 | 3331-OP-4205 - 3331-SA-4001 PLC Panel LCP01 600Wx600Hx200D | S1 - Stage 1 Construction Completion | Vendor trafolite incorrect | 2: B-Low
E | Incorrect Labels | ELEC | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-04-27 06:18 | 2021-04-13 06:18 |  |  |  | Originated | PL-01539 | 3331-OP-4207 - 3331-SA-4001 Primary Sampler JB22 | S1 - Stage 1 Construction Completion | Correct vendor label adding 4207 to existing engraving | 2: B-Low
E | Incorrect Labels | ELEC | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-04-27 06:29 | 2021-04-13 06:29 |  |  |  | Originated | PL-01540 | 3331-OP-4206 - 3331-SA-4001 Primary Sampler JB21 | S1 - Stage 1 Construction Completion | 4206 added to existing trafolite engraving as in pen on existing label pic attached | 2: B-Low
E | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 06:26 | 2021-01-23 06:25 |  |  |  | Originated | PL-00270 | 3334-FIT-2113 - Flow Indicating Transmitter | S1 - Stage 1 Construction Completion | Vendor Supplied Labels not Supplied | 2: B-Low
E | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 06:34 | 2021-01-23 06:33 |  |  |  | Originated | PL-00271 | 3334-FIT-2115 - Flow Indicating Transmitter | S1 - Stage 1 Construction Completion | Vendor Supplied label not supplied. | 2: B-Low
E | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 06:40 | 2021-01-23 06:40 |  |  |  | Originated | PL-00274 | 3334-FIT-2117 - Flow Indicating Transmitter | S1 - Stage 1 Construction Completion | Vendor Supplied Labels to be supplied | 2: B-Low
E | Incorrect Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-06 06:50 | 2021-01-23 06:50 |  |  |  | Originated | PL-00275 | 3334-FIT-2119 - Flow Indicating Transmitter | S1 - Stage 1 Construction Completion | Vendor Supplied Labels To be Supplied | 2: B-Low
E | Incorrect Labels | INST | CS25 - Copper Concentrate Thickener | CS25-01 - Copper Concentrate Thickener (Top) |  | 2021-01-22 05:06 |  |  |  | Submitted | PL-00247 | 3331-LL-2101 - TH4001 WATER LEVEL LOW | S1 - Stage 1 Construction Completion | Free issued equipment not supplied with instrument tag.
E | Item Incomplete | CABL | CS25 - Copper Concentrate Thickener | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | 2021-04-10 22:33 | 2021-03-27 21:32 |  |  |  | Originated | PL-01387 | 3331OP4206-C1 - 3331-SA-4001 - COPPER CONCENTRATE THICKENER FEED METALLURGICAL SAMPLER TO PRIMARY SAMPLER (TBJ1) | S1 - Stage 1 Construction Completion | No actual termination “drawing” showing interface: vendor drawings show vendor numbers only and 2 versions of termination schedule in system | 2: B-Low
E | Item Incomplete | ELEC | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-05-03 01:35 | 2021-04-19 01:34 |  |  |  | Originated | PL-01574 | 3332-MB-4046 - Regrind Mill Instrumentation Box | S1 - Stage 1 Construction Completion | Spare vendor glands require plugging if not going to be used. Worley to take care if this with vendor. | 2: B-Low
E | Item Incomplete | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-05 06:38 | 2021-01-22 06:37 |  | Fuller, Lachlan | 2021-04-18 03:18 | Closed | PL-00252 | 3331-LIT-0022 - CONCENTRATE STORAGE TANK | S2 - Stage 2 Pre Commissioning | No loop drawing provided | 2: B-Low
E | Item Incomplete | INST | CS25 - Copper Concentrate Thickener | CS25-08 - Copper Concentrate Thickener Froth Hopper |  | 2021-04-12 02:25 |  |  |  | Accepted | PL-01532 | 3331-FV-1109 - OUTLET CONCENTRATE THICKENER FROTH OVERFLOW HOPPER | S2 - Stage 2 Pre Commissioning | Terminal box needs to be mounted to valve
E | Item not secured | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) |  | 2021-03-21 01:43 |  |  |  | Submitted | PL-01331 | 3331-FV-1005 - PROCESS WATER TO COPPER CONCENTRATE THICKENER | S1 - Stage 1 Construction Completion | Fix termination action box to fv
E | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-04 02:50 | 2021-02-18 02:48 |  |  |  | Originated | PL-00627 | 3332-PI-0134 - NITROGEN TO ROUGHER SCAVENGER FLOATATION CELL AGIT. | S1 - Stage 1 Construction Completion | Missing vendor supplied ID tag | 2: B-Low
E | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-04 02:53 | 2021-02-18 02:53 |  |  |  | Originated | PL-00628 | 3332-PI-0143 - NITROGEN TO ROUGHER SCAVENGER FLOATATION CELL AGIT. | S1 - Stage 1 Construction Completion | Missing vendor supplied ID tag | 2: B-Low
E | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-04 02:55 | 2021-02-18 02:55 |  |  |  | Originated | PL-00629 | 3332-PI-0170 - NITROGEN TO ROUGHER FLOTATION CELL 3 AGITATOR | S1 - Stage 1 Construction Completion | Missing vendor supplied ID tag | 2: B-Low
E | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-04 03:38 | 2021-02-18 03:37 |  |  |  | Originated | PL-00633 | 3332-PI-0174 - NITROGEN TO ROUGHER FLOTATION CELL 5 AGITATOR | S1 - Stage 1 Construction Completion | Missing vendor supplied ID tag | 2: B-Low
E | Missing Labels | INST | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells | 2021-03-04 03:40 | 2021-02-18 03:40 |  |  |  | Originated | PL-00634 | 3332-PI-0172 - NITROGEN TO ROUGHER FLOTATION CELL 4 AGITATOR | S1 - Stage 1 Construction Completion | Missing vendor supplied ID tag | 2: B-Low
E | Missing Labels | INST | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-05-07 07:42 | 2021-04-23 07:42 |  |  |  | Originated | PL-01645 | 3332-PI-0314 - NITROGEN TO SECOND CLEANER FLOTATION CELL 3 AGITATOR | S1 - Stage 1 Construction Completion | Vendor I’d label not supplied | 2: B-Low
E | Missing Labels | INST | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-05-07 20:26 | 2021-04-23 20:24 |  |  |  | Originated | PL-01646 | 3332-PI-0308 - NITROGEN TO SECOND CLEANER FLOTATION CELL 2 AGITATOR | S1 - Stage 1 Construction Completion | Supply and fit vendor I’d tags | 2: B-Low
E | Missing Labels | INST | CS05 - 2nd Cleaner Flotation | CS05-08 - Second Cleaner Flotation Cells | 2021-05-07 21:12 | 2021-04-23 21:12 |  |  |  | Originated | PL-01647 | 3332-PI-0302 - NITROGEN TO SECOND CLEANER FLOTATION CELL 1 AGITATOR | S1 - Stage 1 Construction Completion | Vendor I’d tag to be supplied and fitted by worley | 2: B-Low
E | Missing Labels | INST | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-02-08 05:29 | 2021-01-25 05:29 |  |  |  | Originated | PL-00298 | 3334-FIT-0770 - RAW WATER TO FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Free issued equipment supplied without ID tag | 2: B-Low
E | Missing Labels | INST | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-02-08 06:25 | 2021-01-25 06:25 |  |  |  | Originated | PL-00299 | 3334-FIT-0791 - RAW WATER TO FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Free issued equipment supplied without ID tag | 2: B-Low
E | Missing Labels | INST | CS0C - Raw Water | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | 2021-02-08 06:28 | 2021-01-25 06:27 |  |  |  | Originated | PL-00300 | 3334-FIT-0790 - RAW WATER TO FLOCCULANT STATIC MIXER | S1 - Stage 1 Construction Completion | Free issued equipment supplied without ID tag | 2: B-Low
E | Missing Labels | INST | CS0D - Fire Water | CS0D-03 - Fire Water Skid |  | 2021-02-19 01:59 |  |  |  | Submitted | PL-00648 | 3335-PK-4012 - FIRE WATER PUMP VENDOR PACKAGE | S1 - Stage 1 Construction Completion | Make and attach labels to vendor skid instrumentation
E | Missing Labels | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-07 05:08 | 2021-01-24 05:08 |  |  |  | Originated | PL-00289 | 3335-LIT-0840 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Free issued equipment supplied without any id tags | 2: B-Low
E | Missing Labels | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-08 02:27 | 2021-01-25 02:27 |  |  |  | Originated | PL-00294 | 3335-FIT-0849 - PROCESS WATER TO PROCESS WATER HEADER | S1 - Stage 1 Construction Completion | Free issued equipment supplied without ID tags. | 2: B-Low
E | Missing Labels | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-08 02:40 | 2021-01-25 02:39 |  |  |  | Originated | PL-00295 | 3335-AIT-0854 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Free issued equipment supplied without ID tags. | 2: B-Low
E | Missing Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 01:10 | 2021-01-24 01:09 |  |  |  | Originated | PL-00284 | 3334-LIT-2121 - Pressure Indicating Transmitter used to measure level | S1 - Stage 1 Construction Completion | Free issued equipment supplied without Id tags. | 2: B-Low
E | Missing Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 02:47 | 2021-01-24 02:47 |  |  |  | Submitted | PL-00285 | 3334-LS-2103 - LEVEL SWITCH | S1 - Stage 1 Construction Completion | Free issued equipment supplied without Id tags. | 2: B-Low
E | Missing Labels | INST | CS13 - Flocculant Preparation & Distribution | CS13-01 - Flocculant Plant and Distribution | 2021-02-07 05:42 | 2021-01-24 05:42 |  |  |  | Originated | PL-00292 | 3334-LIT-2101 - Level Indicating Transmitter | S1 - Stage 1 Construction Completion | No equipment I’d tag provided with vendor devices | 2: B-Low
E | Missing Parts | ELEC | CS03 - Intermediate Thickener and Regrind Mill | CS03-07 - Regrind mill | 2021-05-01 04:40 | 2021-04-17 04:03 |  |  |  | Originated | PL-01550 | 3332-MB-4046 - Regrind Mill Instrumentation Box | S1 - Stage 1 Construction Completion | 1 vendor cover screw is missing not supplied with box | 2: B-Low
E | Missing Parts | INST | CS0E - Process Water Distribution | CS0E-01 - Process Water Tank, Pumps and Header | 2021-02-07 05:10 | 2021-01-24 05:09 |  |  |  | Originated | PL-00290 | 3335-LIT-0840 - PROCESS WATER TANK | S1 - Stage 1 Construction Completion | Flange size not correct | 2: B-Low
E | Not to Contract Spec | ELEC | CSED - Switch Room & MCCs | CSED-04 - MCC | 2020-11-26 02:17 | 2020-11-12 02:11 |  |  |  | Originated | PL-00045 | 3338-MC-4001 - Motor Control Centre No 1 | S1 - Stage 1 Construction Completion | MCC does not match GA. General arrangement drawing to be As Built | 2: B-Low
E | Not to Contract Spec | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-05 06:52 | 2021-01-22 06:51 |  |  |  | Originated | PL-00253 | 3331-LI-0022A - Level Indicator | S2 - Stage 2 Pre Commissioning | No loop drawing provided. | 2: B-Low
E | Not to Contract Spec | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | 2021-02-05 07:13 | 2021-01-22 07:13 |  |  |  | Originated | PL-00254 | 3331-FV-1004 - OUTLET CONCENTRATE STORAGE DIVERTER BOX | S2 - Stage 2 Pre Commissioning | No loop drawing provided | 2: B-Low
E | Not to Drawings | PIPE | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-01B - Concentrate Storage Tank 2 (PART B) |  | 2021-03-23 01:52 |  | Nutt, Richard | 2021-04-07 19:54 | Closed | PL-01358 | 3331-150-CSL-0007-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Align Flexi vertical pipe 3331-SP-4009
E | Other | INST | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-11 22:10 |  | Fuller, Lachlan | 2021-04-26 15:48 | Closed | PL-01529 | 3331-FV-0047 - OUTLET COPPER CONCENTRATE THICKENER | S2 - Stage 2 Pre Commissioning | Cylinder on valve leaking a lot of air
E | Other | PIPE | CS0C - Raw Water | CS0C-04 - Raw Water Pump & Header |  | 2021-02-24 21:42 |  |  |  | Submitted | PL-00903 | 3335-AIT-0868 - OUTLET INLINE SODIUM HYDROXIDE MIXER | S1 - Stage 1 Construction Completion | rotate pH probe 90deg
E | Other | PIPE | CS25 - Copper Concentrate Thickener | CS25-02 - Copper Concentrate Thickener (Bottom) |  | 2021-04-05 19:23 |  | Lanser, Richard | 2021-04-16 21:04 | Closed | PL-01477 | 3331-150-CSL-0002-R5 - CSL Process Line | S1 - Stage 1 Construction Completion | Trim pipe supports under concentrate thickener 3331-TH-4001
E | Value Add | CABL | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-08 - Concentrate Storage Area Sump |  | 2021-03-21 01:43 |  |  |  | Submitted | PL-01330 | 3331PU4011-P2 - CONCENTRATE STORAGE SUMP PUMP | S2 - Stage 2 Pre Commissioning | Look at fix for cable slack storage
E | Value Add | INST | CS01 - Cu Concentrate Feed Tanks & Bypass | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) |  | 2021-04-08 07:00 |  |  |  | Submitted | PL-01493 | 3331-LIT-0022 - CONCENTRATE STORAGE TANK | S2 - Stage 2 Pre Commissioning | Data sheet needs to be updated calibrated range 0-10m
E | Value Add | MECH | CS02 - Rougher & Scavenger Cells | CS02-08 - Rougher Scavenger Flotation Cells |  | 2021-02-28 02:50 |  |  |  | Submitted | PL-00953 | 3332-FB-4001 - ROUGHER SCAVENGER FLOTATION CELL 1 | S1 - Stage 1 Construction Completion | All rougher flotation process water valves rotate 180 degrees to prevent trip hazard