## Exported from SC
Task ID | Description | Discipline (Name) | Asset - Tag | Asset - Asset Type (Summary) | Work Breakdown - Activity (Summary) | Work Breakdown - Stage (Summary) | Work Breakdown - Phase (Summary) | Systemization - Subsystem (Summary) | Systemization - System (Summary) | Task Status | Closing Date | Schedule Start Date | Schedule End Date | Task Duration | Submitted Date | Asset - Service | Actual End Date
T-00070-0001 | E.T003 Batteries and Chargers Stage 1 | ELEC | 3338-BR-4001 | BR - BATTERY CHARGER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-11T06:19:37.2270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.5 | 2020-12-11T05:24:34.0000000 |  | 2020-12-11T05:50:40.5500000
T-00071-0023 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4112 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:21:48.0230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:40:34.4930000 |  | 2021-03-26T02:40:42.7470000
T-00071-0024 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4102 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T22:28:20.5070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-02-01T02:33:55.8470000 |  | 2021-02-04T09:24:47.9930000
T-00071-0025 | M1.T004 Agitator Stage 1 | MECH | 3331-AG-4002 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-09T13:32:56.8030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.5 | 2021-02-28T06:22:11.0000000 |  | 2021-02-28T19:15:44.6330000
T-00071-0026 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4110 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T04:24:51.2970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-26T00:45:47.7230000 |  | 2021-03-26T00:45:54.9570000
T-00071-0027 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4105 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T22:29:12.5300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-02-01T03:24:55.2230000 |  | 2021-02-04T09:25:37.1630000
T-00071-0028 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4111 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:21:03.9100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:38:43.0330000 |  | 2021-03-26T02:38:49.8870000
T-00071-0029 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4117 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-26T20:23:14.2070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:45:54.5930000 |  | 2021-03-26T02:46:01.1530000
T-00071-0030 | M1.T004 Agitator Stage 1 | MECH | 3333-AG-4006 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00071-0031 | M1.T004 Agitator Stage 1 | MECH | 3334-AG-4012 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.5
T-00071-0032 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4107 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T04:25:29.6870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-26T00:47:59.5670000 |  | 2021-03-26T00:48:05.7730000
T-00071-0033 | M1.T004 Agitator Stage 1 | MECH | 3331-AG-4001 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T03:36:52.7800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.5 | 2021-02-21T03:32:47.9500000 |  | 2021-02-21T03:33:11.1030000
T-00071-0034 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4004 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T16:24:26.6400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-08T16:08:38.0670000 |  | 2021-03-08T16:08:45.2170000
T-00071-0035 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4109 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T04:26:00.6170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-26T00:46:29.6200000 |  | 2021-03-26T00:46:36.5130000
T-00071-0036 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4103 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T22:29:42.9630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-02-01T03:02:20.3030000 |  | 2021-02-04T09:27:27.2870000
T-00071-0037 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4104 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T22:30:40.9000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-02-01T03:20:42.7930000 |  | 2021-02-04T09:31:30.1470000
T-00071-0038 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4101 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T22:31:22.5470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-02-01T03:27:41.6300000 |  | 2021-02-04T09:32:44.1800000
T-00071-0039 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4005 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T16:24:46.1770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-08T16:09:25.3830000 |  | 2021-03-08T16:09:32.6070000
T-00071-0040 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4118 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-26T20:23:51.9030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:47:18.1770000 |  | 2021-03-26T02:47:26.9930000
T-00071-0041 | M1.T004 Agitator Stage 1 | MECH | 3334-AG-4013 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-09T18:48:53.6670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.5 | 2021-03-09T18:43:49.1570000 |  | 2021-03-09T18:43:59.2100000
T-00071-0042 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4114 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:24:37.3030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:43:25.1830000 |  | 2021-03-26T02:43:31.4200000
T-00071-0043 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4113 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:25:12.0330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-03-26T02:41:37.7670000 |  | 2021-03-26T02:41:46.8200000
T-00071-0044 | M1.T004 Agitator Stage 1 | MECH | 3332-AG-4108 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T04:26:29.9200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5 | 2021-03-26T00:47:20.1070000 |  | 2021-03-26T00:47:25.9870000
T-00072-0001 | E2.T003A Batteries and Chargers Stage 2A | ELEC | 3338-BR-4001 | BR - BATTERY CHARGER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-30T21:49:59.6600000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5 | 2021-01-30T01:00:35.8570000 |  | 2021-01-30T06:48:39.5770000
T-00073-0001 | E2.T003B Batteries and Chargers Stage 2B | ELEC | 3338-BR-4001 | BR - BATTERY CHARGER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:54:12.2270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-04-23T04:53:36.8600000 |  | 2021-04-23T04:55:30.2870000
T-00077-0003 | M1.T005 Air Blower Stage 1 | MECH | 3334-BL-4001 | BL - BLOWER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-09T18:49:10.2900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-09T18:44:39.0270000 |  | 2021-03-09T18:44:46.5400000
T-00079-0004 | M1.T006 Air Compressor Stage 1 | MECH | 3335-CP-4001 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00079-0005 | M1.T006 Air Compressor Stage 1 | MECH | 3335-CP-4003 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00079-0006 | M1.T006 Air Compressor Stage 1 | MECH | 3335-CP-4002 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00081-0004 | M1.T013 Bin Stage 1 | MECH | 3334-BN-4003 | BN - BIN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-09T18:49:35.6270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-09T18:45:31.0270000 |  | 2021-03-09T18:45:37.7200000
T-00081-0005 | M1.T013 Bin Stage 1 | MECH | 3333-BN-4002 | BN - BIN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00081-0006 | M1.T013 Bin Stage 1 | MECH | 3333-BN-4001 | BN - BIN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00082-0004 | M3.T006 Air Compressor Stage 3 | MECH | 3335-CP-4001 | CP - COMPRESSOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00082-0005 | M3.T006 Air Compressor Stage 3 | MECH | 3335-CP-4003 | CP - COMPRESSOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00082-0006 | M3.T006 Air Compressor Stage 3 | MECH | 3335-CP-4002 | CP - COMPRESSOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00083-0015 | M1.T014 Chute Stage 1 | MECH | 3332-CH-4012 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-13T20:20:40.8100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-13T20:17:34.4100000 |  | 2021-03-13T20:17:41.3970000
T-00083-0016 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4015 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00083-0017 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4005 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00083-0018 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4014 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00083-0019 | M1.T014 Chute Stage 1 | MECH | 3332-CH-4010 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-15T21:47:39.2470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-13T21:12:41.2930000 |  | 2021-03-13T21:12:47.1970000
T-00083-0020 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4004 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00083-0021 | M1.T014 Chute Stage 1 | MECH | 3331-CH-4007 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T10:13:00.3330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T03:10:46.0000000 |  | 2021-04-21T03:12:37.0470000
T-00083-0022 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4006 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00083-0023 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4002 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00083-0024 | M1.T014 Chute Stage 1 | MECH | 3332-CH-4011 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-15T21:48:05.7600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-13T21:13:13.9030000 |  | 2021-03-13T21:13:21.6100000
T-00083-0025 | M1.T014 Chute Stage 1 | MECH | 3331-CH-4008 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T10:24:02.4270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T03:14:42.9100000 |  | 2021-04-21T03:14:49.6870000
T-00083-0026 | M1.T014 Chute Stage 1 | MECH | 3331-CH-4009 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T10:25:17.6030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T03:01:41.4270000 |  | 2021-04-21T03:01:51.5270000
T-00083-0027 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4013 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00083-0028 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4003 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00083-0029 | M1.T014 Chute Stage 1 | MECH | 3333-CH-4001 | CH - CHUTE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00086-0009 | M1.T025 Dust Collector Stage 1 | MECH | 3334-DE-4001 | DE - DUST EXTRACTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-09T18:50:00.3800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-09T18:46:24.5700000 |  | 2021-03-09T18:47:02.5300000
T-00086-0010 | M1.T025 Dust Collector Stage 1 | MECH | 3333-DC-4004 | DC - DUST COLLECTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00086-0011 | M1.T025 Dust Collector Stage 1 | MECH | 3333-DC-4003 | DC - DUST COLLECTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00087-0009 | M3.T025 Dust Collector Stage 3 | MECH | 3334-DE-4001 | DE - DUST EXTRACTOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00087-0010 | M3.T025 Dust Collector Stage 3 | MECH | 3333-DC-4004 | DC - DUST COLLECTOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00087-0011 | M3.T025 Dust Collector Stage 3 | MECH | 3333-DC-4003 | DC - DUST COLLECTOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00088-0055 | M1.T029 Filter (Strainer) Stage 1 | MECH | 3333-FI-4001 | FI - FILTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00089-0017 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4001 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T05:48:36.5770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T03:21:27.0430000 |  | 2021-02-22T03:21:34.6700000
T-00089-0018 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4007 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-22T06:13:21.8770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:00:04.5870000 |  | 2021-02-22T06:00:11.8600000
T-00089-0019 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4017 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T06:23:16.7230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:05:09.2770000 |  | 2021-02-22T06:05:16.1800000
T-00089-0020 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4005 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T06:11:56.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:10:48.7330000 |  | 2021-02-22T06:10:56.7670000
T-00089-0021 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4008 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-22T06:14:08.7100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:01:02.1400000 |  | 2021-02-22T06:01:12.1170000
T-00089-0022 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4018 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T06:23:51.4430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:05:36.8830000 |  | 2021-02-22T06:05:44.1700000
T-00089-0024 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4013 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T06:17:21.9400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:02:58.8170000 |  | 2021-02-22T06:03:06.1500000
T-00089-0025 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4002 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T05:51:59.2930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T03:23:02.2000000 |  | 2021-02-22T03:23:11.2500000
T-00089-0026 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4012 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T06:18:10.8930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:03:37.3830000 |  | 2021-02-22T06:03:49.2600000
T-00089-0027 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4010 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-22T06:15:19.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:01:46.9070000 |  | 2021-02-22T06:01:53.9530000
T-00089-0028 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4004 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T05:52:46.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T03:23:38.5070000 |  | 2021-02-22T03:23:44.8970000
T-00089-0029 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4014 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T06:21:11.1730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:04:13.3470000 |  | 2021-02-22T06:04:21.5500000
T-00089-0030 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4009 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-22T06:16:09.4030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:02:25.5300000 |  | 2021-02-22T06:02:33.3430000
T-00089-0031 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4011 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T06:21:55.5100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T06:04:42.0870000 |  | 2021-02-22T06:04:49.3430000
T-00089-0032 | M1.T033 Flotation Cell Stage 1 | MECH | 3332-FB-4003 | FB - FLOTATION CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T05:53:24.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T03:24:12.8070000 |  | 2021-02-22T03:24:21.7130000
T-00090-0057 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4003 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-27T20:24:52.8270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-27T20:23:45.0570000 |  | 2021-01-27T20:23:57.8630000
T-00090-0058 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4006 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0059 | M1.T037 General Mechanical Stage 1 | MECH | 3332-CY-4015 | CY - JAMESON CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-18T04:08:01.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:48:20.7870000 |  | 2021-04-18T03:48:27.7970000
T-00090-0061 | M1.T037 General Mechanical Stage 1 | MECH | 3332-FH-4004 | FH - FUME HOOD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T04:52:59.4770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-26T04:20:16.5430000 |  | 2021-04-26T04:20:27.2130000
T-00090-0062 | M1.T037 General Mechanical Stage 1 | MECH | 3333-PK-4003 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0063 | M1.T037 General Mechanical Stage 1 | MECH | 3332-ML-4001 | ML - REGRIND MILL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-18T03:31:30.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:11:59.0070000 |  | 2021-04-18T03:12:05.8570000
T-00090-0064 | M1.T037 General Mechanical Stage 1 | MECH | 3333-FD-4001 | FD - SCREW FEEDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0065 | M1.T037 General Mechanical Stage 1 | MECH | 3335-MX-4005 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-22T20:50:45.3370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T04:51:37.5400000 |  | 2021-02-21T04:51:43.4400000
T-00090-0066 | M1.T037 General Mechanical Stage 1 | MECH | 3334-FD-4003 | FD - SCREW FEEDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:44:49.4800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T20:41:20.5470000 |  | 2021-03-10T20:41:27.0470000
T-00090-0067 | M1.T037 General Mechanical Stage 1 | MECH | 3335-DY-4002 | DY - AIR DRYER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0068 | M1.T037 General Mechanical Stage 1 | MECH | 3335-DY-4004 | DY - AIR DRYER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0069 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4026 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0070 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4012 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-12T01:28:21.5130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-12T00:51:40.6270000 |  | 2021-02-12T00:52:37.8770000
T-00090-0071 | M1.T037 General Mechanical Stage 1 | MECH | 3332-SR-4001 | SR - SRUBBER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0072 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4001 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0073 | M1.T037 General Mechanical Stage 1 | MECH | 3332-CY-4001 | CY - JAMESON CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-16T21:15:51.6700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-10T01:33:17.0470000 |  | 2021-04-16T20:18:17.2470000
T-00090-0074 | M1.T037 General Mechanical Stage 1 | MECH | 3333-PK-4004 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0075 | M1.T037 General Mechanical Stage 1 | MECH | 3332-PK-4001 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0077 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4004 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-27T20:26:06.5300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-27T20:24:39.6430000 |  | 2021-01-27T20:24:47.1930000
T-00090-0078 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4028 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0079 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4027 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0080 | M1.T037 General Mechanical Stage 1 | MECH | 3333-HE-4002 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0081 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4010 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0083 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4025 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-01 - Septic Tank | CS29 - Bio sewage Treatment | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0084 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4007 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0085 | M1.T037 General Mechanical Stage 1 | MECH | 3332-FH-4001 | FH - FUME HOOD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00090-0087 | M1.T037 General Mechanical Stage 1 | MECH | 3335-PK-4009 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0088 | M1.T037 General Mechanical Stage 1 | MECH | 3334-MX-4002 | MX - MIXER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-27T20:24:17.2800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-27T20:21:21.0270000 |  | 2021-01-27T20:21:57.4330000
T-00090-0089 | M1.T037 General Mechanical Stage 1 | MECH | 3332-CY-4016 | CY - JAMESON CELL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-18T04:56:48.8270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T04:16:29.8670000 |  | 2021-04-18T04:16:37.4200000
T-00090-0090 | M1.T037 General Mechanical Stage 1 | MECH | 3333-SR-4002 | SR - SRUBBER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0091 | M1.T037 General Mechanical Stage 1 | MECH | 3333-PK-4006 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0092 | M1.T037 General Mechanical Stage 1 | MECH | 3333-FD-4002 | FD - SCREW FEEDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0094 | M1.T037 General Mechanical Stage 1 | MECH | 3334-PK-4007 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0095 | M1.T037 General Mechanical Stage 1 | MECH | 3332-FH-4002 | FH - FUME HOOD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00090-0096 | M1.T037 General Mechanical Stage 1 | MECH | 3334-PK-4008 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-27T20:34:59.1200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-27T20:33:02.1530000 |  | 2021-01-27T20:33:10.5630000
T-00090-0097 | M1.T037 General Mechanical Stage 1 | MECH | 3335-DY-4003 | DY - AIR DRYER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0098 | M1.T037 General Mechanical Stage 1 | MECH | 3332-FH-4003 | FH - FUME HOOD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00090-0099 | M1.T037 General Mechanical Stage 1 | MECH | 3333-PK-4012 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0100 | M1.T037 General Mechanical Stage 1 | MECH | 3332-AN-4001 | AN - ANALYSER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0101 | General Mechanical Stage 1 | MECH | 3333-DY-4001 | DY - AIR DRYER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0110 | M1.T037 General Mechanical Stage 1 | MECH | 3334-HE-4002 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0116 | M1.T037 General Mechanical Stage 1 | MECH | 3332-HE-4007A | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00090-0118 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CO-4001 | CO - OIL COOLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0119 | M1.T037 General Mechanical Stage 1 | MECH | 3331-HE-4004 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-10T23:37:31.6800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-10T23:03:07.9270000 |  | 2021-03-10T23:03:15.0070000
T-00090-0124 | M1.T037 General Mechanical Stage 1 | MECH | 3334-HE-4001 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00090-0127 | M1.T037 General Mechanical Stage 1 | MECH | 3331-HE-4003 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-10T23:37:54.4470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-10T23:03:33.5470000 |  | 2021-03-10T23:03:39.6670000
T-00090-0128 | M1.T037 General Mechanical Stage 1 | MECH | 3333-HE-4001 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00090-0129 | M1.T037 General Mechanical Stage 1 | MECH | 3331-HE-4006 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-10T23:38:19.9030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-10T23:03:59.8970000 |  | 2021-03-10T23:04:06.4600000
T-00090-0130 | M1.T037 General Mechanical Stage 1 | MECH | 3331-HE-4005 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-10T23:38:44.5770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-10T23:04:28.6700000 |  | 2021-03-10T23:04:37.5730000
T-00090-0138 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CV-4001 | CV - CONVEYOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0139 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CV-4004 | CV - CONVEYOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0140 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CV-4005 | CV - CONVEYOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0141 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CV-4003 | CV - CONVEYOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0142 | M1.T037 General Mechanical Stage 1 | MECH | 3333-CV-4002 | CV - CONVEYOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00090-0143 | M1.T037 General Mechanical Stage 1 | MECH | Firebox-FWA-0001 | FB - Fire Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0144 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0016 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0145 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0014 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0146 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0015 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0147 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0013 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0148 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0011 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0149 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0020 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0150 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0017 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0151 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0019 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0152 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0018 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0153 | M1.T037 General Mechanical Stage 1 | MECH | SP4300-FWA-0012 | FHR - Fire Hose Reel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Created |  |  |  | 0.25
T-00090-0154 | M1.T037 General Mechanical Stage 1 | MECH | 3332-HE-4007B | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  |  |  | 0.25
T-00090-0155 | M1.T037 General Mechanical Stage 1 | MECH | 3332-HE-4007C | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.25
T-00090-0156 | M1.T037 General Mechanical Stage 1 | MECH | 3334-HE-4008 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  |  |  | 0.25
T-00091-0057 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4003 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0058 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4006 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0059 | M3.T037 General Mechanical Stage 3 | MECH | 3332-CY-4015 | CY - JAMESON CELL | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0061 | M3.T037 General Mechanical Stage 3 | MECH | 3332-FH-4004 | FH - FUME HOOD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T06:33:39.2500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-26T04:29:39.4530000 |  | 2021-04-26T04:29:46.9400000
T-00091-0062 | M3.T037 General Mechanical Stage 3 | MECH | 3333-PK-4003 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0063 | M3.T037 General Mechanical Stage 3 | MECH | 3332-ML-4001 | ML - REGRIND MILL | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0064 | M3.T037 General Mechanical Stage 3 | MECH | 3333-FD-4001 | FD - SCREW FEEDER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0065 | M3.T037 General Mechanical Stage 3 | MECH | 3335-MX-4005 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00091-0066 | M3.T037 General Mechanical Stage 3 | MECH | 3334-FD-4003 | FD - SCREW FEEDER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0067 | M3.T037 General Mechanical Stage 3 | MECH | 3335-DY-4002 | DY - AIR DRYER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0068 | M3.T037 General Mechanical Stage 3 | MECH | 3335-DY-4004 | DY - AIR DRYER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0069 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4026 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0070 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4012 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Started |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00091-0071 | M3.T037 General Mechanical Stage 3 | MECH | 3332-SR-4001 | SR - SRUBBER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0072 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4001 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0073 | M3.T037 General Mechanical Stage 3 | MECH | 3332-CY-4001 | CY - JAMESON CELL | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00091-0074 | M3.T037 General Mechanical Stage 3 | MECH | 3333-PK-4004 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0075 | M3.T037 General Mechanical Stage 3 | MECH | 3332-PK-4001 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0077 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4004 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0078 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4028 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0079 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4027 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0080 | M3.T037 General Mechanical Stage 3 | MECH | 3333-HE-4002 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0081 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4010 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0082 | M3.T037 General Mechanical Stage 3 | MECH | 3334-FD-4004 | FD - SCREW FEEDER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0083 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4025 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS29-01 - Septic Tank | CS29 - Bio sewage Treatment | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0084 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4007 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0085 | M3.T037 General Mechanical Stage 3 | MECH | 3332-FH-4001 | FH - FUME HOOD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0087 | M3.T037 General Mechanical Stage 3 | MECH | 3335-PK-4009 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0088 | M3.T037 General Mechanical Stage 3 | MECH | 3334-MX-4002 | MX - MIXER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0089 | M3.T037 General Mechanical Stage 3 | MECH | 3332-CY-4016 | CY - JAMESON CELL | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0090 | M3.T037 General Mechanical Stage 3 | MECH | 3333-SR-4002 | SR - SRUBBER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0091 | M3.T037 General Mechanical Stage 3 | MECH | 3333-PK-4006 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0092 | M3.T037 General Mechanical Stage 3 | MECH | 3333-FD-4002 | FD - SCREW FEEDER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0094 | M3.T037 General Mechanical Stage 3 | MECH | 3334-PK-4007 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0095 | M3.T037 General Mechanical Stage 3 | MECH | 3332-FH-4002 | FH - FUME HOOD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0096 | M3.T037 General Mechanical Stage 3 | MECH | 3334-PK-4008 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00091-0097 | M3.T037 General Mechanical Stage 3 | MECH | 3335-DY-4003 | DY - AIR DRYER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0098 | M3.T037 General Mechanical Stage 3 | MECH | 3332-FH-4003 | FH - FUME HOOD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0099 | M3.T037 General Mechanical Stage 3 | MECH | 3333-PK-4012 | PK - PACKAGE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0100 | M3.T037 General Mechanical Stage 3 | MECH | 3332-AN-4001 | AN - ANALYSER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0101 | M3.T037 General Mechanical Stage 3 | MECH | 3333-DY-4001 | DY - AIR DRYER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0110 | M3.T037 General Mechanical Stage 3 | MECH | 3334-HE-4002 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0116 | M3.T037 General Mechanical Stage 3 | MECH | 3332-HE-4007A | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00091-0118 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CO-4001 | CO - OIL COOLER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0119 | M3.T037 General Mechanical Stage 3 | MECH | 3331-HE-4004 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00091-0124 | M3.T037 General Mechanical Stage 3 | MECH | 3334-HE-4001 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0127 | M3.T037 General Mechanical Stage 3 | MECH | 3331-HE-4003 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00091-0128 | M3.T037 General Mechanical Stage 3 | MECH | 3333-HE-4001 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00091-0129 | M3.T037 General Mechanical Stage 3 | MECH | 3331-HE-4006 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00091-0130 | M3.T037 General Mechanical Stage 3 | MECH | 3331-HE-4005 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00091-0138 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CV-4001 | CV - CONVEYOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0139 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CV-4004 | CV - CONVEYOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0140 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CV-4005 | CV - CONVEYOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0141 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CV-4003 | CV - CONVEYOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0142 | M3.T037 General Mechanical Stage 3 | MECH | 3333-CV-4002 | CV - CONVEYOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00091-0143 | M3.T037 General Mechanical Stage 3 | MECH | 3332-HE-4007B | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  |  |  | 0.25
T-00091-0144 | M3.T037 General Mechanical Stage 3 | MECH | 3332-HE-4007C | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  |  |  | 0.25
T-00091-0145 | M3.T037 General Mechanical Stage 3 | MECH | 3334-HE-4008 | HE - HEATER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  |  |  | 0.25
T-00092-0005 | M1.T041 Hydraulic Powerpack Stage 1 | MECH | 3332-HY-4002 | HY - HYDRAULIC POWER UNIT | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-19T22:14:18.9370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T02:57:49.5570000 |  | 2021-04-19T02:58:09.9770000
T-00092-0007 | M1.T041 Hydraulic Powerpack Stage 1 | MECH | 3332-HY-4003 | HY - HYDRAULIC POWER UNIT | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00092-0008 | M1.T041 Hydraulic Powerpack Stage 1 | MECH | 3333-HY-4002 | HY - HYDRAULIC POWER UNIT | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00093-0002 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-VE-4040 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0003 | M1.T053 Pressure Vessel Stage 1 | MECH | 3333-VE-4037 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00093-0004 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-VE-4039 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0005 | M1.T053 Pressure Vessel Stage 1 | MECH | 3333-AR-4001 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00093-0006 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-AR-4007 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0007 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-AR-4005 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0008 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-AR-4006 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0009 | M1.T053 Pressure Vessel Stage 1 | MECH | 3335-AR-4002 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00093-0010 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4009 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T20:16:08.9070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:56:56.9100000 |  | 2021-03-26T05:57:02.7930000
T-00093-0011 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4013 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:27:28.4100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T05:59:12.3700000 |  | 2021-03-26T05:59:19.3570000
T-00093-0012 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4003 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T21:53:14.8270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T21:50:53.5200000 |  | 2021-02-22T21:52:08.9870000
T-00093-0013 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4005 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T21:54:07.9570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T21:52:50.4300000 |  | 2021-02-22T21:52:56.5170000
T-00093-0015 | M1.T053 Pressure Vessel Stage 1 | MECH | 3331-VE-4002 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-11T01:46:16.7130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-11T01:05:34.5800000 |  | 2021-03-11T01:05:44.9300000
T-00093-0016 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4007 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T20:16:36.8230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:55:50.9430000 |  | 2021-03-26T05:55:57.1730000
T-00093-0017 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4010 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T20:17:01.5530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:57:28.6930000 |  | 2021-03-26T05:57:34.7500000
T-00093-0018 | M1.T053 Pressure Vessel Stage 1 | MECH | 3334-VE-4038 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00093-0020 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4017 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-26T20:27:49.1630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T06:50:10.7800000 |  | 2021-03-26T06:50:17.6930000
T-00093-0021 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4001 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T22:33:17.8830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T22:31:10.6230000 |  | 2021-02-22T22:31:19.4570000
T-00093-0022 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4012 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:28:20.2800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T05:58:30.5530000 |  | 2021-03-26T05:58:37.0330000
T-00093-0023 | M1.T053 Pressure Vessel Stage 1 | MECH | 3331-VE-4001 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-11T20:05:18.7870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-11T20:02:34.3130000 |  | 2021-03-11T20:02:43.4500000
T-00093-0024 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4018 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-26T20:28:43.2170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T06:50:41.5470000 |  | 2021-03-26T06:50:48.7670000
T-00093-0025 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4008 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-26T20:17:30.3570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:56:22.0270000 |  | 2021-03-26T05:56:27.6170000
T-00093-0026 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4011 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:29:09.8800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T05:58:03.4330000 |  | 2021-03-26T05:58:09.9130000
T-00093-0027 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4014 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-26T20:29:32.9270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-26T05:59:43.4370000 |  | 2021-03-26T05:59:49.2430000
T-00093-0028 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4002 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T22:27:47.9070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T22:14:17.5100000 |  | 2021-02-22T22:14:24.2470000
T-00093-0029 | M1.T053 Pressure Vessel Stage 1 | MECH | 3332-VE-4004 | VE - VESSEL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T22:28:15.6030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T22:15:03.1030000 |  | 2021-02-22T22:15:10.3000000
T-00093-0030 | M1.T053 Pressure Vessel Stage 1 | MECH | 3331-VE-4008 | AR - AIR RECEIVER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  |  |  | 0.25
T-00094-0077 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3333-PSV-0627 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0078 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2202 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0079 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3332-RD-0342 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T03:43:54.5700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:20:00.4530000 |  | 2021-04-18T03:24:30.5670000
T-00094-0080 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-0837 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0081 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2210 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0082 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1059 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0083 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1065 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0085 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1058 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0086 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3332-PSV-1186 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00094-0087 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1062 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0089 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1066 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0090 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-0827 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0091 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1060 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0092 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3331-RD-0001 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T12:33:55.4630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-09T12:31:23.6000000 |  | 2021-03-09T12:31:32.5630000
T-00094-0093 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1064 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0095 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1183 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0096 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1052 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0097 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-0724 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0098 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3332-RD-0003 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-19T22:18:17.6030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T02:33:22.7900000 |  | 2021-04-19T02:33:33.2970000
T-00094-0099 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3332-RD-0001 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00094-0100 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1061 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0101 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1050 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0102 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2207 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0103 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2205 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0104 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-0727 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0105 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-0836 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0106 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3331-PSV-0079 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-09T08:58:07.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-08T20:37:38.4170000 |  | 2021-03-08T20:37:47.2870000
T-00094-0107 | M1.T054 Pressure Relief / Safety Valve Stage 1 | MECH | 3331-RD-0002 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T12:34:20.1670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-09T12:32:02.4300000 |  | 2021-03-09T12:32:10.5630000
T-00094-0108 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1048 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0109 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-0756 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0110 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1051 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0111 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2211 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0112 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-0826 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0113 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1057 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0114 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1063 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0115 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3335-PSV-2203 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00094-0116 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3334-PSV-1053 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00094-0118 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3332-PSV-0420 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:09:02.6500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-12T06:40:56.9130000 |  | 2021-04-12T07:46:25.5600000
T-00094-0120 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3333-PSV-2222 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00094-0121 | M1.T054 Pressure Relief / Safety Valve Stage 1 | INST | 3333-PSV-2221 | PSV - Pressure Safety Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00095-0066 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3331-PSV-0079 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00095-0077 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3333-PSV-0627 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0078 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2202 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0079 | M3.T054 Pressure Relief / Safety Valve Stage 3 | MECH | 3332-RD-0342 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00095-0080 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-0837 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0081 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2210 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0082 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1059 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0083 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1065 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0085 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1058 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0086 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3332-PSV-1186 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00095-0087 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1062 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0089 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1066 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0090 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-0827 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0091 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1060 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0092 | M3.T054 Pressure Relief / Safety Valve Stage 3 | MECH | 3331-RD-0001 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00095-0093 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1064 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0095 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1183 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0096 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1052 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0097 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-0724 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0098 | M3.T054 Pressure Relief / Safety Valve Stage 3 | MECH | 3332-RD-0003 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00095-0099 | M3.T054 Pressure Relief / Safety Valve Stage 3 | MECH | 3332-RD-0001 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00095-0100 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1061 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0101 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1050 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0102 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2207 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0103 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2205 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0104 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-0727 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0105 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-0836 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0106 | M3.T054 Pressure Relief / Safety Valve Stage 3 | MECH | 3331-RD-0002 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00095-0107 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1048 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0108 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-0756 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0109 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1051 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0110 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2211 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0111 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-0826 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0112 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1057 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0113 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1063 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0114 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3335-PSV-2203 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0115 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3334-PSV-1053 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00095-0117 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3332-PSV-0420 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00095-0119 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3333-PSV-2222 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00095-0120 | M3.T054 Pressure Relief / Safety Valve Stage 3 | INST | 3333-PSV-2221 | PSV - Pressure Safety Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00096-0001 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4029 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0002 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4005 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0003 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4033 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0005 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4009 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0006 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4034 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0007 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4032 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0008 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4027 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0009 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4016 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0010 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4017 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0011 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4026 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0012 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4001 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0013 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4030 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0014 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4006 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0015 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4035 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0016 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4014 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0017 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4011 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0018 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4003 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0020 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4007 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0022 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4015 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0023 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4004 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0024 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4002 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0026 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4031 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0027 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4008 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0028 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4013 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0030 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4020 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00096-0034 | M1.T062 Safety Shower Stage 1 | MECH | 3335-EW-4019 | EW - EYE WASH STATION | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00097-0001 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4029 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0002 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4005 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0003 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4033 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0005 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4009 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0006 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4034 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0007 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4032 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0008 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4027 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0009 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4016 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0010 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4017 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0011 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4026 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0012 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4001 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0013 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4030 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0014 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4006 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0015 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4035 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0016 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4014 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0017 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4011 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0018 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4003 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0020 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4007 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0022 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4015 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0023 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4004 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0024 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4002 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0026 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4031 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0027 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4008 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0028 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4013 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0030 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4020 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00097-0034 | M3.T062 Safety Shower Stage 3 | MECH | 3335-EW-4019 | EW - EYE WASH STATION | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00098-0013 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4009 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00098-0014 | M1.T063 Sampler Stage 1 | MECH | 3331-SA-4001C | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T10:41:12.5470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:19:25.0200000 |  | 2021-04-21T01:19:32.9800000
T-00098-0015 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4002C | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-23T12:36:29.7970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T02:42:53.8170000 |  | 2021-04-23T02:43:03.7170000
T-00098-0016 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4011 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00098-0017 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4008 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T03:22:13.7530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T02:43:12.8430000 |  | 2021-04-18T02:43:22.7000000
T-00098-0018 | M1.T063 Sampler Stage 1 | MECH | 3331-SA-4001B | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T11:10:19.0970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T02:54:48.1800000 |  | 2021-04-21T02:55:09.3270000
T-00098-0019 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4010 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00098-0020 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4004 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:02:23.6130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-22T02:29:15.8430000 |  | 2021-04-22T02:29:22.8070000
T-00098-0021 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4003 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T03:22:40.8430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T02:58:07.0200000 |  | 2021-04-18T02:58:17.1900000
T-00098-0022 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4002A | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-21T11:12:37.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:44:37.5770000 |  | 2021-04-21T01:44:43.8070000
T-00098-0023 | M1.T063 Sampler Stage 1 | MECH | 3331-SA-4001A | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T11:13:54.1430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:28:55.3170000 |  | 2021-04-21T01:29:01.6000000
T-00098-0024 | M1.T063 Sampler Stage 1 | MECH | 3332-SA-4002B | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-21T11:16:41.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:42:36.7130000 |  | 2021-04-21T01:42:42.3930000
T-00099-0004 | M1.T064 Screen Stage 1 | MECH | 3332-SN-4003 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00099-0005 | M1.T064 Screen Stage 1 | MECH | 3331-SN-4001 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T11:18:17.8570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T00:56:05.2100000 |  | 2021-04-21T00:56:52.5900000
T-00099-0006 | M1.T064 Screen Stage 1 | MECH | 3333-SN-4004 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00100-0017 | M1.T065 Sump Pump Stage 1 | MECH | 3331-SU-4009 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T10:13:12.3470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-09T10:05:40.2000000 |  | 2021-03-09T10:05:47.5770000
T-00100-0019 | M1.T065 Sump Pump Stage 1 | MECH | 3332-PU-4012 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T01:26:40.5770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T00:00:57.6700000 |  | 2021-04-18T00:01:06.1800000
T-00100-0020 | M1.T065 Sump Pump Stage 1 | MECH | 3332-PU-4034 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-20T00:51:56.8900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-19T02:30:29.3670000 |  | 2021-04-19T02:30:37.9200000
T-00100-0021 | M1.T065 Sump Pump Stage 1 | MECH | 3332-PU-4028 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T09:18:41.1970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-24T05:43:17.2300000 |  | 2021-04-24T05:43:22.9670000
T-00100-0022 | M1.T065 Sump Pump Stage 1 | MECH | 3334-PU-4045 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-22T09:45:19.8230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-22T04:31:44.5100000 |  | 2021-04-22T04:31:52.8430000
T-00100-0023 | M1.T065 Sump Pump Stage 1 | MECH | 3333-PU-4040 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-24T09:25:06.0370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-24T05:32:02.7370000 |  | 2021-04-24T05:32:09.4470000
T-00100-0024 | M1.T065 Sump Pump Stage 1 | MECH | 3331-PU-4009 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T10:14:13.5730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-09T10:05:01.0800000 |  | 2021-03-09T10:05:08.4800000
T-00100-0025 | M1.T065 Sump Pump Stage 1 | MECH | 3334-PU-4056 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-22T09:33:37.7500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-04-22T04:21:23.7330000 |  | 2021-04-22T04:21:34.3530000
T-00100-0026 | M1.T065 Sump Pump Stage 1 | MECH | 3331-PU-4011 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-08T10:54:33.4870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-08T04:24:38.0000000 |  | 2021-03-08T04:24:46.1500000
T-00100-0027 | M1.T065 Sump Pump Stage 1 | MECH | 3332-PU-4013 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T03:23:29.7830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T02:49:19.6730000 |  | 2021-04-18T02:49:26.5800000
T-00101-0019 | M3.T065 Sump Pump Stage 3 | MECH | 3332-PU-4012 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00101-0020 | M3.T065 Sump Pump Stage 3 | MECH | 3332-PU-4034 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00101-0021 | M3.T065 Sump Pump Stage 3 | MECH | 3332-PU-4028 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00101-0022 | M3.T065 Sump Pump Stage 3 | MECH | 3334-PU-4045 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00101-0023 | M3.T065 Sump Pump Stage 3 | MECH | 3333-PU-4040 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00101-0024 | M3.T065 Sump Pump Stage 3 | MECH | 3331-PU-4009 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00101-0025 | M3.T065 Sump Pump Stage 3 | MECH | 3334-PU-4056 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00101-0026 | M3.T065 Sump Pump Stage 3 | MECH | 3331-PU-4011 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00101-0027 | M3.T065 Sump Pump Stage 3 | MECH | 3332-PU-4013 | PU - SUMP PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0057 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4006 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:22:25.4070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T03:34:07.6130000 |  | 2021-04-21T03:34:15.1430000
T-00102-0058 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4005 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T16:25:14.2000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T16:06:12.1530000 |  | 2021-03-08T16:06:22.5170000
T-00102-0059 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4004 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T16:25:41.4970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T16:07:18.3570000 |  | 2021-03-08T16:07:25.8630000
T-00102-0060 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4008 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-19T23:10:18.1030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T05:15:27.7730000 |  | 2021-04-19T05:15:48.3000000
T-00102-0061 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4042 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-06T07:38:51.6630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-06T01:42:09.2400000 |  | 2021-04-06T01:42:16.0370000
T-00102-0062 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4030 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0063 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4007 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:03:12.6600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-22T02:25:53.9500000 |  | 2021-04-22T02:26:01.0070000
T-00102-0064 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4026 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0065 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3331-TA-4001 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T04:12:44.3700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-21T04:01:35.4430000 |  | 2021-02-21T04:01:47.2430000
T-00102-0066 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4038 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0067 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4006 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0068 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4003 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-31T16:06:58.5300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-30T04:17:33.9800000 |  | 2021-03-30T04:17:41.1530000
T-00102-0069 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4012 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0070 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4009 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0071 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TH-4002 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-19T23:17:34.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T03:06:56.9000000 |  | 2021-04-19T03:10:35.9670000
T-00102-0072 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4025 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0073 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3335-TA-4022 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-23T06:25:20.6600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-19T22:39:26.7170000 |  | 2021-02-23T06:23:10.4700000
T-00102-0074 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4031 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T16:06:22.9070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-09T15:00:43.8370000 |  | 2021-03-09T16:03:46.3700000
T-00102-0076 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3331-TH-4001 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-21T02:51:15.0970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T02:48:29.3870000 |  | 2021-02-21T02:48:45.7230000
T-00102-0077 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4011 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0078 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4043 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0079 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4036 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0080 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4014 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:45:07.9700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T20:43:00.6730000 |  | 2021-03-10T20:43:07.4570000
T-00102-0081 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4005 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-31T16:07:42.3630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-30T04:11:31.9730000 |  | 2021-03-30T04:11:39.9370000
T-00102-0082 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4018 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0083 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4005 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00102-0084 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3335-TA-4021 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-18T22:06:07.9170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T21:14:52.5100000 |  | 2021-02-18T22:02:58.8170000
T-00102-0085 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4017 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0086 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4008 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:04:05.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-22T01:56:25.6600000 |  | 2021-04-22T02:01:05.0570000
T-00102-0087 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4001 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-05T21:27:47.2230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-05T06:53:05.0730000 |  | 2021-04-05T06:53:12.7130000
T-00102-0088 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3331-HP-4011 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T14:02:24.4470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-28T06:29:16.0000000 |  | 2021-03-08T13:06:34.2870000
T-00102-0089 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4010 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-04T03:10:27.6630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T21:49:31.4270000 |  | 2021-04-03T21:49:37.8400000
T-00102-0090 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4007 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0091 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4004 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00102-0092 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4016 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0093 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3335-TA-4023 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00102-0094 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4007 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T03:49:39.1000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T03:44:08.5070000 |  | 2021-02-22T03:44:16.7770000
T-00102-0096 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TA-4035 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00102-0097 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3334-TA-4013 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:45:38.9200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T20:44:00.4100000 |  | 2021-03-10T20:44:08.0070000
T-00102-0098 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3333-TA-4029 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0099 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4001 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T04:11:46.5730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T02:22:20.6900000 |  | 2021-02-22T02:22:26.5430000
T-00102-0100 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-TH-4003 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00102-0101 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-LD-4002 | LD - LAUNDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-19T23:18:55.9100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T05:38:46.3000000 |  | 2021-04-19T05:39:15.6430000
T-00102-0102 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3331-TA-4002 | TA - TANK | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-09T13:34:26.6030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-28T20:31:24.5730000 |  | 2021-02-28T20:31:31.4970000
T-00102-0103 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-HP-4009 | HP - HOPPER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T17:49:11.4430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T17:44:36.8700000 |  | 2021-03-08T17:44:45.6770000
T-00102-0104 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-DI-4001 | DI - DISTRIBUTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-09T13:08:09.1070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T17:41:02.1170000 |  | 2021-03-08T17:41:12.4470000
T-00102-0105 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-DI-4009 | DI - DISTRIBUTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-19T23:23:17.5570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T03:14:17.8370000 |  | 2021-04-19T03:14:30.0570000
T-00102-0107 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-DI-4005 | DI - DISTRIBUTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:24:05.4870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T03:25:45.2130000 |  | 2021-04-21T03:25:51.9700000
T-00102-0108 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3331-DI-4005 | DI - DISTRIBUTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T04:13:40.5470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-21T04:08:55.5470000 |  | 2021-02-21T04:09:04.8470000
T-00102-0109 | M1.T066 Tank-Hopper-Box Atmospheric Stage 1 | MECH | 3332-DI-4010 | DI - DISTRIBUTOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00103-0004 | M1.T067 Thickener Rake Stage 1 | MECH | 3332-TH-4002 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T03:41:14.7830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-06T01:59:11.6530000 |  | 2021-04-06T01:59:19.9830000
T-00103-0005 | M1.T067 Thickener Rake Stage 1 | MECH | 3331-TH-4001 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-21T02:51:39.3500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T02:49:31.4700000 |  | 2021-02-21T02:49:37.3100000
T-00103-0006 | M1.T067 Thickener Rake Stage 1 | MECH | 3332-TH-4003 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00104-0004 | M3.T067 Thickener Rake Stage 3 | MECH | 3332-TH-4002 | TH - THICKENER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00104-0005 | M3.T067 Thickener Rake Stage 3 | MECH | 3331-TH-4001 | TH - THICKENER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00104-0006 | M3.T067 Thickener Rake Stage 3 | MECH | 3332-TH-4003 | TH - THICKENER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00105-0002 | M1.T070 Vibrating Feeder Stage 1 | MECH | 3334-VI-4001 | VI - VIBRATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:50:07.2070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T20:46:22.0670000 |  | 2021-03-10T20:46:28.1000000
T-00105-0003 | M1.T070 Vibrating Feeder Stage 1 | MECH | 3334-AT-4001 | AT - ACTIVATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:46:18.0730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T20:45:18.7030000 |  | 2021-03-10T20:45:27.8800000
T-00105-0004 | M1.T070 Vibrating Feeder Stage 1 | MECH | 3333-VI-4002 | VI - VIBRATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00105-0005 | M1.T070 Vibrating Feeder Stage 1 | MECH | 3333-VI-4003 | VI - VIBRATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00106-0002 | HV Ring Main Unit Stage 1 | ELEC | 3338-RU-4001 | RU - RING MAIN UNIT | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-21T02:12:25.3000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T01:36:50.0500000 |  | 2020-12-21T01:52:59.7930000
T-00107-0002 | E2.T018 HV Ring Main Unit Stage 2 | ELEC | 3338-RU-4001 | RU - RING MAIN UNIT |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00108-0007 | E1.T041 LV Distribution Stage 1 | ELEC | 3331-DB-4007 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T05:35:25.1570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.5 | 2021-03-21T04:27:30.9430000 |  | 2021-03-21T05:14:31.8430000
T-00108-0008 | E1.T041 LV Distribution Stage 1 | ELEC | 3333-DB-4009 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.5
T-00108-0009 | E1.T041 LV Distribution Stage 1 | ELEC | 3331-DB-4011 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-25T06:12:44.1870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.5 | 2021-01-25T02:02:57.6000000 |  | 2021-01-25T03:01:34.3970000
T-00108-0010 | LV Distribution Stage 1 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:08:05.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T01:28:59.0470000 |  | 2020-11-06T01:02:37.7570000
T-00108-0011 | E1.T041 LV Distribution Stage 1 | ELEC | 3332-DB-4008 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-28T04:19:49.7200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-02-27T07:06:12.3570000 |  | 2021-02-27T20:29:05.9030000
T-00108-0012 | LV Distribution Stage 1 | ELEC | 3338-DB-4003 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-02T22:49:20.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-18T06:31:33.0000000 |  | 2020-11-20T02:52:40.4370000
T-00108-0013 | E1.T041 LV Distribution Stage 1 | ELEC | 3334-DB-4010 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.5
T-00108-0014 | LV Distribution Stage 1 | ELEC | 3338-DB-4001 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:08:44.8700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 |  | 2020-11-01T21:13:56.0000000 |  | 2020-11-04T04:25:16.0000000
T-00108-0015 | LV Distribution Stage 1 | ELEC | 3338-DB-4002 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-02T23:27:44.4830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-18T06:36:40.0000000 |  | 2020-11-20T02:53:12.4630000
T-00108-0016 | LV Distribution Stage 1 | ELEC | 3338-DB-1396 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T11:28:32.9000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-06T04:59:37.0000000 |  | 2020-11-06T05:18:00.6770000
T-00108-0017 | LV Distribution Stage 1 | ELEC | 3338-DB-1225 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T11:29:07.8900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-06T04:52:40.0000000 |  | 2020-11-06T05:18:31.9470000
T-00108-0018 | LV Distribution Stage 1 | ELEC | 3338-DB-1385 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T11:29:43.2530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-06T05:05:30.0000000 |  | 2020-11-06T05:19:13.6530000
T-00108-0019 | LV Distribution Stage 1 | ELEC | 3338-DB-1377 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T11:30:51.0830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-06T05:10:21.0000000 |  | 2020-11-06T05:19:44.4330000
T-00108-0020 | E1.T041 LV Distribution Stage 1 | ELEC | 3332-DB-4013 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.5
T-00108-0021 | E1.T041 LV Distribution Stage 1 | ELEC | 3338-DB-4005 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00108-0022 | E1.T041 LV Distribution Stage 1 | ELEC | 3332-DB-4012 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Started |  |  |  | 0.5
T-00108-0023 | E1.T041 LV Distribution Stage 1 | ELEC | 3332-DB-4006 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.5
T-00109-0002 | E2.T033 HV Transformer Stage 2 | ELEC | 3338-TF-4002 | TF - TRANSFORMER | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:54:48.3970000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-04-23T05:13:20.1570000 |  | 2021-04-23T05:18:26.3400000
T-00109-0003 | E2.T033 HV Transformer Stage 2 | ELEC | 3338-TF-4001 | TF - TRANSFORMER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:55:13.3100000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-04-23T05:09:10.0770000 |  | 2021-04-23T05:10:54.3470000
T-00110-0007 | E2.T041 LV Distribution Stage 2 | ELEC | 3331-DB-4007 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T08:06:02.9370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:08:13.6970000 |  | 2021-04-10T03:51:30.9070000
T-00110-0008 | E2.T041 LV Distribution Stage 2 | ELEC | 3333-DB-4009 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00110-0009 | E2.T041 LV Distribution Stage 2 | ELEC | 3331-DB-4011 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T03:26:01.4370000 |  | 2021-04-26T04:46:00.1470000
T-00110-0010 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-01-21T02:53:24.1270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T01:11:14.7770000 |  | 2021-01-16T20:29:52.1530000
T-00110-0011 | E2.T041 LV Distribution Stage 2 | ELEC | 3332-DB-4008 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00110-0012 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-4003 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00110-0013 | E2.T041 LV Distribution Stage 2 | ELEC | 3334-DB-4010 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00110-0014 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-4001 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00110-0015 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-4002 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-15T12:31:33.2970000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T01:37:19.3500000 |  | 2021-01-13T21:34:57.5800000
T-00110-0016 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-1396 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-01-21T02:53:55.4200000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T02:34:51.9430000 |  | 2021-01-16T20:36:18.7170000
T-00110-0017 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-1225 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-01-29T21:15:45.9070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T02:49:11.0770000 |  | 2021-01-16T20:36:38.3500000
T-00110-0018 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-1385 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-01-29T21:16:10.2430000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T02:53:01.7230000 |  | 2021-01-16T20:37:04.6400000
T-00110-0019 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-1377 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-01-29T21:16:45.3300000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-10T02:59:39.4930000 |  | 2021-01-16T20:37:25.4530000
T-00110-0020 | E2.T041 LV Distribution Stage 2 | ELEC | 3332-DB-4013 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00110-0021 | E2.T041 LV Distribution Stage 2 | ELEC | 3338-DB-4005 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00110-0022 | E2.T041 LV Distribution Stage 2 | ELEC | 3332-DB-4012 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  |  |  | 0.25
T-00110-0023 | E2.T041 LV Distribution Stage 2 | ELEC | 3332-DB-4006 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.25
T-00114-0117 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0108 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:00:37.2200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T20:44:48.9600000 |  | 2021-02-11T21:35:05.5200000
T-00114-0222 | I1.T026 Control Valve Stage 1 | INST | 3331-LCV-2147 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T00:20:58.0900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T05:24:52.6200000 |  | 2021-01-22T21:25:56.2270000
T-00114-0236 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0185A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T22:22:47.8970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T01:56:19.2700000 |  | 2021-02-08T04:12:29.0970000
T-00114-0237 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0315B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:25:55.2730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:46:15.8870000 |  | 2021-02-24T21:44:33.6030000
T-00114-0238 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0490 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:05:55.6170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:08:41.4930000 |  | 2021-02-08T04:44:51.5200000
T-00114-0239 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0718 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0240 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0132 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:03:57.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:58:05.5100000 |  | 2021-01-31T02:00:43.3200000
T-00114-0241 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-0888 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0243 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0324 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0244 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-0837 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0245 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0453 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:03:57.7670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-20T07:36:16.2700000 |  | 2021-04-20T07:41:29.2030000
T-00114-0246 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0731 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0247 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-1052 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0248 | I1.T026 Control Valve Stage 1 | INST | 3333-PCV-1111 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00114-0249 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0456 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:08:46.0630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T21:25:23.8870000 |  | 2021-04-02T00:33:41.2530000
T-00114-0251 | I1.T026 Control Valve Stage 1 | INST | 3335-LCV-0840 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-11T14:01:08.9700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T00:33:50.4370000 |  | 2021-02-11T04:57:15.8070000
T-00114-0252 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0315A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:26:19.9030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:43:06.9870000 |  | 2021-02-24T21:47:22.1000000
T-00114-0253 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0710 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0254 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0449 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:50:38.9700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:29:23.8070000 |  | 2021-04-14T07:11:14.2500000
T-00114-0255 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0148 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0256 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0348 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:10:07.5430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T21:19:00.7170000 |  | 2021-04-02T00:34:18.8200000
T-00114-0257 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-0847 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:26:36.1700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T05:41:15.5830000 |  | 2021-02-07T07:05:10.2070000
T-00114-0258 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0457 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-14T07:51:00.9330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:43:58.4670000 |  | 2021-04-14T04:09:52.2370000
T-00114-0259 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0133 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:04:30.4770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:55:14.1200000 |  | 2021-01-31T02:02:23.3300000
T-00114-0260 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-1026 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0261 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-1038 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0262 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0499A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:06:25.3770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:10:52.3400000 |  | 2021-02-08T04:45:12.8830000
T-00114-0263 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0190B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-25T13:56:18.0130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T00:10:52.7870000 |  | 2021-02-24T21:34:18.9900000
T-00114-0264 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0113 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:06:12.3170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T21:16:19.2700000 |  | 2021-02-11T21:35:28.5430000
T-00114-0265 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0445 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:51:32.3070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T01:01:21.4670000 |  | 2021-04-14T07:11:33.0570000
T-00114-0266 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0164A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:09:15.6400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:48:38.2370000 |  | 2021-01-31T02:03:16.4700000
T-00114-0268 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0185B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T22:23:50.0970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:13:20.2870000 |  | 2021-02-08T04:12:57.7100000
T-00114-0269 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-1105 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0270 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0165 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:09:53.8000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:43:47.6970000 |  | 2021-01-31T02:04:03.3600000
T-00114-0271 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0720 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0272 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-0859 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-08T22:21:05.5200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-08T00:18:31.1500000 |  | 2021-02-08T04:11:35.2500000
T-00114-0273 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0161 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:10:24.9270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:50:05.2500000 |  | 2021-01-31T02:04:28.1570000
T-00114-0274 | I1.T026 Control Valve Stage 1 | INST | 3335-FCV-0855 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-22T09:21:36.0170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-21T22:32:04.7300000 |  | 2021-02-21T22:39:24.4100000
T-00114-0275 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0468 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T06:34:44.8400000 |  | 2021-04-26T06:37:41.7630000
T-00114-0276 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0213 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0277 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0195 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:04:20.6200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:18:43.1700000 |  | 2021-02-08T04:42:48.7570000
T-00114-0279 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0210 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0280 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0499B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:06:54.8630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:11:28.5600000 |  | 2021-02-08T04:45:36.0630000
T-00114-0281 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0652B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:15:52.5030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T00:00:46.5970000 |  | 2021-03-07T00:03:18.6670000
T-00114-0282 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-1034 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Closed | 2021-04-24T03:04:21.0970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T06:59:22.7630000 |  | 2021-04-22T07:13:48.9670000
T-00114-0284 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0169B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:10:54.1370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:40:17.5730000 |  | 2021-01-31T02:05:15.1500000
T-00114-0285 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0466 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00114-0287 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0164B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:11:53.3370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:49:07.2470000 |  | 2021-01-31T02:05:38.4200000
T-00114-0288 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0156 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:12:19.9300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:52:14.2970000 |  | 2021-01-31T02:07:24.3700000
T-00114-0289 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0486 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-23T00:31:22.0270000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T07:32:38.7000000 |  | 2021-04-20T07:41:04.3670000
T-00114-0290 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0790 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-19T06:16:09.5670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-15T06:16:14.3300000 |  | 2021-01-16T20:17:38.0200000
T-00114-0291 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-1032 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0292 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-0897 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0295 | I1.T026 Control Valve Stage 1 | INST | 3335-FCV-0691 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0296 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0712 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0297 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0191 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:08:03.2300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T02:30:39.7270000 |  | 2021-02-08T04:13:17.0770000
T-00114-0298 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0169A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:12:45.9370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:40:59.6230000 |  | 2021-01-31T02:09:44.3930000
T-00114-0299 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0494A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-10T05:33:03.7770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:07:08.8000000 |  | 2021-02-08T04:45:59.6430000
T-00114-0300 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0141A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:13:21.3230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:53:53.2470000 |  | 2021-01-31T02:10:08.1300000
T-00114-0301 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0658 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Completed |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-26T07:30:25.1430000 |  | 2021-04-27T07:17:14.4070000
T-00114-0302 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0722 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0303 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0160A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:13:52.8770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:30:08.9530000 |  | 2021-01-31T02:11:12.2870000
T-00114-0304 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0200A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-25T13:19:37.0970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T00:11:44.2800000 |  | 2021-02-24T21:35:19.5030000
T-00114-0305 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-0754 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0306 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0480 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T03:44:34.6570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:12:32.4200000 |  | 2021-04-16T07:27:43.1500000
T-00114-0308 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0177 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0309 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0488 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0310 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0320A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:26:45.3330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:37:20.0830000 |  | 2021-02-24T21:47:54.8900000
T-00114-0311 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0186 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T06:31:18.1630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-08T04:14:11.2570000 |  | 2021-02-08T04:48:49.5400000
T-00114-0313 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-1029 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0314 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-0895 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Closed | 2021-02-19T22:08:30.1370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-19T06:34:27.5370000 |  | 2021-02-19T19:03:41.2930000
T-00114-0315 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0141B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:14:15.5700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:54:31.1130000 |  | 2021-01-31T02:11:52.1300000
T-00114-0316 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0304A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:27:06.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:58:27.0930000 |  | 2021-02-24T21:49:09.1930000
T-00114-0317 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0662 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:17:17.9900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T02:08:12.3870000 |  | 2021-03-07T04:11:05.5600000
T-00114-0318 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0494B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:26:10.3800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:07:45.6200000 |  | 2021-02-08T04:46:23.2530000
T-00114-0320 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0714 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0321 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0160B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:14:38.6670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:24:59.3630000 |  | 2021-01-31T02:12:33.3570000
T-00114-0322 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-0871 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00114-0323 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0194A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:09:26.1270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T02:42:56.3630000 |  | 2021-02-08T04:13:48.0500000
T-00114-0324 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0652A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:17:50.6170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T23:58:49.2970000 |  | 2021-03-07T00:03:51.6070000
T-00114-0325 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0182 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:10:25.9570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:12:21.2600000 |  | 2021-02-08T04:16:30.7430000
T-00114-0326 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0435 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:10:37.1270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T21:43:38.5200000 |  | 2021-04-02T00:34:50.1130000
T-00114-0327 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0194B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:11:20.6470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:16:36.9700000 |  | 2021-02-08T04:17:25.0230000
T-00114-0328 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0791 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-19T06:16:35.9130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-15T06:05:28.5370000 |  | 2021-01-16T20:18:04.0070000
T-00114-0329 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0312 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:30:21.0200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:06:41.7270000 |  | 2021-03-06T21:15:51.7830000
T-00114-0330 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0716 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0331 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0304B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:27:28.5330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:59:58.1630000 |  | 2021-02-24T21:52:32.1600000
T-00114-0332 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0310B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:27:57.2070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:54:36.7800000 |  | 2021-02-24T21:53:52.6130000
T-00114-0333 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0301 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:30:56.9730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:03:54.4400000 |  | 2021-03-06T21:41:17.3530000
T-00114-0334 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-0896 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Closed | 2021-02-19T22:09:11.3870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-19T06:38:28.4800000 |  | 2021-02-19T19:03:04.6270000
T-00114-0337 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0496 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:28:57.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T04:06:05.4970000 |  | 2021-02-08T04:46:47.0570000
T-00114-0338 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0306 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:31:34.0270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:05:14.0370000 |  | 2021-03-06T21:41:44.7870000
T-00114-0339 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0413 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T06:20:23.7800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-02T05:33:08.0630000 |  | 2021-03-04T02:09:38.9300000
T-00114-0340 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0138A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:15:51.8530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:56:41.5130000 |  | 2021-01-31T02:12:59.1000000
T-00114-0341 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0447 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:52:15.5970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T00:58:58.0000000 |  | 2021-04-14T07:11:53.0170000
T-00114-0342 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0310A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:28:19.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:48:42.5370000 |  | 2021-02-24T21:55:19.0200000
T-00114-0343 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0770 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-19T06:17:04.4370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-15T06:01:57.8830000 |  | 2021-01-16T20:18:37.2270000
T-00114-0344 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0200B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-25T13:20:07.9030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T00:12:23.9900000 |  | 2021-02-24T21:36:32.4000000
T-00114-0345 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0320B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-25T13:28:40.6030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T03:40:58.0670000 |  | 2021-02-24T21:55:54.8800000
T-00114-0346 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0190A | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-08T23:12:12.2070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:15:29.1070000 |  | 2021-02-08T04:17:55.4770000
T-00114-0347 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-1148 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0348 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0317 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:32:07.6200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:09:05.1270000 |  | 2021-03-06T21:42:13.3770000
T-00114-0349 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-1145 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0350 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-0766 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0351 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-1144 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0352 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-1143 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0353 | I1.T026 Control Valve Stage 1 | INST | 3332-PCV-0557 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00114-0354 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-1146 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0355 | I1.T026 Control Valve Stage 1 | INST | 3335-PCV-0854 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T09:06:48.9800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T20:17:51.9430000 |  | 2021-02-11T21:36:32.5500000
T-00114-0356 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-0138B | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T21:16:16.1430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:57:12.4370000 |  | 2021-01-31T02:13:36.3030000
T-00114-0357 | I1.T026 Control Valve Stage 1 | INST | 3334-FCV-0691 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0358 | I1.T026 Control Valve Stage 1 | INST | 3334-PCV-1147 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0359 | I1.T026 Control Valve Stage 1 | INST | 3332-FCV-0250 | FCV - Flow Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:08:53.8770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:49:22.6230000 |  | 2021-02-22T00:19:16.2100000
T-00114-0360 | I1.T026 Control Valve Stage 1 | INST | 3333-PCV-1149 | PCV - Pressure Control Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00114-0361 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-2242 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T00:56:00.0600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:22:46.2270000 |  | 2021-02-28T05:16:22.6870000
T-00114-0362 | I1.T026 Control Valve Stage 1 | INST | 3332-LCV-2365 | LCV - LEVEL CONTROL VALVE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T21:48:17.9930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-25T04:34:54.4670000 |  | 2021-04-25T07:19:37.7600000
T-00115-0236 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0185A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0237 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0315B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0238 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0490 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0239 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0718 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0240 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0132 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0243 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0324 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0244 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0108 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0246 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0453 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00115-0247 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0731 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0250 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0456 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0252 | I2.T026A Control Valve Stage 2A | INST | 3335-LCV-0840 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-12T05:32:04.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-04T06:48:24.9230000 |  | 2021-04-12T05:12:20.1730000
T-00115-0253 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0315A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0254 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0710 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0255 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0449 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0256 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0148 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0257 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0348 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0259 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0457 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0260 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0133 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0261 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-1026 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0263 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0499A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0264 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0190B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0265 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0113 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0266 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0445 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0267 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0164A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0269 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0185B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0270 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-1105 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0271 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0165 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0272 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0720 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0274 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0161 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0275 | I2.T026A Control Valve Stage 2A | INST | 3335-FCV-0855 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-04-02T03:35:18.1430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T03:09:32.7170000 |  | 2021-04-02T03:35:08.0000000
T-00115-0276 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0468 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0277 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0213 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0278 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0195 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0280 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0210 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0281 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0499B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0282 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0652B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0285 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0169B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0286 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0466 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0288 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0164B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0289 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0156 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0290 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0486 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0291 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0790 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-20T06:07:10.3170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T03:06:48.0000000 |  | 2021-04-20T04:52:31.3730000
T-00115-0296 | I2.T026A Control Valve Stage 2A | INST | 3335-FCV-0691 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0297 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0712 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0298 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0191 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0299 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0169A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0300 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0494A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0301 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0141A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0302 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0658 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0303 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0722 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0304 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0160A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0305 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0200A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0307 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0480 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0309 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0177 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0310 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0488 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0311 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0320A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0312 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0186 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00115-0314 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-1029 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0316 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0141B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0317 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0304A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0318 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0662 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0319 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0494B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0321 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0714 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0322 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0160B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0324 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0194A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0325 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0652A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0326 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0182 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0327 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0435 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0328 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0194B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0329 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0791 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-12T05:33:20.0000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-04T23:18:23.3600000 |  | 2021-04-12T05:13:26.4430000
T-00115-0330 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0312 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0331 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0716 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0332 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0304B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0333 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0310B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0334 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0301 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0338 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0496 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0339 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0306 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0340 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0413 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0341 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0138A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0342 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0447 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0343 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0310A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0344 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0770 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-20T22:17:11.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T21:06:06.5470000 |  | 2021-04-20T21:09:24.9900000
T-00115-0345 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0200B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0346 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0320B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0347 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0190A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0349 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0317 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0351 | I2.T026A Control Valve Stage 2A | INST | 3331-LCV-2147 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00115-0358 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-0138B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0359 | I2.T026A Control Valve Stage 2A | INST | 3334-FCV-0691 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00115-0361 | I2.T026A Control Valve Stage 2A | INST | 3332-FCV-0250 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00115-0363 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-2242 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00115-0364 | I2.T026A Control Valve Stage 2A | INST | 3332-LCV-2365 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0236 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0185A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0237 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0315B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0238 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0490 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0239 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0718 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0240 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0132 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0243 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0324 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0244 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0108 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0246 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0453 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00116-0247 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0731 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0250 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0456 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0252 | I2.T026B Control Valve Stage 2B | INST | 3335-LCV-0840 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-06T05:13:08.3070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T06:58:39.8000000
T-00116-0253 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0315A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0254 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0710 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0255 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0449 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0256 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0148 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0257 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0348 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0259 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0457 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0260 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0133 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0261 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-1026 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0263 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0499A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0264 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0190B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0265 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0113 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0266 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0445 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0267 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0164A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0269 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0185B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0270 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-1105 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0271 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0165 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0272 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0720 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0274 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0161 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0275 | I2.T026B Control Valve Stage 2B | INST | 3335-FCV-0855 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-04-06T05:13:50.2300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T03:12:17.1170000
T-00116-0276 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0468 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0277 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0213 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0278 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0195 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0280 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0210 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0281 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0499B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0282 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0652B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0285 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0169B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0286 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0466 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0288 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0164B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0289 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0156 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0290 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0486 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0291 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0790 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-20T06:07:50.5530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-20T05:46:49.0670000
T-00116-0296 | I2.T026B Control Valve Stage 2B | INST | 3335-FCV-0691 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0297 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0712 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0298 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0191 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0299 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0169A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0300 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0494A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0301 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0141A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0302 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0658 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0303 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0722 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0304 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0160A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0305 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0200A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0307 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0480 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0309 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0177 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0310 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0488 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0311 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0320A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0312 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0186 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00116-0314 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-1029 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0316 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0141B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0317 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0304A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0318 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0662 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0319 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0494B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0321 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0714 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0322 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0160B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0324 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0194A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0325 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0652A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0326 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0182 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0327 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0435 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0328 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0194B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0329 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0791 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-06T05:14:19.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T06:09:42.2530000
T-00116-0330 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0312 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0331 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0716 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0332 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0304B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0333 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0310B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0334 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0301 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0338 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0496 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0339 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0306 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0340 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0413 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0341 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0138A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0342 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0447 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0343 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0310A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0344 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0770 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-06T05:14:45.8130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T06:35:03.2270000
T-00116-0345 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0200B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0346 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0320B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0347 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0190A | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0349 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0317 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0351 | I2.T026B Control Valve Stage 2B | INST | 3331-LCV-2147 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-06T04:40:27.6070000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-05T05:38:04.6370000
T-00116-0358 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-0138B | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0359 | I2.T026B Control Valve Stage 2B | INST | 3334-FCV-0691 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00116-0361 | I2.T026B Control Valve Stage 2B | INST | 3332-FCV-0250 | FCV - Flow Control Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00116-0363 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-2242 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00116-0364 | I2.T026B Control Valve Stage 2B | INST | 3332-LCV-2365 | LCV - LEVEL CONTROL VALVE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00117-0131 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-2111 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:48:30.7570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T06:23:25.8770000 |  | 2021-01-23T07:21:23.9500000
T-00117-0140 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-2113 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:49:12.1800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T06:29:49.4530000 |  | 2021-01-23T07:21:50.0430000
T-00117-0149 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-2117 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:49:31.3500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T06:42:10.1170000 |  | 2021-01-23T07:22:19.6330000
T-00117-0158 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-2115 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:49:55.7330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T06:38:36.9000000 |  | 2021-01-23T07:22:45.9800000
T-00117-0161 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-2119 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:50:19.9330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T06:52:43.5570000 |  | 2021-01-23T07:23:03.5270000
T-00117-0163 | I1.T008 Flow Transmitter Stage 1 | INST | 3331-FIT-0032 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-10T05:07:45.1230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-09T04:57:42.5870000 |  | 2021-02-09T06:36:29.5570000
T-00117-0198 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0324 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0209 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0191 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T01:27:24.5470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T02:32:58.9830000 |  | 2021-02-08T04:18:16.4230000
T-00117-0210 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0362 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-25T21:46:06.1330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-25T03:20:05.2500000 |  | 2021-04-25T07:14:50.3570000
T-00117-0211 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0488 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0212 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0761 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0213 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0453 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:04:42.2230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T05:55:12.3870000 |  | 2021-04-22T07:14:16.0400000
T-00117-0214 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0824 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0215 | I1.T008 Flow Transmitter Stage 1 | INST | 3335-FIT-0851 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Closed | 2021-02-07T22:24:00.9330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-07T03:40:57.2230000 |  | 2021-02-07T04:39:45.3500000
T-00117-0217 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0317 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:34:09.0600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:44:03.8170000 |  | 2021-03-06T22:02:03.6370000
T-00117-0219 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0210 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0220 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0133 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:44:54.1470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:55:44.2530000 |  | 2021-01-31T02:13:54.6230000
T-00117-0221 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0545 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:16:48.7600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-29T23:52:10.8400000 |  | 2021-03-30T05:22:32.1470000
T-00117-0222 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1026 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0223 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0770 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-29T20:21:54.6270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T05:30:57.3730000 |  | 2021-01-25T06:31:15.9470000
T-00117-0224 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1055 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:07:16.7030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T05:41:22.4730000 |  | 2021-04-23T07:00:27.0930000
T-00117-0225 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0731 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0226 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0348 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:41:46.5400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T05:58:10.2900000 |  | 2021-04-02T00:35:19.5100000
T-00117-0227 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1104 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0228 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0456 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:42:17.7230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:35:05.2400000 |  | 2021-04-02T00:35:49.4800000
T-00117-0229 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0132 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:45:19.0030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T18:02:28.7370000 |  | 2021-01-31T02:14:17.2570000
T-00117-0230 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0177 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0231 | I1.T008 Flow Transmitter Stage 1 | INST | 3335-FIT-0849 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:22:21.9130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T02:28:53.7270000 |  | 2021-01-25T03:02:03.2170000
T-00117-0233 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0712 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0234 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0312 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:34:36.6200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:42:51.8270000 |  | 2021-03-06T22:01:07.0030000
T-00117-0235 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0790 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-29T20:22:43.6370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T06:29:06.4330000 |  | 2021-01-25T06:31:44.8400000
T-00117-0236 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0729 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0237 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0306 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:35:10.9300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:40:08.5670000 |  | 2021-03-06T21:45:36.4270000
T-00117-0238 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0113 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:09:44.6430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:46:03.6430000 |  | 2021-02-22T00:19:42.2770000
T-00117-0239 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0161 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:45:46.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:51:03.7970000 |  | 2021-01-31T02:15:39.6570000
T-00117-0240 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0435 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:42:43.7670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:32:19.1530000 |  | 2021-04-02T00:36:24.2330000
T-00117-0241 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0490 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:29:34.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T00:57:51.9630000 |  | 2021-02-08T04:47:15.4300000
T-00117-0242 | I1.T008 Flow Transmitter Stage 1 | INST | 3335-FIT-0691 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0243 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0690 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0244 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0186 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T06:29:59.6770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T02:10:32.8270000 |  | 2021-02-08T04:47:43.0770000
T-00117-0245 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0486 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-23T00:31:46.8030000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T05:53:39.8830000 |  | 2021-04-22T07:11:24.7670000
T-00117-0246 | I1.T008 Flow Transmitter Stage 1 | INST | 3335-FIT-0855 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-20T23:57:06.8730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-20T22:36:46.8970000 |  | 2021-02-20T22:44:42.1570000
T-00117-0247 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0842 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0248 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0830 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0249 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0108 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:07:17.6600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T20:31:08.7470000 |  | 2021-02-11T21:37:42.8670000
T-00117-0250 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0658 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:20:05.7270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T04:24:46.4800000 |  | 2021-03-07T06:01:43.7000000
T-00117-0251 | I1.T008 Flow Transmitter Stage 1 | INST | 3335-FIT-0864 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-18T23:01:01.2000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T19:55:13.7270000 |  | 2021-02-18T21:39:52.2830000
T-00117-0252 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0716 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0253 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1029 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0254 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0823 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0255 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0213 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0256 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0575 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0259 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0596 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0260 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0718 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0261 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0496 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:30:31.7400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T00:37:09.3530000 |  | 2021-02-08T04:48:04.0830000
T-00117-0262 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0445 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0263 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0726 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0264 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0126 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T09:34:34.3900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T18:48:54.5330000 |  | 2021-02-21T19:48:52.9630000
T-00117-0265 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0662 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00117-0266 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0182 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T01:28:24.0030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T01:47:01.2800000 |  | 2021-02-08T04:18:36.7800000
T-00117-0268 | I1.T008 Flow Transmitter Stage 1 | INST | 3331-FIT-0004 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:54:15.4630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-20T22:21:52.2970000 |  | 2021-02-20T22:36:37.6670000
T-00117-0269 | I1.T008 Flow Transmitter Stage 1 | INST | 3331-FIT-0056 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:30:56.3100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T23:56:29.9230000 |  | 2021-02-09T06:39:27.8370000
T-00117-0270 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0840 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0271 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0468 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0272 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0832 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0273 | I1.T008 Flow Transmitter Stage 1 | INST | 3331-FIT-0074 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T22:23:04.1400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T21:50:14.5130000 |  | 2021-02-06T23:28:59.1000000
T-00117-0274 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0447 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:52:41.3630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T01:19:41.7470000 |  | 2021-04-14T07:12:18.8570000
T-00117-0275 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0250 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:10:36.0770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:42:35.1170000 |  | 2021-02-22T00:20:36.1270000
T-00117-0276 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0010 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0277 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0195 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T01:29:02.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:25:33.6700000 |  | 2021-02-08T04:43:21.5030000
T-00117-0278 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0457 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-14T07:53:05.3670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:28:37.9070000 |  | 2021-04-14T04:10:19.9870000
T-00117-0279 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0156 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:46:15.0130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:53:03.5170000 |  | 2021-01-31T02:16:02.9870000
T-00117-0280 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0301 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:35:44.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:38:08.4070000 |  | 2021-03-06T21:42:42.0870000
T-00117-0281 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0825 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0282 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1105 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0283 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0720 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0284 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0148 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0285 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0527 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:19:26.4970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:15:08.1900000 |  | 2021-02-28T05:16:46.1830000
T-00117-0286 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0165 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:46:39.1500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T17:47:14.8270000 |  | 2021-01-31T02:16:24.1670000
T-00117-0287 | I1.T008 Flow Transmitter Stage 1 | INST | 3333-FIT-0593 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0288 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0710 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0289 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0722 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0290 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0413 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:18:58.4170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-02T02:30:01.5730000 |  | 2021-03-02T04:37:47.1430000
T-00117-0291 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0791 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-29T20:23:05.9170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T06:25:59.8570000 |  | 2021-01-25T06:32:42.3800000
T-00117-0292 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0714 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0294 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1066 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:19:48.1470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-02T03:41:06.8830000 |  | 2021-03-02T04:41:05.6270000
T-00117-0295 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1102 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0296 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0876 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0297 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1100 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0298 | I1.T008 Flow Transmitter Stage 1 | INST | 3331-FIT-0087 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Closed | 2021-04-24T21:24:11.6330000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-24T06:34:52.5330000 |  | 2021-04-24T07:14:28.1170000
T-00117-0299 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-1158 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0300 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-0691 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0301 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0466 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00117-0302 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0869 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00117-0303 | I1.T008 Flow Transmitter Stage 1 | INST | 3332-FIT-0579 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0304 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1040 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0305 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1042 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0306 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1072 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0307 | I1.T008 Flow Transmitter Stage 1 | INST | 3333-FIT-0678 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0308 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1079 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0309 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1077 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0310 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1075 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0311 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1080 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0312 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1071 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0313 | I1.T008 Flow Transmitter Stage 1 | INST | 3333-FIT-2209 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0315 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1073 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0316 | I1.T008 Flow Transmitter Stage 1 | INST | 3333-FIT-0668 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00117-0317 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1074 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0318 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1044 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0319 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1078 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0320 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1043 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0321 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1076 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00117-0322 | I1.T008 Flow Transmitter Stage 1 | INST | 3334-FIT-1041 | FIT - Flow Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00119-0209 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0191 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0210 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0362 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0211 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0488 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0212 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0761 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0213 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0453 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00119-0214 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0824 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0215 | I2.T008A Flow Transmitter Stage 2A | INST | 3335-FIT-0851 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00119-0217 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0317 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0219 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0210 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0220 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0133 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0221 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0545 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0222 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1026 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0223 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0770 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-12T05:34:05.7130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:25:09.4100000 |  | 2021-04-12T05:14:34.3000000
T-00119-0224 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1055 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0225 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0731 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0226 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0348 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0227 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1104 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0228 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0456 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0229 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0132 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0230 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0177 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0231 | I2.T008A Flow Transmitter Stage 2A | INST | 3335-FIT-0849 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T03:54:20.0400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:33:32.7100000 |  | 2021-04-18T05:37:31.8770000
T-00119-0232 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-2111 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-02T01:12:40.1370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:19:35.1430000 |  | 2021-04-02T01:10:34.5800000
T-00119-0234 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0712 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0235 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0312 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0236 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0790 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-12T04:51:02.9770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:20:53.4470000 |  | 2021-04-12T04:00:40.3870000
T-00119-0237 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0729 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0238 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0306 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0239 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0113 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0240 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0161 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0241 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-2113 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-02T03:34:11.7370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:12:06.0400000 |  | 2021-04-02T01:15:07.7900000
T-00119-0242 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0435 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0243 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0490 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0244 | I2.T008A Flow Transmitter Stage 2A | INST | 3335-FIT-0691 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0245 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0690 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0246 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0186 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0247 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0486 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0248 | I2.T008A Flow Transmitter Stage 2A | INST | 3335-FIT-0855 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-04-02T06:40:02.5570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T04:48:42.5130000 |  | 2021-04-02T04:53:40.0500000
T-00119-0249 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0842 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0250 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-2117 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-02T03:35:01.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:35:22.7100000 |  | 2021-04-02T01:13:09.9800000
T-00119-0251 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0830 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0252 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0108 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0253 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0658 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0254 | I2.T008A Flow Transmitter Stage 2A | INST | 3335-FIT-0864 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-20T01:31:50.9030000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-16T01:32:53.0000000 |  | 2021-04-18T05:30:04.6070000
T-00119-0255 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0716 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0256 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1029 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0257 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0823 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0258 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0213 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0259 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-2115 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-02T03:35:43.6770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:09:05.6830000 |  | 2021-04-02T01:12:44.6270000
T-00119-0260 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0575 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0262 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-2119 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T00:30:37.7170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-26T00:04:46.2330000 |  | 2021-01-26T05:10:12.9400000
T-00119-0264 | I2.T008A Flow Transmitter Stage 2A | INST | 3331-FIT-0032 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:39:33.9870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-07T01:24:46.4430000 |  | 2021-04-10T23:10:32.8700000
T-00119-0265 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0596 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0266 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0718 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0267 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0496 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0268 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0445 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0269 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0726 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0270 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0126 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0271 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0662 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0272 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0182 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0274 | I2.T008A Flow Transmitter Stage 2A | INST | 3331-FIT-0004 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:58:02.4270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T21:40:53.8330000 |  | 2021-04-12T01:46:15.3400000
T-00119-0275 | I2.T008A Flow Transmitter Stage 2A | INST | 3331-FIT-0056 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:56:39.9430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-12T01:41:35.5130000 |  | 2021-04-12T01:47:03.2730000
T-00119-0276 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0840 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0277 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0468 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0278 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0832 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0279 | I2.T008A Flow Transmitter Stage 2A | INST | 3331-FIT-0074 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:31:07.9130000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-09T01:30:51.2670000 |  | 2021-04-11T01:34:44.5900000
T-00119-0280 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0447 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0281 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0250 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0282 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0010 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0283 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0195 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0284 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0457 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0285 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0156 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0286 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0301 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0287 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0825 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0288 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1105 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0289 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0720 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0290 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0148 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0291 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0527 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0292 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0165 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0293 | I2.T008A Flow Transmitter Stage 2A | INST | 3333-FIT-0593 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0294 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0710 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0295 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0722 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0296 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0413 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0297 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0791 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-12T05:17:47.2700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:22:36.6500000 |  | 2021-04-12T04:01:18.2100000
T-00119-0298 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0714 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0299 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0324 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0301 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1066 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0302 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1102 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0303 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0876 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0304 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1100 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0305 | I2.T008A Flow Transmitter Stage 2A | INST | 3331-FIT-0087 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0306 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-1158 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0307 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-0691 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0308 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0466 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00119-0309 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0869 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00119-0310 | I2.T008A Flow Transmitter Stage 2A | INST | 3332-FIT-0579 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0311 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1040 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0312 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1042 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0313 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1072 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0314 | I2.T008A Flow Transmitter Stage 2A | INST | 3333-FIT-0678 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0315 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1079 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0316 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1077 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0317 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1075 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0318 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1080 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0319 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1071 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0320 | I2.T008A Flow Transmitter Stage 2A | INST | 3333-FIT-2209 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0322 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1073 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0323 | I2.T008A Flow Transmitter Stage 2A | INST | 3333-FIT-0668 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0324 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1074 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0325 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1044 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0326 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1078 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0327 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1043 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0328 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1076 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00119-0329 | I2.T008A Flow Transmitter Stage 2A | INST | 3334-FIT-1041 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0209 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0191 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0210 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0362 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0211 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0488 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0212 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0761 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0213 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0453 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00120-0214 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0824 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0215 | I2.T008B Flow Transmitter Stage 2B | INST | 3335-FIT-0851 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00120-0217 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0317 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0219 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0210 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0220 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0133 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0221 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0545 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0222 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1026 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0223 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0770 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-09T03:56:32.4300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T04:23:48.6670000
T-00120-0224 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1055 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0225 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0731 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0226 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0348 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0227 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1104 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0228 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0456 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0229 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0132 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0230 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0177 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0231 | I2.T008B Flow Transmitter Stage 2B | INST | 3335-FIT-0849 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T03:55:10.3430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-17T22:12:01.4830000
T-00120-0232 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-2111 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-09T03:57:37.9900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T01:25:11.8230000
T-00120-0234 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0712 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0235 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0312 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0236 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0790 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-09T03:58:17.5330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T04:04:36.6600000
T-00120-0237 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0729 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0238 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0306 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0239 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0113 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0240 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0161 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0241 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-2113 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-09T04:00:07.2770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T01:32:45.2370000
T-00120-0242 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0435 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0243 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0490 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0244 | I2.T008B Flow Transmitter Stage 2B | INST | 3335-FIT-0691 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0245 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0690 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0246 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0186 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0247 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0486 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0248 | I2.T008B Flow Transmitter Stage 2B | INST | 3335-FIT-0855 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-04-09T04:00:59.7100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T04:55:44.4100000
T-00120-0249 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0842 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0250 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-2117 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-09T04:01:41.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T02:17:36.4070000
T-00120-0251 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0830 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0252 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0108 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0253 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0658 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0254 | I2.T008B Flow Transmitter Stage 2B | INST | 3335-FIT-0864 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-09T03:21:40.2630000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T01:47:44.2470000
T-00120-0255 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0716 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0256 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1029 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0257 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0823 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0258 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0213 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0259 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-2115 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-09T04:02:34.2230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T02:13:44.5900000
T-00120-0260 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0575 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0262 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-2119 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-09T04:03:34.8000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T02:22:45.5470000
T-00120-0264 | I2.T008B Flow Transmitter Stage 2B | INST | 3331-FIT-0032 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:18:28.7270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T02:16:59.4630000
T-00120-0265 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0596 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0266 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0718 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0267 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0496 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0268 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0445 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0269 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0726 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0270 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0126 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0271 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0662 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0272 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0182 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0274 | I2.T008B Flow Transmitter Stage 2B | INST | 3331-FIT-0004 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-27T08:47:30.5730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T03:35:53.2270000
T-00120-0275 | I2.T008B Flow Transmitter Stage 2B | INST | 3331-FIT-0056 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-10T07:47:36.3530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-10T07:32:29.4000000
T-00120-0276 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0840 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0277 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0468 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0278 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0832 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0279 | I2.T008B Flow Transmitter Stage 2B | INST | 3331-FIT-0074 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:42:37.8370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T01:45:47.0870000
T-00120-0280 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0447 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0281 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0250 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0282 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0010 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0283 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0195 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0284 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0457 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0285 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0156 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0286 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0301 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0287 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0825 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0288 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1105 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0289 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0720 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0290 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0148 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0291 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0527 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0292 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0165 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0293 | I2.T008B Flow Transmitter Stage 2B | INST | 3333-FIT-0593 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0294 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0710 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0295 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0722 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0296 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0413 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0297 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0791 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-04-09T04:04:19.3370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:49:47.2670000
T-00120-0298 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0714 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0299 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0324 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0301 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1066 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0302 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1102 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0303 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0876 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0304 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1100 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0305 | I2.T008B Flow Transmitter Stage 2B | INST | 3331-FIT-0087 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0306 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-1158 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0307 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-0691 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0308 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0466 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00120-0309 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0869 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00120-0310 | I2.T008B Flow Transmitter Stage 2B | INST | 3332-FIT-0579 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0311 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1040 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0312 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1042 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0313 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1072 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0314 | I2.T008B Flow Transmitter Stage 2B | INST | 3333-FIT-0678 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0315 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1079 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0316 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1077 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0317 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1075 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0318 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1080 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0319 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1071 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0320 | I2.T008B Flow Transmitter Stage 2B | INST | 3333-FIT-2209 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0322 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1073 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0323 | I2.T008B Flow Transmitter Stage 2B | INST | 3333-FIT-0668 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0324 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1074 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0325 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1044 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0326 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1078 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0327 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1043 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0328 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1076 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00120-0329 | I2.T008B Flow Transmitter Stage 2B | INST | 3334-FIT-1041 | FIT - Flow Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0209 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0191 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0210 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0362 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0211 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0488 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0212 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0761 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0213 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0453 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0214 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0824 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0215 | I3.T008 Flow Transmitter Stage 3 | INST | 3335-FIT-0851 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0217 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0317 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0219 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0210 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0220 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0133 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0221 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0545 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0222 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1026 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0223 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0770 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0224 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1055 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0225 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0731 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0226 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0348 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0227 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1104 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0228 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0456 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0229 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0132 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0230 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0177 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0231 | I3.T008 Flow Transmitter Stage 3 | INST | 3335-FIT-0849 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0232 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-2111 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0234 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0712 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0235 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0312 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0236 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0790 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0237 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0729 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0238 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0306 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0239 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0113 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0240 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0161 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0241 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-2113 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Cancelled |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T06:13:19.0000000
T-00121-0242 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0435 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0243 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0490 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0244 | I3.T008 Flow Transmitter Stage 3 | INST | 3335-FIT-0691 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0245 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0690 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0246 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0186 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0247 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0486 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0248 | I3.T008 Flow Transmitter Stage 3 | INST | 3335-FIT-0855 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0249 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0842 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0250 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-2117 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Cancelled |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T06:13:24.0000000
T-00121-0251 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0830 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0252 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0108 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0253 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0658 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0254 | I3.T008 Flow Transmitter Stage 3 | INST | 3335-FIT-0864 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00121-0255 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0716 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0256 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1029 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0257 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0823 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0258 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0213 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0259 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-2115 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0260 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0575 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0262 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-2119 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0264 | I3.T008 Flow Transmitter Stage 3 | INST | 3331-FIT-0032 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0265 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0596 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0266 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0718 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0267 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0496 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0268 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0445 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0269 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0726 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0270 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0126 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0271 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0662 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0272 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0182 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0274 | I3.T008 Flow Transmitter Stage 3 | INST | 3331-FIT-0004 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0275 | I3.T008 Flow Transmitter Stage 3 | INST | 3331-FIT-0056 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00121-0276 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0840 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0277 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0468 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0278 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0832 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0279 | I3.T008 Flow Transmitter Stage 3 | INST | 3331-FIT-0074 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00121-0280 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0447 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0281 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0250 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0282 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0010 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0283 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0195 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0284 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0457 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0285 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0156 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0286 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0301 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0287 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0825 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0288 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1105 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0289 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0720 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0290 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0148 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0291 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0527 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0292 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0165 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0293 | I3.T008 Flow Transmitter Stage 3 | INST | 3333-FIT-0593 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0294 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0710 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0295 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0722 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0296 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0413 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0297 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0791 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00121-0298 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0714 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0299 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0324 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0301 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1066 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0302 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1102 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0303 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0876 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0304 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1100 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0305 | I3.T008 Flow Transmitter Stage 3 | INST | 3331-FIT-0087 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0306 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-1158 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0307 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-0691 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0308 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0466 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00121-0309 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0869 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00121-0310 | I3.T008 Flow Transmitter Stage 3 | INST | 3332-FIT-0579 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0311 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1040 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0312 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1042 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0313 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1072 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0314 | I3.T008 Flow Transmitter Stage 3 | INST | 3333-FIT-0678 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0315 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1079 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0316 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1077 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0317 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1075 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0318 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1080 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0319 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1071 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0320 | I3.T008 Flow Transmitter Stage 3 | INST | 3333-FIT-2209 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0322 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1073 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0323 | I3.T008 Flow Transmitter Stage 3 | INST | 3333-FIT-0668 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00121-0324 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1074 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0325 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1044 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0326 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1078 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0327 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1043 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0328 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1076 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00121-0329 | I3.T008 Flow Transmitter Stage 3 | INST | 3334-FIT-1041 | FIT - Flow Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00122-2195 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0029-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-14T06:11:55.9270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:03:26.0300000
T-00122-2196 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0002-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2197 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0012-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2198 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-32-MCS-0165-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2199 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0083-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-26T20:55:08.7500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-21T04:23:07.1500000
T-00122-2200 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0039-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2201 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0019-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2202 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FLOC-0002-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T14:50:44.6500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T10:07:34.1530000
T-00122-2203 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0039-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2204 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0027-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2205 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0106-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2206 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-180-PD-0205-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2207 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-PWL-0001-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2208 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0063-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-16T22:23:05.2870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-16T22:21:46.1270000
T-00122-2209 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0057-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2210 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-PWL-0009-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T15:21:46.5430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T15:02:44.2070000
T-00122-2211 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0036-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2212 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0015-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-21T09:17:52.4370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-20T21:57:44.5070000
T-00122-2213 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0107-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2214 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0019-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2215 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0020-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2216 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0278-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2217 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-100-PWL-0010-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2218 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0014-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2219 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0014-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2220 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0323-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-17T23:32:50.9030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T22:43:01.4870000
T-00122-2221 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0066-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2222 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-PWH-0105-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-02 - Process Water to Concentrate Feed Pumps | CS0E - Process Water Distribution | Closed | 2021-02-19T21:56:52.5970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T06:02:14.7000000
T-00122-2223 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0272-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T05:06:00.2530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:25:38.8730000
T-00122-2224 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-FRO3-0008-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2225 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0051-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2226 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-MCS-0120-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2227 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0089-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-26T22:51:42.1270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-17T22:34:03.4700000
T-00122-2228 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0029-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:36:40.7800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:27:36.4500000
T-00122-2229 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0041-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-31T07:53:25.8170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:12:01.6830000
T-00122-2230 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0003-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2231 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-SU-0192-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2232 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-RWA-0021-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2233 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-CSL-0060-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T04:15:53.0030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T04:07:18.4770000
T-00122-2234 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PWH-0012-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-15T06:03:33.8970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T21:54:03.8030000
T-00122-2235 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0189-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-27T02:34:30.1630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T21:43:33.9830000
T-00122-2236 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0009-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2237 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-COL5-0006-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2239 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0210-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2240 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0017-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2241 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0008-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2243 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-PD-0219-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2244 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0299-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2245 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0016-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-13T21:29:38.9630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T20:54:53.5000000
T-00122-2246 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0103-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-22T09:50:40.9970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-21T22:49:24.5870000
T-00122-2247 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0031-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2248 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-RWA-0024-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:11:43.9700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T21:08:32.9470000
T-00122-2250 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-63-MCS-0007-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2251 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-CSL-0059-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-28T11:40:30.7630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T05:44:07.4570000
T-00122-2252 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-MCS-0052-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-16T04:25:43.1730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T05:23:52.8230000
T-00122-2253 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0050-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T07:20:00.0730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:13:14.2030000
T-00122-2254 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0318-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2255 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0276-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2256 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0300-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2257 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-RWA-0004-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:27:19.9130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T15:08:28.0430000
T-00122-2258 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0273-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2259 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0061-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2260 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0012-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-26T06:37:06.1070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T05:21:06.2570000
T-00122-2261 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PWH-0031-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-26T09:01:45.1230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T19:30:19.5800000
T-00122-2262 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0010-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2263 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0359-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2264 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0002-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2265 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0014-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2266 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSH-0004-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T02:24:48.6670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-26T20:25:23.6430000
T-00122-2267 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0314-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2268 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-CO2-0007-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2269 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0168-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2270 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-RWA-0007-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:17:08.7270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T12:48:17.0830000
T-00122-2271 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0006-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-28T00:56:46.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T01:34:43.2600000
T-00122-2274 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0180-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2275 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0203-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2276 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0010-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-04T03:25:29.4600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-04T02:45:44.7600000
T-00122-2278 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-PWL-0012-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T21:57:19.3330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T23:40:55.3630000
T-00122-2279 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0054-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2280 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0053-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2281 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0210-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2282 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0256-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2283 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0012-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-15T04:21:44.2430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T00:34:50.1870000
T-00122-2284 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0007-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T23:22:14.2800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-20T04:55:11.5270000
T-00122-2285 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0328-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2286 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0146-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2287 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-75-MCS-0303-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2288 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0029-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2289 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-NAHS-0001-S6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2290 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-CSL-0031-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-16T05:12:04.2330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T05:03:52.9230000
T-00122-2291 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-315-MCS-0120-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2292 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0206-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2293 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-100-PWL-0011-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2294 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0009-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:07:06.2630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T20:02:08.5530000
T-00122-2295 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PWH-0032-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2298 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-PD-0153-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2299 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FLOC-0047-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:37:21.5570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T03:00:13.6770000
T-00122-2300 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0055-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-14T00:39:41.5270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T00:24:34.4070000
T-00122-2301 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0246-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:25:57.9770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T03:09:15.4800000
T-00122-2302 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-VGN-0234-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2303 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0070-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2304 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-100-PWH-0013-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-15T21:18:36.5170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:12:30.1870000
T-00122-2305 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0056-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T23:59:08.8430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T23:28:20.3900000
T-00122-2306 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0300-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2307 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0319-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-07T14:07:48.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:18:01.5330000
T-00122-2308 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0037-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-08T07:10:31.5300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:23:04.5970000
T-00122-2309 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0218-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2310 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0011-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2311 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0006-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2312 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0034-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2314 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0124-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2315 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0316-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2316 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-PD-0198-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T12:29:34.9970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T10:31:25.7570000
T-00122-2317 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-PD-0222-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T12:30:15.8500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T10:32:27.2130000
T-00122-2318 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-CSL-0011-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-16T02:01:03.1700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-15T22:22:57.4530000
T-00122-2319 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0003-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:26:33.4900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T20:10:54.7500000
T-00122-2320 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0258-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2321 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0031-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2323 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0262-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2325 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0020-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2326 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0164-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2329 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-15-DEF-0059-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2330 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0005-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2333 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0324-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-26T09:49:45.0100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T21:37:34.6330000
T-00122-2334 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0012-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2335 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0265-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2336 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PWH-0033-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2337 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0019-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2338 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0321-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2339 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0240-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2341 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0050-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2342 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-PD-0154-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2343 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0056-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2345 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0040-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2346 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0016-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2347 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0215-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2348 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-SU-0194-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2349 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-250-NAHS-0030-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2350 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0196-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2351 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0252-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T05:08:32.4830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T02:58:01.6870000
T-00122-2352 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0247-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:38:11.2200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:27:56.7930000
T-00122-2353 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0165-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2354 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0007-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T20:58:38.0500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T06:06:16.6700000
T-00122-2356 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0036-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2357 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0350-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2358 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0025-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2359 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSH-0108-C23 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T23:46:16.7770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T23:42:09.8670000
T-00122-2360 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0010-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T05:10:54.8270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T02:48:39.1400000
T-00122-2361 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0055-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2362 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FRO3-0017-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2363 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0054-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T12:43:20.5230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T04:31:19.9370000
T-00122-2364 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0109-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2366 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0018-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2367 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-ASC-0002-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2368 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-15-PWH-0358-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2369 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0006-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:27:27.0000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T20:12:55.4100000
T-00122-2370 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-280-PD-0038-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2371 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0289-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-24T09:19:17.3900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T03:47:56.1370000
T-00122-2372 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0260-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2373 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0305-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2375 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0015-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2376 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0004-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2377 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0025-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2378 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-MCS-0270-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T22:26:01.7670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T21:03:09.6730000
T-00122-2379 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-90-PD-0002-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00122-2380 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-100-PWL-0006-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2381 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0257-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2382 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0291-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2383 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0038-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2384 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-NG-0002-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2385 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-PWH-0006-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2386 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0001-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2387 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-PWH-0042-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-24T23:23:48.8030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T04:08:05.3170000
T-00122-2388 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0063-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2389 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0022-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-25T21:23:51.5270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T22:51:37.5330000
T-00122-2391 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0043-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2392 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0167-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2393 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0012-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2394 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-NG-0024-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2395 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0034-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2396 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0025-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2397 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0102-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-19T23:36:33.2970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T22:33:12.7370000
T-00122-2398 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0327-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2399 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-LD-4006 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T04:53:56.9600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T00:34:07.8000000
T-00122-2401 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0007-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-27T09:40:13.9670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-27T03:35:00.0300000
T-00122-2402 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0231-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2403 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0248-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:27:59.3930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T03:34:36.2230000
T-00122-2404 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0008-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T03:53:05.3070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T03:37:08.8630000
T-00122-2405 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0075-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2406 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0057-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2407 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-PD-0040-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-27T02:47:15.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T22:40:11.9800000
T-00122-2408 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0111-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2409 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0015-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2410 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0023-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2411 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-MCS-0155-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2412 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-100-CSL-0021-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T02:31:59.1700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T02:28:43.2770000
T-00122-2413 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0077-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2414 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0007-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:28:47.8570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T02:23:37.7070000
T-00122-2415 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0302-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2416 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0012-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2417 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-MCS-0245-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:07:07.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T04:44:32.7300000
T-00122-2418 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0205-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2419 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0036-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2420 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NaHS-0035-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2422 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0031-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2423 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0030-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:38:40.0600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:28:17.3530000
T-00122-2424 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-PWL-0019-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:28:32.2900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T04:16:42.6470000
T-00122-2426 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0376-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2427 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0133-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2428 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0065-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2429 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-CSL-0050-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-28T11:40:04.9230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T04:12:07.7570000
T-00122-2430 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-225-MCS-0283-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-27T01:52:56.2470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T23:43:08.6330000
T-00122-2431 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-280-PD-0007-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T02:30:30.2000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T02:19:05.8730000
T-00122-2433 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0020-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-04T03:15:35.0170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T02:12:09.7730000
T-00122-2435 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-90-PWL-0016-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2436 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0053-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2437 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0217-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2438 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0004-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:26:16.5400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T04:22:01.1500000
T-00122-2439 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0120-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2440 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0362-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-01T09:37:54.4230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-16T04:39:06.7730000
T-00122-2441 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-300-VGN-0041-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2442 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0269-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2443 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-PD-0001-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00122-2444 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0010-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2445 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0037-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2446 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-RWA-0248-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2447 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0261-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2448 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0004-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T06:36:42.4870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T06:18:53.4130000
T-00122-2449 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0011-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-27T21:58:02.5500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-21T02:00:01.0330000
T-00122-2450 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0006-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2452 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0024-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2453 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-VGN-0222-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2454 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-PWL-0007-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T21:57:54.6070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T23:39:44.9100000
T-00122-2455 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0157-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2456 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0204-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2457 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0286-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2459 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-25-PWH-0353-C6-TI-ET | Line - Line/Piping |  |  | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2460 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0057-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2461 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0200-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-09T14:14:22.3930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T13:52:07.1230000
T-00122-2462 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0266-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2463 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-RWA-0020-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Checked Out by Dennis Liang |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2464 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0355-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2465 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0058-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2466 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0091-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2467 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0324-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2468 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0022-G10-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2469 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0048-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-15T21:40:13.5970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T05:11:10.0870000
T-00122-2470 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-MCS-90-0250-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:12:22.6200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T04:58:46.1030000
T-00122-2471 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0052-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2473 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0326-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2474 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-VGN-0229-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2475 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0255-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2476 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0044-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T09:19:06.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:06:28.4730000
T-00122-2478 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0100-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-27T09:41:29.8670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-27T03:43:30.8670000
T-00122-2479 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0207-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-16T22:25:23.6030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-16T22:19:05.3630000
T-00122-2480 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-ASC-0002-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-21T23:04:20.1630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-19T20:56:50.4200000
T-00122-2481 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0311-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2482 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0249-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2483 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-CSL-0064-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-24T23:25:08.2670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T05:35:13.8100000
T-00122-2484 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0027-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-14T06:12:18.7670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:02:23.9600000
T-00122-2485 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-FWA-0001-C9 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-21T01:46:48.2100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T00:48:36.8870000
T-00122-2486 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-MCS-0304-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T12:31:00.5000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T10:53:05.3670000
T-00122-2487 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0056-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2488 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0064-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-16T05:48:32.8570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T05:38:41.8170000
T-00122-2489 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-PWL-0026-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T04:03:03.3400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T03:55:36.6870000
T-00122-2490 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0264-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2491 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0367-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2492 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0338-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2493 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0006-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2494 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0059-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-17T06:50:41.3800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-04-17T06:47:12.2100000
T-00122-2495 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0004-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:04:50.3070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T05:17:19.5370000
T-00122-2496 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-PWH-0030-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-15T21:19:28.0200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-02-15T06:57:01.2870000
T-00122-2498 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0133-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T16:52:11.9030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T16:01:09.0300000
T-00122-2499 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-350-MCS-0003-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:28:01.4900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T23:19:48.2370000
T-00122-2500 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0165-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2501 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0026-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2502 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0013-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2503 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0013-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-28T01:29:50.4970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T01:25:30.8600000
T-00122-2504 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0271-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T04:02:09.7000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T03:12:12.6370000
T-00122-2505 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0034-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-24T09:20:01.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T05:59:50.2370000
T-00122-2506 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0199-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2507 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0010-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:16:46.3770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T21:14:38.6100000
T-00122-2508 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0029-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2509 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0010-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2510 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-225-PD-0223-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2511 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0280-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:49:14.4030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:28:59.2070000
T-00122-2512 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0038-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2513 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-NAHS-0017-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2514 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0274-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2515 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0263-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2516 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0060-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2517 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0006-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:13:05.1130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T05:44:40.9470000
T-00122-2518 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-IA-0071-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-21T01:48:44.2530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-19T04:39:22.0330000
T-00122-2519 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0009-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T08:04:29.2070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:50:40.6730000
T-00122-2520 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-400-MCS-0112-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T02:44:05.1970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T02:25:20.1000000
T-00122-2521 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0123-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2522 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0058-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2523 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-CO2-0008-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2524 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0268-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2525 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-CSH-0111-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T02:36:22.5200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T02:31:04.7800000
T-00122-2526 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-RWA-0018-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-15 - Raw Water to Filter Building | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2528 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FRO3-0022-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2529 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-HPA-0002-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2530 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0023-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Closed | 2021-03-29T03:22:04.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T00:54:04.4430000
T-00122-2531 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0006-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:07:37.5500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:53:27.9100000
T-00122-2532 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-MCS-0143-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2533 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0298-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2534 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0172-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2535 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-CSL-0063-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:29:36.3830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T05:03:04.2570000
T-00122-2536 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0061-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-17T06:52:28.1100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-04-17T06:44:58.0000000
T-00122-2537 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0143-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2538 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0268-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:49:37.8300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:29:19.6870000
T-00122-2539 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0037-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2540 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0260-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2541 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0276-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2542 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSH-0109-C23 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T23:47:30.5600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T23:44:30.0100000
T-00122-2544 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-150-PWH-0002-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-18T02:37:09.1630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T02:30:51.6130000
T-00122-2545 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0270-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2546 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0033-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2547 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-RWA-0015-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2548 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-280-PD-0003-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-27T09:41:54.2570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-27T03:58:03.3470000
T-00122-2549 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0036-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2550 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0032-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2552 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0250-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-04T03:32:09.7570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T02:15:59.1770000
T-00122-2553 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-250-MCS-0313-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:07:36.1670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-29T05:05:09.2370000
T-00122-2554 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-40-FLOC-0048-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-02-12T05:43:17.3370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-04T01:57:13.4270000
T-00122-2555 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0014-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2557 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0004-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2558 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0262-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2559 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0348-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2560 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0055-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Closed | 2021-03-30T01:55:28.0270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T00:10:47.5330000
T-00122-2561 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0003-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-18T06:37:04.3400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T05:56:13.5130000
T-00122-2562 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0060-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-01T23:48:27.3570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T21:20:21.9700000
T-00122-2563 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0062-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-27T02:49:55.8300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T21:58:10.2600000
T-00122-2564 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-CSL-0102-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2565 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0334-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2566 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0337-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2567 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0216-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2568 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0251-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T02:47:10.8930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T02:42:25.0970000
T-00122-2569 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0003-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2570 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0048-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2571 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-PD-0024-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T05:40:49.4630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T22:10:17.1770000
T-00122-2572 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-400-MCS-0314-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2573 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0015-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2574 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0264-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2575 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0046-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2577 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0093-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2578 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0115-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2579 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0019-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T07:25:09.0500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:51:11.8270000
T-00122-2580 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0062-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-25T21:08:03.7200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-21T02:00:45.1730000
T-00122-2581 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-MCS-0274-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2582 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0036-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2583 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-RWA-0133-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2584 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0013-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2586 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-1137-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2587 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0369-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2588 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0296-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2591 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0261-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-09T14:14:59.3370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T14:00:08.4470000
T-00122-2592 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0281-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2593 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-100-COL5-0005-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2594 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0045-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2595 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0257-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2596 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-CSL-0106-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T06:00:16.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T03:29:06.3570000
T-00122-2598 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0110-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2599 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-PD-0002-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-02T02:32:58.1330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T19:20:55.4230000
T-00122-2600 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-MCS-0315-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T12:38:18.4370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T03:06:46.2970000
T-00122-2601 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0004-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:29:14.5130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T20:11:56.5670000
T-00122-2602 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0019-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2604 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-CO2-0007-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2605 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0101-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2607 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0073-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2608 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0011-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2609 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-63-RWA-0132-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2610 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0264-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-27T03:05:41.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T22:31:56.5830000
T-00122-2611 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0292-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2613 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0255-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2614 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-150-FWA-0004-C9 | Line - Line/Piping |  |  | S2 - Stage 2 Pre Commissioning | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-03-24T21:35:04.7970000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-03-16T05:10:49.3330000
T-00122-2615 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0280-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2616 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0020-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2617 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0061-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2618 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-COL5-0007-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2619 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-225-PWL-0018-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-15T05:29:32.4030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-15T01:18:21.0470000
T-00122-2620 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0121-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2621 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0003-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2622 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0356-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-07T14:10:06.5930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:23:31.0270000
T-00122-2623 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0351-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2624 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0019-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2625 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0002-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2626 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-160-RWU-0021-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-24T02:58:49.4200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T23:02:04.6830000
T-00122-2627 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0105-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2628 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0017-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-13T21:31:37.0370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T20:58:14.3970000
T-00122-2629 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0041-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2631 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0018-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-30T03:03:21.9270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-30T01:38:50.5570000
T-00122-2632 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-PWH-0372-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2633 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-63-MCS-0286-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2634 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0033-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2635 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-280-PD-0209-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2636 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0016-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T07:26:15.2070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:52:07.6270000
T-00122-2637 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0143-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T12:39:45.9900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T03:27:03.0630000
T-00122-2638 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-RWA-0002-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:30:30.6700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T14:13:31.2700000
T-00122-2639 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0293-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2640 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-63-MCS-0305-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-16T01:01:29.4730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-04-16T00:00:18.5770000
T-00122-2641 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0049-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2643 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0019-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2644 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0335-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-15T05:26:58.4170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-15T03:24:23.8700000
T-00122-2645 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0283-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2646 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0020-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:31:38.1900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T05:15:48.2170000
T-00122-2649 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0330-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2650 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-PD-0003-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2651 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-SU-0190-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2652 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FRO3-0014-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2653 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-COL5-0003-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2654 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-MCS-0117-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2655 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0009-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2657 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0273-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-27T03:49:53.4770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T22:27:52.2570000
T-00122-2658 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0279-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2659 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0008-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2660 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0021-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2661 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-VGN-0082-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2662 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0011-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2663 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0258-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-31T18:29:30.4600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-30T02:02:18.3130000
T-00122-2664 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0262-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T04:04:13.0670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T00:43:19.8670000
T-00122-2665 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0016-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-23T08:53:25.4400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T21:40:16.2300000
T-00122-2666 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-FRO3-0003-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2667 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0202-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-16T06:49:50.0600000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T22:57:37.8800000
T-00122-2668 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-315-MCS-0138-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2669 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0026-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2670 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-PWL-0015-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2671 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0024-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2672 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0006-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T08:14:54.4330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:20:38.1130000
T-00122-2673 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-VGN-0230-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2674 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-CSL-0103-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T06:24:25.9400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T03:26:01.3700000
T-00122-2675 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0188-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-04T05:41:33.0630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T02:08:01.3600000
T-00122-2676 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-IA-0001-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T09:27:07.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:55:34.7100000
T-00122-2677 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0277-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2678 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0300-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2679 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FLOC-0044-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:38:27.8230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T03:53:16.2000000
T-00122-2680 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0007-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2681 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0014-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-15T22:07:45.6870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T05:50:07.1700000
T-00122-2682 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0279-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T04:05:16.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T03:18:24.3070000
T-00122-2683 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-200-MCS-0197-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2684 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0008-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2685 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-HPA-0248-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2686 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0001-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T06:20:02.8370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T05:22:26.8130000
T-00122-2687 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0005-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2688 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-MCS-0027-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2689 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0060-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:41:10.7770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-21T06:10:50.2470000
T-00122-2690 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0007-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2691 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0038-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-07T14:10:30.9200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:24:02.6430000
T-00122-2692 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0343-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2693 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0011-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2694 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0147-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-02T23:56:04.4630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T20:36:16.2870000
T-00122-2695 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0071-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2696 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0111-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:29:10.4270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-02T00:53:35.5700000
T-00122-2697 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0013-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-26T06:46:47.1970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T05:21:47.2230000
T-00122-2698 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0290-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2699 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0198-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2700 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0062-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2701 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-SU-0191-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2702 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0005-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2703 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-RWA-0001-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:31:14.3270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T15:12:02.4730000
T-00122-2704 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0249-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:13:03.3800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T04:51:13.3070000
T-00122-2705 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0013-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T05:41:21.3570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T04:04:31.2870000
T-00122-2706 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0308-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2707 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0001-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-17T02:55:01.0100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-04-17T01:05:37.8770000
T-00122-2708 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0005-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2709 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FRO3-0020-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2710 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-MCS-0187-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2711 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0116-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2712 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0263-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2713 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0017-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T05:42:26.5570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T20:39:15.1730000
T-00122-2714 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0252-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2715 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0206-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2716 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0004-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:30:02.8000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T06:51:00.5230000
T-00122-2717 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0008-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2718 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0169-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-19T23:38:16.9400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T22:42:21.8400000
T-00122-2719 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-HPA-0304-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2720 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0307-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2721 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0028-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:50:03.5800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:30:01.0170000
T-00122-2722 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0016-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2723 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0325-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2724 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0008-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-13T03:33:00.0270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T02:48:23.6400000
T-00122-2725 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0215-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-07T14:11:11.2430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:24:34.8170000
T-00122-2726 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-FWA-0002-C9 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-01 - Fire Water Ring Main & Distribution | CS0D - Fire Water | Closed | 2021-03-27T22:35:18.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-19T06:27:22.0870000
T-00122-2727 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0012-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2728 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-PD-0211-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T05:43:39.0800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T22:04:42.5570000
T-00122-2729 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-POA-0043-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2730 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-MCS-0282-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2732 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-15-DEF-0058-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2733 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0258-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T06:21:50.6670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:10:56.9030000
T-00122-2734 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0117-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2735 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0183-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2736 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0054-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2737 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0299-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2738 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-MCS-0033-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:50:30.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:30:26.9870000
T-00122-2739 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0310-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-14 - Process Water to Copper Thickener Area | CS0E - Process Water Distribution | Closed | 2021-04-16T07:08:55.0570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  |  | 2021-04-14T05:29:48.9000000
T-00122-2740 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0007-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2741 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0026-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T03:38:59.5000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-04-14T22:44:03.5200000
T-00122-2742 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0206-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2743 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0032-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T10:51:01.5400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:31:20.4800000
T-00122-2745 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0062-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:38:40.2700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T04:30:43.4500000
T-00122-2746 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-MCS-0134-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-09T16:49:07.0430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T14:31:36.8330000
T-00122-2747 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-PD-0197-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2748 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0083-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-03T00:28:23.9170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T20:38:54.6070000
T-00122-2749 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0212-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2750 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0148-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2751 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0184-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2753 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0035-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2754 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0004-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T00:43:27.5300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T23:24:21.0330000
T-00122-2756 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0178-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2757 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-NAHS-0008-S6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2759 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-PWH-0004-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T05:04:33.5970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-12T04:17:54.4170000
T-00122-2760 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0288-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2761 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0021-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T21:52:37.1830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T22:45:39.5170000
T-00122-2763 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PWH-0084-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-26T09:08:04.0670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T23:21:08.0430000
T-00122-2764 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-300-MCS-0125-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-22T09:52:43.7000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T02:42:57.6730000
T-00122-2765 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0282-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2766 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0019-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2768 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0174-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2769 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0259-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2770 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-PD-0212-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-16T05:50:33.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T06:10:15.1570000
T-00122-2771 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0288-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2772 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0340-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2773 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0004-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2774 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0265-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2775 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0370-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2776 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0072-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2777 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0036-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2778 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-63-VGN-0214-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2779 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0116-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:29:43.7130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T02:43:35.2630000
T-00122-2780 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0275-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2782 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0010-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2783 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0201-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2784 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0251-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2785 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0030-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:40:24.1600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T04:37:30.3230000
T-00122-2786 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-VGN-0232-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2788 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0004-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2790 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0016-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2791 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0060-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2792 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0063-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-27T07:06:51.2070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T21:53:53.0630000
T-00122-2793 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-SU-0196-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2796 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0247-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:30:05.6300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T03:26:14.2370000
T-00122-2797 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-VGN-0223-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2798 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0026-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-14T06:12:41.9500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:01:42.0630000
T-00122-2799 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-RWA-0013-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-15 - Raw Water to Filter Building | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2800 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-SU-0187-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2801 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0005-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2802 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0013-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2803 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0059-C6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2804 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-PWL-0008-C5 | Line - Line/Piping |  |  | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-26T08:43:36.8400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T23:45:16.3870000
T-00122-2805 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0317-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2806 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-315-MCS-0117-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T12:41:20.5670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T02:24:26.9700000
T-00122-2808 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0336-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2809 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0267-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2810 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-63-VGN-0213-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2811 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-CSL-0104-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-26T06:29:00.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T03:30:21.1570000
T-00122-2813 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-POA-0007-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2814 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-PWH-0159-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2816 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0056-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2817 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-CSL-0010-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-15T21:39:33.6000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-14T21:39:52.0730000
T-00122-2818 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0002-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:30:32.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T06:28:20.4570000
T-00122-2819 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0014-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2820 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0032-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2822 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0011-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T06:23:28.2170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:02:01.7070000
T-00122-2823 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0209-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2824 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0344-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2825 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0038-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2826 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0185-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2827 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-VGN-0212-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-04T22:05:20.3070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T01:53:29.3930000
T-00122-2828 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0011-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2829 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0001-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2830 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0227-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2831 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0141-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-27T07:32:37.4730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-27T07:31:36.7900000
T-00122-2832 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0245-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:30:25.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T02:57:46.5130000
T-00122-2833 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0258-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2834 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0015-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2835 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-350-MCS-0202-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:33:46.0470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-02T02:30:40.8500000
T-00122-2836 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-NO-0002-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2837 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-250-PD-0199-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-04T23:39:23.1670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-04T22:02:18.7770000
T-00122-2838 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-63-MCS-0285-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2839 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-CSL-0105-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-04T22:06:17.6830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T00:57:54.6600000
T-00122-2840 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-PD-0046-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2842 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-CSL-0061-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-28T11:41:12.5530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T06:53:29.6370000
T-00122-2843 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-PWH-0002-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-14 - Process Water to Copper Thickener Area | CS0E - Process Water Distribution | Closed | 2021-02-19T22:03:50.4300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-19T21:22:16.9070000
T-00122-2844 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0014-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-15T22:28:34.0870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T00:44:37.3370000
T-00122-2845 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-VGN-0023-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2846 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0302-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2847 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0296-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2848 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0263-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2849 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0074-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T22:48:59.7900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-05T22:35:03.4000000
T-00122-2850 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0049-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2851 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0228-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-03T02:20:01.2430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T01:57:44.5870000
T-00122-2853 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0188-S6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2854 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0241-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2855 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0070-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2856 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0067-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2857 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0264-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2858 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-25-RWA-0245-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-15 - Raw Water to Filter Building | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2859 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0039-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T12:59:36.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T04:58:45.3430000
T-00122-2860 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0007-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T08:15:24.8730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:26:36.7930000
T-00122-2861 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0251-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2862 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-VGN-0233-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2863 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0302-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-14 - Process Water to Copper Thickener Area | CS0E - Process Water Distribution | Closed | 2021-02-12T03:58:03.8470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-12T01:32:55.0000000
T-00122-2864 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0013-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2866 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0060-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2867 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0002-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2868 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FLOC-0046-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:39:15.1500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T02:55:46.0270000
T-00122-2870 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0267-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2871 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0047-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T09:20:18.8600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:08:08.6700000
T-00122-2872 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0006-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-27T09:42:15.7930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-27T03:34:07.5070000
T-00122-2873 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-MCS-0142-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2874 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0104-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T23:58:04.7200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-13T01:14:02.8900000
T-00122-2876 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0258-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2877 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0012-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2878 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0011-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2880 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0033-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2881 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0122-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2882 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0002-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2883 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0266-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2884 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0108-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2885 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWL-0176-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-21T09:41:16.2570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-20T23:53:17.9000000
T-00122-2886 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-NO-0001-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2887 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0025-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T22:22:57.3600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T21:52:17.6700000
T-00122-2888 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-DEF-0001-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2889 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0271-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2890 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0341-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T21:59:28.1030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T06:00:56.2670000
T-00122-2891 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0140-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2892 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0013-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-16T00:37:21.2800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T00:39:28.5570000
T-00122-2893 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0119-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T13:00:55.1300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T02:42:05.7670000
T-00122-2894 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0009-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2895 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0285-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2896 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0173-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2900 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-SU-0195-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2901 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0002-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2902 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-MCS-0135-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2903 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-PD-0213-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-03T01:29:52.7430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T21:00:10.4270000
T-00122-2904 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-ASC-0001-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2905 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0011-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2906 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0293-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2907 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-PWH-0006-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Closed | 2021-04-03T01:35:03.1430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T21:06:35.2000000
T-00122-2908 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0028-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2909 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0006-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-19T23:55:24.6700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-19T02:21:48.8700000
T-00122-2911 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0040-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2912 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-100-NAHS-0016-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2914 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0013-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2915 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0249-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-04T22:24:06.3930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T02:04:32.2730000
T-00122-2916 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0256-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-01T09:44:33.6970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-30T01:49:24.1670000
T-00122-2917 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0339-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2918 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0303-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2919 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0003-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-16T01:03:20.5900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-06T20:14:10.4470000
T-00122-2920 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-MCS-0035-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T13:35:16.5700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T14:31:57.2830000
T-00122-2921 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0250-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2922 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0005-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:17:55.4800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T05:30:59.9430000
T-00122-2923 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0013-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2924 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0262-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2925 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0008-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-24T23:26:35.2670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-20T04:55:47.8670000
T-00122-2927 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0263-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:13:29.6830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T05:03:35.8670000
T-00122-2928 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0268-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2929 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-90-RWU-0025-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-21T21:18:48.2870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T06:12:43.0930000
T-00122-2930 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0080-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-31T16:10:47.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T01:29:59.7570000
T-00122-2931 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0010-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2932 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0045-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2933 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0055-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2934 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0002-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-11T22:15:55.4800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T05:38:51.9770000
T-00122-2935 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-MCS-0284-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2936 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0301-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2937 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-15-PWH-0355-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-2938 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0048-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2939 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0253-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T06:25:06.4630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:06:52.5470000
T-00122-2940 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-150-RWA-0001-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-21T23:05:34.1170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T23:00:37.7570000
T-00122-2941 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0253-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2942 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0012-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2944 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-CSH-0110-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T02:25:40.8730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-26T20:26:17.9330000
T-00122-2946 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-PWL-0001-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T02:53:38.5670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-12T00:37:09.0000000
T-00122-2947 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0003-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T06:36:01.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-17T05:23:30.9200000
T-00122-2949 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0305-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2950 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0200-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2951 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0224-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2952 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PWH-0373-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2953 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0297-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2954 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-250-MCS-0113-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-31T17:31:10.9330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T00:36:18.8070000
T-00122-2955 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0112-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-02-16T00:09:54.9570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T09:07:09.3670000
T-00122-2956 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-LPA-0041-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2957 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0022-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:46:55.3270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T04:51:56.9900000
T-00122-2958 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-MCS-0061-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2959 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0144-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T13:02:08.7070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T02:57:25.8930000
T-00122-2960 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0381-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2961 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0216-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2962 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0035-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2963 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-PWH-0003-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2964 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0182-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2966 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0074-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2967 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FLOC-0020-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:39:51.7030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T05:32:17.9630000
T-00122-2968 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-PD-0066-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T12:03:38.8670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T06:10:44.0000000
T-00122-2969 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0101-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-26T09:07:30.2130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T23:09:44.8200000
T-00122-2970 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0167-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-2971 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0329-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2972 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0061-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Closed | 2021-04-01T09:06:47.6400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T00:17:02.0730000
T-00122-2973 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0025-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2975 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0151-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-04-01T10:11:21.0000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-22T01:07:53.8470000
T-00122-2976 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0255-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2977 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0322-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2978 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0013-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-2979 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-PD-0065-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T12:04:14.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T06:16:44.0000000
T-00122-2980 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-300-PWL-0001-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T00:27:07.4500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T00:11:53.5670000
T-00122-2981 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-MCS-0063-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2982 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0024-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-2983 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0056-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-01T23:49:25.7370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T21:14:32.0170000
T-00122-2984 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0096-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-26T08:55:03.1930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T00:32:43.1670000
T-00122-2985 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0209-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-24T09:20:28.7570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T04:53:58.1930000
T-00122-2986 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PWL-0013-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-22T09:56:13.8270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T01:27:59.5570000
T-00122-2987 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0035-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2988 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-PWL-0003-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T03:19:20.6270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-11T20:12:40.0000000
T-00122-2989 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0058-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-14T02:41:35.4600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T02:12:46.7500000
T-00122-2990 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0175-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2991 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0179-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2992 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0055-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-2994 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0244-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T10:30:50.4270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-31T02:50:53.2700000
T-00122-2995 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0098-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T22:25:41.8300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T20:38:50.3670000
T-00122-2996 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0303-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2997 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0353-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-2998 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-90-SU-0189-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3000 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-RWA-0005-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:40:55.7170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T15:38:01.9030000
T-00122-3001 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0081-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3002 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0217-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3003 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0037-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3004 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0294-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3005 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0259-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3006 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-RWA-0016-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-15 - Raw Water to Filter Building | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3007 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0021-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3009 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0011-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-16T01:08:11.1830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T00:26:37.6500000
T-00122-3010 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0019-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3011 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0011-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3012 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0197-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3013 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-225-MCS-0009-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T13:35:43.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T14:32:26.2630000
T-00122-3014 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0315-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3015 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0207-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3016 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0032-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-24T09:21:01.8370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T06:04:27.8870000
T-00122-3017 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0024-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3018 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0076-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3019 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0291-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3020 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0009-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3021 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0046-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3022 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0017-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T16:00:50.1670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T15:25:48.4700000
T-00122-3023 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0266-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:04:41.8500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T00:53:20.0230000
T-00122-3024 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0001-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3025 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSH-0002-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T03:16:57.8830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T03:08:14.5500000
T-00122-3026 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0371-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3027 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-MCS-0316-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-27T07:33:17.5600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T22:36:25.2200000
T-00122-3028 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0295-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3029 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0269-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3030 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0319-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3031 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-IA-0065-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Closed | 2021-02-14T04:18:04.1500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-18T21:28:03.9530000
T-00122-3032 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-PD-0002-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3033 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0020-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3034 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0187-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-03-07T14:11:48.8830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-06T23:25:07.1070000
T-00122-3035 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-MCS-0006-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3037 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0256-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3038 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0081-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:21:25.3200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T04:09:34.3930000
T-00122-3039 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0255-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-01T10:24:00.3730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-30T02:10:17.3870000
T-00122-3040 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-280-MCS-0114-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-01T09:31:23.8000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T01:10:43.9270000
T-00122-3041 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSH-0001-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T02:37:11.0830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T02:32:09.9730000
T-00122-3042 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0059-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3043 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0207-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3044 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0145-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:43:18.1930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T00:28:11.9300000
T-00122-3045 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0119-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3046 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0320-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3048 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0008-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T08:23:28.5100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:49:04.4470000
T-00122-3049 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0380-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-24T09:21:34.4700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T05:35:58.5730000
T-00122-3051 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0080-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3052 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0345-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3053 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-COL5-0017-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3055 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0166-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3056 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0008-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3057 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-RWA-0019-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3059 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0023-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T22:26:31.2100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T21:11:40.2130000
T-00122-3060 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0001-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-26T09:09:16.7900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-02-25T05:32:28.8300000
T-00122-3061 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0211-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3062 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0039-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3063 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-63-PD-0199-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3064 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0009-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3065 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0187-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3066 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0064-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-27T22:00:57.2070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-21T02:04:43.1770000
T-00122-3067 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0208-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T16:01:12.1800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-09T15:26:21.4100000
T-00122-3068 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0342-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3069 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0053-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3070 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0292-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3071 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0047-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3072 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0028-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-14T06:13:02.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:02:50.1100000
T-00122-3073 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0111-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3074 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0309-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3076 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-25-RWA-0179-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3077 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0040-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-27T07:33:49.1000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T21:39:00.1330000
T-00122-3078 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0015-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-16T01:36:24.1730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T06:03:38.6270000
T-00122-3079 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0029-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T13:36:17.6500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T14:32:50.2670000
T-00122-3080 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0290-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3081 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0306-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3082 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0347-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3083 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0250-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3084 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FLOC-0004-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:36:17.9030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T18:23:28.0530000
T-00122-3085 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0315-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3086 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-PD-0008-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-13T23:25:33.1670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T22:51:08.0400000
T-00122-3087 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0203-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-04T21:50:23.6570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T05:49:24.8770000
T-00122-3088 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0134-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-04T22:27:26.4370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T20:46:37.1700000
T-00122-3089 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0019-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3090 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0272-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3091 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0247-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3094 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-PWH-0313-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T12:31:34.3000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T11:54:10.7770000
T-00122-3095 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0030-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3096 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-400-PD-0202-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-04T21:51:19.3530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T05:46:48.9630000
T-00122-3097 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0306-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3098 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0331-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3099 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWL-0019-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-15T05:26:08.6330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-15T03:47:41.8300000
T-00122-3100 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0002-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:31:03.0070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-02T00:44:05.7170000
T-00122-3102 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0177-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3103 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-FRO3-0001-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3104 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-CO2-0001-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3105 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0254-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3106 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0016-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3107 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0097-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-3108 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0025-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-02-16T00:18:06.0600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T21:37:56.1500000
T-00122-3109 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0068-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3110 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0030-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3111 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0146-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-16T02:05:23.6900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-13T01:08:19.2200000
T-00122-3112 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-PWH-0013-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-02 - Process Water to Concentrate Feed Pumps | CS0E - Process Water Distribution | Closed | 2021-02-13T21:40:09.7770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T21:29:12.2370000
T-00122-3114 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-400-RWA-0002-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-13T04:46:05.3000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-13T03:00:58.9130000
T-00122-3115 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-MCS-0005-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3116 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0208-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3118 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWL-0020-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T03:59:26.6400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-12T01:45:29.0000000
T-00122-3119 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0005-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-31T08:23:53.2770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:17:34.0300000
T-00122-3120 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-280-PD-0210-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3122 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0332-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3123 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0138-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3124 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0248-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-3125 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-80-SU-0188-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3126 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-CO2-0008-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3127 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0050-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3128 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0156-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3129 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0254-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T06:27:32.8530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:15:52.2270000
T-00122-3130 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0213-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3131 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0118-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3132 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0028-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-31T16:17:38.1630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-17T22:54:13.7870000
T-00122-3133 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-NG-0022-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3134 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0033-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-24T09:21:55.4530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T06:07:19.9770000
T-00122-3135 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-RWA-0006-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:40:06.8300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T15:32:30.2970000
T-00122-3136 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-300-POA-0005-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3137 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FLOC-0045-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:40:20.2000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T04:22:30.2370000
T-00122-3138 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0191-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3139 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-160-PD-0006-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-28T11:39:05.7630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-28T04:18:00.5330000
T-00122-3140 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0100-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-25T22:01:10.5600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T21:12:43.6500000
T-00122-3141 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0216-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3142 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0009-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3143 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-40-MCS-0294-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3144 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0169-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3145 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0361-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3146 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-400-PD-0003-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T06:39:58.0070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-02T21:39:04.2930000
T-00122-3147 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0008-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3149 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0267-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:51:38.4000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T03:07:15.4030000
T-00122-3150 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-200-PWH-0349-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T05:05:46.6070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-12T04:21:50.3300000
T-00122-3152 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0287-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3153 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0259-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3154 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-80-DEF-0003-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3155 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0011-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-22T10:01:38.1230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-21T22:47:00.5530000
T-00122-3156 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0039-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Closed | 2021-04-01T12:37:25.5000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-18T06:05:41.0600000
T-00122-3158 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0051-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3159 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0005-S6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3160 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0020-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3163 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0301-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3164 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0170-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-16T03:34:07.9870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T23:20:58.2230000
T-00122-3165 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0034-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3166 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-VGN-0092-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3167 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0006-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3168 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0265-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3169 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0005-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Closed | 2021-04-04T22:32:07.1670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T06:14:41.4500000
T-00122-3170 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-150-CSL-0032-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-26T08:56:26.7300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T04:20:20.4800000
T-00122-3171 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-VGN-0099-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-27T07:34:42.2700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-26T21:47:55.1500000
T-00122-3172 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-280-PD-0139-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3173 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-40-MCS-0209-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3174 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-110-SU-0193-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3175 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0115-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3176 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0186-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3177 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0004-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3178 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0008-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:31:41.5970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-02T01:29:14.4600000
T-00122-3179 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0257-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3180 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PWH-0011-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-27T09:42:35.7700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-27T04:04:06.0570000
T-00122-3181 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-NG-0021-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3182 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0360-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-03-31T17:28:13.9970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-03-16T04:37:25.6400000
T-00122-3183 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0201-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3184 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0032-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-31T07:51:03.8300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-30T19:13:34.2930000
T-00122-3185 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0018-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3186 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0171-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3187 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0354-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3188 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-CSH-0102-C11 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-27T02:37:48.6670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-27T02:33:02.8800000
T-00122-3189 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-CSL-0057-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-14T02:42:10.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T02:08:19.6870000
T-00122-3190 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0078-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3191 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0014-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-3193 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-PD-0050-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:53:24.3900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T04:10:32.5170000
T-00122-3194 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0073-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T05:55:03.3430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-12T00:14:28.1930000
T-00122-3195 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0307-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3196 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0014-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3197 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-HPA-0254-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3198 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0168-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-02T02:32:17.6530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-02T01:19:42.9270000
T-00122-3200 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-VGN-0069-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3201 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0167-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3202 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0124-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3204 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0044-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3205 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0012-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T21:16:31.3800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-03T03:49:55.2770000
T-00122-3206 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-RWA-0260-C5-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3207 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0297-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3208 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0333-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3209 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0346-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3210 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-IA-0038-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-30T09:25:10.1500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-29T20:09:33.9000000
T-00122-3211 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FRO3-0024-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3212 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0035-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3213 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0318-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3214 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0057-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-01T23:50:15.4430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T00:09:12.6230000
T-00122-3215 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-DEF-0125-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3216 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-RWA-0003-C5-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T15:56:39.8530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T15:43:24.7230000
T-00122-3217 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-15-NG-0043-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3218 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-200-VGN-0040-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3219 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0379-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-24T09:23:51.5830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T05:50:07.5470000
T-00122-3220 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-HPA-0001-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3221 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0023-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3222 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-110-PD-0025-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T22:32:59.7770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T22:17:32.3570000
T-00122-3223 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0031-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-24T09:24:25.0770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T06:13:22.3200000
T-00122-3224 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-PD-0055-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-16T04:03:48.6530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T21:14:49.3500000
T-00122-3225 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0166-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3226 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0317-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3227 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-HPA-0304-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3228 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0017-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3230 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NG-0023-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3231 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-PWH-0301-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3234 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0020-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3235 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-PD-0018-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3236 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0042-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-04T22:33:52.7930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-04T06:53:44.8130000
T-00122-3237 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-MCS-0208-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-04T22:36:40.9130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-01T21:57:23.3700000
T-00122-3238 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0034-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3239 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0044-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3240 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-MCS-0298-H15 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3241 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0284-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3242 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0289-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3243 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0063-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-28T00:57:13.5500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-28T00:20:23.0100000
T-00122-3244 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0043-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3245 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-PD-0214-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3247 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-VGN-0213-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-3248 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-NG-0030-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-14T06:14:22.4470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-02-14T06:04:06.9470000
T-00122-3249 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-HPA-0295-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3250 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0019-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3251 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-FLOC-0003-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:36:39.8870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-03-07T18:32:08.1370000
T-00122-3252 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-100-VGN-0017-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-04T23:40:25.9370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-04T22:46:03.2870000
T-00122-3253 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-50-PWH-0040-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-26T09:45:05.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-22T04:10:10.8270000
T-00122-3254 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-PD-0220-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3256 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0170-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3257 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0352-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-21T00:15:51.6170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-20T23:40:39.8770000
T-00122-3258 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PWH-0035-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-14 - Process Water to Copper Thickener Area | CS0E - Process Water Distribution | Closed | 2021-02-15T05:24:58.5270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  |  | 2021-02-15T01:37:21.3830000
T-00122-3259 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-100-PWL-0007-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3261 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-150-MCS-0277-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T10:14:03.9300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-22T05:11:25.5770000
T-00122-3262 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0003-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3263 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-90-VGN-0110-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3264 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-FWA-0003-C9 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-21T23:13:17.1970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-21T23:11:22.9270000
T-00122-3265 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0323-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3266 | M1.T049 Piping Installation Stage 1 | PIPE | 333550-FWA-0016-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-3267 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0054-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3269 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-RWA-0261-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3271 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-110-VGN-0038-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3272 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0027-G1-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3273 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-100-VGN-0045-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3274 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0017-C6-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00122-3275 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-80-PD-0054-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T00:34:18.9730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T22:46:24.4500000
T-00122-3276 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-80-PD-0058-R5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-01T23:50:54.9730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-01T21:18:48.0430000
T-00122-3278 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-200-COL5-0004-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3279 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-25-NAHS-0037-S6-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3280 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-90-PD-0221-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T12:32:07.9870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-08T11:55:30.9400000
T-00122-3282 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-CO2-0009-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3283 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-FWA-0018-C9-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-02 - Fire Water Above Ground | CS0D - Fire Water | Past Due |  | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25
T-00122-3284 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-NAHS-0013-S6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3286 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-80-POA-0006-G1 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3287 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-110-VGN-0016-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T22:31:42.3400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-02-18T22:29:51.3800000
T-00122-3288 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-160-MCS-0118-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-23T13:02:33.8070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T02:32:31.1730000
T-00122-3289 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-25-PWH-0313-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3290 | Piping Installation Stage 1 | PIPE | Raw Water Temp Pipe | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS00-02 - Raw Water Tie-in | CS00 - Tie-in (System) | Closed | 2020-12-01T05:59:08.0000000 |  |  | 0.25 |  |  | 2020-12-01T05:58:43.0000000
T-00122-3291 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FLOC-0042-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-30T09:40:54.2400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 |  | Flocculant Distribution | 2021-01-30T05:24:32.9270000
T-00122-3292 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0010-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3294 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-FRO3-0022-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3295 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-500-VGN-0041-C3 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3297 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-IA-0115-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-03-31T17:35:27.1430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  |  | 2021-03-17T22:27:56.7570000
T-00122-3300 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0308-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3302 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-50-POA-0016-G1-TI | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3303 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-IA-0075-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00122-3304 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-15-COL5-0018-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00122-3306 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-IA-0020-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00122-3308 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-NO-0007-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00122-3309 | M1.T049 Piping Installation Stage 1 | PIPE | 3334-50-IA-0117-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:12:41.7900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-03-15T02:59:47.4030000
T-00122-3310 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-100-RWA-0257-C5 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-02T23:52:15.0770000 |  |  | 0.25 |  | Raw Water | 2021-04-01T20:40:13.1430000
T-00122-3311 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0022-C6-TI-ET | Line - Heat Traced Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.25 |  | PWH
T-00122-3312 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-25-PWH-0085-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-25T23:03:23.6930000 |  |  | 0.25 |  |  | 2021-04-25T22:22:45.5570000
T-00122-3313 | M1.T049 Piping Installation Stage 1 | PIPE | 3331-25-PWH-0086-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-25T23:04:01.7830000 |  |  | 0.25 |  |  | 2021-04-25T22:27:03.0600000
T-00122-3314 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0012-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3315 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0013-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3316 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0011-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3317 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-PWH-0375-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Created |  |  |  | 0.25
T-00122-3318 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0001-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3319 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-VGN-0243-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.25
T-00122-3320 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0014-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3321 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-VGN-0244-C3-TI-ET | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.25
T-00122-3322 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-NG-0023-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Created |  |  |  | 0.25
T-00122-3323 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0015-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3324 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-400-VGN-0219-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25
T-00122-3325 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-25-CO2-0010-C4 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25
T-00122-3326 | M1.T049 Piping Installation Stage 1 | PIPE | 3333-50-PWH-0155-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Created |  |  |  | 0.25
T-00122-3327 | M1.T049 Piping Installation Stage 1 | PIPE | 3335-63-PD-0001-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.25
T-00122-3328 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-63-MCS-0319-H14 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.25
T-00122-3329 | M1.T049 Piping Installation Stage 1 | PIPE | 3332-50-PWH-0390-C6 | Line - Line/Piping | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Created |  |  |  | 0.25
T-00126-0003 | E2.T042 Miscellaneous Load Stage 2 | ELEC | 3338-XE-4101 | XE - Load Bank |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00127-0049 | E1.T042 Miscellaneous Load Stage 1 | ELEC | 3338-GE-4001 | GE - GENERATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00127-0050 | E1.T042 Miscellaneous Load Stage 1 | ELEC | 3338-XE-4101 | XE - Load Bank | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00128-0002 | E1.T044 LV Junction Box Stage 1 | ELEC | 3332-JB-4001 | JB - JUNCTION BOX | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T03:55:42.1530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T03:32:54.3000000 |  | 2021-04-17T04:01:49.0630000
T-00129-0001 | Structural Steel Stage 1 | STRU | Steel Phase 1 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2020-11-30T21:25:27.1570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2020-11-30T21:18:07.6200000
T-00129-0002 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 2 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:25:37.3330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:10:43.6730000
T-00129-0003 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 3 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:30:46.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:11:24.6000000
T-00129-0004 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 4 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:39:59.8070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T05:54:55.0570000
T-00129-0005 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 5 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:41:02.0600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:14:40.5030000
T-00129-0006 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 6 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:41:31.1800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:15:42.4300000
T-00129-0007 | S1.T012 Structural Steel Stage 1 | STRU | Steel Phase 7 | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:42:11.8370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:16:55.8800000
T-00129-0009 | Structural Steel Stage 1 | STRU | Con. Tank Access Structure | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2020-12-16T04:42:51.0870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2020-12-16T04:40:35.4670000
T-00129-0010 | S1.T012 Structural Steel Stage 1 | STRU | Filter Building Steel & Stair Tower | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-21T00:58:51.0270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-21T00:44:06.1670000
T-00129-0011 | S1.T012 Structural Steel Stage 1 | STRU | Steel Shed | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00129-0012 | S1.T012 Structural Steel Stage 1 | STRU | 331 East West Pipe Rack | Steel - Combined Steel Structure | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Closed | 2021-02-22T06:42:54.9000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-02-22T06:20:00.0870000
T-00130-0137 | M1.T058 Pump Installation Stage 1 | MECH | 3335-PU-4092 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-12T01:47:52.5570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.5 | 2021-02-12T01:35:20.8600000 |  | 2021-02-12T01:35:36.7370000
T-00130-0171 | M1.T058 Pump Installation Stage 1 | MECH | 3335-PU-4094 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-12T01:48:35.4770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.5 | 2021-02-12T01:44:14.4900000 |  | 2021-02-12T01:44:58.0400000
T-00131-0003 | Switchboard MCC Stage 1 | ELEC | 3338-MC-4001 | MC - MOTOR CONTROL CENTRE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-17T13:54:59.0430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 1 | 2020-12-13T21:26:52.0170000 |  | 2020-12-17T10:00:03.4870000
T-00131-0004 | Switchboard MCC Stage 1 | ELEC | 3338-MC-4002 | MC - MOTOR CONTROL CENTRE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-17T13:56:01.7170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 1 | 2020-12-14T04:44:00.9900000 |  | 2020-12-17T10:00:44.8030000
T-00132-0003 | E2.T047A Switchboard MCC Stage 2A | ELEC | 3338-MC-4001 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Started |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.75
T-00132-0004 | E2.T047A Switchboard MCC Stage 2A | ELEC | 3338-MC-4002 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.75
T-00133-0003 | E2.T047B Switchboard MCC Stage 2B | ELEC | 3338-MC-4001 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Started |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00133-0004 | E2.T047B Switchboard MCC Stage 2B | ELEC | 3338-MC-4002 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00134-0038 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4015 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T02:39:12.8030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-02T17:00:23.0000000 |  | 2021-01-02T19:40:01.2030000
T-00134-0039 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4028 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:13:25.7670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-03T20:37:24.9470000 |  | 2021-01-03T20:37:56.1900000
T-00134-0040 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4005 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-07T06:57:26.2270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-07T03:20:57.8970000 |  | 2021-04-07T05:27:20.3630000
T-00134-0041 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4035 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-10T04:14:05.9370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-02T10:29:19.0000000 |  | 2021-01-02T19:40:20.5070000
T-00134-0042 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4008 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-10T04:14:31.2970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-03T12:59:29.3800000 |  | 2021-01-03T19:24:38.5800000
T-00134-0043 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3331-VS-4003 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:23:50.6130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T09:13:18.0000000 |  | 2021-01-24T19:17:23.5800000
T-00134-0044 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4012 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T04:15:13.3600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T12:50:58.2300000 |  | 2021-01-03T19:26:36.8630000
T-00134-0045 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4021 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-07T06:58:53.3330000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-07T03:38:15.7870000 |  | 2021-04-07T05:27:36.5400000
T-00134-0046 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4017 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-07T06:59:18.0400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-07T03:49:56.0900000 |  | 2021-04-07T05:32:00.5700000
T-00134-0047 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4032 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T04:15:47.2000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-02T09:14:04.0000000 |  | 2021-01-02T19:46:07.6500000
T-00134-0048 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4010 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T04:16:14.1930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T12:43:38.3800000 |  | 2021-01-03T19:27:24.0500000
T-00134-0049 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4007 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T04:16:36.0830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-03T12:33:10.4270000 |  | 2021-01-03T19:27:55.3130000
T-00134-0050 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3331-VS-4041 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T04:16:57.5870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T12:31:27.3600000 |  | 2021-01-03T19:28:15.6170000
T-00134-0051 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4040 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-01-10T04:18:04.6770000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-02T10:50:05.0000000 |  | 2021-01-02T19:47:51.7030000
T-00134-0052 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3331-VS-4004 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:27:25.3270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T02:23:33.9730000 |  | 2021-02-21T05:04:04.0070000
T-00134-0053 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4037 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-04-22T06:39:57.1570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:20:41.3730000 |  | 2021-04-22T04:34:37.8430000
T-00134-0054 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4024 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-27T07:17:26.2730000 |  | 2021-04-27T07:27:38.8030000
T-00134-0055 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4023 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-22T06:40:23.1630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:13:59.0570000 |  | 2021-04-22T04:35:29.5300000
T-00134-0056 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4029 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:18:38.8270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-02T16:45:12.0000000 |  | 2021-01-02T19:48:15.0400000
T-00134-0057 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4026 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:19:03.3670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-02T15:30:31.0000000 |  | 2021-01-02T19:48:30.5070000
T-00134-0058 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4033 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2021-01-10T04:19:23.7800000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-02T16:42:00.0000000 |  | 2021-01-02T19:48:47.0100000
T-00134-0059 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4030 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:19:44.9970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-02T16:42:49.0000000 |  | 2021-01-02T19:49:06.0770000
T-00134-0060 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4022 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-27T07:14:54.7870000 |  | 2021-04-27T07:18:50.9470000
T-00134-0061 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4018 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-27T07:07:20.6930000 |  | 2021-04-27T07:19:17.6830000
T-00134-0062 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4019 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-27T07:11:56.1070000 |  | 2021-04-27T07:19:40.3000000
T-00134-0063 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3331-VS-4001 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:20:07.6200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-03T13:05:59.0400000 |  | 2021-01-03T19:28:34.5170000
T-00134-0064 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4038 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T07:00:17.3900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-07T05:07:10.3670000 |  | 2021-04-07T05:34:00.3170000
T-00134-0065 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4013 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T04:20:29.7970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T12:54:07.2070000 |  | 2021-01-03T19:28:53.4200000
T-00134-0066 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4025 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-27T07:20:01.0770000 |  | 2021-04-27T07:28:03.2330000
T-00134-0067 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4014 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T04:20:54.2470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T15:12:57.7470000 |  | 2021-01-03T20:24:08.8600000
T-00134-0068 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3334-VS-4027 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:21:14.6700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-02T15:26:17.0000000 |  | 2021-01-02T19:49:55.0130000
T-00134-0069 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4036 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-04-22T06:40:49.6770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:17:59.4900000 |  | 2021-04-22T04:36:26.5830000
T-00134-0070 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4031 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T04:21:39.1400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T13:04:01.4800000 |  | 2021-01-03T20:31:50.0670000
T-00134-0071 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4034 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-01-10T04:22:06.4630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-02T10:00:56.0000000 |  | 2021-01-02T19:52:38.6270000
T-00134-0072 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3331-VS-4002 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:24:24.2530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T09:11:36.0000000 |  | 2021-01-24T21:07:14.0670000
T-00134-0073 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4016 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-07T06:59:47.5900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-07T04:54:37.7170000 |  | 2021-04-07T05:32:17.3130000
T-00134-0074 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4009 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T04:22:33.9770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-03T12:37:27.7470000 |  | 2021-01-03T20:32:24.6470000
T-00134-0075 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3333-VS-4020 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00134-0076 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4006 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:10:06.0130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T06:19:11.3570000 |  | 2021-02-19T07:21:11.0730000
T-00134-0077 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4039 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-01-10T04:24:02.0700000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-02T10:46:47.0000000 |  | 2021-01-02T19:52:56.8770000
T-00134-0078 | E1.T048 Variable Speed Controller Stage 1 | ELEC | 3332-VS-4011 | VS - VSD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T04:24:42.5430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-03T12:46:06.7370000 |  | 2021-01-03T20:34:20.0070000
T-00135-0043 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3331-VS-4003 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:11:27.8970000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-15T07:20:26.0000000 |  | 2021-04-15T07:48:31.3900000
T-00135-0052 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3331-VS-4004 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5
T-00135-0063 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3331-VS-4001 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-20T03:56:29.2070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-18T07:14:52.2670000 |  | 2021-04-18T07:18:44.9970000
T-00135-0072 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3331-VS-4002 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:11:59.9530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-15T07:31:04.3900000 |  | 2021-04-15T07:47:28.2870000
T-00135-0079 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4015 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0080 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4028 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:26:44.6100000 |  |  | 0.5 | 2021-04-24T21:50:26.8470000 |  | 2021-04-24T21:55:34.2570000
T-00135-0081 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4005 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00135-0082 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4035 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00135-0083 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4008 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00135-0084 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4012 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0085 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4021 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00135-0086 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4017 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0087 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4032 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0088 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4010 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00135-0089 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4007 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00135-0090 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3331-VS-4041 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Created |  |  |  | 0.5
T-00135-0091 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4040 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.5
T-00135-0095 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4029 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:02:02.2230000 |  |  | 0.5 | 2021-04-23T20:56:05.8200000 |  | 2021-04-23T23:01:50.7900000
T-00135-0096 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4026 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:27:17.8670000 |  |  | 0.5 | 2021-04-24T22:15:13.3770000 |  | 2021-04-24T23:04:43.8700000
T-00135-0097 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4033 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Created |  |  |  | 0.5
T-00135-0098 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4030 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:02:40.0930000 |  |  | 0.5 | 2021-04-23T21:22:50.2730000 |  | 2021-04-23T22:57:02.2170000
T-00135-0102 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4038 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.5
T-00135-0103 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4013 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0105 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4014 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0106 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3334-VS-4027 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:27:54.9600000 |  |  | 0.5 | 2021-04-24T22:05:21.2000000 |  | 2021-04-24T23:02:51.5200000
T-00135-0108 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4031 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0109 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4034 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00135-0110 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4016 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00135-0111 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4009 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00135-0113 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4006 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Started |  |  |  | 0.5
T-00135-0114 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4039 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.5
T-00135-0115 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3332-VS-4011 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00135-0116 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4037 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0117 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4024 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0118 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4023 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00135-0119 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4022 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00135-0120 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4018 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0121 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4019 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0122 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4025 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0123 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4036 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00135-0124 | E2.T048A Variable Speed Controller Stage 2A | ELEC | 3333-VS-4020 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  |  |  | 0.5
T-00136-0003 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4015 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0004 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4028 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0005 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4005 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00136-0006 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4035 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00136-0007 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4008 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00136-0008 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3331-VS-4003 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.5
T-00136-0009 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4012 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0010 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4021 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0011 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4017 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0012 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4032 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0013 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4010 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0014 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4007 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00136-0015 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3331-VS-4041 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Predecessors Pending |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.5
T-00136-0016 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4040 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00136-0017 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3331-VS-4004 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.5
T-00136-0018 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4037 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0019 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4024 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0020 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4023 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0021 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4029 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0022 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4026 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0023 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4033 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00136-0024 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4030 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0025 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4022 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0026 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4018 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0027 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4019 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0028 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3331-VS-4001 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0029 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4038 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00136-0030 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4013 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0031 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4025 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0032 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4014 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0033 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3334-VS-4027 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00136-0034 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4036 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0035 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4031 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0036 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4034 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00136-0037 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3331-VS-4002 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.5
T-00136-0038 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4016 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.5
T-00136-0039 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4009 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00136-0040 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3333-VS-4020 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00136-0041 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4006 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00136-0042 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4039 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00136-0043 | E3.T048 Variable Speed Controller Stage 3 | ELEC | 3332-VS-4011 | VS - VSD | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00137-0038 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4015 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0039 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4028 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00137-0040 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4005 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00137-0041 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4035 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00137-0042 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4008 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00137-0043 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3331-VS-4003 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T03:31:47.8930000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-18T04:12:48.9400000
T-00137-0044 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4012 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0045 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4021 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0046 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4017 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0047 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4032 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0048 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4010 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0049 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4007 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00137-0050 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3331-VS-4041 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00137-0051 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4040 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0052 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3331-VS-4004 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5
T-00137-0053 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4037 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0054 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4024 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0055 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4023 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0056 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4029 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:07:47.2500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-24T01:41:26.6870000
T-00137-0057 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4026 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00137-0058 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4033 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0059 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4030 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:08:16.3970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-24T01:45:13.1930000
T-00137-0060 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4022 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0061 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4018 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0062 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4019 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0063 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3331-VS-4001 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-27T00:34:32.2670000
T-00137-0064 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4038 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0065 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4013 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0066 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4025 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0067 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4014 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0068 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3334-VS-4027 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T03:59:41.6470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-24T03:38:18.3030000
T-00137-0069 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4036 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0070 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4031 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0071 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4034 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00137-0072 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3331-VS-4002 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:16:09.2470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-15T07:43:35.5400000
T-00137-0073 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4016 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0074 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4009 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00137-0075 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3333-VS-4020 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00137-0076 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4006 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00137-0077 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4039 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00137-0078 | E2.T048B Variable Speed Controller Stage 2B | ELEC | 3332-VS-4011 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00138-0017 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-OP-4002 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T13:57:12.8470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T05:37:48.0000000 |  | 2020-12-17T07:39:02.4030000
T-00138-0018 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-OP-4001 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T22:07:50.0670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-11T05:32:17.0000000 |  | 2020-12-11T05:50:06.6700000
T-00138-0019 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4001 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:08:36.7900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T20:47:49.0000000 |  | 2020-12-13T21:14:59.3970000
T-00138-0020 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4003 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:09:05.1430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T20:54:03.0000000 |  | 2020-12-13T21:15:38.9530000
T-00138-0021 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4016 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0022 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4010 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-18T07:10:45.6230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:15:57.0000000 |  | 2020-12-17T19:27:17.6370000
T-00138-0023 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4004 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:42:15.6000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T22:47:01.8430000 |  | 2020-12-13T21:16:21.6270000
T-00138-0024 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4012 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:43:40.8000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:20:42.0000000 |  | 2020-12-13T21:16:41.8630000
T-00138-0025 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4008 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:51:37.4600000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:12:37.0000000 |  | 2020-12-13T21:17:00.4370000
T-00138-0026 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4007 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:51:59.9270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:10:57.0000000 |  | 2020-12-13T21:17:19.2700000
T-00138-0027 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4006 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:52:26.3270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:08:42.0000000 |  | 2020-12-13T21:17:43.1900000
T-00138-0028 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4002 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:52:58.6200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T20:56:39.0000000 |  | 2020-12-13T21:18:05.3930000
T-00138-0029 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4005 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-18T07:11:08.4630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:05:25.0000000 |  | 2020-12-17T19:27:41.5900000
T-00138-0030 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4011 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:53:28.5570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:18:23.0000000 |  | 2020-12-13T21:19:19.9970000
T-00138-0031 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4009 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:53:53.9670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:14:49.0000000 |  | 2020-12-13T21:19:45.8800000
T-00138-0032 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4013 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-15T22:54:19.3670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-21T21:25:47.0000000 |  | 2020-12-13T21:20:09.7000000
T-00138-0033 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4015 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0034 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3338-XE-4014 | XE - DCS Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0035 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4007 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:10:37.4570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T01:55:45.4670000 |  | 2021-02-20T02:44:46.1570000
T-00138-0036 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4042 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:22:02.5530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T02:07:38.6670000 |  | 2021-04-15T03:41:24.6170000
T-00138-0037 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4084 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0038 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4048 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:42:03.0830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-09T05:45:24.0200000 |  | 2021-03-09T22:31:13.6270000
T-00138-0039 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4054 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-25T05:51:08.9470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-23T22:46:42.2630000 |  | 2021-03-24T18:37:24.9130000
T-00138-0040 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4055 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0041 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4051 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-25T02:17:21.3830000 |  | 2021-04-26T06:38:59.0900000
T-00138-0042 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4072 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0043 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4024 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:35:25.0830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:26:35.6330000 |  | 2021-02-18T01:45:50.0870000
T-00138-0044 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4026 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:28:31.3900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:55:04.2430000 |  | 2021-04-13T07:01:22.2370000
T-00138-0045 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4040 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T03:57:05.1430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T06:44:17.9700000 |  | 2021-04-17T07:09:39.6170000
T-00138-0046 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4093 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0047 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4094 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0048 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4064 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:42:35.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-09T05:49:09.3570000 |  | 2021-03-09T22:54:31.2900000
T-00138-0049 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4003 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T22:19:36.6000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-17T21:18:01.9400000 |  | 2021-02-17T21:44:46.1000000
T-00138-0050 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4032 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0051 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4035 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:43:33.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-09T06:12:39.4700000 |  | 2021-03-09T22:57:34.8600000
T-00138-0052 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4036 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:44:13.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-09T06:24:46.0770000 |  | 2021-03-09T22:58:03.9100000
T-00138-0053 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4092 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:51:19.9570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-20T06:21:28.4970000 |  | 2021-04-20T07:06:26.3570000
T-00138-0054 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4031 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-10T00:45:15.7070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-09T05:40:02.8200000 |  | 2021-03-09T22:59:04.8570000
T-00138-0055 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4091 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:24:53.9570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T06:43:20.4100000 |  | 2021-01-24T19:24:57.1270000
T-00138-0056 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4083 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0057 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4025 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:36:17.9970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:09:54.0300000 |  | 2021-02-18T01:46:25.0600000
T-00138-0058 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4073 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0059 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4002 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T22:37:42.7270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:15:30.2970000 |  | 2021-02-20T06:28:48.4600000
T-00138-0060 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4021 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-25T05:51:47.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-24T06:06:48.6430000 |  | 2021-03-24T18:37:57.1930000
T-00138-0061 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4006 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:11:41.1200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T01:47:23.4800000 |  | 2021-02-20T02:28:18.8370000
T-00138-0062 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4043 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:27:11.4770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T07:08:58.4870000 |  | 2021-04-20T07:13:00.3900000
T-00138-0063 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4050 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-21T07:58:30.6700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T07:07:37.7930000 |  | 2021-04-21T07:25:37.5870000
T-00138-0064 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4061 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0065 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4010 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:51:39.2200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T06:55:05.3730000 |  | 2021-01-11T07:00:46.0370000
T-00138-0066 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4046 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T04:04:59.7970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T05:35:53.1630000 |  | 2021-04-16T06:12:46.3670000
T-00138-0067 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4039 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:22:26.7270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T02:09:09.9570000 |  | 2021-04-15T03:41:03.0630000
T-00138-0068 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4022 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-25T05:52:33.6230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-24T06:04:42.7000000 |  | 2021-03-24T18:38:29.1670000
T-00138-0069 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4047 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:43:05.2100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-09T05:43:00.2730000 |  | 2021-03-09T22:57:07.9900000
T-00138-0070 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4029 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:44:58.2570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T01:46:05.4770000 |  | 2021-03-07T03:44:32.8970000
T-00138-0071 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4071 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0072 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4001 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T13:56:03.2300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-10T06:56:49.4430000 |  | 2021-02-11T04:50:24.8270000
T-00138-0073 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4005 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:15:02.3270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T01:46:32.5470000 |  | 2021-02-20T02:14:43.1730000
T-00138-0074 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4081 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0075 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4082 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0076 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4049 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-10T00:44:46.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-09T06:14:58.3270000 |  | 2021-03-09T22:58:29.6300000
T-00138-0077 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4038 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00138-0078 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4009 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:16:13.3770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T02:26:06.6800000 |  | 2021-02-20T02:45:03.0530000
T-00138-0079 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4028 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T20:21:46.0630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T01:50:42.4730000 |  | 2021-03-07T06:00:39.0630000
T-00138-0080 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4033 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-01T06:20:06.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T02:56:42.2000000 |  | 2021-03-01T04:22:37.0730000
T-00138-0081 | PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4004 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T22:38:22.3170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:16:41.4170000 |  | 2021-02-20T06:29:07.0170000
T-00138-0082 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4571 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-22T09:22:16.2870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-21T22:36:27.6800000 |  | 2021-02-21T22:40:44.5400000
T-00138-0083 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4546 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-10T00:45:59.3800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-09T06:32:51.1000000 |  | 2021-03-09T22:59:22.6570000
T-00138-0084 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4562 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-12T09:15:21.0300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T05:55:50.4870000 |  | 2021-02-11T21:43:37.7830000
T-00138-0085 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4544 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T22:33:22.9970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:14:53.1370000 |  | 2021-03-07T06:15:56.4800000
T-00138-0086 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4539 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-23T08:49:23.3970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-23T06:57:24.0470000 |  | 2021-02-23T07:15:37.4930000
T-00138-0087 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4556 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-23T08:51:30.7170000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-23T07:02:09.5230000 |  | 2021-02-23T07:17:29.6730000
T-00138-0088 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4532 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:05:08.2430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T06:46:03.4900000 |  | 2021-04-22T07:14:54.1730000
T-00138-0089 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4531 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:43:50.1000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T20:18:30.3770000 |  | 2021-04-02T00:37:04.4570000
T-00138-0090 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4529 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:44:26.7300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T20:37:57.3170000 |  | 2021-04-02T00:37:35.9870000
T-00138-0091 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4552 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-23T08:52:12.0600000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-23T07:03:59.2370000 |  | 2021-02-23T07:17:59.3830000
T-00138-0092 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4573 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-10T05:25:32.8330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-09T06:42:39.9900000 |  | 2021-02-09T06:46:25.9430000
T-00138-0093 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4521 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:08:02.7570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T21:36:48.4070000 |  | 2021-02-11T21:38:14.3500000
T-00138-0094 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4540 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T07:58:53.6770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T07:17:23.3900000 |  | 2021-04-21T07:26:30.2230000
T-00138-0095 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4067 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-20T03:40:43.2570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T05:55:20.3930000 |  | 2021-04-18T22:24:23.4500000
T-00138-0096 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4557 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T06:02:34.2170000 |  | 2021-04-27T07:20:29.1970000
T-00138-0097 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4572 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-10T05:26:56.4900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-09T06:39:52.1870000 |  | 2021-02-09T06:46:52.2430000
T-00138-0098 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4561 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-12T09:15:49.5970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T05:49:47.3400000 |  | 2021-02-11T21:44:04.8070000
T-00138-0099 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4559 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:29:51.5870000 |  | 2021-04-27T07:20:54.2070000
T-00138-0100 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4545 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:13:43.4470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T06:59:38.3330000 |  | 2021-03-27T22:10:18.6900000
T-00138-0101 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4534 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-20T22:23:42.5800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T06:43:12.1270000 |  | 2021-04-20T07:06:01.3270000
T-00138-0102 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4536 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0103 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4533 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T01:44:59.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T20:30:03.5530000 |  | 2021-04-02T00:37:58.8130000
T-00138-0104 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4554 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:32:35.2370000 |  | 2021-04-27T07:21:28.8870000
T-00138-0105 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4547 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-03T03:16:01.3670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:40:26.6530000 |  | 2021-04-03T00:42:12.3230000
T-00138-0106 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4542 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T02:27:56.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:39:21.6870000 |  | 2021-02-21T00:54:20.0530000
T-00138-0107 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4526 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:51:56.8100000 |  | 2021-04-27T07:21:53.1070000
T-00138-0108 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4555 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:27:01.6930000 |  | 2021-04-27T07:22:13.2300000
T-00138-0109 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4065 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T09:36:19.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T14:53:12.5270000 |  | 2021-02-21T19:49:31.5830000
T-00138-0110 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4066 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T09:40:15.2070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T15:07:11.6300000 |  | 2021-02-21T19:53:56.4630000
T-00138-0111 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4523 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T06:04:24.3270000 |  | 2021-04-27T07:22:33.0130000
T-00138-0112 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4563 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0113 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4558 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:57:57.9270000 |  | 2021-04-27T07:22:55.8430000
T-00138-0114 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4553 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:56:11.6470000 |  | 2021-04-27T07:23:19.2800000
T-00138-0115 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4535 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-22T07:26:54.8970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T06:42:30.6800000 |  | 2021-04-22T07:12:50.2430000
T-00138-0116 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4541 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:03:37.2170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T07:25:06.7300000 |  | 2021-04-21T07:42:17.8770000
T-00138-0117 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4548 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:17:03.0470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:43:55.5330000 |  | 2021-04-03T00:43:48.7100000
T-00138-0118 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4537 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-02-23T08:50:06.0770000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-23T06:58:56.4600000 |  | 2021-02-23T07:15:59.6000000
T-00138-0119 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4524 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0120 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4525 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T05:54:14.3030000 |  | 2021-04-27T07:24:03.9230000
T-00138-0121 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4551 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Closed | 2021-02-11T14:10:51.1970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-11T00:31:29.8070000 |  | 2021-02-11T05:10:00.3700000
T-00138-0122 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4530 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:58:56.4770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T02:43:28.6330000 |  | 2021-03-01T04:38:50.1870000
T-00138-0123 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-OP-4560 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-12T09:16:15.6570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T05:42:11.0970000 |  | 2021-02-11T22:08:08.1100000
T-00138-0124 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4543 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T02:28:39.5000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:40:39.3270000 |  | 2021-02-21T00:55:07.1970000
T-00138-0125 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4574 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-20T21:00:03.0300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:59:45.4670000 |  | 2021-02-20T19:13:38.6570000
T-00138-0126 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4538 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-02-23T08:50:54.4300000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-23T07:00:21.7170000 |  | 2021-02-23T07:17:02.4330000
T-00138-0127 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4522 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:08:31.6300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T22:14:14.5170000 |  | 2021-02-11T23:01:04.3300000
T-00138-0128 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4528 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-27T06:11:19.9300000 |  | 2021-04-27T07:24:27.3570000
T-00138-0129 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4008 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T22:39:10.9670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T07:04:40.0170000 |  | 2021-02-20T19:14:00.5900000
T-00138-0130 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4068 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T04:33:19.1300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T05:55:27.2700000 |  | 2021-04-17T05:59:54.4170000
T-00138-0131 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4527 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:09:01.8870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T22:02:53.3270000 |  | 2021-02-11T22:09:44.0570000
T-00138-0132 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4035 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:52:04.7600000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T02:54:30.7000000 |  | 2021-03-01T04:39:34.9830000
T-00138-0133 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4087 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0134 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4030 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-05T04:30:22.1370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T02:30:54.2600000 |  | 2021-03-05T04:22:58.8470000
T-00138-0135 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4086 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0136 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4078 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0137 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-MB-4092 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:54:51.9000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T02:45:50.9330000 |  | 2021-03-01T04:40:05.1330000
T-00138-0138 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4001 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:51:17.5430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T01:32:01.7870000 |  | 2021-03-04T02:14:24.2530000
T-00138-0139 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4002 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:51:44.4400000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T01:36:41.2130000 |  | 2021-03-04T02:14:55.5300000
T-00138-0140 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4022 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0141 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-MB-4071 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-04 - Marshalling boxes Molybdenum Concentrate Handling | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0142 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4080 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0143 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4031 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:52:20.2200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-03T05:48:32.6500000 |  | 2021-03-04T02:15:29.8630000
T-00138-0144 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4082 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-05T04:31:17.6200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T02:49:20.1170000 |  | 2021-03-05T04:23:29.1930000
T-00138-0145 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4028 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0146 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4085 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0147 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4075 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0148 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4084 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:52:57.2570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T02:52:53.1230000 |  | 2021-03-02T05:14:05.3970000
T-00138-0149 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4023 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0150 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4033 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Completed |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-27T06:18:03.6970000 |  | 2021-04-27T07:27:03.3170000
T-00138-0151 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4037 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-05T04:31:52.8130000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T02:23:07.7230000 |  | 2021-03-05T04:23:52.5700000
T-00138-0152 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3334-MB-4081 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0153 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-MB-4091 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:54:17.0270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T02:47:41.5400000 |  | 2021-03-02T05:15:21.5530000
T-00138-0154 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4022 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:54:56.3870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T01:58:03.7270000 |  | 2021-03-04T02:15:56.7900000
T-00138-0155 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4081 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-03-05T04:29:45.9570000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-04T02:45:22.3370000 |  | 2021-03-05T04:24:13.4300000
T-00138-0156 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4034 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0157 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-MB-4093 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0158 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4021 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0159 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4060 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0160 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-MB-4020 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0161 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4079 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0162 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4021 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:55:25.3270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T01:53:28.4630000 |  | 2021-03-04T02:16:20.9030000
T-00138-0163 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4026 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:55:54.7770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-04T02:07:11.3370000 |  | 2021-03-04T02:16:38.5200000
T-00138-0164 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4117 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T07:48:09.6070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T05:02:03.2570000 |  | 2021-04-10T06:41:10.4670000
T-00138-0165 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4110 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T20:27:42.8370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T07:02:06.7600000 |  | 2021-03-07T07:04:51.9300000
T-00138-0166 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4108 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T20:28:29.7500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:51:30.5930000 |  | 2021-03-07T07:05:15.7500000
T-00138-0167 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4102 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T00:35:11.8870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:19:47.8970000 |  | 2021-02-21T00:30:34.5800000
T-00138-0168 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4105 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T02:29:31.1070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:30:45.9570000 |  | 2021-02-21T00:34:00.6970000
T-00138-0169 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4103 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T00:36:09.2200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:23:37.9400000 |  | 2021-02-21T00:31:43.2800000
T-00138-0170 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4112 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:54:05.7570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:15:13.9430000 |  | 2021-04-10T02:26:02.4230000
T-00138-0171 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4111 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:54:40.2770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:06:49.7970000 |  | 2021-04-10T02:27:26.7900000
T-00138-0172 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4114 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-12T05:19:05.3300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T01:24:06.5230000 |  | 2021-04-12T01:23:31.4230000
T-00138-0173 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4107 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T20:29:57.0600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:49:49.1530000 |  | 2021-03-07T07:05:37.8770000
T-00138-0174 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4118 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T07:48:31.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T06:46:06.1730000 |  | 2021-04-10T06:47:22.4230000
T-00138-0175 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4109 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T20:30:33.0530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:53:06.0530000 |  | 2021-03-07T07:06:33.5930000
T-00138-0176 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4113 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:55:04.0530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:13:35.4630000 |  | 2021-04-10T02:29:10.8070000
T-00138-0177 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4101 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T00:37:14.7500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:17:17.0670000 |  | 2021-02-21T00:32:05.4670000
T-00138-0178 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4104 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T02:30:17.4470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:26:23.0270000 |  | 2021-02-21T00:32:29.6970000
T-00138-0179 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4076 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0181 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4234 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-03-29T05:08:27.4070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-28T23:33:13.9700000 |  | 2021-03-29T00:45:29.0430000
T-00138-0182 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4205 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-30T06:12:06.8000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-30T00:59:15.8330000 |  | 2021-03-30T01:02:50.9500000
T-00138-0183 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4207 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:30:49.1270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:19:46.0470000 |  | 2021-04-13T06:25:04.2770000
T-00138-0186 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4203 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0187 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4201 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0188 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4228 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T04:38:13.6800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-19T05:45:41.2970000 |  | 2021-04-19T06:30:08.0230000
T-00138-0190 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4235 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:35:43.6130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:24:24.2070000 |  | 2021-04-13T06:26:32.6070000
T-00138-0191 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4224 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0192 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4206 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T21:48:48.1770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-25T02:33:50.0900000 |  | 2021-04-25T07:21:11.4830000
T-00138-0193 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4225 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T07:05:22.1970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-20T05:38:07.2000000 |  | 2021-04-20T06:10:00.2070000
T-00138-0194 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4205 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:37:18.2530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T05:57:17.0300000 |  | 2021-04-13T06:18:53.0670000
T-00138-0195 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4203 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0196 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4237 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:37:45.1270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T01:31:57.1130000 |  | 2021-04-13T06:19:29.0070000
T-00138-0197 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4227 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0198 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4206 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:38:31.9670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:33:43.8170000 |  | 2021-04-13T06:41:47.6800000
T-00138-0199 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3331-OP-4201 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-22T15:39:38.0570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T02:37:11.2530000 |  | 2021-02-21T06:33:33.3730000
T-00138-0200 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4222 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0201 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4231 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:07:41.7430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T23:33:53.4730000 |  | 2021-03-29T00:42:43.1600000
T-00138-0202 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4204 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0203 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4221 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0204 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4202 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00138-0205 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4236 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:38:53.0670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:22:15.7600000 |  | 2021-04-13T06:26:53.4070000
T-00138-0206 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4223 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00138-0207 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4226 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T12:46:05.5500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T00:43:00.3470000 |  | 2021-02-21T20:00:18.8100000
T-00138-0208 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3335-OP-4204 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00138-0209 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4230 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T04:39:03.9600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-19T05:11:55.4270000 |  | 2021-04-19T06:30:28.8330000
T-00138-0210 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4046 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:21:28.0130000 |  |  | 0.25 | 2021-04-19T01:37:45.9200000 |  | 2021-04-19T03:46:12.6870000
T-00138-0211 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-MB-4086 | MB - Marshalling Box | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:22:14.9370000 |  |  | 0.25 | 2021-04-18T05:52:22.1430000 |  | 2021-04-18T22:23:09.2670000
T-00138-0212 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4069 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  |  |  | 0.25
T-00138-0213 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4056 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.25
T-00138-0214 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4057 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Started |  |  |  | 0.25
T-00138-0215 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3332-OP-4233 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00138-0216 | E1.T050 PCS / Marshalling Cabinet Stage 1 | ELEC | 3333-OP-4210 | OP - Operation Panel | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25
T-00139-0068 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4001 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0069 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4003 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0070 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4016 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0071 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4010 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0072 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4004 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0073 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4012 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0074 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4008 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0075 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4007 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0076 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4006 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0077 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4002 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0078 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4005 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0079 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4011 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0080 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4009 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0081 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4013 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0082 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4015 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0083 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3338-XE-4014 | XE - DCS Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0180 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4035 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0181 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4087 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0182 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4030 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0183 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4086 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0184 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4078 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0185 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3335-MB-4092 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0186 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4001 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0187 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4002 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Started |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0188 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4022 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0189 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-MB-4071 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-04 - Marshalling boxes Molybdenum Concentrate Handling | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0190 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4080 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00139-0191 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4031 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0192 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4082 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0193 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4028 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0194 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4085 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0195 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4075 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0196 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4084 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0197 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4023 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0198 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4033 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0199 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4037 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0200 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-MB-4081 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0201 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3335-MB-4091 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0202 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4022 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0203 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4081 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00139-0204 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4034 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0205 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3335-MB-4093 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0206 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4021 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0207 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4060 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00139-0208 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-MB-4020 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0209 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4079 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0210 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4021 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0211 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4026 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0227 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-MB-4076 | MB - Marshalling Box |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00139-0258 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4001 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T04:32:01.1330000 |  |  | 0.5 | 2021-04-12T02:45:26.0000000 |  | 2021-04-12T02:49:37.1330000
T-00139-0259 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4007 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:45:46.0800000 |  |  | 0.5 | 2021-04-11T22:17:04.0000000 |  | 2021-04-11T22:44:39.0870000
T-00139-0260 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4003 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:32:29.8730000 |  |  | 0.5 | 2021-04-12T01:51:27.0000000 |  | 2021-04-12T02:32:42.9400000
T-00139-0261 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4002 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T04:33:11.0970000 |  |  | 0.5 | 2021-04-12T02:42:46.5600000 |  | 2021-04-12T02:47:58.1870000
T-00139-0262 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4006 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:54:31.4370000 |  |  | 0.5 | 2021-04-11T22:13:15.0000000 |  | 2021-04-11T22:48:09.8400000
T-00139-0263 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4005 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:55:00.0230000 |  |  | 0.5 | 2021-04-11T22:14:48.0000000 |  | 2021-04-11T22:47:29.0830000
T-00139-0264 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4009 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:55:25.7830000 |  |  | 0.5 | 2021-04-11T22:30:51.0000000 |  | 2021-04-11T22:48:58.9830000
T-00139-0265 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4004 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-15T21:10:43.5230000 |  |  | 0.5 | 2021-04-15T01:47:58.1300000 |  | 2021-04-15T02:25:48.9770000
T-00139-0268 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4042 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0269 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4084 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0270 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4048 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0271 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4054 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0272 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4055 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0273 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4051 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00139-0274 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4072 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  |  |  | 0.5
T-00139-0275 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4024 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0276 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4026 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0277 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4040 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0278 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4064 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0279 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4032 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  |  |  | 0.5
T-00139-0280 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4035 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0281 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4036 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0282 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4031 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0283 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4083 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0284 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4025 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0285 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4073 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  |  |  | 0.5
T-00139-0286 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4021 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0287 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4043 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0288 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4050 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00139-0289 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4061 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  |  |  | 0.5
T-00139-0290 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4010 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Created |  |  |  | 0.5
T-00139-0291 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4046 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0292 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4039 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0293 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4022 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0294 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4047 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0295 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4029 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0296 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4071 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  |  |  | 0.5
T-00139-0297 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4081 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0298 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4082 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0299 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4049 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0300 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4038 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  |  |  | 0.5
T-00139-0301 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4028 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0302 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4033 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0303 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4546 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0304 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4544 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0305 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4539 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0306 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4532 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0307 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4531 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0308 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4529 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0309 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4521 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0310 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4540 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00139-0311 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4067 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0312 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4545 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0313 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4534 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0314 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4536 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0315 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4533 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0316 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4547 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0317 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4542 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0318 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4526 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0319 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4065 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0320 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4066 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0321 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4523 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0322 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4535 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0323 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4541 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00139-0324 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4548 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Started |  |  |  | 0.5
T-00139-0325 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4537 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0326 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4524 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  |  |  | 0.5
T-00139-0327 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4525 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0328 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4530 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0329 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4543 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0330 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4538 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0331 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4522 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0332 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4528 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00139-0333 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4008 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-25T21:53:55.9330000 |  |  | 0.5 | 2021-04-25T06:39:35.0000000 |  | 2021-04-25T21:08:24.5730000
T-00139-0334 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4068 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0335 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4527 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00139-0336 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4117 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Created |  |  |  | 0.5
T-00139-0337 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4110 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0338 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4108 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0339 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4102 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0340 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4105 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0341 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4103 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0342 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4112 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0343 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4111 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0344 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4114 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0345 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4107 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0346 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4118 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Created |  |  |  | 0.5
T-00139-0347 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4109 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0348 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4113 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0349 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4101 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0350 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4104 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0352 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4234 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00139-0353 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4205 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00139-0354 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4207 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Created |  |  |  | 0.5
T-00139-0356 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4201 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  |  |  | 0.5
T-00139-0357 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4228 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00139-0359 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4235 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0360 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4224 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0361 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4206 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00139-0362 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4225 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0363 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4205 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Created |  |  |  | 0.5
T-00139-0364 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4203 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  |  |  | 0.5
T-00139-0365 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4237 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0366 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4227 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0367 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4206 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Created |  |  |  | 0.5
T-00139-0368 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3331-OP-4201 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  |  |  | 0.5
T-00139-0369 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4222 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0370 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4231 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0371 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4204 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  |  |  | 0.5
T-00139-0372 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4221 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0373 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4202 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  |  |  | 0.5
T-00139-0374 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4236 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0375 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4223 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0376 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4226 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0377 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4230 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00139-0378 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4069 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  |  |  | 0.5
T-00139-0379 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4202 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  |  |  | 0.5
T-00139-0380 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3334-OP-4201 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T05:44:37.7130000 |  |  | 0.5 | 2021-04-24T03:14:07.0000000 |  | 2021-04-24T04:56:55.8370000
T-00139-0381 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4056 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0382 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4057 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.5
T-00139-0383 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3332-OP-4233 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  |  |  | 0.5
T-00139-0384 | E2.T050 PCS / Marshalling Cabinet Stage 2 | ELEC | 3333-OP-4210 | OP - Operation Panel |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  |  |  | 0.5
T-00140-0003 | UPS Stage 1 | ELEC | 3338-JX-4010 | MC - MOTOR CONTROL CENTRE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00140-0004 | UPS Stage 1 | ELEC | 3338-JX-4001 | JX - UPS | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-17T13:57:49.6800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T02:31:52.0000000 |  | 2020-12-17T07:14:13.8970000
T-00141-0003 | E2.T055A UPS Stage 2B | ELEC | 3338-JX-4010 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00141-0004 | E2.T055A UPS Stage 2B | ELEC | 3338-JX-4001 | JX - UPS |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:55:37.7270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-04-23T05:16:04.8770000 |  | 2021-04-23T05:21:54.1100000
T-00142-0003 | E2.T055A UPS Stage 2A | ELEC | 3338-JX-4010 | MC - MOTOR CONTROL CENTRE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 1
T-00142-0004 | UPS Stage 2A | ELEC | 3338-JX-4001 | JX - UPS |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:56:24.2270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 1 | 2021-04-23T05:46:18.8870000 |  | 2021-04-23T05:56:36.3500000
T-00143-0034 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0142 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-24T10:55:58.5830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T02:44:45.0670000 |  | 2021-02-24T06:45:25.1770000
T-00143-0037 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0441 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:53:46.9330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T03:52:18.0070000 |  | 2021-04-14T07:12:59.1870000
T-00143-0054 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-1061 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0066 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0166 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-24T10:56:26.2800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T02:45:26.2400000 |  | 2021-02-24T06:45:54.2130000
T-00143-0067 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0155 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0068 | I1.T003 Analytic Transmitter Stage 1 | INST | 3331-AIT-0085 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-22T05:09:29.6200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T04:47:04.5570000 |  | 2021-01-22T04:47:51.0070000
T-00143-0069 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0187 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T22:27:39.9300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-03T21:45:04.0670000 |  | 2021-04-03T22:16:10.5830000
T-00143-0070 | I1.T003 Analytic Transmitter Stage 1 | INST | 3335-AIT-0868 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-20T21:01:28.2230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:00:17.0030000 |  | 2021-02-20T06:03:53.9330000
T-00143-0071 | I1.T003 Analytic Transmitter Stage 1 | INST | 3331-AIT-0064 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0072 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0323 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0073 | I1.T003 Analytic Transmitter Stage 1 | INST | 3334-AIT-0694 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0074 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0577 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00143-0075 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0437 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0076 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0196 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-05T06:13:09.9300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-04T01:04:30.2970000 |  | 2021-04-05T04:23:21.3500000
T-00143-0077 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0135 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0078 | I1.T003 Analytic Transmitter Stage 1 | INST | 3331-AIT-0021 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0079 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0131 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0080 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0216 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0082 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0580 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00143-0083 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0491 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-13T07:39:23.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:37:19.3300000 |  | 2021-04-13T06:40:46.7030000
T-00143-0084 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0104 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-28T04:11:02.0070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:42:58.3100000 |  | 2021-02-27T20:20:28.6570000
T-00143-0085 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0110 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-27T04:08:48.1030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T00:19:29.7900000 |  | 2021-02-27T03:47:10.7930000
T-00143-0086 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0307 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T03:17:45.3900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T05:56:50.0570000 |  | 2021-04-03T00:44:25.5670000
T-00143-0087 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0672 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-27T08:34:36.5370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T05:01:39.4930000 |  | 2021-03-27T05:08:57.3600000
T-00143-0089 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0106 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T00:49:31.1600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T21:56:29.4470000 |  | 2021-02-18T23:43:43.2530000
T-00143-0090 | I1.T003 Analytic Transmitter Stage 1 | INST | 3331-AIT-0091 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0091 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0503 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00143-0092 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0462 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-25T21:46:36.0000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-25T05:02:34.2270000 |  | 2021-04-25T07:18:29.9770000
T-00143-0093 | I1.T003 Analytic Transmitter Stage 1 | INST | 3335-AIT-0854 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:26:22.3830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T03:45:15.6630000 |  | 2021-01-25T06:34:42.5370000
T-00143-0094 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0584 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Submitted |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T04:52:17.1830000
T-00143-0095 | I1.T003 Analytic Transmitter Stage 1 | INST | 3333-MT-2230 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00143-0096 | I1.T003 Analytic Transmitter Stage 1 | INST | 3332-AIT-0585 | AIT - ANALYSIS INDICATING TRANSMITTER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Submitted |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:10:39.0130000
T-00144-0066 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0142 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0067 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0166 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0068 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0155 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0069 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0441 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00144-0070 | I2.T003A Analytic Transmitter Stage 2A | INST | 3331-AIT-0085 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-04T02:59:50.7630000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-02T22:52:34.3200000 |  | 2021-04-04T01:36:57.5930000
T-00144-0071 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0187 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0072 | I2.T003A Analytic Transmitter Stage 2A | INST | 3335-AIT-0868 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-12T05:27:56.2530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-12T04:39:21.6230000 |  | 2021-04-12T04:44:07.8870000
T-00144-0073 | I2.T003A Analytic Transmitter Stage 2A | INST | 3331-AIT-0064 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0074 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0323 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0075 | I2.T003A Analytic Transmitter Stage 2A | INST | 3334-AIT-0694 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0076 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0577 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0077 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0437 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0078 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0196 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0079 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0135 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0080 | I2.T003A Analytic Transmitter Stage 2A | INST | 3331-AIT-0021 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0081 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0131 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0082 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0216 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0084 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0580 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0085 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0491 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00144-0086 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-1061 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0087 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0104 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0088 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0110 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0089 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0307 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00144-0090 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0672 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0092 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0106 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00144-0093 | I2.T003A Analytic Transmitter Stage 2A | INST | 3331-AIT-0091 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0094 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0503 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0095 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0462 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00144-0096 | I2.T003A Analytic Transmitter Stage 2A | INST | 3335-AIT-0854 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-26T04:22:24.9670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-21T01:48:20.9730000 |  | 2021-04-26T02:03:09.2170000
T-00144-0097 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0584 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0098 | I2.T003A Analytic Transmitter Stage 2A | INST | 3333-MT-2230 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00144-0099 | I2.T003A Analytic Transmitter Stage 2A | INST | 3332-AIT-0585 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0066 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0142 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0067 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0166 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0068 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0155 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0069 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0441 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00145-0070 | I2.T003B Analytic Transmitter Stage 2B | INST | 3331-AIT-0085 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:43:50.2530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-04T05:26:58.0900000
T-00145-0071 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0187 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0072 | I2.T003B Analytic Transmitter Stage 2B | INST | 3335-AIT-0868 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-09T03:45:07.2700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-04T06:47:55.5830000
T-00145-0073 | I2.T003B Analytic Transmitter Stage 2B | INST | 3331-AIT-0064 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0074 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0323 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0075 | I2.T003B Analytic Transmitter Stage 2B | INST | 3334-AIT-0694 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0076 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0577 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0077 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0437 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0078 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0196 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0079 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0135 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0080 | I2.T003B Analytic Transmitter Stage 2B | INST | 3331-AIT-0021 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0081 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0131 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0082 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0216 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0084 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0580 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0085 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0491 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00145-0086 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-1061 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0087 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0104 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0088 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0110 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0089 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0307 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00145-0090 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0672 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0092 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0106 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00145-0093 | I2.T003B Analytic Transmitter Stage 2B | INST | 3331-AIT-0091 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0094 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0503 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0095 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0462 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00145-0096 | I2.T003B Analytic Transmitter Stage 2B | INST | 3335-AIT-0854 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-25T21:46:59.5970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-25T07:03:58.7500000
T-00145-0097 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0584 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0098 | I2.T003B Analytic Transmitter Stage 2B | INST | 3333-MT-2230 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00145-0099 | I2.T003B Analytic Transmitter Stage 2B | INST | 3332-AIT-0585 | AIT - ANALYSIS INDICATING TRANSMITTER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00146-0017 | I1.T007 Density Transmitter Stage 1 | INST | 3331-DIT-0032 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-10T05:28:26.6900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-09T00:01:09.2000000 |  | 2021-02-09T06:36:54.5800000
T-00146-0018 | I1.T007 Density Transmitter Stage 1 | INST | 3332-DIT-0126 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00146-0019 | I1.T007 Density Transmitter Stage 1 | INST | 3331-DIT-0056 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T21:26:17.5070000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:42:21.5830000 |  | 2021-04-24T07:16:24.4100000
T-00146-0020 | I1.T007 Density Transmitter Stage 1 | INST | 3332-DIT-0527 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-04T02:53:18.2430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T05:36:16.2570000 |  | 2021-03-04T02:12:26.1630000
T-00146-0021 | I1.T007 Density Transmitter Stage 1 | INST | 3332-DIT-0545 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:18:24.9500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T07:06:40.4870000 |  | 2021-04-24T07:16:56.6470000
T-00146-0022 | I1.T007 Density Transmitter Stage 1 | INST | 3331-DIT-0033 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-10T05:29:41.1870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-09T00:02:02.4170000 |  | 2021-02-09T06:37:33.5900000
T-00146-0023 | I1.T007 Density Transmitter Stage 1 | INST | 3332-DIT-1055 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00146-0024 | I1.T007 Density Transmitter Stage 1 | INST | 3331-DIT-0074 | DIT - Density Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-10T05:30:45.3530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-09T00:04:10.9170000 |  | 2021-02-09T06:52:40.4230000
T-00147-0017 | I2.T007A Density Transmitter Stage 2A | INST | 3331-DIT-0032 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0018 | I2.T007A Density Transmitter Stage 2A | INST | 3332-DIT-0126 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0019 | I2.T007A Density Transmitter Stage 2A | INST | 3331-DIT-0056 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0020 | I2.T007A Density Transmitter Stage 2A | INST | 3332-DIT-0527 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0021 | I2.T007A Density Transmitter Stage 2A | INST | 3332-DIT-0545 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0022 | I2.T007A Density Transmitter Stage 2A | INST | 3331-DIT-0033 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0023 | I2.T007A Density Transmitter Stage 2A | INST | 3332-DIT-1055 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00147-0024 | I2.T007A Density Transmitter Stage 2A | INST | 3331-DIT-0074 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0017 | I2.T007B Density Transmitter Stage 2B | INST | 3331-DIT-0032 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0018 | I2.T007B Density Transmitter Stage 2B | INST | 3332-DIT-0126 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0019 | I2.T007B Density Transmitter Stage 2B | INST | 3331-DIT-0056 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0020 | I2.T007B Density Transmitter Stage 2B | INST | 3332-DIT-0527 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0021 | I2.T007B Density Transmitter Stage 2B | INST | 3332-DIT-0545 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0022 | I2.T007B Density Transmitter Stage 2B | INST | 3331-DIT-0033 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0023 | I2.T007B Density Transmitter Stage 2B | INST | 3332-DIT-1055 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00148-0024 | I2.T007B Density Transmitter Stage 2B | INST | 3331-DIT-0074 | DIT - Density Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0017 | I3.T007 Density Transmitter Stage 3 | INST | 3331-DIT-0032 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0018 | I3.T007 Density Transmitter Stage 3 | INST | 3332-DIT-0126 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0019 | I3.T007 Density Transmitter Stage 3 | INST | 3331-DIT-0056 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0020 | I3.T007 Density Transmitter Stage 3 | INST | 3332-DIT-0527 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0021 | I3.T007 Density Transmitter Stage 3 | INST | 3332-DIT-0545 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0022 | I3.T007 Density Transmitter Stage 3 | INST | 3331-DIT-0033 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0023 | I3.T007 Density Transmitter Stage 3 | INST | 3332-DIT-1055 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00149-0024 | I3.T007 Density Transmitter Stage 3 | INST | 3331-DIT-0074 | DIT - Density Indicating Transmitter | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00150-1115 | I2.T009 Indicator Stage 2 | INST | 3333-LI-0671A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1137 | I2.T009 Indicator Stage 2 | INST | 3331-LI-0022A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-29T20:26:49.9830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-22T06:56:04.3330000 |  | 2021-01-22T21:26:44.2300000
T-00150-1151 | I2.T009 Indicator Stage 2 | INST | 3335-LI-0840A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-21T03:17:26.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:28:23.1900000 |  | 2021-04-21T01:28:51.6470000
T-00150-1155 | I2.T009 Indicator Stage 2 | INST | 3334-LI-0821A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1163 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0111A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00150-1182 | I2.T009 Indicator Stage 2 | INST | 3333-LI-0580A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1183 | I2.T009 Indicator Stage 2 | INST | 3334-LI-0693A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1204 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0470A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00150-1207 | I2.T009 Indicator Stage 2 | INST | 3335-LI-0870A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00150-1210 | I2.T009 Indicator Stage 2 | INST | 3334-LI-0740A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1230 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0458A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00150-1239 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0349A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00150-1257 | I2.T009 Indicator Stage 2 | INST | 3331-PI-0002 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:13:46.2570000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-26T03:36:30.2070000 |  | 2021-03-26T05:30:50.0500000
T-00150-1275 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0565A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1281 | I2.T009 Indicator Stage 2 | INST | 3333-LI-0661A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1298 | I2.T009 Indicator Stage 2 | INST | 3334-LI-0790A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1299 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0414A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00150-1305 | I2.T009 Indicator Stage 2 | INST | 3331-LI-0063A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:28:24.8870000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-05T00:46:59.9000000 |  | 2021-04-12T04:44:28.7270000
T-00150-1342 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0106A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00150-1345 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0555A | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1383 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1029 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1385 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1031 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1386 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1034 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1390 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1030 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1394 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1033 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1395 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1020 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1396 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1026 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1400 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1023 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1401 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1032 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1402 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1021 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1403 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1022 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1405 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1027 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1406 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1018 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1407 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1035 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1409 | I2.T009 Indicator Stage 2 | INST | 3334-FI-1028 | FI - FLOW INDICATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1413 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2224 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1414 | I2.T009 Indicator Stage 2 | INST | 3333-TG-2212 | TI - Temperature Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1415 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2228 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1419 | I2.T009 Indicator Stage 2 | INST | 3333-TG-2206 | TI - Temperature Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1420 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2223 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1422 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2229 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1423 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2210 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1424 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2235 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1432 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2203 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1433 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2201 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1435 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2204 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1439 | I2.T009 Indicator Stage 2 | INST | 3333-PG-2202 | PI - Pressure Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1440 | I2.T009 Indicator Stage 2 | INST | 3333-LG-2226 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1443 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0564 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1444 | I2.T009 Indicator Stage 2 | INST | 3333-LI-0661 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1445 | I2.T009 Indicator Stage 2 | INST | 3333-LG-2217 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1446 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0551 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1447 | I2.T009 Indicator Stage 2 | INST | 3333-LI-0671 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00150-1453 | I2.T009 Indicator Stage 2 | INST | 3332-LI-0436 | LI - Level Indicator |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1103 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0308 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-24T22:22:04.2100000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T20:26:52.5130000 |  | 2021-04-24T07:18:03.6970000
T-00151-1105 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0475 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:46:08.8430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T07:24:07.1970000 |  | 2021-04-20T07:40:13.8370000
T-00151-1111 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1115 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:47:22.9670000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T05:47:08.3070000 |  | 2021-04-11T06:08:36.2130000
T-00151-1115 | I1.T009 Indicator Stage 1 | INST | 3333-LI-0671A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1116 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1139 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1123 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0502 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-11T02:40:44.1730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T07:21:10.7370000 |  | 2021-04-11T00:59:45.7870000
T-00151-1127 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0314 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-24T02:59:52.7170000 | 2021-04-22T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T07:43:52.3270000 |  | 2021-04-23T07:51:01.7170000
T-00151-1131 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0302 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-24T22:22:58.3930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T21:13:33.8000000 |  | 2021-04-24T07:19:23.0300000
T-00151-1132 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1113 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1133 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0803 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1136 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0793 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1137 | I1.T009 Indicator Stage 1 | INST | 3331-LI-0022A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:26:11.9600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-09T06:14:20.2470000 |  | 2021-01-09T06:58:06.1800000
T-00151-1146 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0801 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1147 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1130 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1150 | I1.T009 Indicator Stage 1 | INST | 3335-LI-0840A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T10:52:29.3430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T21:12:16.0830000 |  | 2021-01-13T21:28:32.3670000
T-00151-1151 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0795 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1152 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0170 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:38:41.8670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T02:56:04.0200000 |  | 2021-02-18T04:29:19.8200000
T-00151-1154 | I1.T009 Indicator Stage 1 | INST | 3334-LI-0821A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1157 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0874 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1162 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0111A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T05:24:02.3100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T01:25:03.8470000 |  | 2021-02-21T05:06:51.0530000
T-00151-1163 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0147 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-09T03:53:16.4870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T06:06:50.5470000 |  | 2021-04-07T08:11:52.7000000
T-00151-1165 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0550 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1168 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0571 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1169 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1131 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1173 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1119 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1175 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1125 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-05T06:30:23.9870000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-04T02:49:44.7570000 |  | 2021-04-05T04:28:55.0870000
T-00151-1178 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1118 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:47:44.1370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T06:13:54.5070000 |  | 2021-04-11T06:24:41.1400000
T-00151-1179 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1142 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1180 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0570 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1181 | I1.T009 Indicator Stage 1 | INST | 3333-LI-0580A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1182 | I1.T009 Indicator Stage 1 | INST | 3334-LI-0693A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1186 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0789 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Completed |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-04-27T07:08:23.4730000 |  | 2021-04-27T07:16:00.0130000
T-00151-1187 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0819 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1190 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1116 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:48:06.4100000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T05:46:36.2070000 |  | 2021-04-11T06:09:28.0500000
T-00151-1192 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0742 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1195 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0805 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1198 | I1.T009 Indicator Stage 1 | INST | 3331-PI-0026 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T20:29:09.0270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T05:32:07.2930000 |  | 2021-02-07T07:06:29.5030000
T-00151-1202 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0470A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T04:39:28.2230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T04:47:28.3730000 |  | 2021-04-17T04:55:54.7070000
T-00151-1205 | I1.T009 Indicator Stage 1 | INST | 3335-LI-0870A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1207 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1123 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-05T06:40:28.9830000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-04T02:47:56.4670000 |  | 2021-04-05T04:29:21.7270000
T-00151-1208 | I1.T009 Indicator Stage 1 | INST | 3334-LI-0740A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1209 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0440 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T04:39:54.6570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T21:58:03.4700000 |  | 2021-04-16T03:54:53.2770000
T-00151-1210 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0558 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1212 | I1.T009 Indicator Stage 1 | INST | 3333-PI-0616 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1219 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0746 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1226 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0810 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1227 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0873 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1228 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0458A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:31:13.9470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T07:16:44.3070000 |  | 2021-04-20T07:21:00.8400000
T-00151-1230 | I1.T009 Indicator Stage 1 | INST | 3331-PI-0069 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T21:23:39.8630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-07T03:48:12.2470000 |  | 2021-02-07T04:37:17.8800000
T-00151-1231 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0799 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1235 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0744 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1237 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0349A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T04:48:31.6170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:19:27.9200000 |  | 2021-04-17T20:07:11.4370000
T-00151-1240 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0699 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1246 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1134 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1248 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1114 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:48:37.9700000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T05:47:54.8770000 |  | 2021-04-11T06:08:09.6730000
T-00151-1249 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0807 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1251 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1155 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1252 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0174 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:39:37.1630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T03:38:32.9500000 |  | 2021-02-18T04:30:52.4300000
T-00151-1254 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0822 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1255 | I1.T009 Indicator Stage 1 | INST | 3331-PI-0002 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T21:25:16.8930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-07T03:48:53.2770000 |  | 2021-02-07T04:39:11.0100000
T-00151-1258 | I1.T009 Indicator Stage 1 | INST | 3333-PI-0676 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1260 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0134 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:40:13.8930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T02:52:00.1130000 |  | 2021-02-18T04:32:18.4470000
T-00151-1264 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0748 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1272 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1129 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1273 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0565A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1277 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0843 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:30:31.1930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T05:39:06.4270000 |  | 2021-02-07T07:06:55.0730000
T-00151-1279 | I1.T009 Indicator Stage 1 | INST | 3333-LI-0661A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1280 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1117 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:49:05.4400000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T05:50:23.7530000 |  | 2021-04-11T06:10:01.6630000
T-00151-1281 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1122 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-05T06:40:59.7030000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-04T02:51:39.0270000 |  | 2021-04-05T04:29:49.3070000
T-00151-1286 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0750 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1287 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0460 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00151-1288 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0857 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-07T20:57:46.9170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-07T05:29:06.5770000 |  | 2021-02-07T07:07:55.7630000
T-00151-1295 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0809 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1296 | I1.T009 Indicator Stage 1 | INST | 3334-LI-0790A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1297 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0414A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T06:21:05.3630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T21:48:16.9130000 |  | 2021-03-04T02:10:32.3970000
T-00151-1303 | I1.T009 Indicator Stage 1 | INST | 3331-LI-0063A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:35:00.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-09T06:17:08.4070000 |  | 2021-01-09T06:58:26.8830000
T-00151-1304 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0501 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-11T02:41:11.1830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T07:18:05.3230000 |  | 2021-04-11T00:59:17.5800000
T-00151-1305 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0143 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:40:48.8370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T02:54:00.6270000 |  | 2021-02-18T04:33:23.2570000
T-00151-1316 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1120 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-06T23:48:01.9470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-04T02:39:46.8470000 |  | 2021-04-06T07:35:57.1770000
T-00151-1319 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1061 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00151-1324 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0172 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:41:30.3500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T03:40:48.7100000 |  | 2021-02-18T04:35:54.3700000
T-00151-1325 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1132 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1326 | I1.T009 Indicator Stage 1 | INST | 3333-PI-0628 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1330 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1112 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1335 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0797 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1336 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0559 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1338 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1133 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1341 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0106A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T02:10:59.9530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T22:07:24.2100000 |  | 2021-02-18T23:44:07.7230000
T-00151-1342 | I1.T009 Indicator Stage 1 | INST | 3331-PI-0053 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:25:56.6970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T02:23:08.3200000 |  | 2021-02-20T02:45:47.5270000
T-00151-1344 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0555A | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1345 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1121 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-11T06:49:29.4030000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-11T05:59:36.5570000 |  | 2021-04-11T06:10:37.9000000
T-00151-1354 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0698 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1357 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0844 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:32:05.2270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T05:34:37.7530000 |  | 2021-02-07T07:07:24.7700000
T-00151-1359 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1074 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1363 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0118 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-28T04:11:25.0470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T05:54:43.8800000 |  | 2021-02-27T20:21:09.2900000
T-00151-1367 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0319 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T02:41:37.6230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T00:58:51.8100000 |  | 2021-04-11T01:09:02.3470000
T-00151-1370 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0858 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-07T21:18:49.4870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-07T03:56:16.6070000 |  | 2021-02-07T04:36:49.4700000
T-00151-1372 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0837 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:32:53.2670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-07T03:44:12.3400000 |  | 2021-02-07T04:31:53.8470000
T-00151-1379 | I1.T009 Indicator Stage 1 | INST | 3331-PI-0049 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:26:37.3670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T02:49:06.8500000 |  | 2021-02-20T04:24:54.2870000
T-00151-1381 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1063 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00151-1382 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1029 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1383 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1161 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1384 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1031 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1385 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1034 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1386 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0192 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T21:34:28.8030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:08:22.3600000 |  | 2021-03-07T06:17:36.1570000
T-00151-1387 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1160 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1388 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1039 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-27T06:57:13.7400000 |  | 2021-04-27T07:17:58.9170000
T-00151-1389 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1030 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1390 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1201 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1391 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0188 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T21:35:03.2730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:05:07.6830000 |  | 2021-03-07T06:22:50.7470000
T-00151-1392 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0183 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T21:35:50.6730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:00:58.0530000 |  | 2021-03-07T06:02:40.9330000
T-00151-1393 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1033 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1394 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1020 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1395 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1026 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1396 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0197 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T21:36:42.1700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:11:28.6530000 |  | 2021-03-07T06:23:09.5930000
T-00151-1397 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1037 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-27T06:51:45.9630000 |  | 2021-04-27T07:18:24.4170000
T-00151-1398 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1031 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:23:03.3600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:51:08.7070000 |  | 2021-04-15T03:41:51.9370000
T-00151-1399 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1023 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1400 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1032 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1401 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1021 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1402 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1022 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1403 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1033 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:23:26.6700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:53:03.5200000 |  | 2021-04-15T03:45:33.8000000
T-00151-1404 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1027 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1405 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1018 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1406 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1035 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1407 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0624 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-25T05:53:06.4370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-23T22:42:50.8770000 |  | 2021-03-24T18:38:54.1370000
T-00151-1408 | I1.T009 Indicator Stage 1 | INST | 3334-FI-1028 | FI - FLOW INDICATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1410 | I1.T009 Indicator Stage 1 | INST | 3332-PI-1128 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1412 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2224 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1413 | I1.T009 Indicator Stage 1 | INST | 3333-TG-2212 | TI - Temperature Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1414 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2228 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1415 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0598 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1416 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2104 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1418 | I1.T009 Indicator Stage 1 | INST | 3333-TG-2206 | TI - Temperature Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1419 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2223 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1420 | I1.T009 Indicator Stage 1 | INST | 3333-PI-7826 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1421 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2229 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1422 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2210 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1423 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2235 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1425 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2109 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1426 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2135 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1427 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2167 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1428 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2163 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1429 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2159 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1430 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0591 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1431 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2203 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1432 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2201 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1433 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0592 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1434 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2204 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1435 | I1.T009 Indicator Stage 1 | INST | 3332-PI-0597 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1436 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2129 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1437 | I1.T009 Indicator Stage 1 | INST | 3333-PI-2136 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1438 | I1.T009 Indicator Stage 1 | INST | 3333-PG-2202 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1439 | I1.T009 Indicator Stage 1 | INST | 3333-LG-2226 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1442 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0564 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1443 | I1.T009 Indicator Stage 1 | INST | 3333-LI-0661 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1444 | I1.T009 Indicator Stage 1 | INST | 3333-LG-2217 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1445 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0551 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1446 | I1.T009 Indicator Stage 1 | INST | 3333-LI-0671 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00151-1447 | I1.T009 Indicator Stage 1 | INST | 3335-PI-2201 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1449 | I1.T009 Indicator Stage 1 | INST | 3335-PI-2212 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1450 | I1.T009 Indicator Stage 1 | INST | 3335-PI-2209 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1451 | I1.T009 Indicator Stage 1 | INST | 3334-PI-0757 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00151-1452 | I1.T009 Indicator Stage 1 | INST | 3332-LI-0436 | LI - Level Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:31:48.1570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T07:15:46.1170000 |  | 2021-04-20T07:21:34.9470000
T-00151-1453 | I1.T009 Indicator Stage 1 | INST | 3335-PI-2208 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1455 | I1.T009 Indicator Stage 1 | INST | 3335-PI-0877 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1456 | I1.T009 Indicator Stage 1 | INST | 3335-PI-2206 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00151-1459 | I1.T009 Indicator Stage 1 | INST | 3331-PI-1184 | PI - Pressure Indicator | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-03T05:34:26.3970000 |  |  | 0.25 | 2021-04-03T04:18:13.3700000 |  | 2021-04-03T05:01:29.4230000
T-00152-0012 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0169 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-08T21:49:33.6070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T00:50:47.6570000 |  | 2021-02-08T04:06:08.5730000
T-00152-0032 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-0034 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:44:17.0670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:17:45.3900000 |  | 2021-02-20T22:37:59.2170000
T-00152-0044 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-0022 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:53:17.2770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-08T05:47:13.0570000 |  | 2021-01-11T03:12:39.8430000
T-00152-0057 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-1110 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-05T05:31:08.5830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-05T02:58:57.0230000 |  | 2021-03-05T04:44:17.8470000
T-00152-0076 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0175 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:14:05.1030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T06:56:42.1770000 |  | 2021-03-28T07:06:15.6530000
T-00152-0077 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0315 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:55:28.8700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:32:58.7930000 |  | 2021-04-10T02:35:56.2070000
T-00152-0079 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0310 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:55:52.3670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:19:21.2000000 |  | 2021-04-10T02:31:18.7170000
T-00152-0080 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LT-0555 | LT - Level Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0081 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0141 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-08T21:50:22.8930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T00:38:18.1100000 |  | 2021-02-08T04:07:54.6630000
T-00152-0082 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0138 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-08T21:51:04.7770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T00:32:08.8470000 |  | 2021-02-08T04:09:00.5300000
T-00152-0083 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0508 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:18:39.3370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T02:48:41.2470000 |  | 2021-04-03T00:46:36.0570000
T-00152-0084 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-0821 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0085 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0480A | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T04:49:16.7370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T22:34:53.1800000 |  | 2021-04-16T03:55:21.9600000
T-00152-0086 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LT-0790 | LT - Level Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0087 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0111 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T05:25:41.0300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T01:33:16.4170000 |  | 2021-02-21T05:06:23.0330000
T-00152-0088 | I1.T010 Level Transmitter Stage 1 | INST | 3335-LIT-0840 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:27:33.5330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T05:10:08.5330000 |  | 2021-01-24T05:12:03.2570000
T-00152-0089 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-2101 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T05:46:50.2970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T05:43:52.3470000 |  | 2021-01-24T05:45:13.4430000
T-00152-0091 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0470 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T05:42:00.8170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T01:18:57.9000000 |  | 2021-04-17T04:07:31.0800000
T-00152-0092 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-0740 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0093 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-0039 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T09:55:05.7600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T06:57:23.7130000 |  | 2021-03-19T06:59:52.1130000
T-00152-0094 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LIT-0615 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0095 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0146 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-30T06:13:08.5030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-30T01:09:59.8570000 |  | 2021-03-30T05:21:36.6930000
T-00152-0096 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0458 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T06:44:52.6570000 |  | 2021-04-26T06:47:43.0200000
T-00152-0097 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0180 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-20T03:41:13.4130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T03:56:40.9830000 |  | 2021-04-19T04:02:12.0870000
T-00152-0098 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0200 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T01:29:58.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T04:34:58.1070000 |  | 2021-02-08T04:43:45.3170000
T-00152-0099 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0436 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:46:39.4500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T07:24:51.4730000 |  | 2021-04-20T07:40:34.9300000
T-00152-0100 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0349 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-02T01:56:42.4430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T05:52:38.8430000 |  | 2021-04-02T00:38:19.8370000
T-00152-0101 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0532 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0102 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0652B | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:26:41.0470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:53:58.7100000 |  | 2021-03-06T23:23:41.7230000
T-00152-0103 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0194 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T06:04:06.8870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T02:37:25.4470000 |  | 2021-02-08T04:18:58.5470000
T-00152-0105 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0106 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:11:38.1400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T22:02:29.8800000 |  | 2021-02-19T22:48:15.3670000
T-00152-0106 | I1.T010 Level Transmitter Stage 1 | INST | 3335-LIT-0850 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00152-0107 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0304 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T02:56:14.5500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:22:04.5070000 |  | 2021-04-10T02:31:50.5930000
T-00152-0109 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0185 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T06:04:40.0700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T01:52:02.7370000 |  | 2021-02-08T04:19:20.6570000
T-00152-0110 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0449A | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T05:42:26.1530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T00:39:39.3200000 |  | 2021-04-16T03:56:04.3600000
T-00152-0111 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0329 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-02T02:02:50.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T05:46:08.2270000 |  | 2021-04-02T00:38:39.2030000
T-00152-0112 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0190 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-09T06:05:07.3830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T02:14:08.0600000 |  | 2021-02-08T04:44:07.6700000
T-00152-0113 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0164 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-08T21:51:59.8770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T00:59:39.6730000 |  | 2021-02-08T04:10:37.6270000
T-00152-0114 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0320 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T03:00:05.4530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:06:10.2470000 |  | 2021-04-10T02:32:16.3130000
T-00152-0115 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0600 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T06:14:14.9270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:27:51.3200000 |  | 2021-02-28T06:06:27.0570000
T-00152-0116 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-0063 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:53:42.5500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-08T04:21:35.0930000 |  | 2021-01-11T03:15:26.7470000
T-00152-0117 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LT-0565 | LT - Level Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0118 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0160 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-08T21:52:37.8130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-08T01:05:23.4030000 |  | 2021-02-08T04:11:06.3270000
T-00152-0119 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0179 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:13:22.0930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-20T02:36:10.2470000 |  | 2021-02-20T02:46:07.1830000
T-00152-0120 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0494 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-09T06:30:54.7000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-08T00:39:42.4670000 |  | 2021-02-08T04:48:27.3570000
T-00152-0121 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-0693 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0122 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0452 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:04:25.3400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T05:53:56.4600000 |  | 2021-04-23T06:55:12.0230000
T-00152-0123 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0499 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T07:48:58.6870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T05:45:47.1470000 |  | 2021-04-10T06:44:50.5670000
T-00152-0124 | I1.T010 Level Transmitter Stage 1 | INST | 3335-LIT-0856 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-03-01T05:16:06.1000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:43:07.4270000 |  | 2021-02-20T22:45:35.2000000
T-00152-0125 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0652A | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:28:46.2530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:51:03.8670000 |  | 2021-03-06T23:24:00.3430000
T-00152-0126 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0173 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-30T06:13:56.5300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-30T01:12:06.1830000 |  | 2021-03-30T05:22:07.9130000
T-00152-0127 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-2109 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:49:28.7770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T17:35:12.0000000 |  | 2021-01-23T19:25:20.2170000
T-00152-0128 | I1.T010 Level Transmitter Stage 1 | INST | 3335-LIT-0870 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00152-0129 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LIT-0580 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0130 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LT-2236 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00152-0131 | I1.T010 Level Transmitter Stage 1 | INST | 3334-LIT-0790 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0132 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0414 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:20:52.0000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-02T04:20:07.3670000 |  | 2021-03-02T05:01:23.0800000
T-00152-0133 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LIT-2147 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-11T13:54:44.8070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-07T02:53:52.8670000 |  | 2021-02-11T04:47:08.7330000
T-00152-0134 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LT-2113 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T00:18:58.8330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T02:53:34.0530000 |  | 2021-01-22T04:35:48.7070000
T-00152-0135 | I1.T010 Level Transmitter Stage 1 | INST | 3331-LT-2103 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T00:22:09.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T05:18:57.8630000 |  | 2021-01-22T22:40:00.8770000
T-00152-0139 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LT-2336 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00152-0140 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LT-2102 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00152-0141 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0555 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T07:53:45.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T05:52:34.5730000 |  | 2021-04-19T06:30:48.2970000
T-00152-0142 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0581 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0143 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0582 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0144 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LIT-0671 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0145 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LIT-7821 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0146 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0565 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:54:47.0430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T06:18:31.6600000 |  | 2021-04-19T06:31:16.6430000
T-00152-0147 | I1.T010 Level Transmitter Stage 1 | INST | 3333-LIT-0661 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00152-0148 | I1.T010 Level Transmitter Stage 1 | INST | 3332-ZIT-2240 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:14:27.4230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T06:13:01.7830000 |  | 2021-03-28T06:25:34.5470000
T-00152-0150 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LT-2311 | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.25
T-00152-0153 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0449B | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T01:22:53.1870000 |  |  | 0.25 | 2021-04-16T00:42:38.0830000 |  | 2021-04-16T03:53:34.6830000
T-00152-0154 | I1.T010 Level Transmitter Stage 1 | INST | 3332-LIT-0480B | LIT - Level Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T01:23:26.5170000 |  |  | 0.25 | 2021-04-15T22:33:33.9770000 |  | 2021-04-16T03:53:54.9400000
T-00153-0120 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0175 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0121 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0315 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0123 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0310 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0124 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0169 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0125 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-0555 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0126 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0141 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0127 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0138 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0128 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0508 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0129 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-0821 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0130 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0480A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0131 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LT-0790 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0132 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0111 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0133 | I2.T010A Level Transmitter Stage 2A | INST | 3335-LIT-0840 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T05:43:11.4030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-18T04:00:54.9970000 |  | 2021-04-18T05:53:30.6370000
T-00153-0134 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-2101 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00153-0136 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0470 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0137 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-0740 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0138 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-0039 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Rejected |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-23T01:34:54.8530000
T-00153-0139 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LIT-0615 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0140 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0146 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0141 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0458 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0142 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0180 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0143 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0200 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0144 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-0034 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-15T21:16:36.6400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-11T07:19:27.8270000 |  | 2021-04-15T03:50:50.5300000
T-00153-0145 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0436 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0146 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0349 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0147 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0532 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0148 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0652B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0149 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0194 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0151 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0106 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0152 | I2.T010A Level Transmitter Stage 2A | INST | 3335-LIT-0850 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00153-0153 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0304 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0155 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0185 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0156 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-0022 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-21T03:18:33.8670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-11T07:29:13.9730000 |  | 2021-04-20T22:39:06.3770000
T-00153-0157 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0449A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0158 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0329 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0159 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0190 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0160 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0164 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0161 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0320 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0162 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0600 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0163 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-0063 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-13T00:55:09.4800000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-12T03:53:17.5070000 |  | 2021-04-12T03:54:25.8570000
T-00153-0164 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-0565 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0165 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0160 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0166 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0179 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0167 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0494 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0168 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-0693 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0169 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-1110 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T03:12:44.6770000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-20T23:15:01.4700000 |  | 2021-04-20T23:15:37.4900000
T-00153-0170 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0452 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0171 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0499 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0172 | I2.T010A Level Transmitter Stage 2A | INST | 3335-LIT-0856 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-25T13:13:25.1330000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-02-25T02:56:17.9600000 |  | 2021-02-25T05:03:39.7570000
T-00153-0173 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0652A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0174 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0173 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0175 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-2109 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00153-0176 | I2.T010A Level Transmitter Stage 2A | INST | 3335-LIT-0870 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00153-0177 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LIT-0580 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0178 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-2236 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0179 | I2.T010A Level Transmitter Stage 2A | INST | 3334-LIT-0790 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0180 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0414 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0181 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LIT-2147 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T03:34:58.5270000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-18T00:40:22.1700000 |  | 2021-04-18T01:26:08.0200000
T-00153-0182 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LT-2113 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T23:48:46.2700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-06T07:35:01.9700000 |  | 2021-04-12T04:52:17.4700000
T-00153-0183 | I2.T010A Level Transmitter Stage 2A | INST | 3331-LT-2103 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00153-0184 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-2211 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0185 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-2451 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00153-0186 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-2311 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0187 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LT-2336 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0188 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LT-2102 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00153-0189 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0555 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0190 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0581 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0191 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0582 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0192 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LIT-0671 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0193 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LIT-7821 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0194 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0565 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0195 | I2.T010A Level Transmitter Stage 2A | INST | 3333-LIT-0661 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00153-0196 | I2.T010A Level Transmitter Stage 2A | INST | 3332-ZIT-2240 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00153-0199 | I2.T010A Level Transmitter Stage 2A | INST | 3331-ZIT-2146 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:34:03.9970000 |  |  | 0.5 | 2021-04-06T07:45:42.6070000 |  | 2021-04-12T02:36:53.4870000
T-00153-0200 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0449B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00153-0201 | I2.T010A Level Transmitter Stage 2A | INST | 3332-LIT-0480B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00154-0077 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0175 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0078 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0315 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0080 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0310 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0081 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0169 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0082 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-0555 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0083 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0141 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0084 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0138 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0085 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0508 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0086 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-0821 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0087 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0480A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0088 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LT-0790 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0089 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0111 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0090 | I2.T010B Level Transmitter Stage 2B | INST | 3335-LIT-0840 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-26T04:22:53.9030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 |  |  | 2021-04-26T03:39:07.4270000
T-00154-0091 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-2101 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00154-0093 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0470 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0094 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-0740 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0095 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-0039 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-23T07:58:15.3270000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-23T01:31:08.4070000
T-00154-0096 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LIT-0615 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0097 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0146 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0098 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0458 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0099 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0180 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0100 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0200 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0101 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-0034 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:45:53.4870000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-07T00:34:04.9370000
T-00154-0102 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0436 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0103 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0349 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0104 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0532 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0105 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0652B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0106 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0194 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0108 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0106 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0109 | I2.T010B Level Transmitter Stage 2B | INST | 3335-LIT-0850 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00154-0110 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0304 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0112 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0185 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0113 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-0022 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-23T02:45:16.8670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-02-09T07:15:12.0570000 |  | 2021-02-22T04:02:22.8370000
T-00154-0114 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0449A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0115 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0329 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0116 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0190 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0117 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0164 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0118 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0320 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0119 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0600 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0120 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-0063 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:46:36.0970000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-05T05:25:55.4870000
T-00154-0121 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-0565 | LT - Level Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0122 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0160 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0123 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0179 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0124 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0494 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0125 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-0693 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0126 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-1110 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:32:18.5400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-10T23:44:20.8800000
T-00154-0127 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0452 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0128 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0499 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0129 | I2.T010B Level Transmitter Stage 2B | INST | 3335-LIT-0856 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-25T13:14:07.2070000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-02-25T03:36:50.2830000
T-00154-0130 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0652A | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0131 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0173 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0132 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-2109 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00154-0133 | I2.T010B Level Transmitter Stage 2B | INST | 3335-LIT-0870 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00154-0134 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LIT-0580 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0135 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-2236 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0136 | I2.T010B Level Transmitter Stage 2B | INST | 3334-LIT-0790 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0137 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0414 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0138 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LIT-2147 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T07:08:38.3530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-12T04:52:51.8970000
T-00154-0139 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LT-2113 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T07:09:29.1170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 |  |  | 2021-04-12T05:52:01.8730000
T-00154-0140 | I2.T010B Level Transmitter Stage 2B | INST | 3331-LT-2103 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00154-0141 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-2211 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0142 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-2451 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00154-0143 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-2311 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0144 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LT-2336 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0145 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LT-2102 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00154-0146 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0555 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0147 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0581 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0148 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0582 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0149 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LIT-0671 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0150 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LIT-7821 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0151 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0565 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0152 | I2.T010B Level Transmitter Stage 2B | INST | 3333-LIT-0661 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00154-0153 | I2.T010B Level Transmitter Stage 2B | INST | 3332-ZIT-2240 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00154-0156 | I2.T010B Level Transmitter Stage 2B | INST | 3331-ZIT-2146 | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T07:06:57.0130000 |  |  | 0.5 |  |  | 2021-04-12T06:14:00.0430000
T-00154-0157 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0449B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00154-0158 | I2.T010B Level Transmitter Stage 2B | INST | 3332-LIT-0480B | LIT - Level Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00156-0003 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2189 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0004 | I2.T012A Position Switch Stage 2A | INST | 3331-ZL-2147 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00156-0005 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2181 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00156-0006 | I2.T012A Position Switch Stage 2A | INST | 3332-ZSC-0595 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0007 | I2.T012A Position Switch Stage 2A | INST | 3332-ZH-2240 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00156-0008 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2186 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0009 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2147 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0010 | I2.T012A Position Switch Stage 2A | INST | 3333-ZSC-2234 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0011 | I2.T012A Position Switch Stage 2A | INST | 3333-ZSC-2233 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0012 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2150 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0013 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2157 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0014 | I2.T012A Position Switch Stage 2A | INST | 3332-ZL-2340 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0015 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2132 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0016 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2187 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0017 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2182 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00156-0018 | I2.T012A Position Switch Stage 2A | INST | 3332-ZSO-0595 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0019 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2191 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0020 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2126 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0021 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2127 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0022 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2128 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0023 | I2.T012A Position Switch Stage 2A | INST | 3332-ZSC-0578 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0024 | I2.T012A Position Switch Stage 2A | INST | 3332-ZH-2340 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0025 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2158 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0026 | I2.T012A Position Switch Stage 2A | INST | 3332-ZSO-0578 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00156-0027 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2188 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0028 | I2.T012A Position Switch Stage 2A | INST | 3333-XS-2177 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0029 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2149 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0030 | I2.T012A Position Switch Stage 2A | INST | 3332-ZL-2240 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00156-0031 | I2.T012A Position Switch Stage 2A | INST | 3333-ZS-2148 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00156-0032 | I2.T012A Position Switch Stage 2A | INST | 3331-ZH-2146 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00157-0003 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2189 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0004 | I2.T012B Position Switch Stage 2B | INST | 3331-ZL-2147 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00157-0005 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2181 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00157-0006 | I2.T012B Position Switch Stage 2B | INST | 3332-ZSC-0595 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0007 | I2.T012B Position Switch Stage 2B | INST | 3332-ZH-2240 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00157-0008 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2186 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0009 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2147 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0010 | I2.T012B Position Switch Stage 2B | INST | 3333-ZSC-2234 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0011 | I2.T012B Position Switch Stage 2B | INST | 3333-ZSC-2233 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0012 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2150 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0013 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2157 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0014 | I2.T012B Position Switch Stage 2B | INST | 3332-ZL-2340 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0015 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2132 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0016 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2187 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0017 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2182 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00157-0018 | I2.T012B Position Switch Stage 2B | INST | 3332-ZSO-0595 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0019 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2191 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0020 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2126 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0021 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2127 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0022 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2128 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0023 | I2.T012B Position Switch Stage 2B | INST | 3332-ZSC-0578 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0024 | I2.T012B Position Switch Stage 2B | INST | 3332-ZH-2340 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0025 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2158 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0026 | I2.T012B Position Switch Stage 2B | INST | 3332-ZSO-0578 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00157-0027 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2188 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0028 | I2.T012B Position Switch Stage 2B | INST | 3333-XS-2177 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0029 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2149 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0030 | I2.T012B Position Switch Stage 2B | INST | 3332-ZL-2240 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00157-0031 | I2.T012B Position Switch Stage 2B | INST | 3333-ZS-2148 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00157-0032 | I2.T012B Position Switch Stage 2B | INST | 3331-ZH-2146 | ZS - Position Switch |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00158-0011 | I1.T013 Pressure Switch Stage 1 | INST | 3331-PSH-0084 | PSH - Pressure Switch High | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T22:36:19.2770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T21:25:02.9830000 |  | 2021-02-06T23:29:58.9230000
T-00158-0015 | I1.T013 Pressure Switch Stage 1 | INST | 3333-PSH-2218 | PSH - Pressure Switch High | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00158-0018 | I1.T013 Pressure Switch Stage 1 | INST | 3333-PS-2160 | PSH - Pressure Switch High | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00159-0011 | I2.T013A Pressure Switch Stage 2A | INST | 3331-PSH-0084 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T02:57:01.6570000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-25T23:49:51.2400000 |  | 2021-03-26T01:10:07.8330000
T-00159-0015 | I2.T013A Pressure Switch Stage 2A | INST | 3333-PSH-2218 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00159-0016 | I2.T013A Pressure Switch Stage 2A | INST | 3332-PS-2242 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00159-0017 | I2.T013A Pressure Switch Stage 2A | INST | 3332-PS-2245 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00159-0018 | I2.T013A Pressure Switch Stage 2A | INST | 3333-PS-2160 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00159-0019 | I2.T013A Pressure Switch Stage 2A | INST | 3331-PS-2151 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00159-0020 | I2.T013A Pressure Switch Stage 2A | INST | 3332-PS-2462 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00159-0021 | I2.T013A Pressure Switch Stage 2A | INST | 3332-PS-2369 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00159-0022 | I2.T013A Pressure Switch Stage 2A | INST | 3331-PS-2148 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00159-0023 | I2.T013A Pressure Switch Stage 2A | INST | 3332-PS-2366 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00160-0011 | I2.T013B Pressure Switch Stage 2B | INST | 3331-PSH-0084 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T02:57:45.2500000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T23:45:39.9900000
T-00160-0015 | I2.T013B Pressure Switch Stage 2B | INST | 3333-PSH-2218 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00160-0016 | I2.T013B Pressure Switch Stage 2B | INST | 3332-PS-2242 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00160-0017 | I2.T013B Pressure Switch Stage 2B | INST | 3332-PS-2245 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00160-0018 | I2.T013B Pressure Switch Stage 2B | INST | 3333-PS-2160 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00160-0019 | I2.T013B Pressure Switch Stage 2B | INST | 3331-PS-2151 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00160-0020 | I2.T013B Pressure Switch Stage 2B | INST | 3332-PS-2462 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00160-0021 | I2.T013B Pressure Switch Stage 2B | INST | 3332-PS-2369 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00160-0022 | I2.T013B Pressure Switch Stage 2B | INST | 3331-PS-2148 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00160-0023 | I2.T013B Pressure Switch Stage 2B | INST | 3332-PS-2366 | PSH - Pressure Switch High |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00161-0007 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0654 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:29:17.9100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T02:12:06.3330000 |  | 2021-03-07T04:16:06.0270000
T-00161-0008 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1136 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-24T03:00:16.6200000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-23T06:28:11.5000000 |  | 2021-04-23T07:06:06.7530000
T-00161-0009 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0464 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00161-0010 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0715 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0011 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0176 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T12:46:47.4000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T20:50:39.6570000 |  | 2021-02-22T00:26:44.6870000
T-00161-0012 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PIT-0848 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-19T06:17:56.4630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-15T05:48:46.5170000 |  | 2021-01-16T20:19:03.4500000
T-00161-0013 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0354 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T05:45:03.0330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:08:49.8930000 |  | 2021-04-17T07:10:05.3030000
T-00161-0014 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1052 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:23:48.2130000 |  | 2021-04-26T06:40:55.3170000
T-00161-0015 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0759 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0016 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PDIT-0852 | PDIT - Pressure Differential Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:27:57.2900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T07:02:05.2470000 |  | 2021-01-25T07:20:44.3530000
T-00161-0017 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0463 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T05:45:31.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:19:59.8570000 |  | 2021-04-16T07:28:10.3500000
T-00161-0018 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PIT-0902 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-02-15T00:05:14.5000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-13T19:51:49.6200000 |  | 2021-02-13T19:52:19.7270000
T-00161-0019 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0752 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0021 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1135 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0022 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0841 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0023 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1056 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0024 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1050 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-24T03:58:53.8730000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T06:38:21.3770000 |  | 2021-04-20T07:15:09.3870000
T-00161-0025 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-LIT-2121 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:34:55.6070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T01:24:52.8930000 |  | 2021-01-24T01:29:18.6030000
T-00161-0027 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1046 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-24T03:01:19.5270000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-23T06:14:01.2400000 |  | 2021-04-23T07:06:44.9830000
T-00161-0028 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0719 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0029 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1152 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0030 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0769 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-25T21:55:27.1770000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T01:24:30.7930000 |  | 2021-04-25T07:23:33.5370000
T-00161-0031 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0758 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0032 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0872 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0033 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0833 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0034 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0717 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0035 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PIT-0031 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T20:47:44.6900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-06T21:21:58.6400000 |  | 2021-02-06T23:31:00.1200000
T-00161-0036 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0768 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-25T21:59:25.6630000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T01:22:29.8400000 |  | 2021-04-25T07:23:57.6370000
T-00161-0037 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1126 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0038 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PIT-0877 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00161-0039 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0843 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0040 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1167A | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T03:33:12.1170000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-18T06:21:35.3330000 |  | 2021-04-18T22:30:45.7870000
T-00161-0041 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1045 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:14:25.6100000 |  | 2021-04-26T06:41:16.6570000
T-00161-0042 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0711 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0043 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1005 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-25T05:53:46.3800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-24T04:10:09.3570000 |  | 2021-03-24T18:39:32.9370000
T-00161-0045 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0544 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:17:23.1700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:04:01.6830000 |  | 2021-03-30T05:24:15.8500000
T-00161-0046 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1167C | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:32:54.1400000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-18T06:31:47.0570000 |  | 2021-04-18T22:31:14.8930000
T-00161-0047 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1051 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0048 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0713 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0049 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1124 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:33:17.1230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T06:55:29.4000000 |  | 2021-04-22T07:13:21.7030000
T-00161-0050 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1167B | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:33:37.9900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-18T06:25:58.8270000 |  | 2021-04-18T22:31:37.2200000
T-00161-0051 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1153 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0052 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PDIT-1162 | PDIT - Pressure Differential Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00161-0053 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0723 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0054 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PIT-0860 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-20T21:02:29.7670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:02:08.4200000 |  | 2021-02-20T06:04:10.3130000
T-00161-0055 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0804 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0057 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1138 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0058 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0831 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0059 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0767 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-25T22:00:13.6630000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T01:19:03.2400000 |  | 2021-04-25T07:24:17.2230000
T-00161-0060 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0576 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:34:02.5230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-18T06:35:44.6530000 |  | 2021-04-18T22:32:39.5170000
T-00161-0061 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PDIT-0853 | PDIT - Pressure Differential Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:28:19.6500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T06:45:15.8870000 |  | 2021-01-25T07:21:15.8070000
T-00161-0062 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1137 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0063 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1141 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0064 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0702 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0065 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1049 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0066 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0685 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0067 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1154 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0068 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PIT-0903 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-01-29T20:28:44.0630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-25T06:17:43.0700000 |  | 2021-01-25T06:35:21.3170000
T-00161-0069 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0721 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0070 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1053 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0071 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0442 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:55:43.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T03:46:58.3670000 |  | 2021-04-14T07:20:39.6700000
T-00161-0072 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0419 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T06:22:22.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-02T05:28:07.8070000 |  | 2021-03-04T02:11:22.9900000
T-00161-0073 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-0590 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0074 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1047 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0075 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0728 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0076 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1127 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0077 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0656 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00161-0078 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0521 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:19:58.9530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:19:53.5230000 |  | 2021-02-28T05:17:11.4800000
T-00161-0079 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1057 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0082 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1048 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0083 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0725 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0084 | I1.T014 Pressure Transmitter Stage 1 | INST | 3334-PIT-0732 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0085 | I1.T014 Pressure Transmitter Stage 1 | INST | 3335-PDIT-1163 | PDIT - Pressure Differential Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00161-0086 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-1140 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00161-0087 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-0443 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00161-0088 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PT-2104 | PT - Pressure Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T04:37:48.5770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-08T01:00:24.4070000 |  | 2021-01-08T01:25:45.1230000
T-00161-0090 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PT-2337 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-22T02:04:27.1100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T07:00:36.0770000 |  | 2021-04-21T07:27:07.5800000
T-00161-0091 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-2237 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:20:25.1600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:22:00.8530000 |  | 2021-02-28T05:18:00.1570000
T-00161-0093 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-0667 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0094 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PDIT-7829 | PDIT - Pressure Differential Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0095 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PIT-2104 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T01:24:28.8070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T06:01:08.7700000 |  | 2021-01-23T00:34:17.3630000
T-00161-0096 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-0688 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0097 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-2205 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0098 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-0687 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0099 | I1.T014 Pressure Transmitter Stage 1 | INST | 3332-PIT-2337 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:15:24.8870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-30T00:25:46.0070000 |  | 2021-03-30T02:10:56.5670000
T-00161-0100 | I1.T014 Pressure Transmitter Stage 1 | INST | 3333-PIT-2214 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00161-0101 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PIT-0055 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:31:23.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-09T00:06:36.1730000 |  | 2021-02-09T06:40:01.2800000
T-00161-0102 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PIT-0083 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-07T22:37:09.5400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T21:28:15.3770000 |  | 2021-02-06T23:31:49.5930000
T-00161-0104 | I1.T014 Pressure Transmitter Stage 1 | INST | 3331-PIT-0073 | PIT - Pressure Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-08T21:48:05.7570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T21:45:15.3730000 |  | 2021-02-06T23:32:42.7030000
T-00162-0007 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0654 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0008 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1136 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0009 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0464 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0010 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0715 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0011 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0176 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0012 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PIT-0848 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:08:18.3530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-16T05:49:03.1570000 |  | 2021-04-20T04:54:44.1600000
T-00162-0013 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0354 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0014 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1052 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0015 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0759 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0016 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PDIT-0852 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-21T07:45:27.9370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-21T03:56:41.3470000 |  | 2021-04-21T04:06:19.8130000
T-00162-0017 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0463 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0018 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PIT-0902 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0019 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0752 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0021 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1135 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0022 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0841 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0023 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1056 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0024 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1050 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0025 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-LIT-2121 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5
T-00162-0027 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1046 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0028 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0719 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0029 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1152 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0030 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0769 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0031 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0758 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0032 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0872 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0033 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0833 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0034 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0717 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0035 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PIT-0031 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:22:48.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-11T06:59:15.3430000 |  | 2021-04-12T03:58:29.3970000
T-00162-0036 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0768 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0037 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1126 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0038 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PIT-0877 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00162-0039 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0843 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0040 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1167A | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0041 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1045 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0042 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0711 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0043 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1005 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0045 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0544 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0046 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1167C | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0047 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1051 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0048 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0713 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0049 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1124 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0050 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1167B | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0051 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1153 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0052 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PDIT-1162 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00162-0053 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0723 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0054 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PIT-0860 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-20T03:37:28.5200000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-18T05:34:42.4900000 |  | 2021-04-18T05:35:56.0100000
T-00162-0055 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0804 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0057 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1138 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0058 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0831 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0059 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0767 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0060 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0576 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0061 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PDIT-0853 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-21T07:46:15.8900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-21T03:55:04.8870000 |  | 2021-04-21T04:07:34.7470000
T-00162-0062 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1137 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0063 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1141 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0064 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0702 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0065 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1049 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0066 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0685 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0067 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1154 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0068 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PIT-0903 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-04-20T01:30:35.9270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5 | 2021-04-18T02:03:49.1530000 |  | 2021-04-18T02:04:27.1970000
T-00162-0069 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0721 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0070 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1053 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0071 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0442 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0072 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0419 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0073 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-0590 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0074 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1047 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0075 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0728 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0076 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1127 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0077 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0656 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0078 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0521 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0079 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1057 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0082 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1048 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0083 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0725 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0084 | I2.T014A Pressure Transmitter Stage 2A | INST | 3334-PIT-0732 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0085 | I2.T014A Pressure Transmitter Stage 2A | INST | 3335-PDIT-1163 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00162-0086 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-1140 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0087 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-0443 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00162-0088 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PT-2104 | PT - Pressure Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00162-0090 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PT-2337 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0091 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-2237 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0093 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-0667 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0094 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PDIT-7829 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0095 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PIT-2104 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00162-0096 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-0688 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0097 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-2205 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0098 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-0687 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0099 | I2.T014A Pressure Transmitter Stage 2A | INST | 3332-PIT-2337 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00162-0100 | I2.T014A Pressure Transmitter Stage 2A | INST | 3333-PIT-2214 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00162-0101 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PIT-0055 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:57:30.6600000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-12T01:45:09.1670000 |  | 2021-04-12T01:48:04.0670000
T-00162-0102 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PIT-0083 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T02:59:02.2100000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5 | 2021-03-26T02:01:16.4730000 |  | 2021-03-26T02:38:05.7000000
T-00162-0104 | I2.T014A Pressure Transmitter Stage 2A | INST | 3331-PIT-0073 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:32:58.0770000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-08T23:47:37.5100000 |  | 2021-04-11T01:28:53.9370000
T-00163-0007 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0654 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0008 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1136 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0009 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0464 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0010 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0715 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0011 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0176 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0012 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PIT-0848 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:06:33.9170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 5 |  |  | 2021-04-16T05:33:51.9100000
T-00163-0013 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0354 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0014 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1052 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0015 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0759 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0016 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PDIT-0852 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:09:01.8100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 5 |  |  | 2021-04-16T21:57:45.5000000
T-00163-0017 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0463 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0018 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PIT-0902 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0019 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0752 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0021 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1135 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0022 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0841 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0023 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1056 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0024 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1050 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0025 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-LIT-2121 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 5
T-00163-0027 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1046 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0028 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0719 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0029 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1152 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0030 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0769 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0031 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0758 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0032 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0872 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0033 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0833 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0034 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0717 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0035 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PIT-0031 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T04:05:22.3270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 5 |  |  | 2021-04-08T23:39:55.4100000
T-00163-0036 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0768 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0037 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1126 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0038 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PIT-0877 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 5
T-00163-0039 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0843 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0040 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1167A | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0041 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1045 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0042 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0711 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0043 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1005 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0045 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0544 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0046 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1167C | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0047 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1051 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0048 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0713 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0049 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1124 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0050 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1167B | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0051 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1153 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0052 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PDIT-1162 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 5
T-00163-0053 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0723 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0054 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PIT-0860 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-09T03:48:42.3100000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 5 |  |  | 2021-04-04T07:08:59.1570000
T-00163-0055 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0804 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0057 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1138 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0058 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0831 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0059 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0767 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0060 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0576 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0061 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PDIT-0853 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:09:44.2470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 5 |  |  | 2021-04-16T21:32:19.4070000
T-00163-0062 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1137 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0063 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1141 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0064 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0702 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0065 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1049 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0066 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0685 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0067 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1154 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0068 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PIT-0903 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-04-12T07:07:44.0700000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 5 | 2021-04-12T05:57:43.5270000 |  | 2021-04-12T05:57:51.7400000
T-00163-0069 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0721 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0070 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1053 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0071 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0442 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0072 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0419 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0073 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-0590 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0074 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1047 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0075 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0728 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0076 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1127 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0077 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0656 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0078 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0521 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0079 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1057 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0082 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1048 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0083 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0725 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0084 | I2.T014B Pressure Transmitter Stage 2B | INST | 3334-PIT-0732 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0085 | I2.T014B Pressure Transmitter Stage 2B | INST | 3335-PDIT-1163 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 5
T-00163-0086 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-1140 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0087 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-0443 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 5
T-00163-0088 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PT-2104 | PT - Pressure Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 5
T-00163-0090 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PT-2337 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0091 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-2237 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0093 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-0667 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0094 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PDIT-7829 | PDIT - Pressure Differential Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0095 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PIT-2104 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 5
T-00163-0096 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-0688 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0097 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-2205 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0098 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-0687 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0099 | I2.T014B Pressure Transmitter Stage 2B | INST | 3332-PIT-2337 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 5
T-00163-0100 | I2.T014B Pressure Transmitter Stage 2B | INST | 3333-PIT-2214 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 5
T-00163-0101 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PIT-0055 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-10T08:05:16.2230000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 5 |  |  | 2021-04-10T07:23:30.9500000
T-00163-0102 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PIT-0083 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T23:34:40.8670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 5 |  |  | 2021-03-25T22:34:15.7530000
T-00163-0104 | I2.T014B Pressure Transmitter Stage 2B | INST | 3331-PIT-0073 | PIT - Pressure Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:49:22.0130000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 5 |  |  | 2021-04-08T23:54:52.3030000
T-00164-1443 | I1.T019 Switch General Stage 1 | INST | 3334-LS-2103 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T03:58:44.2330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T03:39:30.0270000 |  | 2021-01-24T03:44:36.2370000
T-00164-1465 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-1042 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1466 | I1.T019 Switch General Stage 1 | INST | 3332-LL-2301 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00164-1468 | I1.T019 Switch General Stage 1 | INST | 3331-LL-2101 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T00:23:15.0830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-23T02:31:15.3830000 |  | 2021-01-23T02:33:56.7770000
T-00164-1469 | I1.T019 Switch General Stage 1 | INST | 3332-LSH-0564 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:55:18.1470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T03:36:56.3070000 |  | 2021-04-19T03:49:40.9030000
T-00164-1470 | I1.T019 Switch General Stage 1 | INST | 3333-LSL-1044 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1471 | I1.T019 Switch General Stage 1 | INST | 3332-LSL-0564 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T07:54:30.7170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T03:31:38.9130000 |  | 2021-04-19T03:51:24.2430000
T-00164-1472 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-2232 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1473 | I1.T019 Switch General Stage 1 | INST | 3331-LL-2102 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-24T00:19:43.8830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-22T02:55:02.0030000 |  | 2021-01-22T04:36:46.8030000
T-00164-1474 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-2220 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1475 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-2108 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00164-1476 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-2101A | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00164-1477 | I1.T019 Switch General Stage 1 | INST | 3333-LS-0682 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1478 | I1.T019 Switch General Stage 1 | INST | 3333-LSH-2101B | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00164-1479 | I1.T019 Switch General Stage 1 | INST | 3332-LSL-0551 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T07:54:55.8870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T03:24:43.4530000 |  | 2021-04-19T03:51:45.4300000
T-00164-1480 | I1.T019 Switch General Stage 1 | INST | 3333-LS-0690 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1481 | I1.T019 Switch General Stage 1 | INST | 3332-LSH-0551 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:55:44.9000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T03:41:41.0030000 |  | 2021-04-19T03:52:04.2930000
T-00164-1482 | I1.T019 Switch General Stage 1 | INST | 3333-LSL-2219 | LS - LEVEL SWITCH | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00164-1483 | I1.T019 Switch General Stage 1 | INST | 3334-LS-2104 | LS - LEVEL SWITCH | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00165-0053 | I2.T019A Switch General Stage 2A | INST | 3334-LS-2103 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00165-0059 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-1042 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0060 | I2.T019A Switch General Stage 2A | INST | 3332-LL-2301 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0061 | I2.T019A Switch General Stage 2A | INST | 3332-LL-2201 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00165-0062 | I2.T019A Switch General Stage 2A | INST | 3331-LL-2101 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00165-0063 | I2.T019A Switch General Stage 2A | INST | 3332-LSH-0564 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0064 | I2.T019A Switch General Stage 2A | INST | 3333-LSL-1044 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0065 | I2.T019A Switch General Stage 2A | INST | 3332-LSL-0564 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0066 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-2232 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0067 | I2.T019A Switch General Stage 2A | INST | 3331-LL-2102 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T05:29:43.3470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-06T07:48:21.8770000 |  | 2021-04-12T04:53:44.6770000
T-00165-0068 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-2220 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0069 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-2108 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00165-0070 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-2101A | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00165-0071 | I2.T019A Switch General Stage 2A | INST | 3333-LS-0682 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0072 | I2.T019A Switch General Stage 2A | INST | 3333-LSH-2101B | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00165-0073 | I2.T019A Switch General Stage 2A | INST | 3332-LSL-0551 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0074 | I2.T019A Switch General Stage 2A | INST | 3333-LS-0690 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0075 | I2.T019A Switch General Stage 2A | INST | 3332-LSH-0551 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0076 | I2.T019A Switch General Stage 2A | INST | 3333-LSL-2219 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00165-0077 | I2.T019A Switch General Stage 2A | INST | 3334-LS-2104 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00166-0053 | I2.T019B Switch General Stage 2B | INST | 3334-LS-2103 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00166-0059 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-1042 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0060 | I2.T019B Switch General Stage 2B | INST | 3332-LL-2301 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0061 | I2.T019B Switch General Stage 2B | INST | 3332-LL-2201 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00166-0062 | I2.T019B Switch General Stage 2B | INST | 3331-LL-2101 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00166-0063 | I2.T019B Switch General Stage 2B | INST | 3332-LSH-0564 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0064 | I2.T019B Switch General Stage 2B | INST | 3333-LSL-1044 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0065 | I2.T019B Switch General Stage 2B | INST | 3332-LSL-0564 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0066 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-2232 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0067 | I2.T019B Switch General Stage 2B | INST | 3331-LL-2102 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-06T05:12:31.1400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-06T04:04:24.9570000
T-00166-0068 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-2220 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0069 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-2108 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00166-0070 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-2101A | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00166-0071 | I2.T019B Switch General Stage 2B | INST | 3333-LS-0682 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0072 | I2.T019B Switch General Stage 2B | INST | 3333-LSH-2101B | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00166-0073 | I2.T019B Switch General Stage 2B | INST | 3332-LSL-0551 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0074 | I2.T019B Switch General Stage 2B | INST | 3333-LS-0690 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0075 | I2.T019B Switch General Stage 2B | INST | 3332-LSH-0551 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0076 | I2.T019B Switch General Stage 2B | INST | 3333-LSL-2219 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00166-0077 | I2.T019B Switch General Stage 2B | INST | 3334-LS-2104 | LS - LEVEL SWITCH |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00168-0020 | I1.T022 Temperature Transmitter Stage 1 | INST | 3335-TIT-0810 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00168-0028 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TIT-2207 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00168-0029 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TIT-2208 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00168-0031 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TIT-2211 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00168-0033 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TT-2232 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00168-0035 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TIT-2215 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00168-0036 | I1.T022 Temperature Transmitter Stage 1 | INST | 3333-TIT-2216 | TIT - Temperature Indicating Transmitter | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00169-0020 | I2.T022A Temperature Transmitter Stage 2A | INST | 3335-TIT-0810 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00169-0027 | I2.T022A Temperature Transmitter Stage 2A | INST | 3332-TT-2450 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00169-0028 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TIT-2207 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0029 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TIT-2208 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0030 | I2.T022A Temperature Transmitter Stage 2A | INST | 3332-TT-2212 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00169-0031 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TIT-2211 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0032 | I2.T022A Temperature Transmitter Stage 2A | INST | 3332-TT-2463 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00169-0033 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TT-2232 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0034 | I2.T022A Temperature Transmitter Stage 2A | INST | 3332-TT-2312 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0035 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TIT-2215 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0036 | I2.T022A Temperature Transmitter Stage 2A | INST | 3333-TIT-2216 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00169-0037 | I2.T022A Temperature Transmitter Stage 2A | INST | 3331-TT-2115 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T05:30:27.8670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-06T07:39:05.2170000 |  | 2021-04-12T05:06:23.8430000
T-00169-0038 | I2.T022A Temperature Transmitter Stage 2A | INST | 3332-TT-2465 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00170-0020 | I2.T022B Temperature Transmitter Stage 2B | INST | 3335-TIT-0810 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00170-0027 | I2.T022B Temperature Transmitter Stage 2B | INST | 3332-TT-2450 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00170-0028 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TIT-2207 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0029 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TIT-2208 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0030 | I2.T022B Temperature Transmitter Stage 2B | INST | 3332-TT-2212 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00170-0031 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TIT-2211 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0032 | I2.T022B Temperature Transmitter Stage 2B | INST | 3332-TT-2463 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00170-0033 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TT-2232 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0034 | I2.T022B Temperature Transmitter Stage 2B | INST | 3332-TT-2312 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0035 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TIT-2215 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0036 | I2.T022B Temperature Transmitter Stage 2B | INST | 3333-TIT-2216 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00170-0037 | I2.T022B Temperature Transmitter Stage 2B | INST | 3331-TT-2115 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Completed | 2021-04-12T05:43:49.8730000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T05:44:44.3970000
T-00170-0038 | I2.T022B Temperature Transmitter Stage 2B | INST | 3332-TT-2465 | TIT - Temperature Indicating Transmitter |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0170 | On Off Valve Stage 1 | INST | 3331-FV-0082 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:38:56.6330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:46:14.0000000 |  | 2021-01-01T19:24:02.5970000
T-00171-0185 | On Off Valve Stage 1 | INST | 3331-FV-0009 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:40:15.0370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:46:00.0000000 |  | 2021-01-01T19:24:26.0030000
T-00171-0198 | On Off Valve Stage 1 | INST | 3331-FV-0007 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:40:33.3430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:46:40.0000000 |  | 2021-01-01T19:24:45.0230000
T-00171-0209 | On Off Valve Stage 1 | INST | 3331-FV-1010 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:06:25.8230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T20:01:20.8700000 |  | 2021-02-18T21:40:21.1570000
T-00171-0212 | On Off Valve Stage 1 | INST | 3331-FV-0005 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:40:56.1870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:47:14.0000000 |  | 2021-01-01T19:25:05.6300000
T-00171-0236 | On Off Valve Stage 1 | INST | 3331-FV-0002 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:41:14.1230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:47:53.0000000 |  | 2021-01-01T19:25:47.5400000
T-00171-0260 | On Off Valve Stage 1 | INST | 3331-FV-0008 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:41:32.8700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:48:14.0000000 |  | 2021-01-01T19:26:04.5970000
T-00171-0266 | On Off Valve Stage 1 | INST | 3332-FV-0602 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:14:46.3900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:37:09.8130000 |  | 2021-03-28T06:12:14.8300000
T-00171-0279 | On Off Valve Stage 1 | INST | 3331-FV-0084 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:42:07.0770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:48:56.0000000 |  | 2021-01-01T19:26:29.5570000
T-00171-0292 | On Off Valve Stage 1 | INST | 3331-FV-0003 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:42:47.8470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:49:25.0000000 |  | 2021-01-01T19:26:45.6470000
T-00171-0329 | On Off Valve Stage 1 | INST | 3331-FV-0081 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:43:17.4200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T08:49:52.0000000 |  | 2021-01-01T19:27:10.6200000
T-00171-0337 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1045 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:34:58.3070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T02:39:03.4300000 |  | 2021-03-27T05:09:42.6200000
T-00171-0338 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1092 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0339 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0461 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:10:29.9300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T23:30:06.9670000 |  | 2021-04-18T01:31:34.4270000
T-00171-0340 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0416 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-06T05:07:38.9500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-05T05:03:37.7500000 |  | 2021-03-05T23:12:36.1630000
T-00171-0341 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0460 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:12:42.0570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T01:37:39.3270000 |  | 2021-04-17T04:07:55.1500000
T-00171-0342 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1024 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0343 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0170 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:44:49.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T02:09:48.6270000 |  | 2021-02-18T04:36:56.6930000
T-00171-0344 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-1166 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0345 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0584 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0346 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0024 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:54:08.1500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T19:58:56.6300000 |  | 2021-01-13T21:29:12.7830000
T-00171-0347 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0122 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:05:53.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T12:32:25.9230000 |  | 2021-02-21T19:54:47.1130000
T-00171-0348 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1050 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0349 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1072 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:56:12.0800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T05:05:23.8500000 |  | 2021-04-19T06:31:39.2470000
T-00171-0350 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0203 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-10T20:07:21.3330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T05:07:32.3100000 |  | 2021-03-10T06:57:50.1030000
T-00171-0351 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0687 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0352 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0057 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:31:47.0230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:55:22.5100000 |  | 2021-02-09T06:40:30.5170000
T-00171-0353 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1086B | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0354 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0415 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:21:30.8370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T06:32:02.7000000 |  | 2021-03-02T04:52:16.0030000
T-00171-0355 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0861 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0356 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0316 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T02:43:28.9270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T22:51:38.9000000 |  | 2021-04-11T01:07:00.4000000
T-00171-0357 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1089C | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00171-0358 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1020 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-21T00:06:40.4870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:50:06.4100000 |  | 2021-02-20T22:58:49.7200000
T-00171-0359 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1073 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0360 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0696 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0361 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1036 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-25T05:56:26.9900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-24T03:57:27.6170000 |  | 2021-03-24T18:39:58.9130000
T-00171-0362 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1080A | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0363 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0841 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:49:02.7470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-05T05:43:44.9070000 |  | 2021-02-06T23:34:42.9930000
T-00171-0364 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0075 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-08T22:01:29.8300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T22:18:06.1300000 |  | 2021-02-06T23:36:14.7600000
T-00171-0365 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1032 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0366 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0204 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:47:33.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:33:06.8930000 |  | 2021-03-06T22:38:15.7400000
T-00171-0367 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0595 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0368 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0451 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:32:55.9470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T05:34:58.8230000 |  | 2021-04-15T06:05:29.8830000
T-00171-0369 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0254 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T12:47:26.5200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T22:52:23.8500000 |  | 2021-02-22T00:24:51.1170000
T-00171-0370 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0047 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:32:42.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:45:34.1870000 |  | 2021-02-09T06:41:29.9600000
T-00171-0371 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0619 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0372 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0471 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:45:49.7600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:37:58.9030000 |  | 2021-04-17T04:08:18.3170000
T-00171-0373 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0433 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-06T05:03:05.0630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-05T05:24:41.6970000 |  | 2021-03-05T23:14:08.5970000
T-00171-0374 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0450 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:46:54.5930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T03:52:05.3000000 |  | 2021-04-16T04:16:52.2030000
T-00171-0375 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1037 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0376 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1083B | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0377 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1040 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:21:13.5030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:20:56.8930000 |  | 2021-02-28T05:18:47.8230000
T-00171-0379 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0202 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:48:34.9170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:26:06.8530000 |  | 2021-03-06T22:39:14.0800000
T-00171-0380 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1004 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:54:28.9430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-11T05:18:18.8170000 |  | 2021-01-11T05:55:20.4430000
T-00171-0381 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0487 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0382 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1157 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0383 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1025 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-24T06:29:47.9300000 |  | 2021-04-24T07:15:39.4800000
T-00171-0384 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0700 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0385 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0025 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-10T06:37:50.5070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-09T05:06:19.2900000 |  | 2021-02-09T06:38:14.9870000
T-00171-0386 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0845 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-18T22:59:12.6000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-18T06:19:41.7370000 |  | 2021-02-18T19:08:26.6330000
T-00171-0387 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0070 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-08T23:00:26.7970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-06T21:35:58.1900000 |  | 2021-02-07T04:38:08.8800000
T-00171-0388 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1021 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-21T00:07:11.9270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:51:26.5370000 |  | 2021-02-20T22:59:33.5300000
T-00171-0389 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0867 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0390 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0050 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:27:33.3530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T01:43:52.1670000 |  | 2021-02-20T02:14:11.0870000
T-00171-0391 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0697 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0392 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1080B | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0393 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0116 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:06:42.1970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T05:49:56.8300000 |  | 2021-02-21T06:09:35.1270000
T-00171-0394 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0495 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T07:49:50.7200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T06:39:01.2430000 |  | 2021-04-10T06:52:43.2800000
T-00171-0395 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0078 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T00:07:44.9930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:30:13.2400000 |  | 2021-02-20T06:36:10.2900000
T-00171-0396 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0515 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:21:48.3030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:09:25.9670000 |  | 2021-02-28T05:19:21.1900000
T-00171-0397 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1083C | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0398 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0481 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-05T06:17:07.0670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T22:48:12.3070000 |  | 2021-04-05T04:25:25.7630000
T-00171-0400 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1042 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:35:16.5670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T02:27:08.6500000 |  | 2021-03-27T05:10:09.5570000
T-00171-0401 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0578 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0403 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1033 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0404 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0052 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:33:05.4470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:52:05.1370000 |  | 2021-02-09T06:43:45.9130000
T-00171-0405 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0418 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-06T05:08:06.7500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-05T05:12:22.5130000 |  | 2021-03-05T23:13:22.2870000
T-00171-0406 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0120 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:07:16.5570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T15:55:59.2430000 |  | 2021-02-21T19:55:46.3430000
T-00171-0407 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0417 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-06T05:08:42.4700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-05T20:16:23.7770000 |  | 2021-03-05T23:13:02.6400000
T-00171-0408 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0951 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0409 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0862 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0410 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0536 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:40:14.1030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:20:58.0770000 |  | 2021-03-30T06:02:45.9470000
T-00171-0411 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1109 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T22:20:37.4200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-17T21:00:33.5670000 |  | 2021-02-17T21:45:39.7730000
T-00171-0412 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0058 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:33:27.4070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:56:52.6470000 |  | 2021-02-09T06:44:08.2200000
T-00171-0413 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0846 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-18T22:59:59.8000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-18T06:21:21.3870000 |  | 2021-02-18T19:09:28.6170000
T-00171-0414 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1046 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:40:21.9930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T02:36:28.6530000 |  | 2021-03-27T05:10:37.9300000
T-00171-0415 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0205 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:49:30.0300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:37:44.5870000 |  | 2021-03-06T22:50:38.3170000
T-00171-0416 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0311 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T02:43:52.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T07:01:08.1230000 |  | 2021-04-11T00:43:23.7870000
T-00171-0417 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0068 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:55:23.6970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T20:02:29.5470000 |  | 2021-01-13T21:29:47.4470000
T-00171-0418 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0866 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0419 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0606 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-25T05:57:06.4300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-23T22:27:53.5370000 |  | 2021-03-24T18:40:25.5430000
T-00171-0420 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1089B | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00171-0421 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-2107 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:50:05.4330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T17:53:53.0000000 |  | 2021-01-23T19:25:53.1970000
T-00171-0422 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-2108 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:50:31.8500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T17:50:45.0000000 |  | 2021-01-23T19:26:14.3270000
T-00171-0423 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0482 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-05T06:17:43.9870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T22:49:37.5400000 |  | 2021-04-05T04:26:03.8570000
T-00171-0424 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1086A | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T06:47:24.9300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:36:46.7370000 |  | 2021-04-18T22:25:22.7230000
T-00171-0425 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0824 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0426 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0848 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T10:56:05.8230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T21:06:32.3570000 |  | 2021-01-13T21:30:40.1400000
T-00171-0427 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0048 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:33:50.4630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:50:30.0900000 |  | 2021-02-09T06:47:19.6430000
T-00171-0428 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0517 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:22:22.3370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:11:14.3800000 |  | 2021-02-28T05:20:16.7570000
T-00171-0429 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0588 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0430 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0683 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:43:34.8230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T22:28:41.9370000 |  | 2021-03-01T00:18:44.7000000
T-00171-0431 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0051 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:34:10.3830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:49:52.1170000 |  | 2021-02-09T06:47:49.1530000
T-00171-0432 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0144 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:45:34.1630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:35:00.3000000 |  | 2021-02-18T01:56:50.6530000
T-00171-0433 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0863 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25
T-00171-0434 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1038 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-25T05:57:42.5530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-24T04:01:03.2170000 |  | 2021-03-24T18:41:05.0500000
T-00171-0435 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1106 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-22T06:37:56.5370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-22T05:42:11.9200000 |  | 2021-04-22T05:53:58.1530000
T-00171-0436 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-1164 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0437 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1083A | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T06:48:07.3600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T05:04:02.8970000 |  | 2021-04-16T06:13:22.3930000
T-00171-0438 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-1165 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0439 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1012 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:29:36.4800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T02:27:47.2730000 |  | 2021-02-20T02:40:10.8870000
T-00171-0440 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0519 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:22:52.9770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:12:25.4170000 |  | 2021-02-28T05:21:21.7570000
T-00171-0441 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1074 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0443 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0865 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0444 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-1107 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0445 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0352 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:40:11.1370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T13:05:47.7400000 |  | 2021-02-21T20:01:56.4770000
T-00171-0447 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0423 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:56:06.3130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T03:10:35.0100000 |  | 2021-04-14T07:21:00.1870000
T-00171-0448 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-1005 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T13:56:43.5030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-08T00:25:20.8570000 |  | 2021-02-11T04:53:29.8670000
T-00171-0449 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1023 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:07:57.7400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T05:52:48.5700000 |  | 2021-02-21T06:10:39.4900000
T-00171-0450 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-1108 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0451 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1086C | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0453 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0114 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:08:31.5630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T05:48:09.7630000 |  | 2021-02-21T06:12:25.3470000
T-00171-0454 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0612 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-05T06:13:51.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-04T02:10:59.1770000 |  | 2021-04-05T04:23:56.3800000
T-00171-0455 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0825 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0456 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0305 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T02:44:20.2900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T01:22:32.4370000 |  | 2021-04-11T01:24:12.6430000
T-00171-0457 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0525 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:23:18.4830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T04:13:52.9600000 |  | 2021-02-28T05:22:11.9530000
T-00171-0458 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0439 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-22T16:06:42.6470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T13:04:52.0770000 |  | 2021-02-21T20:02:17.2470000
T-00171-0459 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0622 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0460 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0171 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:46:09.4100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:04:17.9500000 |  | 2021-02-18T02:01:22.1470000
T-00171-0461 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0473 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:48:38.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:36:46.1700000 |  | 2021-04-16T07:38:32.8070000
T-00171-0462 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0537 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:40:54.6070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:24:30.3200000 |  | 2021-03-30T06:03:05.0070000
T-00171-0463 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0842 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:50:13.0030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-05T05:47:30.8300000 |  | 2021-02-07T00:12:16.3730000
T-00171-0464 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0350 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T00:47:12.3570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-31T11:08:51.3930000 |  | 2021-01-31T23:51:04.8600000
T-00171-0465 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1089A | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T03:41:57.1700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-16T03:34:36.4830000 |  | 2021-04-16T03:54:30.1700000
T-00171-0466 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0005 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-22T16:06:08.2300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T01:01:42.0330000 |  | 2021-02-22T04:02:41.6870000
T-00171-0467 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0428 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T04:50:30.5730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-05T05:18:27.1930000 |  | 2021-03-07T04:09:23.3530000
T-00171-0468 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0631 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-05T06:14:33.9400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-05T00:48:31.5370000 |  | 2021-04-05T04:24:23.0970000
T-00171-0469 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1035 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0470 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0604 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-11T05:06:42.3630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T21:42:35.6270000 |  | 2021-03-11T00:38:06.1570000
T-00171-0471 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1075 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00171-0472 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-7824 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0473 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0839 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0474 | I1.T025 On Off Valve Stage 1 | INST | 3335-FV-0950 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0475 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1044 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:40:44.4900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T02:31:11.8930000 |  | 2021-03-27T05:12:07.0100000
T-00171-0476 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0820 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0477 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0670 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0478 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0019 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:56:54.9870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T06:47:34.3270000 |  | 2021-01-13T06:58:07.5200000
T-00171-0479 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0076 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-10T05:31:52.0030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T23:41:24.2900000 |  | 2021-02-09T06:53:20.0130000
T-00171-0480 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0145 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:46:50.0670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:21:59.4570000 |  | 2021-02-18T02:01:43.2330000
T-00171-0481 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0172 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T23:47:27.2670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:02:25.3370000 |  | 2021-02-18T02:02:04.0070000
T-00171-0482 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0321 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T02:44:45.2530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T06:54:15.3070000 |  | 2021-04-11T00:46:27.5630000
T-00171-0483 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1080C | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0484 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0066 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:57:31.1700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T20:04:30.0500000 |  | 2021-01-13T21:31:46.8930000
T-00171-0485 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0665 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0486 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1024 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0487 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1051 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0488 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0585 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0489 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0660 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0490 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0256 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T12:47:59.9830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T13:41:49.5730000 |  | 2021-02-21T20:01:05.7030000
T-00171-0491 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0546 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:41:34.8630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:11:30.6600000 |  | 2021-03-30T06:03:31.0570000
T-00171-0492 | I1.T025 On Off Valve Stage 1 | INST | 3334-FV-0701 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00171-0493 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0534 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T06:42:17.1900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:16:36.5200000 |  | 2021-03-30T06:04:02.6930000
T-00171-0494 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-0500 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T07:50:14.1770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T06:39:24.7700000 |  | 2021-04-10T06:54:40.2670000
T-00171-0495 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0067 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T10:57:50.5870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T20:07:19.5470000 |  | 2021-01-13T21:32:07.3670000
T-00171-0496 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-2452 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:56:25.6700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T03:52:57.1330000 |  | 2021-04-14T07:21:18.7130000
T-00171-0497 | I1.T025 On Off Valve Stage 1 | INST | 3331-FV-0054 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-10T10:34:29.3430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T22:54:02.9270000 |  | 2021-02-09T06:48:40.6130000
T-00171-0498 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2115 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0499 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2125 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0500 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2137 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0502 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2114 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0503 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2116 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0505 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-2454 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:56:46.9870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T04:00:07.9800000 |  | 2021-04-14T07:21:40.7600000
T-00171-0506 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2144 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0507 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0683 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0508 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2112 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0513 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2145 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0516 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0684 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0518 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2122 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0519 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2142 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0520 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0686 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0521 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2168 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0522 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2140 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0527 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2141 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0528 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2113 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0530 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2123 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0532 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2143 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0533 | I1.T025 On Off Valve Stage 1 | INST | 3333-XV-2214 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0535 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2164 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0536 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0685 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0538 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2146 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0539 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-7823 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0542 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-2453 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:57:07.4900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T03:44:57.7100000 |  | 2021-04-14T07:22:02.3130000
T-00171-0544 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2139 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0545 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2117 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0546 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-0681 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00171-0547 | I1.T025 On Off Valve Stage 1 | INST | 3333-FV-2138 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00171-0550 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-2455 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:57:28.9130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T04:02:20.7070000 |  | 2021-04-14T07:22:27.5270000
T-00171-0551 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1071 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.25
T-00171-0552 | I1.T025 On Off Valve Stage 1 | INST | 3332-FV-1061 | FV - Flow Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.25
T-00172-0337 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1045 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0338 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1092 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0339 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0461 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0340 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0416 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0341 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0460 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0342 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0344 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0170 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0345 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-1166 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0346 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0584 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0347 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:48:06.1030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-08T05:51:56.8730000 |  | 2021-04-10T23:22:35.3900000
T-00172-0348 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0122 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0349 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1050 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0350 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1072 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0351 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0203 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0352 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0687 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0353 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0057 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T01:58:42.6470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-10T23:29:17.0370000 |  | 2021-04-12T01:32:30.2900000
T-00172-0354 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1086B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0355 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0415 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0356 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0861 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0357 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0316 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0359 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1089C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0360 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1020 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-21T03:13:24.5400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T06:33:34.9530000 |  | 2021-04-21T00:26:41.5400000
T-00172-0361 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1073 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0362 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0696 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0363 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1036 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0364 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1080A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0365 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0841 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:49:04.4970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:32:03.1400000 |  | 2021-04-17T07:33:55.5770000
T-00172-0366 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0075 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:33:41.1800000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-09T01:07:58.9430000 |  | 2021-04-10T23:27:09.7100000
T-00172-0367 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1032 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0368 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0204 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0369 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0595 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0370 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0451 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0372 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0254 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0373 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0047 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Submitted |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-25T02:42:19.0000000
T-00172-0374 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0619 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0375 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0471 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0376 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0433 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0377 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0450 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0378 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1037 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0379 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1083B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0380 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1040 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0382 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1010 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:29:34.5330000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T02:37:22.6570000 |  | 2021-04-12T01:35:42.2670000
T-00172-0383 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0202 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0384 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1004 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-20T07:04:28.9400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T06:44:06.5370000 |  | 2021-04-20T06:45:27.4200000
T-00172-0386 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0487 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0387 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1157 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0388 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1025 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0389 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0700 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0390 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0025 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:48:30.0070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-08T05:57:42.9830000 |  | 2021-04-10T23:23:27.7500000
T-00172-0391 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0845 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-21T07:46:44.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T04:05:11.3530000 |  | 2021-04-21T04:14:06.9130000
T-00172-0392 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0070 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:34:11.5570000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-08T05:59:47.2000000 |  | 2021-04-10T23:19:18.8470000
T-00172-0393 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1021 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:43:59.2870000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T06:01:16.5500000 |  | 2021-04-12T01:36:17.3300000
T-00172-0394 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0867 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0395 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0050 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:44:43.1430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T01:16:01.1730000 |  | 2021-04-12T01:36:57.0800000
T-00172-0396 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0697 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0397 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1080B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0398 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0116 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0399 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0495 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0400 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0078 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:34:39.0430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-09T23:15:56.1370000 |  | 2021-04-10T23:29:00.5270000
T-00172-0401 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0515 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0402 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1083C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0403 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0481 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0405 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1042 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0406 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0578 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0409 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1033 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0410 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0052 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:45:10.0770000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T05:37:52.0200000 |  | 2021-04-12T01:37:26.3070000
T-00172-0411 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0418 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0412 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0120 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0413 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0417 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0414 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0951 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0415 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0862 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0416 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0536 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0417 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1109 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:44:29.1270000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-12T02:28:21.8030000 |  | 2021-04-13T07:06:47.3770000
T-00172-0418 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0058 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:45:37.2170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T02:01:44.2930000 |  | 2021-04-12T01:38:02.0500000
T-00172-0419 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0846 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:49:31.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:51:00.4970000 |  | 2021-04-18T05:49:41.3330000
T-00172-0420 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1046 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0421 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0205 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0422 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0311 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0423 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0068 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:35:01.7470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-07T07:44:30.8570000 |  | 2021-04-10T23:16:59.8800000
T-00172-0424 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0866 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0425 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0606 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0426 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1089B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0427 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-2107 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00172-0428 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-2108 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00172-0429 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0482 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0430 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1086A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0431 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0824 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0433 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0848 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:49:57.4530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T03:47:52.0000000 |  | 2021-04-20T04:53:58.8500000
T-00172-0434 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0048 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:46:02.2870000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T02:53:13.6600000 |  | 2021-04-12T01:38:29.5870000
T-00172-0435 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0517 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0436 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0588 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0437 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0683 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0438 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0602 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0439 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0051 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:46:34.7430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T03:28:05.2700000 |  | 2021-04-12T01:39:19.9300000
T-00172-0440 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0144 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0441 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0863 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0442 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1038 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0443 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1106 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0444 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-1164 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0445 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1083A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0446 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-1165 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0447 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1012 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:47:05.8200000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T03:37:26.0170000 |  | 2021-04-12T01:40:07.1370000
T-00172-0448 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0519 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0449 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1074 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0452 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0865 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0453 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-1107 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0454 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0352 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0456 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0423 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0457 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-1005 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:48:51.1370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-08T06:01:00.9530000 |  | 2021-04-11T00:56:17.1700000
T-00172-0458 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1023 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0459 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-1108 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0460 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1086C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0462 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0114 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0463 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0612 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0465 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0825 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0466 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0305 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0467 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0525 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0468 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0439 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0469 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0622 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0470 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0171 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0471 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0473 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0472 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0537 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0473 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0842 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:50:46.4170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:46:16.5700000 |  | 2021-04-18T05:46:37.4430000
T-00172-0474 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0350 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0475 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1089A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0476 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0005 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0477 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0428 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0478 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0631 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0479 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1035 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0480 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0604 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0481 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1075 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0482 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-7824 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0483 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0839 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0484 | I2.T025A On Off Valve Stage 2A | INST | 3335-FV-0950 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0485 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1044 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0486 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0820 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0487 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0670 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0488 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0019 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:49:17.2330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-08T05:51:07.0270000 |  | 2021-04-10T23:21:23.6870000
T-00172-0489 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0076 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:35:30.2200000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-09T01:18:09.4070000 |  | 2021-04-10T23:27:47.3000000
T-00172-0490 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0145 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0491 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0172 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0492 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0321 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0493 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1080C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0494 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0066 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:35:52.0300000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-07T03:01:29.6900000 |  | 2021-04-10T23:13:25.9100000
T-00172-0495 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0665 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0496 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0497 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1051 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0498 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0585 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0499 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0660 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0500 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0256 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0502 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0546 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0503 | I2.T025A On Off Valve Stage 2A | INST | 3334-FV-0701 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0504 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0534 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0505 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-0500 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0506 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0067 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-11T02:36:12.7770000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-07T07:43:02.9300000 |  | 2021-04-10T23:15:23.9330000
T-00172-0507 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-2452 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0508 | I2.T025A On Off Valve Stage 2A | INST | 3331-FV-0054 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:47:44.5770000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-11T01:27:11.0570000 |  | 2021-04-12T01:44:58.1600000
T-00172-0509 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2115 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0510 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2125 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0511 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2137 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0512 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2368 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0513 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2114 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0514 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2116 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0515 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2206 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0516 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-2454 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0517 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2144 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0518 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0683 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0519 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2112 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0520 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2305 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0521 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2369 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0522 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2243 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0523 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2307 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0524 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2145 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0525 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2110 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0526 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2109 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0527 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0684 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0528 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2149 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0529 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2122 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0530 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2142 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0531 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0686 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0532 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2168 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0533 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2140 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0534 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2244 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0535 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2208 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0536 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2150 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0537 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2207 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0538 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2141 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0539 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2113 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0540 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2308 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0541 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2123 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0542 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2151 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Checked Out by Connor Clark |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0543 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2143 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0544 | I2.T025A On Off Valve Stage 2A | INST | 3333-XV-2214 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0545 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2245 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0546 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2164 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0547 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0685 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0548 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2306 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0549 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2146 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0550 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-7823 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0551 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2112 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0552 | I2.T025A On Off Valve Stage 2A | INST | 3331-XV-2111 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00172-0553 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-2453 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0554 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2209 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00172-0555 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2139 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0556 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2117 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0557 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-0681 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0558 | I2.T025A On Off Valve Stage 2A | INST | 3333-FV-2138 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00172-0559 | I2.T025A On Off Valve Stage 2A | INST | 3332-XV-2367 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00172-0561 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-2455 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00172-0562 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1071 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.25
T-00172-0563 | I2.T025A On Off Valve Stage 2A | INST | 3332-FV-1061 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  |  |  | 0.25
T-00173-0337 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1045 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0338 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1092 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0339 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0461 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0340 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0416 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0341 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0460 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0342 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0344 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0170 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0345 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-1166 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0346 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0584 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0347 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T04:06:04.0770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-08T03:50:09.4100000
T-00173-0348 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0122 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0349 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1050 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0350 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1072 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0351 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0203 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0352 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0687 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0353 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0057 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:36:36.4470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-10T23:33:10.7600000
T-00173-0354 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1086B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0355 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0415 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0356 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0861 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0357 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0316 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0359 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1089C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0360 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1020 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T06:43:55.5700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T06:21:03.8430000
T-00173-0361 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1073 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0362 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0696 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0363 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1036 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0364 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1080A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0365 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0841 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:51:29.5400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T04:34:05.9830000
T-00173-0366 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0075 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:50:18.4700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T01:16:16.4200000
T-00173-0367 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1032 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0368 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0204 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0369 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0595 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0370 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0451 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0372 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0254 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0373 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0047 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-25T21:08:41.7900000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-25T06:16:20.4030000
T-00173-0374 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0619 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0375 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0471 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0376 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0433 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0377 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0450 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0378 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1037 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0379 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1083B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0380 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1040 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0382 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1010 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:49:41.6670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T02:33:51.5400000
T-00173-0383 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0202 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0384 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1004 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Submitted |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T06:40:13.3670000
T-00173-0386 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0487 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0387 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1157 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0388 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1025 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0389 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0700 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0390 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0025 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T04:06:21.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-08T03:56:06.3300000
T-00173-0391 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0845 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:51:50.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T04:36:49.7930000
T-00173-0392 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0070 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:50:56.6000000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-08T04:57:19.3970000
T-00173-0393 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1021 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T06:44:13.7800000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T06:16:50.9600000
T-00173-0394 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0867 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0395 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0050 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:37:05.6230000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T01:17:23.0400000
T-00173-0396 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0697 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0397 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1080B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0398 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0116 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0399 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0495 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0400 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0078 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-10T00:34:09.4670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T23:14:02.0000000
T-00173-0401 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0515 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0402 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1083C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0403 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0481 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0405 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1042 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0406 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0578 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0409 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1033 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0410 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0052 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T06:44:33.2670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T06:03:23.2470000
T-00173-0411 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0418 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0412 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0120 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0413 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0417 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0414 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0951 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0415 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0862 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0416 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0536 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0417 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1109 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:48:11.3700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T01:56:33.4870000
T-00173-0418 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0058 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:37:25.5230000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T02:03:43.0730000
T-00173-0419 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0846 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T06:52:34.7800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T04:41:08.9400000
T-00173-0420 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1046 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0421 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0205 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0422 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0311 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0423 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0068 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:30:51.8400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-07T07:30:53.9630000 |  | 2021-04-12T05:10:39.8430000
T-00173-0424 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0866 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0425 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0606 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0426 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1089B | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0427 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-2107 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00173-0428 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-2108 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00173-0429 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0482 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0430 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1086A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0431 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0824 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0433 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0848 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T06:41:28.0070000 |  | 2021-04-26T16:56:04.1600000
T-00173-0434 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0048 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T05:38:26.0470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T03:02:33.2470000
T-00173-0435 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0517 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0436 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0588 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0437 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0683 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0438 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0602 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0439 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0051 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T05:38:46.4370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T03:27:35.0470000
T-00173-0440 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0144 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0441 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0863 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0442 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1038 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0443 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1106 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0444 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-1164 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0445 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1083A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0446 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-1165 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0447 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1012 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-12T04:48:32.4370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T02:07:55.1030000
T-00173-0448 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0519 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0449 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1074 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0452 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0865 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0453 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-1107 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0454 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0352 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0456 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0423 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0457 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-1005 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:23:12.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T02:19:42.7200000
T-00173-0458 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1023 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0459 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-1108 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0460 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1086C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0462 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0114 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0463 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0612 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0465 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0825 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0466 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0305 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0467 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0525 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0468 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0439 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0469 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0622 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0470 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0171 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0471 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0473 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0472 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0537 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0473 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0842 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-21T07:47:49.1370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-21T02:54:50.5230000
T-00173-0474 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0350 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0475 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1089A | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0476 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0005 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0477 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0428 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0478 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0631 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0479 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1035 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0480 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0604 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0481 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1075 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0482 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-7824 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0483 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0839 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0484 | I2.T025B On Off Valve Stage 2B | INST | 3335-FV-0950 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0485 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1044 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0486 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0820 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0487 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0670 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0488 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0019 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T04:06:44.3100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-08T03:47:56.8730000
T-00173-0489 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0076 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-09T03:52:50.2230000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-09T01:19:05.9000000
T-00173-0490 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0145 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0491 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0172 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0492 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0321 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0493 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1080C | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0494 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0066 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-07T03:22:18.9700000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-07T03:21:57.1070000
T-00173-0495 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0665 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0496 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1024 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0497 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1051 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0498 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0585 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0499 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0660 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0500 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0256 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0502 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0546 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0503 | I2.T025B On Off Valve Stage 2B | INST | 3334-FV-0701 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0504 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0534 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0505 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-0500 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0506 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0067 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T04:49:00.9870000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-12T01:46:32.6070000
T-00173-0507 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-2452 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0508 | I2.T025B On Off Valve Stage 2B | INST | 3331-FV-0054 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-11T02:37:45.3530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-11T01:27:15.1270000
T-00173-0509 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2115 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0510 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2125 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0511 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2137 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0512 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2368 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0513 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2114 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0514 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2116 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0515 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2206 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0516 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-2454 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0517 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2144 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0518 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0683 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0519 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2112 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0520 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2305 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0521 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2369 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0522 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2243 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0523 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2307 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0524 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2145 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0525 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2110 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0526 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2109 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0527 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0684 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0528 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2149 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0529 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2122 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0530 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2142 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0531 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0686 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0532 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2168 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0533 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2140 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0534 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2244 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0535 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2208 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0536 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2150 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0537 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2207 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0538 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2141 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0539 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2113 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0540 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2308 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0541 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2123 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0542 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2151 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0543 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2143 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0544 | I2.T025B On Off Valve Stage 2B | INST | 3333-XV-2214 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0545 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2245 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0546 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2164 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0547 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0685 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0548 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2306 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0549 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2146 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0550 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-7823 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0551 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2112 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0552 | I2.T025B On Off Valve Stage 2B | INST | 3331-XV-2111 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00173-0553 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-2453 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0554 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2209 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00173-0555 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2139 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0556 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2117 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0557 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-0681 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0558 | I2.T025B On Off Valve Stage 2B | INST | 3333-FV-2138 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00173-0559 | I2.T025B On Off Valve Stage 2B | INST | 3332-XV-2367 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00173-0561 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-2455 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00173-0562 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1071 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  |  |  | 0.25
T-00173-0563 | I2.T025B On Off Valve Stage 2B | INST | 3332-FV-1061 | FV - Flow Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  |  |  | 0.25
T-00174-0003 | M1.T020 Crane Stage 1 | MECH | 3331-CN-4002 | CN - CRANE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-11T06:03:09.8870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 1 | 2021-03-11T06:00:56.5200000 |  | 2021-03-11T06:01:07.5500000
T-00174-0004 | M1.T020 Crane Stage 1 | MECH | 3333-CN-4001 | CN - CRANE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 1
T-00175-0031 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-R55 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-12-22T23:52:53.0400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-30T02:49:08.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-21T21:42:19.3570000
T-00175-0032 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-05T03:00:36.9100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T06:42:26.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-05T01:47:46.9130000
T-00175-0033 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-SW-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:09:58.8030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T21:23:34.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T03:59:33.0000000
T-00175-0034 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4004-W63 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:10:32.5170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T04:06:51.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:00:13.0000000
T-00175-0035 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-05T03:04:04.5500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T02:38:59.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:03.0000000
T-00175-0036 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-W57 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:11:06.9200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T23:30:42.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:18.0000000
T-00175-0037 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-W4 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-05T03:01:38.7170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T01:01:37.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:26.0000000
T-00175-0038 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4004-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:11:38.8130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T03:23:02.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:35.0000000
T-00175-0039 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:17:31.0400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T21:06:42.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:42.0000000
T-00175-0041 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-R8 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-15T03:59:07.3630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-15T02:57:48.7370000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-15T03:45:57.1600000
T-00175-0042 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-B12 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:18:01.8970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T01:06:48.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:23:51.0000000
T-00175-0043 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-B6 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:18:30.3970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T23:25:15.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:00.0000000
T-00175-0050 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4004-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:19:00.1500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T23:58:54.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:16.0000000
T-00175-0051 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4004-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:19:35.3530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-02T00:02:26.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:24.0000000
T-00175-0052 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4004-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:21:01.6970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T23:30:22.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:32.0000000
T-00175-0053 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-W28 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-05T03:05:04.2930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T00:24:14.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:38.0000000
T-00175-0054 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-B59 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:21:39.3570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T19:19:46.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:45.0000000
T-00175-0055 | Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-R50 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T09:22:04.1800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-02T07:18:51.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:24:53.0000000
T-00175-0060 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-29T20:29:29.0330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T21:29:13.6770000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-22T23:23:21.9800000
T-00175-0062 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W10 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:50:13.2370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-19T02:41:09.1430000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:06:02.0170000
T-00175-0064 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B12 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-21T01:52:34.8800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T05:38:41.2430000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-20T21:04:31.0400000
T-00175-0067 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W4 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T02:02:19.2800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T01:34:43.3170000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T02:37:55.7930000
T-00175-0073 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W40 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0074 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R32 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T02:07:05.0130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-21T01:19:09.5500000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-21T01:47:25.3870000
T-00175-0076 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W16 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0077 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W4 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0078 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W28 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-15T10:58:38.9070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T20:22:28.8630000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-13T21:32:33.3430000
T-00175-0079 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R38 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0080 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R1 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00175-0081 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B65 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:51:05.6770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-18T05:00:38.9670000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:06:58.9900000
T-00175-0082 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R1 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:10:17.6600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T04:34:48.4800000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-26T05:04:13.5230000
T-00175-0083 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:51:38.2100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-19T02:44:38.3730000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:08:30.6900000
T-00175-0084 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R25 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00175-0085 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B36 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0086 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R32 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-15T23:58:26.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T05:58:40.3970000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-15T07:30:24.6330000
T-00175-0087 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B42 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:06:34.0730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T03:56:16.9930000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:40:29.9530000
T-00175-0088 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B65 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0089 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B48 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:08:01.4330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T04:24:22.7770000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:41:36.1370000
T-00175-0091 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R37 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-29T20:30:01.3970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T21:13:45.0170000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-22T23:24:44.1830000
T-00175-0092 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B6 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-16T23:03:22.7700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T05:07:51.5000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T20:14:23.6970000
T-00175-0093 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W34 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0094 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R8 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-15T10:59:15.8830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T06:37:01.4500000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-13T21:32:54.8330000
T-00175-0095 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R14 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0096 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R44 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-16T23:04:22.8900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T05:50:01.6730000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T20:39:19.9170000
T-00175-0097 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W34 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T02:09:21.1900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T03:49:20.4530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T04:20:53.4030000
T-00175-0098 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-25T13:20:58.0030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T23:54:01.5200000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-24T21:37:08.8170000
T-00175-0099 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B36 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T02:16:22.9970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-21T01:24:23.5070000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-21T01:47:54.0330000
T-00175-0100 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W10 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:09:58.1200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T04:01:03.5630000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:42:03.7670000
T-00175-0101 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R44 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T02:17:15.1270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T03:45:26.0900000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T04:20:14.1770000
T-00175-0102 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0103 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R14 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0104 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W46 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:11:15.8730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T04:14:56.8100000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:44:13.4730000
T-00175-0105 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0106 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R1 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-21T01:53:17.0800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T21:11:55.2600000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-20T21:14:15.4370000
T-00175-0108 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W63 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:11:12.5130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T06:57:46.9270000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T03:48:24.3270000
T-00175-0109 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R25 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-21T01:53:51.9200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T06:19:37.9530000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-20T21:06:21.3500000
T-00175-0110 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B65 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:11:45.8700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T06:58:59.9970000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T03:52:27.3100000
T-00175-0114 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R13 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-21T01:54:18.4430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T04:56:40.3670000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-20T21:06:53.0100000
T-00175-0115 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B42 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T03:00:23.4130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T03:41:58.4030000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T04:19:13.7630000
T-00175-0116 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R8 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0117 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W63 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T03:19:50.5230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T01:43:41.9070000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T02:40:42.6130000
T-00175-0118 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W63 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0119 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W40 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T03:20:31.4100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T02:16:12.5900000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T02:41:26.9570000
T-00175-0120 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R67 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:53:12.9030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-18T04:52:50.2870000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:09:23.1070000
T-00175-0121 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-W69 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:53:45.0700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-18T05:13:35.2570000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:13:51.8500000
T-00175-0122 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W34 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:55:58.5470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T04:06:21.6700000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:45:11.2770000
T-00175-0123 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R13 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00175-0124 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R38 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-29T20:30:32.2130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T21:24:19.2270000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-22T23:27:00.1670000
T-00175-0125 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R32 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0126 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3338DB4001-W52 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-15T02:57:53.7830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-14T06:55:08.7970000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-14T19:53:32.9800000
T-00175-0127 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B12 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0128 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-B6 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T03:01:19.4230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-20T01:42:38.9030000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-20T02:43:01.3630000
T-00175-0129 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R49 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:12:10.1670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T04:35:29.1700000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-26T05:04:35.0770000
T-00175-0130 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R25 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-07T04:54:29.4000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T22:11:30.6730000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-06T22:40:38.0030000
T-00175-0132 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R13 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:12:43.7970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T23:40:44.7300000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-27T03:53:06.2770000
T-00175-0133 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W10 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0134 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W40 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-16T23:05:52.2930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T04:51:25.1970000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T20:40:00.1200000
T-00175-0135 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B42 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0136 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:57:03.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T06:22:36.3300000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:45:42.8930000
T-00175-0137 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0138 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R44 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0139 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-28T04:25:21.7870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T05:44:02.1470000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T20:31:36.4570000
T-00175-0140 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W28 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-16T23:06:46.5830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T05:24:48.8330000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T20:40:37.7330000
T-00175-0141 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R37 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:18:49.1800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T04:36:45.4770000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-26T05:06:00.3400000
T-00175-0142 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R8 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T10:58:15.9070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T06:29:01.5330000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:46:36.8670000
T-00175-0143 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B6 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0144 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R49 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-21T01:54:53.2500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-20T06:29:09.0000000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-20T21:07:17.4430000
T-00175-0145 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-W4 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-23T11:02:35.9970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T03:46:35.2770000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-23T06:47:06.9930000
T-00175-0146 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-W28 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0147 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-25T13:23:29.2570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-23T23:51:07.3900000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-24T21:38:22.7270000
T-00175-0148 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:54:42.9970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-19T06:47:23.4100000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T06:55:13.5670000
T-00175-0150 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4007-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-19T10:55:15.6530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-18T05:15:20.3000000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T04:31:45.2530000
T-00175-0151 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0152 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4008-R67 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:19:14.0270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-26T06:59:56.4830000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T03:53:55.6300000
T-00175-0153 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3333DB4009-B12 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0155 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R32 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0156 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R2 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0158 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W4 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0159 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0160 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-B6 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0161 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-B36 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0162 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W10 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0163 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R26 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0164 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-B30 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0165 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W63 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0166 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W34 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0167 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R38 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0168 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W40 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0169 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-R8 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0170 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3332DB4013-W28 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0171 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3331DB4011-R61 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.25 |  | 4C+E,10mm2,PVC/SWA/PVC,0.6/1 kV
T-00175-0172 | E1.T037 Lighting and Small Power Energization Stage 1 | CABL | 3338DB4003-R14 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0016 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-R55 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0017 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0018 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-SW-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0019 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4004-W63 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0020 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0021 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-W57 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0022 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-W4 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0023 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4004-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0024 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0025 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-W28 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0026 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-R8 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0027 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-B12 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0028 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-B6 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0035 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4004-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0036 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4004-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0037 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4004-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0038 | Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-B59 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-15T12:31:05.4100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-13T04:43:12.6070000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-13T21:33:36.6200000
T-00176-0039 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-R50 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0044 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T03:00:43.1970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:03:27.0870000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:19:20.7730000
T-00176-0046 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W10 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:50:43.2500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:12:55.2130000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:20:34.3230000
T-00176-0048 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B12 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:51:09.6470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:06:59.3130000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:52:36.9870000
T-00176-0051 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W4 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:51:35.5370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:20:27.0830000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:22:01.0570000
T-00176-0057 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W40 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0058 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R32 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:51:55.7070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:23:42.5270000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:23:23.5370000
T-00176-0060 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W16 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0061 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W4 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0062 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W28 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:52:31.7470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:34:22.6200000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:25:31.4470000
T-00176-0063 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R38 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0064 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R1 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00176-0065 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B65 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:53:09.8670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:47:35.5570000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:32:45.2970000
T-00176-0066 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R1 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-21T20:02:14.2400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T05:58:07.8270000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-21T19:41:23.8500000
T-00176-0067 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:53:31.4000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T21:59:14.3100000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T01:56:10.6400000
T-00176-0068 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R25 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00176-0069 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B36 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0070 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R32 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T04:11:16.1430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T20:53:49.2470000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:09:39.3800000
T-00176-0071 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B42 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:23:57.3700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T20:55:07.0200000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:10:12.9730000
T-00176-0072 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B65 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0073 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B48 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:24:59.8230000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T20:56:34.8530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:10:52.3870000
T-00176-0075 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R37 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:54:14.6500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:27:59.0730000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-10T02:58:10.4470000
T-00176-0076 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B6 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:26:12.5200000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T21:00:02.9170000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:11:22.9830000
T-00176-0077 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W34 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0078 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R8 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:54:40.4270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:08:08.0600000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:59:50.7030000
T-00176-0079 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R14 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0080 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R44 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:27:04.1030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T21:01:23.1700000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:11:47.5330000
T-00176-0081 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W34 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:55:01.2200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:11:24.9770000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:02:18.8470000
T-00176-0082 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T21:57:49.4830000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:40:43.5670000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:28:00.9800000
T-00176-0083 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B36 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:55:21.9470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:14:13.3530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:03:22.6530000
T-00176-0084 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W10 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:38:12.5430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T20:24:59.1830000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:24:58.9300000
T-00176-0085 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R44 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:55:52.3030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:19:16.2270000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:05:41.6630000
T-00176-0086 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0087 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R14 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0088 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W46 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T21:58:18.5000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:43:58.1530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:29:01.1200000
T-00176-0089 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0090 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R1 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:56:20.0100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T00:51:40.9630000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-10T03:16:19.2530000
T-00176-0092 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W63 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T21:58:46.7500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:53:30.0700000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:29:23.0730000
T-00176-0093 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R25 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:56:43.4470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:23:53.3070000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-10T03:15:37.2870000
T-00176-0094 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B65 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T21:59:13.4770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:51:00.4470000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:29:44.5870000
T-00176-0098 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R13 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-14T07:57:55.8900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:35:06.0230000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-13T23:45:11.6430000
T-00176-0099 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B42 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:57:06.1570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:27:02.3070000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:20:10.6530000
T-00176-0100 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R8 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0101 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W63 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:57:43.6630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:31:21.8200000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:21:29.4770000
T-00176-0102 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W63 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0103 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W40 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:58:05.9930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:34:18.5070000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:33:10.8100000
T-00176-0104 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R67 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:58:25.7470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:37:14.6700000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:31:56.0130000
T-00176-0105 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-W69 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:58:46.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:41:52.7170000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:36:52.5630000
T-00176-0106 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W34 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Rejected |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:41:45.1600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0107 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R13 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00176-0108 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R38 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:59:04.9900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:45:30.3100000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:38:13.8600000
T-00176-0109 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R32 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0110 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4001-W52 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0111 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B12 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0112 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-B6 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:59:26.8530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:48:11.6870000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:39:45.5000000
T-00176-0113 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R49 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-26T04:24:16.2700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T06:47:42.5500000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-22T07:30:59.9570000
T-00176-0114 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R25 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:39:00.5600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T20:37:51.5970000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-22T00:25:22.7930000
T-00176-0116 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R13 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:40:45.6800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:02:08.3170000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-22T00:26:34.7330000
T-00176-0117 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W10 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0118 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W40 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T05:57:04.9270000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:09:34.0900000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:26:55.3100000
T-00176-0119 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B42 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0120 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:04:31.9670000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:14:45.3970000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:27:18.5970000
T-00176-0121 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0122 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R44 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0123 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T22:03:10.8570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:57:21.9800000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:31:25.7900000
T-00176-0124 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W28 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:05:04.6930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:19:31.1070000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:27:39.8200000
T-00176-0125 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R37 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:20:58.9470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:21:16.0700000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-22T00:30:09.1600000
T-00176-0126 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R8 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:21:33.5400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:29:02.0600000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:30:33.3030000
T-00176-0127 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B6 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0128 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R49 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T07:59:51.6730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:51:16.7830000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-10T03:40:41.6270000
T-00176-0129 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-W4 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:32:01.5800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:30:36.2930000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:38:42.0030000
T-00176-0130 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-W28 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0131 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T06:33:01.8200000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T22:58:14.6430000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-22T00:38:19.0270000
T-00176-0132 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T08:00:14.1430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:53:54.2230000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:41:48.6030000
T-00176-0134 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4007-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T08:00:36.3130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:56:44.6770000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:43:34.2830000
T-00176-0135 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0136 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4008-R67 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-22T22:03:37.4370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T05:48:03.5400000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-22T07:31:47.2600000
T-00176-0137 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3333DB4009-B12 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0139 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R32 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0140 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R2 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0142 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W4 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0143 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0144 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-B6 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0145 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-B36 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0146 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W10 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0147 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R26 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0148 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-B30 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0149 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W63 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0150 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W34 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0151 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R38 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0152 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W40 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0153 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-R8 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0154 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3332DB4013-W28 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0155 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3331DB4011-R61 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Predecessors Pending |  |  |  | 0.25 |  | 4C+E,10mm2,PVC/SWA/PVC,0.6/1 kV
T-00176-0156 | E2.T037 Lighting and Small Power Energization Stage 2 | CABL | 3338DB4003-R14 | LCBL - Cable for lights of GPO |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Predecessors Pending |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00178-0010 | Earthing Systems Stage 1 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-25T21:08:25.6600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T20:59:31.7770000 |  | 2020-11-25T21:05:40.6570000
T-00178-0016 | Earthing Systems Stage 1 | ELEC | 3338-GE-4001 | GE - GENERATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00178-0017 | Earthing Systems Stage 1 | ELEC | 3338-TF-4002 | TF - TRANSFORMER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T13:58:33.1500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-14T04:52:46.0000000 |  | 2020-12-17T10:01:29.1700000
T-00178-0018 | Earthing Systems Stage 1 | ELEC | 3338-TF-4001 | TF - TRANSFORMER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:00:17.1470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-14T05:50:50.6770000 |  | 2020-12-17T10:02:03.0400000
T-00178-0019 | Earthing Systems Stage 1 | ELEC | 3338-RU-4001 | RU - RING MAIN UNIT | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-21T00:52:18.7300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-14T05:49:10.5530000 |  | 2020-12-17T10:02:19.9570000
T-00178-0021 | Earthing Systems Stage 1 | ELEC | Cadia Molybdenum Plant Earthing System | Earthing - Earthing (General) | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:03:10.9770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-15T04:13:04.6270000 |  | 2020-12-17T10:03:02.5170000
T-00178-0026 | E1.T009 Earthing Systems Stage 1 | ELEC | 3338-SS-4001 | SS - Substation | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-01-14T23:59:45.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2021-01-05T06:09:29.0000000
T-00179-0091 | LV Cable Stage 1 | CABL | 3338BG4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T09:23:44.7870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T00:26:20.5470000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-06T00:20:37.8700000
T-00179-0102 | LV Cable Stage 1 | CABL | 3338BG4003-E1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T09:24:19.3230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T00:20:13.9330000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-06T00:20:55.7000000
T-00179-0106 | LV Cable Stage 1 | CABL | 3338BG4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T09:55:47.1430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T20:57:07.6700000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-06T00:21:15.4070000
T-00179-0107 | LV Cable Stage 1 | CABL | 3338BG4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T09:56:22.4130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T22:15:06.4800000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-06T00:21:47.7930000
T-00179-0117 | LV Cable Stage 1 | CABL | 3338DB4004-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-18T09:57:09.9700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-01T00:18:39.5600000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-06T00:19:44.8770000
T-00179-0118 | LV Cable Stage 1 | CABL | 3338BG4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T10:55:24.2200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T23:43:26.4170000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-06T00:22:06.0500000
T-00179-0126 | LV Cable Stage 1 | CABL | 3338BG4001-E1 | LCBL - Cable for lights of GPO | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T09:47:32.3130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T22:44:13.6470000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-15T06:20:44.5370000
T-00179-0139 | LV Cable Stage 1 | CABL | 3338BG4004-E1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T10:56:42.9870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T23:25:05.4500000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-06T00:22:46.3830000
T-00179-0141 | LV Cable Stage 1 | CABL | 3338DB4001-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-11-18T10:57:14.3230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 |  | 2020-11-02T01:14:33.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-04T04:25:08.0000000
T-00179-0142 | LV Cable Stage 1 | CABL | 3338BG4002-E1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-11-18T10:57:37.9530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-10-31T23:33:03.3900000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-06T00:23:10.6170000
T-00179-0144 | LV Cable Stage 1 | CABL | 3332PU4117-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T10:58:05.0170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T05:11:59.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:42:54.4630000
T-00179-0162 | LV Cable Stage 1 | CABL | 3338MC4002-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T09:48:39.6700000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:01:55.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:31:48.4500000
T-00179-0163 | LV Cable Stage 1 | CABL | 3338MC4002-P4B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:58:59.8100000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:14:59.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:42:43.2630000
T-00179-0167 | LV Cable Stage 1 | CABL | 3338MC4002-P3B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:29:06.8030000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:15:46.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:40:59.6400000
T-00179-0174 | LV Cable Stage 1 | CABL | 3338MC4002-EA | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:59:26.8900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-17T02:21:15.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-17T21:22:00.1770000
T-00179-0175 | LV Cable Stage 1 | CABL | 3331PU4145-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-22T23:53:36.1000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T21:33:55.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:25:04.2570000
T-00179-0186 | LV Cable Stage 1 | CABL | 3332PU4138-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T08:22:45.1400000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-17T04:13:23.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:17:16.1670000
T-00179-0190 | LV Cable Stage 1 | CABL | 3331PU4158-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T10:29:41.2930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-12T05:56:28.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:15:22.4000000
T-00179-0199 | LV Cable Stage 1 | CABL | 3333DY4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:23:23.9600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T01:20:17.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:18:11.6070000
T-00179-0204 | LV Cable Stage 1 | CABL | 3334PU4050-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2020-11-18T10:30:13.7270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-13T06:32:11.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:15:53.7770000
T-00179-0206 | LV Cable Stage 1 | CABL | 3333PU4140-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:23:58.9030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:15:41.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:19:28.8000000
T-00179-0226 | LV Cable Stage 1 | CABL | 3332PU4120-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T10:30:49.4600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-15T04:47:12.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:03:16.8400000
T-00179-0227 | LV Cable Stage 1 | CABL | 3338MC4002-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:31:10.8800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:17:25.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:30:43.4600000
T-00179-0237 | LV Cable Stage 1 | CABL | 3332PU4121-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2020-11-18T10:31:36.8830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-16T02:14:48.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:28:59.3970000
T-00179-0265 | LV Cable Stage 1 | CABL | 3334PU4088-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T10:31:59.3970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T21:11:21.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:17:33.7070000
T-00179-0275 | LV Cable Stage 1 | CABL | 3338MC4002-EB | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:33:07.9470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-17T02:21:31.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-17T21:22:31.0470000
T-00179-0280 | LV Cable Stage 1 | CABL | 3332PU4114-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T10:33:55.7100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T03:38:51.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:04:15.0700000
T-00179-0302 | LV Cable Stage 1 | CABL | 3333PU4141-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:25:29.1530000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:17:23.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:45:30.0070000
T-00179-0308 | LV Cable Stage 1 | CABL | 3334PU4088-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T10:34:29.7730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T21:14:38.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:17:51.8300000
T-00179-0310 | LV Cable Stage 1 | CABL | 3332PU4117-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T09:49:16.3970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T05:15:51.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:43:13.8070000
T-00179-0327 | LV Cable Stage 1 | CABL | 3338MC4002-P4A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:35:02.0800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:19:51.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:42:22.0430000
T-00179-0329 | LV Cable Stage 1 | CABL | 3333PU4153-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:26:02.7030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:19:07.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:49:25.5770000
T-00179-0335 | LV Cable Stage 1 | CABL | 3332PU4118-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T10:35:31.6870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-16T02:17:53.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:26:43.3300000
T-00179-0336 | LV Cable Stage 1 | CABL | 3338MC4002-P2B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:36:30.9270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:20:14.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:38:31.6500000
T-00179-0345 | LV Cable Stage 1 | CABL | 3338MC4002-P3A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T10:37:09.0600000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:20:32.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:40:37.4270000
T-00179-0361 | LV Cable Stage 1 | CABL | 3332PU4032-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-11-18T10:37:54.0870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T04:45:19.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:05:06.9530000
T-00179-0363 | LV Cable Stage 1 | CABL | 3331PU4003-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T11:00:08.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-15T04:58:00.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:23:19.1170000
T-00179-0376 | LV Cable Stage 1 | CABL | 3334PU4086-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:00:42.0370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T20:59:02.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:18:30.5000000
T-00179-0380 | LV Cable Stage 1 | CABL | 3334PU4050-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2020-11-18T11:01:04.1100000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-13T07:01:01.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:18:53.8730000
T-00179-0381 | LV Cable Stage 1 | CABL | 3333PU4152-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:26:31.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:28:44.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:47:59.2070000
T-00179-0384 | LV Cable Stage 1 | CABL | 3338MC4002-P2D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:01:40.3900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:21:41.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:39:31.8830000
T-00179-0385 | LV Cable Stage 1 | CABL | 3332PU4111-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:02:05.0370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:13:00.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:27:45.0800000
T-00179-0390 | LV Cable Stage 1 | CABL | 3338MC4002-P3D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:02:40.7430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:22:50.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:41:57.1300000
T-00179-0391 | LV Cable Stage 1 | CABL | 3332PU4118-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:03:08.3630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-16T02:20:10.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:27:10.8730000
T-00179-0392 | LV Cable Stage 1 | CABL | 3332PU4136-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T08:28:23.8230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-15T04:36:07.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:36:41.9930000
T-00179-0393 | LV Cable Stage 1 | CABL | 3334PU4083-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:03:39.4000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T06:59:35.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:19:14.6970000
T-00179-0400 | LV Cable Stage 1 | CABL | 3332PU4010-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2020-11-18T11:04:03.0870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-16T02:22:17.0000000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-16T06:08:28.8170000
T-00179-0402 | LV Cable Stage 1 | CABL | 3333PU4102-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-12-03T00:39:06.9130000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-18T21:14:32.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T03:11:47.5100000
T-00179-0411 | LV Cable Stage 1 | CABL | 3331PU4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-11-18T11:04:30.9100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-12T01:22:23.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:21:55.2330000
T-00179-0425 | LV Cable Stage 1 | CABL | 3332PU4115-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:05:00.1600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T04:45:43.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:16:51.2200000
T-00179-0427 | LV Cable Stage 1 | CABL | 3332ML4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T11:05:28.2970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-16T02:24:09.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:07:30.1930000
T-00179-0430 | LV Cable Stage 1 | CABL | 3332FN4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:05:52.0930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:13:31.0000000 | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-17T20:26:05.1200000
T-00179-0441 | LV Cable Stage 1 | CABL | 3333FD4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:33:56.0800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:19:18.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:39:30.0270000
T-00179-0442 | LV Cable Stage 1 | CABL | 3331PU4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T11:06:21.8400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-15T05:00:58.0000000 | 3C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-15T06:22:59.5230000
T-00179-0448 | LV Cable Stage 1 | CABL | 3332PU4111-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:06:52.5400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T03:49:59.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:15:34.5430000
T-00179-0451 | LV Cable Stage 1 | CABL | 3332ML4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T11:07:15.4830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-16T02:29:33.0000000 | 3C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-16T06:06:56.1300000
T-00179-0460 | LV Cable Stage 1 | CABL | 3334PU4083-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:07:39.8470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T20:32:14.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:22:21.9930000
T-00179-0461 | LV Cable Stage 1 | CABL | 3331PU4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-11-18T11:09:14.0270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-12T02:36:15.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-11-13T22:51:12.2530000
T-00179-0462 | LV Cable Stage 1 | CABL | 3331PU4004-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T11:10:26.4470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-15T04:46:13.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:25:43.9270000
T-00179-0464 | LV Cable Stage 1 | CABL | 3332PU4030-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T11:11:01.9670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-15T03:57:01.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:12:50.4670000
T-00179-0466 | LV Cable Stage 1 | CABL | 3334PU4084-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:11:27.4530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T20:40:17.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:55:36.6470000
T-00179-0467 | LV Cable Stage 1 | CABL | 3333FD4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:32:09.4900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T01:24:17.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:38:40.3370000
T-00179-0468 | LV Cable Stage 1 | CABL | 3332PU4026-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2020-11-18T11:11:55.6530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-15T04:43:30.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:12:28.9800000
T-00179-0469 | LV Cable Stage 1 | CABL | 3332PU4112-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:12:18.4900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-16T02:35:13.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:20:48.3030000
T-00179-0470 | LV Cable Stage 1 | CABL | 3332PU4114-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:12:45.1370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T04:43:01.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:16:02.4000000
T-00179-0472 | LV Cable Stage 1 | CABL | 3338MC4002-P2A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:13:25.9130000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:25:39.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:36:16.9300000
T-00179-0476 | LV Cable Stage 1 | CABL | 3332PU4136-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T09:27:11.6070000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-15T04:46:08.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:41:35.9200000
T-00179-0481 | LV Cable Stage 1 | CABL | 3332PU4112-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:14:01.5830000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-16T02:37:28.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:21:08.1330000
T-00179-0485 | LV Cable Stage 1 | CABL | 3333PU4141-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:34:30.3930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:45:12.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:44:55.4670000
T-00179-0490 | LV Cable Stage 1 | CABL | 3332PU4135-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T08:34:54.5970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-15T04:58:09.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:41:56.1530000
T-00179-0507 | LV Cable Stage 1 | CABL | 3332PU4014-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2020-11-18T11:14:24.2830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-16T02:40:04.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:09:26.6800000
T-00179-0524 | LV Cable Stage 1 | CABL | 3332PU4121-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2020-11-18T11:14:51.0830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-16T02:41:56.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:29:23.6730000
T-00179-0530 | LV Cable Stage 1 | CABL | 3338MC4002-P2C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:15:26.3930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:25:13.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:39:07.4000000
T-00179-0547 | LV Cable Stage 1 | CABL | 3332PU4138-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T08:35:24.0870000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-17T02:47:08.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:38:06.0870000
T-00179-0549 | LV Cable Stage 1 | CABL | 3333DY4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:36:03.3100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-16T01:46:39.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T05:45:22.7130000
T-00179-0553 | LV Cable Stage 1 | CABL | 3338MC4002-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-19T19:14:55.4970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T22:20:23.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-23T01:11:54.3070000
T-00179-0562 | LV Cable Stage 1 | CABL | 3332PU4014-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2020-11-18T11:15:57.8600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-16T02:44:15.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:09:48.6470000
T-00179-0564 | LV Cable Stage 1 | CABL | 3332PU4135-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-11-18T08:36:30.6230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-15T04:54:21.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:42:25.1800000
T-00179-0565 | LV Cable Stage 1 | CABL | 3332FN4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:17:36.9800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:14:01.0000000 | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-17T20:24:15.3700000
T-00179-0570 | LV Cable Stage 1 | CABL | 3338MC4002-P3C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:18:20.5570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:26:23.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:41:25.3700000
T-00179-0603 | LV Cable Stage 1 | CABL | 3332PU4030-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T11:19:04.0400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-15T04:38:18.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:14:42.5570000
T-00179-0610 | E1.T039 LV Cable Stage 1 | CABL | 3332FN4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-15T21:46:45.1400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-15T07:04:01.0370000 | 3C+3E,50mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-15T07:44:00.0800000
T-00179-0613 | LV Cable Stage 1 | CABL | 3332PU4120-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-11-18T11:19:35.2300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-15T04:37:02.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:17:16.2430000
T-00179-0617 | LV Cable Stage 1 | CABL | 3334PU4084-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:20:09.9470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T20:51:11.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:56:06.6930000
T-00179-0620 | LV Cable Stage 1 | CABL | 3334PU4082-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:20:34.7770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T07:02:22.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:56:28.7800000
T-00179-0623 | LV Cable Stage 1 | CABL | 3334PU4082-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:21:00.8000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T07:05:08.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T22:56:53.8430000
T-00179-0641 | LV Cable Stage 1 | CABL | 3332FN4002-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:21:32.4870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:15:05.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:26:29.7100000
T-00179-0642 | LV Cable Stage 1 | CABL | 3331PU4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T11:22:01.0670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-14T04:42:34.0000000 | 3C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-11-14T19:23:34.6330000
T-00179-0648 | LV Cable Stage 1 | CABL | 3333PU4102-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-12-15T22:56:19.4770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-25T05:31:13.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-07T04:03:51.0400000
T-00179-0651 | LV Cable Stage 1 | CABL | 3338MC4002-P1D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-20T21:45:31.6330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-20T19:55:59.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-12-20T20:03:24.4370000
T-00179-0659 | LV Cable Stage 1 | CABL | 3332PU4026-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2020-11-18T11:23:06.4000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-15T05:02:26.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:11:45.6270000
T-00179-0662 | LV Cable Stage 1 | CABL | 3331PU4158-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2020-11-18T11:25:09.2470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-12T06:54:02.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T23:14:55.6300000
T-00179-0669 | LV Cable Stage 1 | CABL | 3333PU4153-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:36:57.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T04:22:08.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:56:12.9200000
T-00179-0695 | LV Cable Stage 1 | CABL | 3332PU4115-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-11-18T11:25:33.6930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T05:05:13.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:16:25.1830000
T-00179-0702 | LV Cable Stage 1 | CABL | 3333PU4140-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-11-18T08:37:21.0670000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-17T02:49:29.0000000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-17T20:42:39.5700000
T-00179-0709 | LV Cable Stage 1 | CABL | 3332PU4010-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2020-11-18T11:26:01.0200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-16T02:46:15.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-16T06:08:51.7530000
T-00179-0712 | LV Cable Stage 1 | CABL | 3334PU4083-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:44:32.9900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-25T17:53:30.0000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-26T18:54:01.5200000
T-00179-0713 | LV Cable Stage 1 | CABL | 3334PU4086-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2020-11-18T11:26:23.2630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-11-13T21:03:17.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-13T23:15:21.9870000
T-00179-0724 | LV Cable Stage 1 | CABL | 3333PU4103-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-12-03T00:41:09.1400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-18T21:31:39.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T03:13:19.6530000
T-00179-0732 | LV Cable Stage 1 | CABL | 3332PU4032-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-11-18T11:26:48.5030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-15T04:54:38.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-15T06:15:07.0500000
T-00179-0734 | LV Cable Stage 1 | CABL | 3333PU4152-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-12-03T00:41:38.5930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-20T03:34:18.0000000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T07:21:32.7270000
T-00179-0736 | LV Cable Stage 1 | CABL | 3338MC4002-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-11-18T11:27:34.5170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-16T00:27:16.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-16T06:31:24.8170000
T-00179-0756 | LV Cable Stage 1 | CABL | 3338OP4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T22:56:54.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-05T03:42:44.0000000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-07T04:04:34.2470000
T-00179-0763 | LV Cable Stage 1 | CABL | 3338OP4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:05:06.2470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-16T01:15:34.0000000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-17T10:03:19.5900000
T-00179-0767 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4011-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-20T20:15:05.5630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-20T02:37:12.2230000 | 6 mm2 PVC/PVC Trailing with 2P | 2021-03-20T03:17:42.0530000
T-00179-0769 | E1.T039 LV Cable Stage 1 | CABL | 3333SN4004-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0770 | LV Cable Stage 1 | CABL | 3338MC4001-P3B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:51:55.0830000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:50:06.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:01:30.3230000
T-00179-0771 | E1.T039 LV Cable Stage 1 | CABL | 3333AG4006-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0773 | LV Cable Stage 1 | CABL | 3338MC4001-P4A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:51:26.0170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:50:28.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:02:20.0930000
T-00179-0776 | LV Cable Stage 1 | CABL | 3331PU4143-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-22T23:55:45.6870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T21:40:38.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:25:27.1230000
T-00179-0777 | E1.T039 LV Cable Stage 1 | CABL | 3333CO4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0778 | E1.T039 LV Cable Stage 1 | CABL | 3333SN4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0779 | LV Cable Stage 1 | CABL | 3338MC4001-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-21T02:12:58.3430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-21T01:39:15.2370000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-12-21T01:51:18.7500000
T-00179-0780 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4098-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0782 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4012-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:15:11.4070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:09:46.9900000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-28T06:12:38.0270000
T-00179-0783 | LV Cable Stage 1 | CABL | 3333PU4035-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-12-22T23:59:24.2970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-21T22:09:48.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:25:53.0370000
T-00179-0786 | E1.T039 LV Cable Stage 1 | CABL | 3333FD4002-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+3E,16mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0787 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4004-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-11T03:43:02.8270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-10T06:10:16.3700000 | 3C+3E,16mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-11T03:23:39.3400000
T-00179-0789 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4111-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:56:40.1970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-16T05:03:39.9700000 | 3C+3E,10mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-16T06:15:00.2470000
T-00179-0790 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4117-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:29:48.8070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T03:52:36.6500000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-03T00:50:42.2770000
T-00179-0791 | E1.T039 LV Cable Stage 1 | CABL | 3332SN4003-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0792 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4118-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:57:12.2070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T04:47:58.3230000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-18T22:26:54.3100000
T-00179-0793 | E1.T039 LV Cable Stage 1 | CABL | 3333FD4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0794 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4096-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-11T03:43:33.6270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T05:31:22.9230000 | 3C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-11T03:37:38.3100000
T-00179-0795 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4040-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0796 | E1.T039 LV Cable Stage 1 | CABL | 3335DY4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0797 | LV Cable Stage 1 | CABL | 3338XE4008-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T00:52:30.6770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T06:58:23.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T02:32:47.8770000
T-00179-0799 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0800 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4041-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:53:12.3630000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T06:56:49.4500000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-01T04:19:44.8670000
T-00179-0801 | LV Cable Stage 1 | CABL | 3334PU4088-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:45:06.1030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-25T17:56:04.0000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-26T18:54:25.7930000
T-00179-0803 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4009-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T10:22:21.1230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T06:35:09.7000000 | 4 mm2 PVC/PVC Trailing with 3P | 2021-03-19T06:49:35.2000000
T-00179-0804 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4114-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-06T23:14:32.5670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T07:04:20.8070000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:31:30.0100000
T-00179-0807 | E1.T039 LV Cable Stage 1 | CABL | 3332TH4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-15T03:53:35.1800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-13T20:52:57.3000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-14T01:52:42.7270000
T-00179-0808 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4152-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,10mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0809 | LV Cable Stage 1 | CABL | 3338XE4011-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T00:53:01.2000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T07:02:24.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T02:41:53.1730000
T-00179-0810 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4112-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Submitted |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-15T07:34:36.6670000 | 3C+3E,10mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0811 | LV Cable Stage 1 | CABL | 3338MC4001-P1D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:53:29.6830000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:51:33.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:03:06.2270000
T-00179-0812 | E1.T039 LV Cable Stage 1 | CABL | 3333FD4002-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Closed | 2021-04-24T03:05:39.8800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T05:14:56.7370000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-23T07:08:05.2270000
T-00179-0813 | LV Cable Stage 1 | CABL | 3338JX4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:05:42.0300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T02:42:13.0000000 | 4C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-17T07:40:20.2800000
T-00179-0814 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4128-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0815 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4103-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,16mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0816 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4007-P2A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:45:46.7200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T00:42:08.5400000 | 3C+3E,150mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-04T19:20:31.9570000
T-00179-0818 | LV Cable Stage 1 | CABL | 3338TF4001-E | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T23:00:25.6800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-06T06:57:43.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-12-07T04:06:55.9300000
T-00179-0819 | E1.T039 LV Cable Stage 1 | CABL | 3331SN4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0820 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4157-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0822 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4078-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0823 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4118-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:30:20.7030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T03:56:39.1530000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-03T00:51:30.3500000
T-00179-0824 | LV Cable Stage 1 | CABL | 3338DB4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:06:07.6470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-16T00:13:25.0000000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-17T07:40:43.8830000
T-00179-0825 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4022-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-05T06:42:55.0970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-04T20:47:55.3870000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-05T02:31:24.6870000
T-00179-0826 | E1.T039 LV Cable Stage 1 | CABL | 3331HE4006-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-21T01:57:26.2570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-20T05:00:31.6370000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-20T21:09:16.0330000
T-00179-0827 | LV Cable Stage 1 | CABL | 3331PU4146-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-22T23:57:01.3430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T21:44:20.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:26:24.7570000
T-00179-0828 | LV Cable Stage 1 | CABL | 3338MC4001-P3D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:54:00.2770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:51:59.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:03:24.7870000
T-00179-0829 | E1.T039 LV Cable Stage 1 | CABL | 3332FN4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-02-05T06:43:26.1600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-04T20:58:32.7130000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-05T02:47:12.8930000
T-00179-0830 | LV Cable Stage 1 | CABL | 3335PU4091-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2020-12-15T23:01:01.6230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-05T04:02:49.0000000 | 3C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-07T04:07:51.7530000
T-00179-0831 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4014-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T00:47:40.6870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:31:31.1130000 | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-31T02:16:42.4670000
T-00179-0832 | E1.T039 LV Cable Stage 1 | CABL | 3331FN4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:07:41.8570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T05:53:33.8000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T07:07:33.8800000
T-00179-0833 | LV Cable Stage 1 | CABL | 3338MC4001-P4B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:54:33.2000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T06:06:41.3870000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:07:08.1570000
T-00179-0834 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4121-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:48:13.9500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T19:54:47.4070000 | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-31T02:16:59.9370000
T-00179-0835 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4018-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0836 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4081-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0837 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4043-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:45:11.1870000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T07:00:53.0500000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-01T04:20:29.1170000
T-00179-0838 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4015-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0839 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4230-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T06:58:31.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T21:14:21.1600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-16T04:17:25.9530000
T-00179-0840 | LV Cable Stage 1 | CABL | 3338MC4001-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:55:07.7930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T22:12:18.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-23T01:08:04.4370000
T-00179-0841 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4115-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0842 | E1.T039 LV Cable Stage 1 | CABL | 3334PK4007-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0843 | LV Cable Stage 1 | CABL | 3338MC4001-P3A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:55:57.1330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:53:16.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:07:29.1800000
T-00179-0846 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4126-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0847 | E1.T039 LV Cable Stage 1 | CABL | 3338GE4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0850 | LV Cable Stage 1 | CABL | 3334PU4083-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:34:03.7870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T12:00:53.6530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T19:26:47.7670000
T-00179-0851 | LV Cable Stage 1 | CABL | 3331PU4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-22T23:57:35.5870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T02:16:02.3430000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-21T21:05:00.4000000
T-00179-0852 | E1.T039 LV Cable Stage 1 | CABL | 3338PF4001-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-25T13:29:19.0430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T15:34:06.0000000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-24T22:01:40.1700000
T-00179-0853 | LV Cable Stage 1 | CABL | 3331DB4011-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2020-12-22T23:58:24.4130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T22:07:34.0000000 | 4C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-22T02:26:49.5000000
T-00179-0854 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4111-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-06T23:15:07.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T06:56:39.5300000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:31:49.8800000
T-00179-0855 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4097-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0856 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4011-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:00:34.7800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T05:10:38.2200000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-13T07:00:38.4130000
T-00179-0857 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4130-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0858 | LV Cable Stage 1 | CABL | 3331PU4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-23T00:00:20.9200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T02:24:54.6170000 | 3C+3E,10mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-21T21:10:55.0170000
T-00179-0859 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4109-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:56:20.8130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T03:37:37.4100000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-07T03:58:48.5300000
T-00179-0860 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4112-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-06T23:15:39.9800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T06:59:41.1930000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:32:16.1770000
T-00179-0861 | E1.T039 LV Cable Stage 1 | CABL | 3332SA4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-06T23:17:32.7230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T07:07:28.6230000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:33:11.9230000
T-00179-0863 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4076-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0865 | E1.T039 LV Cable Stage 1 | CABL | 3333HE4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0866 | E1.T039 LV Cable Stage 1 | CABL | 3331CN4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-11T06:10:37.6470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-11T05:27:04.8670000 | 4C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-11T06:04:41.9970000
T-00179-0867 | LV Cable Stage 1 | CABL | 3338TF4002-E | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T23:01:37.7370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-06T06:57:09.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-12-07T04:08:22.2930000
T-00179-0868 | LV Cable Stage 1 | CABL | 3338XE4101-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T00:56:34.0400000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T06:42:20.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T02:44:25.3130000
T-00179-0869 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4095-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:01:04.0200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T05:32:55.1100000 | 3C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-11T03:43:46.5000000
T-00179-0870 | E1.T039 LV Cable Stage 1 | CABL | 3333HE4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,50mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0871 | LV Cable Stage 1 | CABL | 3338MC4001-P3C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:57:13.3730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:53:36.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:07:49.4970000
T-00179-0872 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4040-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 6 mm2 PVC/PVC Trailing with 3P
T-00179-0873 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4141-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0874 | E1.T039 LV Cable Stage 1 | CABL | 3333FD4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Closed | 2021-04-24T03:06:04.3530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T05:17:04.6830000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-23T07:09:15.3070000
T-00179-0875 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4013-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:16:21.8800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:24:38.0430000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-28T06:12:59.0330000
T-00179-0877 | E1.T039 LV Cable Stage 1 | CABL | 3333DY4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0878 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4013-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:29:43.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-29T00:15:34.9070000 | 4 mm2 PVC/PVC Trailing with 3P | 2021-03-29T00:43:06.7430000
T-00179-0881 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4102-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:30:57.5170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:36:12.6430000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-23T19:27:08.7430000
T-00179-0883 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4151-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0884 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4001-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0885 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4016-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0886 | E1.T039 LV Cable Stage 1 | CABL | 3334DB4010-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Closed | 2021-02-19T00:40:05.3830000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-18T04:36:32.8870000 | 4C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-18T04:44:16.7530000
T-00179-0887 | E1.T039 LV Cable Stage 1 | CABL | 3331HE4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-21T01:57:59.0030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-20T04:53:37.5570000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-20T21:10:01.0730000
T-00179-0888 | LV Cable Stage 1 | CABL | 3334PU4086-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:46:46.6630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-25T17:44:44.0000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-26T19:01:54.2770000
T-00179-0889 | LV Cable Stage 1 | CABL | 3332PU4022-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-12-03T00:57:48.1600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-20T04:30:48.0000000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T07:21:55.9470000
T-00179-0890 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4003-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0891 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4030-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T03:25:41.9470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-21T01:09:07.8400000 | 3C+3E,4mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-03-21T01:48:16.1870000
T-00179-0892 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:18:21.2100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T04:11:14.7130000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-19T04:35:35.2700000
T-00179-0893 | LV Cable Stage 1 | CABL | 3338MC4001-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:58:17.2870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:53:57.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:08:16.2570000
T-00179-0894 | E1.T039 LV Cable Stage 1 | CABL | 3331TH4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T04:47:35.4070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-02T02:14:03.4600000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-02T19:53:39.2830000
T-00179-0895 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4034-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T22:00:47.8670000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T07:02:34.7270000 | 6 mm2 PVC/PVC Trailing with 3P | 2021-04-25T07:24:52.4370000
T-00179-0896 | LV Cable Stage 1 | CABL | 3338OP4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:06:36.1170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-14T07:45:36.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-17T07:41:14.2430000
T-00179-0897 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4002-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0898 | LV Cable Stage 1 | CABL | 3331AG4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:02:09.5030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-10T19:53:28.0000000 | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-12T05:47:04.0530000
T-00179-0900 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4077-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0901 | LV Cable Stage 1 | CABL | 3338MC4001-EB | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T00:59:19.2430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T20:23:25.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-23T01:10:35.1700000
T-00179-0903 | LV Cable Stage 1 | CABL | 3338XE4101-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T00:59:53.7870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T06:52:44.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC | 2020-11-20T02:46:17.8670000
T-00179-0905 | E1.T039 LV Cable Stage 1 | CABL | 3334AG4012-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0906 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4099-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0907 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4093-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-15T11:01:36.6230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T05:56:58.3270000 | 4C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-11T06:54:34.6500000
T-00179-0909 | LV Cable Stage 1 | CABL | 3334PU4084-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:48:05.7430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-25T17:47:50.0000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-26T20:20:58.8830000
T-00179-0910 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4012-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:31:39.2230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T23:48:39.9400000 | 6 mm2 PVC/PVC Trailing with 3P | 2021-03-29T00:43:26.4770000
T-00179-0911 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4022-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T21:33:24.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:58:10.3230000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-15T03:45:59.8400000
T-00179-0912 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4003-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0913 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4158-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T04:48:32.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T06:37:33.7900000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-31T07:04:10.3370000
T-00179-0915 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4001-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0917 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4026-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:08:43.6100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T05:37:40.0570000 | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-23T07:01:17.9500000
T-00179-0918 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4153-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,10mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0920 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4105-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0922 | E1.T039 LV Cable Stage 1 | CABL | 3332SA4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-27T08:41:09.9930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T02:20:56.4870000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-27T05:12:48.3870000
T-00179-0924 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4014-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T00:48:44.0930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:44:24.0570000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-31T02:18:08.1530000
T-00179-0925 | E1.T039 LV Cable Stage 1 | CABL | 3333CN4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0927 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4018-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0928 | E1.T039 LV Cable Stage 1 | CABL | 3338PF4001-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-25T13:30:41.4870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T15:42:09.0000000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-24T22:03:46.9270000
T-00179-0929 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4123-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0930 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4007-P2B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:49:01.9370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T00:48:48.0830000 | 3C+3E,150mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-04T19:21:09.5800000
T-00179-0931 | LV Cable Stage 1 | CABL | 3334PU4082-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:34:34.5870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T12:00:01.7130000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T19:27:35.5070000
T-00179-0932 | E1.T039 LV Cable Stage 1 | CABL | 3332SA4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-06T23:18:04.3570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T07:09:36.8830000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:33:37.6470000
T-00179-0933 | LV Cable Stage 1 | CABL | 3338MC4001-P2B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:00:32.0400000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:54:25.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:08:43.3830000
T-00179-0934 | E1.T039 LV Cable Stage 1 | CABL | 3338GE4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0938 | LV Cable Stage 1 | CABL | 3338MC4001-EA | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:01:19.2170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T20:27:36.0000000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-11-23T01:11:06.9570000
T-00179-0940 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4094-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-15T11:02:08.5400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T06:06:26.9100000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-11T06:56:11.1370000
T-00179-0941 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4104-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:31:17.3330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:57:42.7500000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-23T19:28:13.3270000
T-00179-0942 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4007-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:08:19.2970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:01:59.1400000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T07:08:01.7670000
T-00179-0943 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4009-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T10:23:06.7700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T05:55:19.4030000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-19T05:56:03.2200000
T-00179-0946 | LV Cable Stage 1 | CABL | 3333PU4035-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2020-12-23T00:00:57.2500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-21T22:00:24.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:27:06.7800000
T-00179-0947 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4110-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T04:57:05.5270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T03:38:27.4700000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-07T04:09:51.4070000
T-00179-0948 | E1.T039 LV Cable Stage 1 | CABL | 3333CN4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0949 | E1.T039 LV Cable Stage 1 | CABL | 3338PF4002-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-28T04:53:07.7870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-27T04:57:12.4370000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-27T21:09:36.3400000
T-00179-0950 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4107-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:25:54.2600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T22:31:29.5400000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T23:09:25.3570000
T-00179-0951 | LV Cable Stage 1 | CABL | 3335PU4090-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2020-12-18T07:19:18.7930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T04:38:21.3430000 | 3C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-18T07:11:26.7300000
T-00179-0952 | LV Cable Stage 1 | CABL | 3331AG4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:04:53.1530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-10T19:55:18.0000000 | 3C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-12T05:47:38.0200000
T-00179-0954 | E1.T039 LV Cable Stage 1 | CABL | 3333MC4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0955 | LV Cable Stage 1 | CABL | 3331PU4144-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-23T00:01:38.3030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T21:47:25.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-22T02:27:24.3370000
T-00179-0956 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4106-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0957 | E1.T039 LV Cable Stage 1 | CABL | 3331SA4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:40:07.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:42:47.5130000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-13T07:02:04.1700000
T-00179-0958 | LV Cable Stage 1 | CABL | 3338XE4008-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T01:04:13.6370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T06:56:21.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T02:46:41.4600000
T-00179-0959 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4032-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-29T20:31:50.7230000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-20T23:57:09.5770000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-22T23:50:42.2470000
T-00179-0960 | E1.T039 LV Cable Stage 1 | CABL | 3331OP4201-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:56:07.8770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T06:32:03.7570000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-03T06:37:44.3230000
T-00179-0961 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4129-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0963 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4124-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0964 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4113-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-06T23:16:08.2070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T07:01:18.1170000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-06T07:34:31.3900000
T-00179-0965 | E1.T039 LV Cable Stage 1 | CABL | 3338PF4002-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-28T04:53:30.4470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-27T04:59:39.2270000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-27T21:10:46.6070000
T-00179-0966 | LV Cable Stage 1 | CABL | 3334PU4082-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:50:33.9070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-25T17:50:20.0000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2020-12-26T19:05:28.7970000
T-00179-0967 | E1.T039 LV Cable Stage 1 | CABL | 3332TH4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-15T03:54:15.9470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-13T20:54:24.7230000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-14T01:53:02.7300000
T-00179-0968 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4131-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0969 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4101-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:32:19.0700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:37:12.9800000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-23T20:04:52.4100000
T-00179-0970 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4002-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0972 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4122-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0974 | E1.T039 LV Cable Stage 1 | CABL | 3332FN4002-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T20:57:40.9100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T23:05:30.8900000 | 3C+3E,50mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-19T03:52:41.4170000
T-00179-0975 | LV Cable Stage 1 | CABL | 3338MC4001-P2D | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:04:43.6000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T06:09:59.0200000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:10:28.3870000
T-00179-0977 | LV Cable Stage 1 | CABL | 3331PU4007-P1C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:03:35.5200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T04:11:24.0000000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-07T04:10:23.2900000
T-00179-0978 | LV Cable Stage 1 | CABL | 3331PU4007-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:06:57.4170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T04:17:01.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-07T04:11:03.2130000
T-00179-0979 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4022-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-01T00:49:10.7900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T21:10:45.0730000 | 3C+3E,4mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-31T02:18:30.5830000
T-00179-0982 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:18:41.6030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T04:03:33.4770000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-19T04:43:37.1270000
T-00179-0983 | LV Cable Stage 1 | CABL | 3338MC4001-P2A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:05:10.4170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:55:26.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:11:19.4670000
T-00179-0984 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4025-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T00:49:38.4130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:15:25.7070000 | 3C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-31T02:19:12.2730000
T-00179-0985 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4079-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0986 | LV Cable Stage 1 | CABL | 3338DB4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T23:07:33.0430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-07T06:03:40.0000000 | 4C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-07T20:30:33.7170000
T-00179-0987 | LV Cable Stage 1 | CABL | 3338XE4011-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-03T01:05:40.9070000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-18T07:00:17.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-20T02:47:10.8170000
T-00179-0988 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4102-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,16mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0990 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4127-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0991 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4156-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0992 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4028-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-25T21:09:36.6870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-25T01:28:12.4130000 | 4 mm2 PVC/PVC Trailing with 3P | 2021-04-25T07:12:52.2300000
T-00179-0993 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4001-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-0994 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4154-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:02:35.6070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-12T06:48:24.9030000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-12T19:14:03.9470000
T-00179-0995 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4080-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-0996 | LV Cable Stage 1 | CABL | 3331PU4007-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:08:18.1700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T04:09:42.0000000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-07T04:12:35.7770000
T-00179-0997 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4034-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-02T03:02:41.7330000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-29T20:04:56.0500000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-02T00:45:24.7870000
T-00179-0998 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4050-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-0999 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4125-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1003 | LV Cable Stage 1 | CABL | 3334PU4086-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:35:21.4600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T12:02:17.6600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T20:05:21.8970000
T-00179-1006 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4105-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:32:40.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T06:16:36.9600000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-23T20:05:54.5200000
T-00179-1008 | E1.T039 LV Cable Stage 1 | CABL | 3331HE4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:08:51.5970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T05:56:42.1170000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-16T07:08:28.0400000
T-00179-1010 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4007-P2C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:51:04.8330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T00:53:29.7330000 | 3C+3E,150mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-04T19:21:40.9430000
T-00179-1011 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4148-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T14:03:40.5170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-10T21:43:49.5730000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-11T05:08:06.8100000
T-00179-1013 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4071-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1014 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4032-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-29T20:33:00.9500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-20T23:52:58.3800000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-22T23:53:03.9470000
T-00179-1015 | E1.T039 LV Cable Stage 1 | CABL | 3332SN4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1017 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4002-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1018 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4010-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:32:15.2770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T18:00:20.3870000 | 3C+3E,35mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-02-21T19:57:37.3070000
T-00179-1019 | LV Cable Stage 1 | CABL | 3331FN4006-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T04:52:40.6670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-26T10:46:45.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-12-26T20:21:40.3600000
T-00179-1021 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4030-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T03:26:08.5370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-21T01:39:22.5670000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-21T01:48:40.0930000
T-00179-1022 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4140-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-1023 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1024 | LV Cable Stage 1 | CABL | 3338MC4001-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-19T19:29:18.0430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:55:46.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:11:52.6300000
T-00179-1025 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4117-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T21:02:04.8470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T04:50:41.7000000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-18T22:28:19.0770000
T-00179-1026 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4138-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:38:06.7700000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:48:05.4330000 | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-06T07:37:01.0700000
T-00179-1027 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4015-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1028 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4120-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:28:14.0770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T01:57:47.7830000 | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-03-28T03:08:44.9970000
T-00179-1029 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4070-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1031 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4108-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:27:25.6530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T20:21:39.6830000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-27T20:42:27.4170000
T-00179-1033 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4119-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-20T21:03:15.4630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T04:41:51.0230000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-19T06:32:30.4170000
T-00179-1035 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4035-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-1036 | LV Cable Stage 1 | CABL | 3334PU4084-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:35:51.2530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T12:01:37.6600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T20:06:55.8700000
T-00179-1037 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4155-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:03:01.3670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T05:02:19.1870000 | 3C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-11T03:47:56.9130000
T-00179-1038 | E1.T039 LV Cable Stage 1 | CABL | 3331SN4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1040 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4072-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1041 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4024-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-21T01:58:31.4470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-20T06:30:34.1000000 | 3C+E,25mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-20T21:10:29.8800000
T-00179-1042 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4044-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:46:04.3770000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T07:05:11.0300000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-01T04:21:01.3000000
T-00179-1043 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4135-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:38:43.3370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:26:14.2130000 | 3C+3E,6mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-06T07:38:16.2670000
T-00179-1044 | E1.T039 LV Cable Stage 1 | CABL | 3335CP4003-P1B | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 3C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1045 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4028-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:04:49.7800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T05:50:24.6200000 | 3C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-23T06:57:04.1870000
T-00179-1046 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4003-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:03:23.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-10T06:11:25.7730000 | 3C+3E,16mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-01-11T03:49:27.7170000
T-00179-1047 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4114-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 3C+3E,2.5mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-1048 | LV Cable Stage 1 | CABL | 3331PU4007-P1A | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-15T23:09:13.3630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T04:08:28.0000000 | 3C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-07T04:13:13.5530000
T-00179-1050 | E1.T039 LV Cable Stage 1 | CABL | 3332ML4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:52:30.5670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T05:40:30.0670000 | 3C+3E,70mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-02-27T21:03:46.8970000
T-00179-1051 | LV Cable Stage 1 | CABL | 3338MC4001-P2C | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:06:48.0900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-11-22T03:56:35.0000000 | 1C, 630 mm2, XLPE/PVC, 0.6/1 kV | 2020-11-22T06:12:13.9570000
T-00179-1052 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4147-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T14:04:11.0130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-10T21:37:40.7670000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-11T05:08:29.8070000
T-00179-1053 | E1.T039 LV Cable Stage 1 | CABL | 3332AG4103-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:33:40.0200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:46:01.9330000 | 3C+E,35mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-23T20:07:32.4970000
T-00179-1054 | E1.T039 LV Cable Stage 1 | CABL | 3334PU4075-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1055 | LV Cable Stage 1 | CABL | 3334PU4088-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:36:19.9630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T12:03:13.8870000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T20:09:54.5900000
T-00179-1058 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4110-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T06:14:42.4970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:02:24.8670000 | 3C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-28T06:07:03.6770000
T-00179-1062 | LV Cable Stage 1 | CABL | 3338OP4001-J6 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:07:31.4900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T03:57:12.0000000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:12:41.4170000
T-00179-1063 | LV Cable Stage 1 | CABL | 3338OP4001-J7 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:08:15.1600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T02:49:37.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:13:06.0170000
T-00179-1064 | LV Cable Stage 1 | CABL | 3338OP4001-J3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:08:53.1770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T02:52:40.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:13:26.9970000
T-00179-1065 | LV Cable Stage 1 | CABL | 3338OP4001-J2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:13:52.9930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T03:42:27.0000000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:13:46.9470000
T-00179-1066 | LV Cable Stage 1 | CABL | 3338OP4001-J4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:15:35.9730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T03:58:00.0000000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:14:05.6270000
T-00179-1067 | LV Cable Stage 1 | CABL | 3338OP4001-J8 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:16:27.3570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T03:41:12.0000000 | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:14:24.0100000
T-00179-1068 | LV Cable Stage 1 | CABL | 3338OP4001-J1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:17:24.5630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T04:01:19.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:14:46.7670000
T-00179-1069 | LV Cable Stage 1 | CABL | 3338OP4001-J5 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-03T01:18:00.2200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T04:04:59.0000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2020-11-22T06:15:12.5400000
T-00179-1076 | E1.T039 LV Cable Stage 1 | CABL | 3338DB4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:58:35.0470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-14T04:11:02.1300000 | 4C+E,70mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-14T05:15:30.2070000
T-00179-1080 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4008-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-15T23:59:34.2830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-15T04:06:12.6400000 | 4C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-02-15T22:47:25.5700000
T-00179-1082 | LV Cable Stage 1 | CABL | 3338BR4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:11:35.8970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T03:48:35.0000000 | 4C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2020-12-18T04:08:12.9370000
T-00179-1087 | LV Cable Stage 1 | CABL | 3338RU4001-E1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-21T02:15:57.8730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T01:58:40.9730000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-12-21T01:58:58.4330000
T-00179-1088 | LV Cable Stage 1 | CABL | 3338RU4001-E2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-21T02:16:30.1900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T01:57:11.4330000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2020-12-21T01:57:51.3870000
T-00179-1091 | E1.T039 LV Cable Stage 1 | CABL | 3332PU4136-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:39:13.4900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:33:53.3970000 | 3C+3E,4mm2,XLPE/SCR/PVC,0.6/1 kV | 2021-04-06T07:40:11.7800000
T-00179-1092 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4016-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1097 | E1.T039 LV Cable Stage 1 | CABL | 3331DB4007-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-10T04:55:37.3970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-02T23:56:43.7600000 | 4C+E,150mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-03T05:08:21.4030000
T-00179-1100 | E1.T039 LV Cable Stage 1 | CABL | 3338DB4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-14T05:58:01.4600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-14T04:15:28.5270000 | 4C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-03-14T05:15:02.5330000
T-00179-1101 | E1.T039 LV Cable Stage 1 | CABL | 3331PU4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-29T20:42:25.8930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-21T02:01:19.3470000 | 3C+E,10mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-22T23:54:18.6130000
T-00179-1102 | E1.T039 LV Cable Stage 1 | CABL | 3333PU4103-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-12T09:16:47.4730000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-12T02:41:48.7670000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-12T06:50:48.8800000
T-00179-1122 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0084-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:04:41.8830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T09:43:10.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:27:40.2970000
T-00179-1123 | E1.T039 LV Cable Stage 1 | CABL | 3331DB4007-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-01-15T11:03:48.9670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T06:35:32.1900000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-12T19:15:18.9200000
T-00179-1124 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4002-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1129 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4113-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T08:01:05.0100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T23:04:46.8170000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:34:43.9270000
T-00179-1131 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1132 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4112-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T08:01:29.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T22:40:27.1630000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:36:30.1500000
T-00179-1133 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4004-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1136 | E1.T039 LV Cable Stage 1 | CABL | 3334FD4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:57:46.6600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T14:19:57.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-04T19:24:56.2230000
T-00179-1138 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4108-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-09T03:54:07.9030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T22:38:08.7600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-07T23:49:17.1930000
T-00179-1141 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4019-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1142 | E1.T039 LV Cable Stage 1 | CABL | 3338OP4002-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-01-21T01:59:32.7800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-20T06:51:54.5700000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-20T21:10:56.2730000
T-00179-1147 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4005-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1148 | E1.T039 LV Cable Stage 1 | CABL | 3338RU4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-01-10T04:58:28.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-07T22:58:50.7230000 | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-08T00:09:22.2100000
T-00179-1153 | E1.T039 LV Cable Stage 1 | CABL | 3331DIT0033-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-18T00:41:38.4530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-17T05:10:12.2900000 | SEE MP1000-RFI-0057 | 2021-03-17T19:04:42.1670000
T-00179-1154 | E1.T039 LV Cable Stage 1 | CABL | 3334BL4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T04:58:56.5570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T13:57:45.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-04T19:25:39.9630000
T-00179-1155 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4205-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-15T03:51:01.7930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-13T20:51:53.6130000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-14T01:00:06.0070000
T-00179-1156 | E1.T039 LV Cable Stage 1 | CABL | 3334AG4013-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:51:20.5200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T17:14:12.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-23T20:10:43.8070000
T-00179-1158 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4118-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T08:01:52.4070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T03:53:01.9530000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:56:09.0430000
T-00179-1162 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0081-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:05:06.3830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T09:23:44.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:30:03.1900000
T-00179-1163 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:06:10.4270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T09:27:16.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:30:18.9770000
T-00179-1164 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4065-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:11:37.4930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T02:31:14.8830000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-19T04:04:31.4730000
T-00179-1165 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4206-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-15T03:51:35.1700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-13T20:47:57.6430000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-14T01:00:24.8100000
T-00179-1166 | E1.T039 LV Cable Stage 1 | CABL | 3332SA4002A-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:40:32.7470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T00:55:18.5070000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-13T06:21:19.7130000
T-00179-1170 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4103-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:21:16.0270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T06:31:33.9430000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-17T19:27:51.1370000
T-00179-1172 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4111-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T08:03:33.3530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:40:21.5330000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:40:51.2270000
T-00179-1173 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:06:33.7470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T09:45:41.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:41:58.1570000
T-00179-1174 | E1.T039 LV Cable Stage 1 | CABL | 3331DIT0056-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-18T00:42:17.1230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-17T05:12:15.6900000 | SEE MP1000-RFI-0057 | 2021-03-17T19:06:10.8500000
T-00179-1176 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1177 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4110-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-09T03:54:33.3530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T22:37:02.5800000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-07T23:49:36.2900000
T-00179-1180 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4019-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1186 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4114-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T08:04:10.4770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-09T23:15:29.5170000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T02:37:41.1870000
T-00179-1187 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4066-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T02:31:36.0830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T00:33:57.8000000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-21T00:55:42.4070000
T-00179-1188 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4067-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-07T06:55:51.3130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T05:21:01.3300000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-07T05:27:03.0830000
T-00179-1190 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4101-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:29:06.6370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T06:24:02.3370000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-17T19:23:25.5700000
T-00179-1192 | E1.T039 LV Cable Stage 1 | CABL | 3333DB4009-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1195 | E1.T039 LV Cable Stage 1 | CABL | 3331SA4001C-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:40:54.6670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T06:48:11.2630000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-13T07:02:35.1170000
T-00179-1196 | E1.T039 LV Cable Stage 1 | CABL | 3338BR4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-10T05:01:13.3200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-07T22:43:03.9070000 | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-08T00:08:25.8000000
T-00179-1198 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4068-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-09T04:07:10.0970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-07T22:38:47.5900000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-08T02:42:42.8400000
T-00179-1204 | E1.T039 LV Cable Stage 1 | CABL | 3332JB4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:09:44.3330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-12T06:27:22.4900000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-12T07:46:54.6770000
T-00179-1205 | E1.T039 LV Cable Stage 1 | CABL | 3338GE4001-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1206 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4006-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1207 | E1.T039 LV Cable Stage 1 | CABL | 3331DIT0032-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T03:13:39.9600000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-20T22:45:59.8100000 | SEE MP1000-RFI-0057 | 2021-04-21T07:40:49.3730000
T-00179-1209 | E1.T039 LV Cable Stage 1 | CABL | 3331SA4001A-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:41:39.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T05:16:53.4530000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-13T06:21:44.5300000
T-00179-1211 | E1.T039 LV Cable Stage 1 | CABL | 3331OP4202-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T05:07:02.6830000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-03T01:38:01.0970000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-03T05:15:44.0570000
T-00179-1213 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1215 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4104-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T02:12:12.6400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T02:12:10.0600000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-18T04:43:34.4770000
T-00179-1218 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0007-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:07:32.0270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T09:59:29.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:42:22.4870000
T-00179-1219 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4109-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-09T03:55:04.3900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T22:35:19.6730000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-07T23:49:53.4700000
T-00179-1221 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0008-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:07:57.2100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T10:02:06.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:46:59.4800000
T-00179-1222 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4006-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1224 | E1.T039 LV Cable Stage 1 | CABL | 3335OP4204-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-11T13:57:46.4730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-10T21:32:43.2670000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-11T04:54:16.7600000
T-00179-1225 | E1.T039 LV Cable Stage 1 | CABL | 3338DB4005-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,50mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1226 | E1.T039 LV Cable Stage 1 | CABL | 3331DIT0074-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T03:14:02.6070000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-20T22:47:14.8830000 | SEE MP1000-RFI-0057 | 2021-04-21T07:41:32.2970000
T-00179-1231 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4105-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:31:48.4230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T06:42:30.9200000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-17T19:25:13.7530000
T-00179-1232 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4221-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1233 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4006-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1235 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4102-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:35:38.9170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T06:27:56.2500000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-17T19:25:45.9630000
T-00179-1236 | E1.T039 LV Cable Stage 1 | CABL | 3338OP4002-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-01-21T02:42:12.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-20T06:55:30.4630000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-20T21:11:21.9370000
T-00179-1238 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4117-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T08:06:24.9900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T03:48:56.6700000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-10T03:55:33.6670000
T-00179-1241 | E1.T039 LV Cable Stage 1 | CABL | 3334OP4201-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:08:22.7000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-03T18:13:10.5000000 | 4C+E,16mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-01-03T20:34:41.2870000
T-00179-1243 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0009-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:04:13.2230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T06:19:56.3470000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-11T06:56:31.2330000
T-00179-1244 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4013-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV
T-00179-1248 | E1.T039 LV Cable Stage 1 | CABL | 3334VI4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:09:52.0670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T13:59:27.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-04T19:26:17.7500000
T-00179-1253 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:10:24.6670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T10:14:19.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:50:00.6070000
T-00179-1256 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4012-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-25T22:01:11.4100000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T07:00:41.7630000 | 4C+E,95mm2,XLPE/SWA/PVC,0.6/1 kV | 2021-04-25T07:25:16.0200000
T-00179-1258 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4003-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1260 | E1.T039 LV Cable Stage 1 | CABL | 3338XE4101-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1263 | E1.T039 LV Cable Stage 1 | CABL | 3333DB4009-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1266 | E1.T039 LV Cable Stage 1 | CABL | 3332HT4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,4mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1267 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4107-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-09T03:55:37.1370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-07T22:37:40.2330000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-07T23:50:11.7870000
T-00179-1274 | E1.T039 LV Cable Stage 1 | CABL | 3338AC4001-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1275 | E1.T039 LV Cable Stage 1 | CABL | 3331FV0082-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:10:50.3230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-01T10:16:33.0000000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-01T19:50:18.8970000
T-00179-1276 | E1.T039 LV Cable Stage 1 | CABL | 3334AT4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:03:02.9670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T13:58:55.0000000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-01-04T19:27:41.8270000
T-00179-1277 | E1.T039 LV Cable Stage 1 | CABL | 3332SA4002C-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:42:03.9670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T00:44:35.9230000 | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-13T06:22:09.9100000
T-00179-1279 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4013-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1280 | E1.T039 LV Cable Stage 1 | CABL | 3332DB4008-W22 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-01T05:24:28.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T20:42:03.3770000 | 4C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-28T21:25:01.9430000
T-00179-1281 | E1.T039 LV Cable Stage 1 | CABL | 3332DIT0527-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-25T21:05:51.1530000 |  |  | 0.25 | 2021-04-24T07:39:30.4370000 | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV | 2021-04-25T07:10:25.6570000
T-00179-1282 | E1.T039 LV Cable Stage 1 | CABL | 3332HE4007C-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.25 |  | VENDOR CABLE
T-00179-1283 | E1.T039 LV Cable Stage 1 | CABL | 3332HE4007A-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Checked Out by Llwyd Saul |  |  |  | 0.25 |  | VENDOR CABLE
T-00179-1284 | E1.T039 LV Cable Stage 1 | CABL | 3332HE4007B-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Started |  |  |  | 0.25 |  | VENDOR CABLE
T-00179-1285 | E1.T039 LV Cable Stage 1 | CABL | 3335PK4009-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1286 | E1.T039 LV Cable Stage 1 | CABL | 3335PK4026-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1287 | E1.T039 LV Cable Stage 1 | CABL | 3333-CV-4001-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1288 | E1.T039 LV Cable Stage 1 | CABL | 3334HE4008-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.25 |  | VENDOR CABLE
T-00179-1289 | E1.T039 LV Cable Stage 1 | CABL | 3333-CV-4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1290 | E1.T039 LV Cable Stage 1 | CABL | 3333-FN-4007-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1291 | E1.T039 LV Cable Stage 1 | CABL | 3333-CV-4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1292 | E1.T039 LV Cable Stage 1 | CABL | 3334HE4008-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1293 | E1.T039 LV Cable Stage 1 | CABL | 3333-FN-4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1294 | E1.T039 LV Cable Stage 1 | CABL | 23PLC08-PWR-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 4C 1.3mm2 Cu PVC/PVC
T-00179-1295 | E1.T039 LV Cable Stage 1 | CABL | 3333-CV-4004-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1296 | E1.T039 LV Cable Stage 1 | CABL | 3334HE4008-P3 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.25 |  | VENDOR CABLE
T-00179-1297 | E1.T039 LV Cable Stage 1 | CABL | 3333-VI-4002-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1298 | E1.T039 LV Cable Stage 1 | CABL | 3333-VI-4003-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1299 | E1.T039 LV Cable Stage 1 | CABL | 3335PU4057-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Created |  |  |  | 0.25 |  | 2C+E,6mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1300 | E1.T039 LV Cable Stage 1 | CABL | 3333HE4002-P2 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 3C+E,50mm2,XLPE/SCR/PVC,0.6/1 kV
T-00179-1301 | E1.T039 LV Cable Stage 1 | CABL | 3333FD4001-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1302 | E1.T039 LV Cable Stage 1 | CABL | 3335-PU-4160-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC
T-00179-1303 | E1.T039 LV Cable Stage 1 | CABL | 3335-PU-4159-P1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Created |  |  |  | 0.25 |  | 3C+E,2.5mm2,PVC/SWA/PVC
T-00179-1304 | E1.T039 LV Cable Stage 1 | CABL | 3333DY4001-P4 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,2.5mm2,PVC/SWA/PVC,0.6/1 kV
T-00179-1305 | E1.T039 LV Cable Stage 1 | CABL | 3332OP4230-E1 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T01:24:25.0500000 |  |  | 0.25 | 2021-04-19T05:33:46.5700000 | 1C, 120 mm2, PVC, 0.6/1 kV (G/Y EARTH CABLE) | 2021-04-19T06:29:26.4470000
T-00180-0010 | Cable Support Stage 1 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2020-11-25T21:09:14.1470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-25T21:01:46.7270000 |  | 2020-11-25T21:05:59.2870000
T-00180-0016 | E.T006 Cable Support Stage 1 | CABL | 3338TF4001-P1 | HVCBL - High Voltage Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:19:56.6970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T00:35:01.7670000 | 3C, 120 mm2, XLPE/SCR/SWA/PVC, 19/33kV | 2020-12-18T07:11:42.4770000
T-00184-0062 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0187 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T00:42:10.0770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T23:41:18.0070000 |  | 2021-03-02T04:14:33.7930000
T-00184-0064 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-1061B | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0065 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0441 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:58:18.6400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:41:45.5700000 |  | 2021-04-14T07:22:55.0030000
T-00184-0066 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0462 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:59:03.6870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T02:14:07.6470000 |  | 2021-04-17T04:08:41.1900000
T-00184-0068 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0577A | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00184-0069 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0491 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-02T02:03:21.8730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:40:06.2900000 |  | 2021-04-02T00:38:56.6030000
T-00184-0071 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0104 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-28T04:11:49.8300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:36:57.4670000 |  | 2021-02-27T20:22:08.2130000
T-00184-0072 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0307 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-10T08:06:46.2400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:58:18.3530000 |  | 2021-04-10T03:02:55.7900000
T-00184-0073 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0491 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-02T02:03:45.2370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T22:42:13.6730000 |  | 2021-04-02T00:39:16.5670000
T-00184-0074 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0307 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T05:39:28.6070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T02:08:57.6830000 |  | 2021-04-11T03:40:41.2970000
T-00184-0076 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0104 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-28T04:18:48.3800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:38:16.7300000 |  | 2021-02-27T20:24:26.0770000
T-00184-0078 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0462 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T06:59:30.8130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:48:49.9030000 |  | 2021-04-16T06:56:58.0370000
T-00184-0079 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0166 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:16:28.3470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T23:45:50.2330000 |  | 2021-02-19T00:06:14.2700000
T-00184-0081 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0142 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:17:08.9400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T23:36:58.6970000 |  | 2021-02-18T23:44:38.4600000
T-00184-0082 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0441 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T07:58:41.3570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:41:17.4730000 |  | 2021-04-14T07:24:41.1070000
T-00184-0083 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-1061A | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0085 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0577B | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00184-0087 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0106 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-21T05:26:40.3730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T01:22:50.5670000 |  | 2021-02-21T05:05:30.1270000
T-00184-0088 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0142 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:18:07.8600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T23:46:35.6700000 |  | 2021-02-19T00:07:05.7000000
T-00184-0089 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-1061 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0090 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0187 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T02:07:27.0030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T23:39:31.6500000 |  | 2021-03-02T05:12:39.6270000
T-00184-0091 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0166 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:18:52.7670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T23:45:10.8100000 |  | 2021-02-19T00:07:33.9700000
T-00184-0107 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3334-UI-0694 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0108 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3338-UI-1151 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0109 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3338-UI-1150 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0110 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0577 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00184-0111 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UI-0196 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T00:43:20.6370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T23:47:42.3030000 |  | 2021-03-02T05:13:17.5000000
T-00184-0112 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3334-UI-0693 | UI - BEACON | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00184-0113 | I1.T027 Warning / Alarm / Beacon Device Stage 1 | INST | 3332-UA-0196 | UA - Siren | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T00:43:46.0170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T23:44:16.9130000 |  | 2021-03-02T05:11:55.5770000
T-00185-0062 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0187 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0064 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-1061B | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0065 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0441 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0066 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0462 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0068 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0577A | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0069 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0491 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0071 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0104 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0072 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0307 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0073 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0491 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0074 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0307 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0076 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0104 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0078 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0462 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0079 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0166 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0081 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0142 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0082 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0441 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00185-0083 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-1061A | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0085 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0577B | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0087 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0106 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0088 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0142 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0089 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-1061 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0090 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0187 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0091 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0166 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0108 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3334-UI-0694 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0109 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3338-UI-1151 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0110 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3338-UI-1150 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0111 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0577 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0112 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UI-0196 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00185-0113 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3334-UI-0693 | UI - BEACON |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00185-0114 | I2.T027 Warning / Alarm / Beacon Device Stage 2 | INST | 3332-UA-0196 | UA - Siren |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00186-0011 | Temp Asset stage 1 | MISC | Temp Cable (3338-BR-4001_P) | Item - Temporary Items used for commissioning and construction only | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-11T22:32:34.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2020-12-11T20:30:13.0000000
T-00186-0012 | Temp Asset stage 1 | MISC | Temp Cable (3338-BR-4001_E) | Item - Temporary Items used for commissioning and construction only | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-11T22:32:51.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  |  | 2020-12-11T20:30:38.0000000
T-00186-0013 | Paper Checksheet Asset Stage 1 | CABL | 3338DB4004-R37 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:08:27.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  | 2C+E,16mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-14T05:07:05.0000000
T-00186-0014 | Paper Checksheet Asset Stage 1 | CABL | 3338DB4004-B41 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:08:15.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  | 2C+E,16mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-14T05:06:28.0000000
T-00186-0015 | Paper Checksheet Asset Stage 1 | CABL | 3338DB4004-R43 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:08:41.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  | 2C+E,16mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-14T05:07:24.0000000
T-00186-0016 | Paper Checksheet Asset Stage 1 | CABL | 3338DB4004-W39 | CBL - General Purpose Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:07:45.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 |  | 2C+E,16mm2,PVC/SWA/PVC,0.6/1 kV | 2021-03-14T05:07:44.0000000
T-00187-0099 | E1.T043 LV Motor Stage 1 | ELEC | 3332-FN-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-15T21:47:23.9800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-15T06:21:20.6530000 |  | 2021-04-15T06:45:34.8170000
T-00187-0100 | E1.T043 LV Motor Stage 1 | ELEC | 3334-AG-4012-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0101 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4084-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:51:49.8730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T11:40:05.8430000 |  | 2021-01-23T20:12:10.9770000
T-00187-0102 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4114-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0103 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4141-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0104 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4005-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T00:50:14.1670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T22:17:45.0900000 |  | 2021-01-31T02:21:27.3400000
T-00187-0105 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4140-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0106 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4007-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:04:49.8630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T21:28:17.1670000 |  | 2021-01-05T00:45:16.4500000
T-00187-0107 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4104-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:43:02.9670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T06:08:12.2130000 |  | 2021-01-29T20:27:56.9370000
T-00187-0108 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4026-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:00:18.3430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T05:03:13.7900000 |  | 2021-04-17T05:05:28.8300000
T-00187-0109 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4044-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:46:35.6470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T22:17:22.6500000 |  | 2021-03-01T04:32:48.1600000
T-00187-0110 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4105-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0111 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4103-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:43:42.8000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:56:51.1500000 |  | 2021-01-29T20:30:03.3270000
T-00187-0112 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4035-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0113 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4110-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:31:31.4870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T05:00:17.4070000 |  | 2021-02-27T20:35:03.2800000
T-00187-0115 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4146-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:13:23.8430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:18:01.4500000 |  | 2021-01-05T00:50:01.7900000
T-00187-0116 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4111-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:24:54.2930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-16T05:42:37.1500000 |  | 2021-04-16T06:20:03.4330000
T-00187-0117 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4118-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T06:12:11.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:13:48.8830000 |  | 2021-04-03T06:06:27.9670000
T-00187-0118 | E1.T043 LV Motor Stage 1 | ELEC | 3333-AG-4006-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0119 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4098-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0121 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4088-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:52:17.2630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T11:49:06.0100000 |  | 2021-01-23T20:12:52.8700000
T-00187-0122 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4004-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-01T03:07:14.3700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-31T04:12:44.1730000 |  | 2021-01-31T23:33:23.5930000
T-00187-0123 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4013-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:17:38.8100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T06:33:00.5330000 |  | 2021-03-28T07:06:51.0100000
T-00187-0124 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FN-4006-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:18:23.5970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-05T05:46:01.4000000 |  | 2021-01-06T20:57:24.5170000
T-00187-0125 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4090-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-01-29T20:44:16.7370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-27T22:21:20.0330000 |  | 2021-01-28T00:52:33.3530000
T-00187-0126 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4095-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:05:16.2470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T05:06:52.8030000 |  | 2021-01-11T03:55:36.5430000
T-00187-0128 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4120-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:41:50.1230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T06:09:17.2800000 |  | 2021-03-26T06:51:19.3570000
T-00187-0129 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4143-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:14:07.9570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T21:38:33.4230000 |  | 2021-01-05T00:47:18.4770000
T-00187-0131 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4109-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:39:01.1600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T04:36:33.3170000 |  | 2021-02-27T20:41:03.1170000
T-00187-0132 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4155-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T05:14:52.9730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T04:43:01.0930000 |  | 2021-01-10T04:53:16.5570000
T-00187-0133 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4050-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0134 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4122-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0135 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4028-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-25T21:31:06.0270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-25T03:50:55.8770000 |  | 2021-04-25T07:13:40.4370000
T-00187-0136 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4158-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:06:05.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-05T00:02:39.5870000 |  | 2021-01-05T00:50:37.2470000
T-00187-0137 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4080-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0138 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4057-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0140 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4102-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0142 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4152-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0143 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4102-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:45:23.8270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:54:26.7100000 |  | 2021-01-29T20:31:14.4170000
T-00187-0144 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4014-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T02:55:57.7500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T22:55:50.3700000 |  | 2021-01-31T02:22:00.9600000
T-00187-0145 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4011-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:06:40.7530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T06:00:50.9430000 |  | 2021-01-13T07:05:06.8870000
T-00187-0146 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4108-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:39:29.0100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T04:38:39.5100000 |  | 2021-02-27T05:21:52.7400000
T-00187-0147 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4121-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:03:06.2900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:50:00.7100000 |  | 2021-01-29T21:02:39.7870000
T-00187-0148 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4009-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-20T20:35:09.0530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-20T00:06:02.3630000 |  | 2021-03-20T03:14:24.4700000
T-00187-0150 | E1.T043 LV Motor Stage 1 | ELEC | 3331-AG-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:21:22.1630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-04T22:25:26.0730000 |  | 2021-01-05T00:42:49.7170000
T-00187-0151 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4094-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-29T20:45:56.8800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-25T22:27:26.9200000 |  | 2021-01-28T05:36:48.1530000
T-00187-0152 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4117-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T06:12:53.4870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:00:22.7230000 |  | 2021-04-03T06:08:41.0930000
T-00187-0153 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4117-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:25:33.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T05:22:14.9330000 |  | 2021-04-18T22:28:49.9100000
T-00187-0154 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4043-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:47:16.1700000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T22:22:16.0130000 |  | 2021-03-01T04:34:14.3370000
T-00187-0155 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4135-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:37:18.8070000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T07:35:31.8370000 |  | 2021-04-06T07:46:08.7330000
T-00187-0156 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4147 M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:09:45.0670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T19:59:15.9370000 |  | 2021-02-16T20:41:01.8230000
T-00187-0157 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4159-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0158 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4105-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:46:46.2570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T06:17:26.0370000 |  | 2021-01-29T20:32:04.8670000
T-00187-0159 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4145-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:20:08.4000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:08:35.1370000 |  | 2021-01-05T00:49:44.5230000
T-00187-0160 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4004-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T00:47:07.0200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T21:50:53.4470000 |  | 2021-02-18T01:00:43.5070000
T-00187-0162 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4093-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-11T13:58:51.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-08T21:09:32.1430000 |  | 2021-02-11T04:55:13.3130000
T-00187-0163 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4151-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0164 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4107-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:25:09.8670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:03:26.0770000 |  | 2021-02-28T05:24:55.0600000
T-00187-0165 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4091-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-01-29T20:47:14.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-27T22:30:02.2600000 |  | 2021-01-28T00:53:04.9270000
T-00187-0166 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4103-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0167 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4096-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:07:11.9030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-10T05:29:41.6330000 |  | 2021-01-11T03:50:44.1870000
T-00187-0168 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4113-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-07T04:51:59.6170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T23:33:43.1070000 |  | 2021-04-06T23:42:11.1230000
T-00187-0169 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4157-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0170 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4111-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-07T04:52:49.2630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T23:12:37.0400000 |  | 2021-04-06T23:42:38.1800000
T-00187-0171 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4138-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:36:30.8000000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T23:05:27.6970000 |  | 2021-04-06T23:48:28.4900000
T-00187-0172 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4156-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0173 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4106-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0174 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4126-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0176 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4030-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T05:37:32.9100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-21T02:53:50.6730000 |  | 2021-03-21T05:16:43.6870000
T-00187-0177 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4076-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0178 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4097-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0179 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4024-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-30T21:46:30.2400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-29T21:43:17.3030000 |  | 2021-01-30T00:22:42.2270000
T-00187-0180 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4115-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0181 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4078-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0182 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4144-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:21:51.0800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T21:54:25.9530000 |  | 2021-01-05T00:48:59.3470000
T-00187-0183 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4112-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-07T04:53:46.5830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T23:17:31.7400000 |  | 2021-04-06T23:43:31.1270000
T-00187-0184 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4082-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:52:52.7370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T11:27:49.8470000 |  | 2021-01-23T20:13:30.2000000
T-00187-0185 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4086-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:53:27.6170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T11:44:48.2330000 |  | 2021-01-23T20:14:11.1330000
T-00187-0186 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4118-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:26:01.9970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T05:38:34.9270000 |  | 2021-04-18T22:29:19.8770000
T-00187-0187 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4131-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0188 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4025-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-30T21:47:24.6670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-29T21:44:15.4600000 |  | 2021-01-30T00:23:06.0970000
T-00187-0189 | E1.T043 LV Motor Stage 1 | ELEC | 3334-FD-4003-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:07:53.3370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-04T18:10:22.1500000 |  | 2021-01-04T19:44:40.6700000
T-00187-0190 | E1.T043 LV Motor Stage 1 | ELEC | 3333-FN-4004-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0191 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4128-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0192 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4072-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0193 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4148-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T14:10:21.1830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-11T00:19:10.5570000 |  | 2021-02-11T05:09:26.9870000
T-00187-0194 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4005-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-29T20:47:39.4600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-21T04:50:05.8070000 |  | 2021-01-22T23:54:53.2400000
T-00187-0195 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4034-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T22:01:42.9670000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T03:53:24.6930000 |  | 2021-04-25T07:25:57.4630000
T-00187-0196 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4154-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:08:22.7400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-12T19:58:11.7970000 |  | 2021-01-13T03:26:35.7700000
T-00187-0197 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4101-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:48:16.8770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:46:27.8200000 |  | 2021-01-29T20:32:27.7030000
T-00187-0198 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4110-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T06:15:17.2500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:42:41.3070000 |  | 2021-02-28T06:07:57.5600000
T-00187-0199 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4083-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:53:53.4270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T11:33:51.9830000 |  | 2021-01-23T20:15:26.5130000
T-00187-0200 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4153-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0201 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4041-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:48:16.5370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T22:26:33.6570000 |  | 2021-03-01T04:35:41.5600000
T-00187-0202 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4119-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:27:43.6530000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T05:21:06.8400000 |  | 2021-04-19T06:33:11.1300000
T-00187-0203 | E1.T043 LV Motor Stage 1 | ELEC | 3333-FD-4002-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0204 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4070-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0205 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4052-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0206 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FN-4005-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:10:34.3470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T20:12:36.1130000 |  | 2021-02-16T20:41:20.9000000
T-00187-0207 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4032-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-03T22:56:28.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-03T06:34:37.2130000 |  | 2021-04-03T22:33:47.7070000
T-00187-0208 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4129-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0209 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4125-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0210 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4060-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0211 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4003-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-01T03:08:14.1070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-31T04:11:27.0000000 |  | 2021-01-31T23:34:16.7900000
T-00187-0212 | E1.T043 LV Motor Stage 1 | ELEC | 3331-PU-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-29T20:48:46.5000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-28T02:17:51.6770000 |  | 2021-01-28T05:33:48.8630000
T-00187-0213 | E1.T043 LV Motor Stage 1 | ELEC | 3332-FN-4002-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:35:06.6170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T23:08:42.5100000 |  | 2021-04-19T03:53:11.0570000
T-00187-0215 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4022-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-01T03:08:49.2570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T21:15:22.0130000 |  | 2021-01-31T02:22:27.4430000
T-00187-0216 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4136-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-07T04:35:43.1430000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T07:38:12.6900000 |  | 2021-04-06T07:48:28.4200000
T-00187-0217 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4124-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0218 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4130-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0219 | E1.T043 LV Motor Stage 1 | ELEC | 3333-FD-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0220 | E1.T043 LV Motor Stage 1 | ELEC | 3334-BL-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:08:55.0970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-04T18:07:01.0600000 |  | 2021-01-04T19:46:55.0800000
T-00187-0221 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4099-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00187-0222 | E1.T043 LV Motor Stage 1 | ELEC | 3332-AG-4114-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-07T04:54:24.7430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T23:45:37.4630000 |  | 2021-04-06T23:48:58.3170000
T-00187-0223 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4079-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0224 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4112-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-21T03:38:53.2570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-16T05:48:43.3800000 |  | 2021-04-16T06:20:30.8030000
T-00187-0225 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4012-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:32:57.1770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T23:45:16.9270000 |  | 2021-03-29T00:44:08.9900000
T-00187-0226 | E1.T043 LV Motor Stage 1 | ELEC | 3333-PU-4040-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0227 | E1.T043 LV Motor Stage 1 | ELEC | 3331-AG-4002-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:23:45.3170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:31:47.9100000 |  | 2021-01-05T00:43:16.9870000
T-00187-0228 | E1.T043 LV Motor Stage 1 | ELEC | 3335-PU-4160-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00187-0229 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4081-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0230 | E1.T043 LV Motor Stage 1 | ELEC | 3334-AG-4013-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:09:27.7230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-05T18:14:22.5470000 |  | 2021-01-06T20:58:39.6400000
T-00187-0231 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4077-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0232 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4123-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0233 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4071-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0234 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4127-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0235 | E1.T043 LV Motor Stage 1 | ELEC | 3334-PU-4075-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00187-0236 | E1.T043 LV Motor Stage 1 | ELEC | 3332-PU-4010-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:33:26.5300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T17:55:22.4170000 |  | 2021-02-21T19:58:18.7570000
T-00187-0237 | E1.T043 LV Motor Stage 1 | ELEC | 3334-VI-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:10:27.9930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-05T17:36:10.0970000 |  | 2021-01-06T21:00:18.0670000
T-00187-0238 | E1.T043 LV Motor Stage 1 | ELEC | 3334-AT-4001-M1 | MO - Motor | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:11:04.7770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-05T17:19:44.0300000 |  | 2021-01-06T21:01:02.7100000
T-00187-0239 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0082 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:24:17.7530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T02:38:58.9030000 |  | 2021-03-19T04:21:34.8300000
T-00187-0240 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0009 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:26:34.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T01:55:10.2230000 |  | 2021-03-19T04:22:26.5570000
T-00187-0241 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0007 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:25:15.6230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T01:56:53.6670000 |  | 2021-03-19T04:23:21.2370000
T-00187-0242 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0005 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T22:25:48.7100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-25T22:06:32.0630000 |  | 2021-03-25T22:07:41.5330000
T-00187-0243 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0002 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:30:41.1830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T01:58:46.8900000 |  | 2021-03-19T04:25:04.7170000
T-00187-0244 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0008 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:31:20.2830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T02:22:56.9530000 |  | 2021-03-19T04:25:43.0200000
T-00187-0245 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0084 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:32:01.4570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T02:23:55.2770000 |  | 2021-03-19T04:26:23.1430000
T-00187-0246 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0003 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:32:41.1400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T01:53:10.7170000 |  | 2021-03-19T04:27:08.2930000
T-00187-0247 | E1.T043 LV Motor Stage 1 | ELEC | 3331-FV-0081 | MOV - Motorised Valve | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-19T10:33:34.5170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T02:33:20.2400000 |  | 2021-03-19T04:30:03.7500000
T-00189-0001 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4155 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:49:10.9000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:45:25.8500000 |  | 2021-01-24T02:59:42.6500000
T-00189-0002 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4112 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T03:09:22.0170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-31T00:45:05.8170000 |  | 2021-01-31T02:28:05.5900000
T-00189-0003 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4014 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T03:10:00.5100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T22:53:50.9770000 |  | 2021-01-31T02:28:45.0030000
T-00189-0004 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4090 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2020-12-15T23:11:51.4670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-05T05:00:42.0000000 |  | 2020-12-07T04:17:39.3530000
T-00189-0005 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4086 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:56:55.6970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:26:15.7430000 |  | 2021-01-24T02:51:17.4870000
T-00189-0006 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4012 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-25T13:16:34.5570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-25T06:18:03.1670000 |  | 2021-02-25T06:21:07.9300000
T-00189-0007 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4034 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T03:10:51.4470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T00:55:10.6330000 |  | 2021-01-31T02:31:51.0770000
T-00189-0008 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4032 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T21:50:20.9100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-25T00:59:44.4300000 |  | 2021-04-25T07:22:19.0370000
T-00189-0009 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4159 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Closed | 2021-02-01T03:11:13.5400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T00:57:26.9170000 |  | 2021-01-31T02:32:40.7000000
T-00189-0010 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4044 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-01T03:11:47.1430000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T01:01:08.1770000 |  | 2021-01-31T03:05:41.6230000
T-00189-0012 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-CN-4002 | CN - CRANE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-01T03:12:17.1100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-31T01:03:46.2900000 |  | 2021-01-31T23:34:48.8230000
T-00189-0013 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4102 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:49:39.6130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:25:24.6970000 |  | 2021-01-29T20:39:32.3430000
T-00189-0014 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4121 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2020-12-03T01:18:57.6370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-20T04:46:41.0000000 |  | 2020-11-20T07:22:27.6370000
T-00189-0015 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-FN-4002 | FN - FAN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:19:23.4400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-20T04:49:50.0000000 |  | 2020-11-20T07:23:29.6830000
T-00189-0017 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-AG-4002 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:26:53.2270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-08T02:47:28.9770000 |  | 2021-01-08T02:55:27.1030000
T-00189-0018 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-ML-4001 | ML - REGRIND MILL | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-12-03T01:19:46.6770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-20T20:42:32.0000000 |  | 2020-11-21T01:59:05.3770000
T-00189-0019 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-FD-4001 | FD - SCREW FEEDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00189-0020 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4110 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-01T03:12:41.1470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-31T01:10:00.5970000 |  | 2021-01-31T23:51:30.5170000
T-00189-0021 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4035 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T03:13:18.2900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T01:12:37.7770000 |  | 2021-01-31T23:37:30.2100000
T-00189-0022 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4084 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:58:53.8670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:37:21.3370000 |  | 2021-01-24T02:51:48.4500000
T-00189-0023 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4026 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2020-12-03T01:20:13.1570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-20T04:58:57.0000000 |  | 2020-11-20T07:23:52.0200000
T-00189-0024 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4010 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2020-12-03T01:20:33.6000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-22T04:14:50.0000000 |  | 2020-11-22T06:16:14.9870000
T-00189-0025 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4117 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-02-01T03:13:58.7700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T01:16:06.5300000 |  | 2021-01-31T23:38:02.7630000
T-00189-0028 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4082 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T03:00:32.1230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:29:40.9670000 |  | 2021-01-24T02:52:07.3870000
T-00189-0029 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4091 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2020-12-15T23:12:19.2770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-05T20:37:19.0000000 |  | 2020-12-07T04:18:04.4770000
T-00189-0030 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4028 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T22:12:02.3330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-01T05:07:18.1870000 |  | 2021-02-01T20:38:22.2730000
T-00189-0031 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-CN-4001 | CN - CRANE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T03:14:27.9930000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T01:19:09.4470000 |  | 2021-01-31T23:40:20.5200000
T-00189-0032 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4030 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:42:17.7570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T05:48:58.8070000 |  | 2021-03-27T05:52:52.0870000
T-00189-0034 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4005 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:11:50.6770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T20:31:19.0000000 |  | 2020-12-21T21:43:19.1770000
T-00189-0035 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4095 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-25T03:32:36.7300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T22:16:23.0800000 |  | 2021-02-24T22:36:30.9130000
T-00189-0036 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4110 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T06:15:47.3170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:29:02.7270000 |  | 2021-03-01T04:18:08.3770000
T-00189-0038 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4105 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-30T21:47:53.1700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:42:20.2000000 |  | 2021-01-30T00:23:26.8000000
T-00189-0041 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4153 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-02-01T03:15:26.0970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T01:24:37.3570000 |  | 2021-02-01T00:51:03.4970000
T-00189-0043 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-CP-4001 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Closed | 2021-02-25T13:40:43.6930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T02:47:37.7500000 |  | 2021-02-25T05:00:56.2370000
T-00189-0045 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4111 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T03:15:51.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-31T01:27:05.3670000 |  | 2021-02-01T00:50:45.4400000
T-00189-0046 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-TH-4002 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-01T03:16:15.0470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-31T01:32:23.8200000 |  | 2021-02-01T00:50:25.7130000
T-00189-0048 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4112 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:20:54.3270000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-20T04:26:10.0000000 |  | 2020-11-20T07:24:38.7830000
T-00189-0053 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4117 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-01T03:16:44.6800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-31T22:26:55.7600000 |  | 2021-02-01T00:50:02.4770000
T-00189-0054 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4120 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-12-03T01:21:17.2270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-11-22T04:16:13.0000000 |  | 2020-11-22T06:16:34.9700000
T-00189-0056 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-AG-4006 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T03:17:55.0900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T22:38:25.2600000 |  | 2021-02-01T00:47:53.7130000
T-00189-0057 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-AG-4012 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2021-02-01T03:18:32.1300000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T22:43:36.3970000 |  | 2021-02-01T00:47:35.0500000
T-00189-0058 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4007 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-16T04:29:10.0000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-16T02:21:20.5600000 |  | 2021-03-16T02:26:44.3370000
T-00189-0059 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4152 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-02-01T03:19:00.2930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T22:48:18.3670000 |  | 2021-02-01T00:47:17.4770000
T-00189-0060 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4107 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-01T03:19:31.0430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-31T22:30:15.9370000 |  | 2021-02-01T00:46:59.4530000
T-00189-0061 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4136 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-01T03:19:59.0330000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T22:53:22.7230000 |  | 2021-02-01T00:46:37.8270000
T-00189-0063 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4052 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00189-0065 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4157 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-02-01T03:20:24.6570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-31T23:41:40.1570000 |  | 2021-02-01T00:46:15.1300000
T-00189-0068 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-HE-4002 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00189-0071 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4004 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-12-03T01:21:42.7730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T04:16:47.0000000 |  | 2020-11-22T06:17:05.1530000
T-00189-0072 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4024 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T03:21:03.9900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T22:46:54.6470000 |  | 2021-01-31T02:33:03.6500000
T-00189-0073 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-TH-4001 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T05:28:38.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T06:59:20.9370000 |  | 2020-12-31T07:04:56.7600000
T-00189-0074 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4111 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:22:03.1200000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-22T04:17:24.0000000 |  | 2020-11-22T06:17:26.9370000
T-00189-0075 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-FN-4001 | FN - FAN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:22:25.5430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-22T04:18:01.0000000 |  | 2020-11-22T06:29:58.6370000
T-00189-0082 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4003 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2020-12-03T01:22:51.8300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-11-22T04:18:37.0000000 |  | 2020-11-22T06:30:36.6800000
T-00189-0084 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4041 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-01T03:21:30.3500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-31T23:47:11.5570000 |  | 2021-02-01T00:45:47.4670000
T-00189-0085 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-SN-4003 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-01T03:22:16.2500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T23:39:59.3870000 |  | 2021-01-31T02:33:25.2430000
T-00189-0087 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4160 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Closed | 2021-02-27T04:22:09.2770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-26T04:04:25.1600000 |  | 2021-02-26T05:07:16.9600000
T-00189-0091 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-CP-4003 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Closed | 2021-02-25T13:41:07.0870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T03:40:57.9070000 |  | 2021-02-25T05:02:35.2000000
T-00189-0092 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4040 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T22:12:30.1500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-01T05:09:54.5630000 |  | 2021-02-01T20:38:51.9370000
T-00189-0093 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4083 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T03:00:52.6900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:48:08.9330000 |  | 2021-01-24T02:52:22.6670000
T-00189-0094 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4099 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Closed | 2021-02-25T13:14:41.4330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T06:46:08.3470000 |  | 2021-02-25T06:59:25.9300000
T-00189-0096 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-AG-4001 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:29:08.6370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-05T03:56:56.1800000 |  | 2021-01-05T04:51:58.3730000
T-00189-0097 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4004 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T22:12:55.4200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-01T05:13:07.4370000 |  | 2021-02-01T20:39:12.2470000
T-00189-0098 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4097 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Closed | 2021-02-01T22:13:21.2200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-01T05:16:46.2470000 |  | 2021-02-01T20:39:29.4070000
T-00189-0102 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4115 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:23:46.1970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-20T20:36:23.0000000 |  | 2020-11-21T22:57:57.4130000
T-00189-0103 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4135 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-01T03:22:47.4930000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-30T23:35:54.5470000 |  | 2021-01-31T02:33:50.9870000
T-00189-0104 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4009 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-02-01T22:13:45.6100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-01T05:22:42.2870000 |  | 2021-02-01T20:39:53.2270000
T-00189-0105 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4158 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T05:29:32.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T06:54:54.7470000 |  | 2020-12-31T07:05:21.1300000
T-00189-0106 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-SA-4004 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T22:14:13.2600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-01T05:25:21.3830000 |  | 2021-02-01T20:42:03.0770000
T-00189-0107 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-FD-4002 | FD - SCREW FEEDER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Closed | 2021-02-27T04:23:29.6330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T21:04:19.1770000 |  | 2021-02-26T05:11:48.7130000
T-00189-0108 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4141 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-12-03T01:24:15.0200000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-22T04:19:07.0000000 |  | 2020-11-22T06:31:05.9570000
T-00189-0111 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4109 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-01T22:15:21.8470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-01T05:28:52.8430000 |  | 2021-02-01T20:42:27.2670000
T-00189-0112 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4050 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00189-0113 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4094 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-15T11:12:14.5170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T22:48:22.4430000 |  | 2021-01-12T05:48:48.1930000
T-00189-0115 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4154 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-02-01T22:15:44.0600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-01T05:35:42.3900000 |  | 2021-02-01T20:42:50.3870000
T-00189-0116 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4103 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-01T22:16:52.2630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-01T05:39:32.0200000 |  | 2021-02-01T20:43:26.3100000
T-00189-0117 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4103 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-30T21:48:23.3400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:29:38.6170000 |  | 2021-01-30T00:23:49.4370000
T-00189-0118 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-SA-4003 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T22:17:22.1730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-01T05:42:14.1130000 |  | 2021-02-01T20:43:59.1630000
T-00189-0119 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4011 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:51:19.7200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T19:49:06.7970000 |  | 2021-02-20T20:46:15.8270000
T-00189-0120 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4104 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-30T21:48:49.1470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:35:48.7570000 |  | 2021-01-30T00:24:07.5500000
T-00189-0121 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4088 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T03:01:59.1170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T02:44:18.8000000 |  | 2021-01-24T02:52:38.9870000
T-00189-0122 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4043 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-27T04:27:58.4300000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-26T00:25:23.6000000 |  | 2021-02-26T05:15:35.8130000
T-00189-0124 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4013 | PU - SUMP PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-03T23:07:55.6700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-02T00:43:12.9700000 |  | 2021-02-02T21:55:32.1900000
T-00189-0126 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4096 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-25T03:33:27.8200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T22:50:23.0570000 |  | 2021-02-24T23:15:08.2770000
T-00189-0128 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4101 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:50:05.6470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T20:21:13.6030000 |  | 2021-01-29T20:43:25.3970000
T-00189-0129 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-SN-4001 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-02-03T23:10:28.6570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T00:44:10.6730000 |  | 2021-02-02T21:56:01.8670000
T-00189-0130 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4005 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-03T23:10:58.2170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-02T00:46:18.0870000 |  | 2021-02-02T21:56:39.9030000
T-00189-0133 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-TH-4003 | TH - THICKENER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-03T23:11:48.4970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-02T00:51:23.3000000 |  | 2021-02-02T21:57:04.1800000
T-00189-0135 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-SN-4004 | SN - SCREEN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-27T04:23:58.5870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-25T21:33:12.9270000 |  | 2021-02-26T05:13:05.4530000
T-00189-0136 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4001 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-23T00:07:10.4500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T20:28:36.0000000 |  | 2020-12-21T21:43:59.6370000
T-00189-0137 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4114 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00189-0138 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4025 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T03:23:16.5570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T22:51:34.0170000 |  | 2021-01-31T02:34:12.2700000
T-00189-0139 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4102 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-03T23:32:12.2100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-02T00:54:10.0330000 |  | 2021-02-02T22:02:12.9830000
T-00189-0140 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4118 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-03T23:34:45.8670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T00:58:48.1030000 |  | 2021-02-02T22:03:10.4170000
T-00189-0141 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4098 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Closed | 2021-02-25T13:15:07.4570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T06:44:27.8800000 |  | 2021-02-25T06:59:06.6870000
T-00189-0142 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4022 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2020-12-03T01:24:43.0470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-11-20T21:07:50.0000000 |  | 2020-11-21T22:57:06.2830000
T-00189-0144 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-SA-4001 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-02-27T04:21:47.7500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-25T23:48:34.3770000 |  | 2021-02-26T05:06:55.3270000
T-00189-0145 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4114 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-03T23:35:23.0570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T01:00:48.0500000 |  | 2021-02-02T22:04:04.1770000
T-00189-0146 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4118 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2020-12-03T01:25:51.6400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-22T04:19:41.0000000 |  | 2020-11-22T06:31:41.3070000
T-00189-0147 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4113 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-03T23:38:41.3270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T01:02:44.6570000 |  | 2021-02-02T22:05:05.4930000
T-00189-0148 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-AG-4108 | AG - AGITATOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-03T23:42:55.1130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-02T01:04:56.3800000 |  | 2021-02-02T22:06:52.4030000
T-00189-0149 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-PU-4138 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2020-12-03T01:26:25.0070000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-11-22T04:20:21.0000000 |  | 2020-11-22T06:32:11.7100000
T-00189-0150 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-PU-4093 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-15T11:12:34.3870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T22:51:09.0600000 |  | 2021-01-12T05:49:25.9700000
T-00189-0152 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4140 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2020-12-03T01:26:55.6800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-11-22T04:21:03.0000000 |  | 2020-11-22T06:33:35.2100000
T-00189-0153 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-DY-4001 | DY - AIR DRYER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-02-27T04:26:08.5970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-25T22:44:18.5370000 |  | 2021-02-26T05:14:41.4600000
T-00189-0154 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3335-CP-4002 | CP - COMPRESSOR | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Closed | 2021-02-25T13:41:31.5770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T02:50:39.1570000 |  | 2021-02-25T05:02:55.2570000
T-00189-0155 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4156 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-02-03T23:43:28.4100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-02T01:07:55.7330000 |  | 2021-02-02T22:10:06.3170000
T-00189-0157 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-DB-4007 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-25T13:24:00.3700000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-25T05:28:39.1570000 |  | 2021-02-25T06:07:07.2070000
T-00189-0159 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-DB-4009 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-27T04:22:39.9530000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-25T22:02:17.9970000 |  | 2021-02-26T05:10:02.5430000
T-00189-0160 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-DB-4011 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-25T06:13:45.5800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T01:53:49.7630000 |  | 2021-01-25T03:02:44.7070000
T-00189-0162 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-DB-4008 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-02-25T13:24:37.4570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-25T05:30:25.6570000 |  | 2021-02-25T06:07:23.0330000
T-00189-0163 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-PF-4002 | PFC - Power Factor Correction | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-03-19T10:49:07.0930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-18T21:47:34.7470000 |  | 2021-03-19T03:59:01.7970000
T-00189-0165 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-DB-4003 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-15T23:12:55.3770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-07T00:26:41.0000000 |  | 2020-12-07T20:31:09.4130000
T-00189-0167 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-DB-4010 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00189-0169 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-PF-4001 | PFC - Power Factor Correction | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-25T13:31:07.2070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-25T03:42:20.7830000 |  | 2021-02-25T05:03:14.8730000
T-00189-0170 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-JX-4001 | JX - UPS | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:12:09.6330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T06:44:57.0000000 |  | 2020-12-18T07:01:41.7800000
T-00189-0171 | LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-DB-4001 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Closed | 2020-12-15T23:15:17.3200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-07T00:11:52.0000000 |  | 2020-12-07T20:31:29.7100000
T-00189-0197 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PK-4006 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00189-0200 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PK-4007 | PK - PACKAGE | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-02-27T04:25:44.2130000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-26T00:00:34.0070000 |  | 2021-02-26T05:13:46.0600000
T-00189-0203 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-14T05:59:04.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-14T04:40:31.9230000 |  | 2021-03-14T05:20:29.9370000
T-00189-0204 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-BR-4001 | BR - BATTERY CHARGER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-15T11:12:57.1170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T02:05:43.1770000 |  | 2021-01-11T03:53:04.7270000
T-00189-0260 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-FN-4005 | FN - FAN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:12:09.6700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T05:40:52.6570000 |  | 2021-02-16T07:10:09.4700000
T-00189-0261 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4146 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:16:04.0030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:41:05.9470000 |  | 2021-02-16T07:10:44.2300000
T-00189-0263 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4143 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:35:34.5570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T20:19:25.9630000 |  | 2021-01-05T00:45:43.7370000
T-00189-0264 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-CO-4001 | CO - OIL COOLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-25T13:39:47.5800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-25T06:05:33.2300000 |  | 2021-02-25T06:07:42.6830000
T-00189-0267 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-FN-4006 | FN - FAN | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:30:49.6030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-05T05:48:29.5030000 |  | 2021-01-06T21:01:32.6370000
T-00189-0268 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-HE-4003 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:16:39.7730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T04:38:05.6900000 |  | 2021-02-16T07:11:09.0870000
T-00189-0269 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4144 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:31:08.1330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T21:57:04.9670000 |  | 2021-01-05T00:48:34.0000000
T-00189-0270 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-PU-4119 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-02-27T04:30:37.4770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-25T22:20:09.5200000 |  | 2021-02-26T05:15:09.3200000
T-00189-0271 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-HE-4001 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-25T13:40:17.9370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-25T06:08:09.4270000 |  | 2021-02-25T06:16:13.8530000
T-00189-0272 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4148 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:17:10.1170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:45:51.0700000 |  | 2021-02-16T07:11:35.9070000
T-00189-0273 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-HE-4005/6 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:18:00.2130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T05:26:07.2130000 |  | 2021-02-16T07:12:14.2270000
T-00189-0274 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-HE-4005/6 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:18:33.0530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T04:51:11.8130000 |  | 2021-02-16T07:13:33.9930000
T-00189-0275 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4145 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:31:27.7100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:13:15.2700000 |  | 2021-01-05T00:49:22.9830000
T-00189-0276 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3333-PU-4151 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00189-0278 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3331-PU-4147 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:19:03.5900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:37:14.7100000 |  | 2021-02-16T07:14:07.7930000
T-00189-0279 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-DB-4005 | DB - DISTRIBUTION BOARD | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Closed | 2021-02-25T13:36:01.8470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T06:21:58.3200000 |  | 2021-02-25T06:22:49.4470000
T-00189-0280 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3338-AC-4002 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Closed | 2021-02-25T13:39:10.9700000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-25T06:39:21.5600000 |  | 2021-02-25T06:59:43.5800000
T-00189-0338 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3332-SA-4002 | SA - SAMPLER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-25T13:34:23.8170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-25T05:23:48.5770000 |  | 2021-02-25T06:15:38.5330000
T-00189-0339 | E1.T046 LV Switchboard MCC Drive Module Stage 1 | ELEC | 3334-HE-4008 | HE - HEATER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  |  |  | 0.25
T-00190-0001 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4155 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0002 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4112 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0003 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4014 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0004 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4090 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-25T21:54:27.9670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-25T06:52:45.8270000 |  | 2021-04-25T21:06:47.2200000
T-00190-0005 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4086 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:09:22.0700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T06:25:20.0170000 |  | 2021-04-23T07:24:23.8070000
T-00190-0006 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4012 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0007 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4034 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0008 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4032 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0009 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4159 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0010 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4044 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0012 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-CN-4002 | CN - CRANE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00190-0013 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4102 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0014 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4121 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0015 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-FN-4002 | FN - FAN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0017 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-AG-4002 | AG - AGITATOR | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-21T07:43:47.2130000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-21T02:21:33.0000000 |  | 2021-04-21T06:20:39.2070000
T-00190-0018 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-ML-4001 | ML - REGRIND MILL |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0019 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-FD-4001 | FD - SCREW FEEDER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0020 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4110 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0021 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4035 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0022 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4084 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0023 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4026 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0024 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4010 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0025 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4117 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0026 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-FD-4003 | FD - SCREW FEEDER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0028 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4082 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T05:54:44.0300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T05:34:40.5030000 |  | 2021-04-24T05:35:04.0730000
T-00190-0029 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4091 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-04-25T21:54:49.4730000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-25T06:52:11.6970000 |  | 2021-04-25T21:07:16.1170000
T-00190-0030 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4028 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0031 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-CN-4001 | CN - CRANE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0032 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4030 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0034 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4005 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T07:47:03.3600000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-13T06:53:04.0000000 |  | 2021-04-13T20:57:54.6900000
T-00190-0035 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4096 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:00:46.6230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:36:03.7370000 |  | 2021-04-18T06:01:17.0030000
T-00190-0036 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4110 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0038 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4105 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0041 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4153 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0043 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-CP-4001 | CP - COMPRESSOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0045 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4111 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0046 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-TH-4002 | TH - THICKENER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0048 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4112 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0053 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4117 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0054 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4120 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0056 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-AG-4006 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0057 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-AG-4012 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0058 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4007 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:14:56.7070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-26T06:26:42.5270000 |  | 2021-03-26T06:43:20.4830000
T-00190-0059 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4152 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0060 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4107 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0061 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4136 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0062 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4092 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-22T08:11:16.2230000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-02-21T06:28:01.7300000 |  | 2021-02-21T06:37:43.6000000
T-00190-0063 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4052 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0065 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4157 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0068 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-HE-4002 | HE - HEATER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0071 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4004 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:17:02.5470000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-15T06:04:15.0000000 |  | 2021-04-15T07:39:25.7100000
T-00190-0072 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4024 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0073 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-TH-4001 | TH - THICKENER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-15T21:25:05.2570000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-03-15T03:58:07.8200000 |  | 2021-03-15T19:09:40.0570000
T-00190-0074 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4111 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0075 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-FN-4001 | FN - FAN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0077 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-FD-4004 | FD - SCREW FEEDER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0082 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4003 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:17:26.7130000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-15T02:12:02.0000000 |  | 2021-04-15T07:35:19.9400000
T-00190-0084 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4041 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0085 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-SN-4003 | SN - SCREEN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0087 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4160 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0091 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-CP-4003 | CP - COMPRESSOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0092 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4040 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0093 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4083 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T05:55:13.0070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T03:40:28.8800000 |  | 2021-04-24T04:50:15.5900000
T-00190-0094 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4099 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0096 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-AG-4001 | AG - AGITATOR | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-21T07:48:40.1230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T01:17:52.7870000 |  | 2021-04-21T01:22:22.8700000
T-00190-0097 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4004 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0098 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4097 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0102 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4115 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0103 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4135 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0104 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4009 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-23T07:58:57.2370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-23T07:02:03.1770000 |  | 2021-04-23T07:02:24.7070000
T-00190-0105 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4158 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00190-0106 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-SA-4004 | SA - SAMPLER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0107 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-FD-4002 | FD - SCREW FEEDER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0108 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4141 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0111 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4109 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0112 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4050 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0113 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4094 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-21T06:09:42.4970000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-02-21T06:03:49.2500000 |  | 2021-02-21T06:07:05.2730000
T-00190-0115 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4154 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T03:38:39.2300000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-18T00:57:36.7600000 |  | 2021-04-18T05:24:35.1070000
T-00190-0116 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4103 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0117 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4103 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0118 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-SA-4003 | SA - SAMPLER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0119 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4011 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T07:47:29.1430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-13T20:49:17.5170000 |  | 2021-04-13T21:04:31.9430000
T-00190-0120 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4104 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0121 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4088 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:29:17.4000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-25T03:17:06.4630000 |  | 2021-04-25T03:23:10.2970000
T-00190-0122 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4043 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0124 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4013 | PU - SUMP PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0126 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4095 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:06:27.7270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:38:30.6630000 |  | 2021-04-18T05:57:44.5400000
T-00190-0128 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4101 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0129 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-SN-4001 | SN - SCREEN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0130 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4005 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0133 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-TH-4003 | TH - THICKENER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0135 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-SN-4004 | SN - SCREEN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0136 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4001 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T07:59:04.8030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:31:35.9370000 |  | 2021-04-13T23:41:49.8130000
T-00190-0137 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4114 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0138 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4025 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0139 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4102 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0140 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4118 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0141 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4098 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0142 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4022 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0144 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-SA-4001 | SA - SAMPLER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0145 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4114 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0146 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4118 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0147 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4113 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0148 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-AG-4108 | AG - AGITATOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00190-0149 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-PU-4138 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0150 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-PU-4093 | PU - PUMP | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-21T06:10:38.5700000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-02-21T03:54:52.5530000 |  | 2021-02-21T06:07:53.0830000
T-00190-0152 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4140 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0153 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-DY-4001 | DY - AIR DRYER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0154 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3335-CP-4002 | CP - COMPRESSOR |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0155 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4156 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0157 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-DB-4007 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-04 - Lighting and Small Power Bulk Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Closed | 2021-04-10T08:07:54.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T02:09:30.1930000 |  | 2021-04-10T03:51:06.7730000
T-00190-0159 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-DB-4009 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0160 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-DB-4011 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Submitted |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T05:26:01.4100000
T-00190-0161 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-DB-4004 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-01 - Admin & Permanent Buildings | CSEF - Permanent Buildings | Closed | 2021-03-16T04:28:09.5270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-15T22:56:48.8830000 |  | 2021-03-16T00:17:22.9770000
T-00190-0162 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-DB-4008 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Closed | 2021-03-22T03:18:57.3230000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-21T19:59:50.2430000 |  | 2021-03-22T00:09:09.3830000
T-00190-0163 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-PF-4002 | PFC - Power Factor Correction |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0164 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-BR-4001 | BR - BATTERY CHARGER | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-04-23T07:56:58.1070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-04-23T04:51:13.9070000 |  | 2021-04-23T04:56:26.0270000
T-00190-0165 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-DB-4003 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00190-0167 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-DB-4010 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0169 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-PF-4001 | PFC - Power Factor Correction |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0170 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-JX-4001 | JX - UPS | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-30T21:50:43.5430000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-01-30T00:41:50.3270000 |  | 2021-01-30T06:50:13.6030000
T-00190-0171 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-DB-4001 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00190-0197 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PK-4006 | PK - PACKAGE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0200 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PK-4007 | PK - PACKAGE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0258 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-FN-4005 | FN - FAN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:15:25.8570000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T06:54:11.0400000 |  | 2021-03-27T07:10:38.4700000
T-00190-0259 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4146 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:15:46.2670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:53:11.6170000 |  | 2021-03-27T05:14:38.7670000
T-00190-0261 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4143 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:16:17.0600000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T00:30:44.2400000 |  | 2021-03-27T03:06:25.4600000
T-00190-0262 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-CO-4001 | CO - OIL COOLER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0265 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-FN-4006 | FN - FAN |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:16:39.9530000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T06:55:47.6870000 |  | 2021-03-27T07:11:24.6470000
T-00190-0266 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-HE-4003 | HE - HEATER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:17:56.9100000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T03:58:35.1230000 |  | 2021-03-27T05:15:10.8300000
T-00190-0267 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4144 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:18:26.7830000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T00:32:19.6470000 |  | 2021-03-27T03:08:29.5030000
T-00190-0268 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-PU-4119 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0269 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-HE-4001 | HE - HEATER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0270 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4148 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:20:32.6030000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T05:15:11.4630000 |  | 2021-03-27T06:12:51.7830000
T-00190-0271 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-HE-4005/6 | HE - HEATER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:20:56.8230000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T03:55:13.8230000 |  | 2021-03-27T05:18:11.7070000
T-00190-0273 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4145 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:21:24.9670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:50:58.9670000 |  | 2021-03-27T06:12:25.9230000
T-00190-0274 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3333-PU-4151 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00190-0276 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3331-PU-4147 | PU - PUMP |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:21:47.4830000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:55:14.4570000 |  | 2021-03-27T05:18:48.9770000
T-00190-0277 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-DB-4005 | DB - DISTRIBUTION BOARD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0278 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3338-AC-4002 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00190-0333 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3332-SA-4002 | SA - SAMPLER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00190-0334 | E2.T046 LV Switchboard MCC Drive Module Stage 2 | ELEC | 3334-HE-4008 | HE - HEATER |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  |  |  | 0.25
T-00191-0011 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C6 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:12:36.8630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T23:47:20.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-18T00:30:38.6130000
T-00191-0013 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C7 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:32:05.5470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T23:50:40.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-18T00:35:52.4900000
T-00191-0014 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334PU4050-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0015 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4022-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-01T03:23:48.4630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T21:13:55.2430000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:34:35.9400000
T-00191-0016 | LV Cable (Control) Stage 1 | CABL | 3334PU4086-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:13:28.4600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T21:20:17.4800000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-13T03:33:29.8200000
T-00191-0018 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4026-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-25T13:34:54.6030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T06:26:24.0870000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-24T22:09:57.0730000
T-00191-0021 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333FD4002-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Closed | 2021-04-24T03:12:53.0630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T05:24:39.5970000 | 20C+E 1.5mm2 PVC/PVC,BLK | 2021-04-23T07:10:15.0170000
T-00191-0022 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4111-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T06:22:35.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:51:45.9800000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-03T06:09:56.5830000
T-00191-0023 | E1.Txxx LV Cable (Control) Stage 1 | CABL | 3331PU4158-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:13:58.1400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T06:35:10.4770000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2021-01-11T06:56:57.8530000
T-00191-0024 | LV Cable (Control) Stage 1 | CABL | 3331PU4144-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:36:02.8770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:47:32.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:28:36.4700000
T-00191-0025 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335PU4097-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0027 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333FD4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0028 | LV Cable (Control) Stage 1 | CABL | 3334PU4084-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:36:26.8070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T23:37:52.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:29:24.2000000
T-00191-0029 | LV Cable (Control) Stage 1 | CABL | 3334PU4083-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:36:46.3600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T23:39:22.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:29:50.8270000
T-00191-0031 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4035-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0033 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4014-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T03:24:19.0300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:51:17.8930000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:34:57.6370000
T-00191-0035 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335PU4155-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:14:31.5670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T05:28:03.8870000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-12T06:32:16.5900000
T-00191-0037 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ML4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-29T20:50:32.8770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-23T06:22:01.9300000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-23T20:15:54.9470000
T-00191-0038 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333AG4006-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0041 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4024-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T03:24:49.8870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:11:21.6630000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:35:17.9670000
T-00191-0042 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4109-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:39:56.5600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T22:44:38.1130000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-27T23:09:54.9270000
T-00191-0043 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4112-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:19:08.1030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T20:56:56.8900000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:20:08.7200000
T-00191-0044 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4103-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 20C+E 1.5mm2 PVC/PVC
T-00191-0045 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333DY4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0046 | LV Cable (Control) Stage 1 | CABL | 3331PU4148-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:37:08.8470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:55:56.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:30:25.0330000
T-00191-0047 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334PU4044-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-03T23:44:13.9170000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-02T21:30:52.4330000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-02T22:11:23.6700000
T-00191-0048 | E1.Txxx LV Cable (Control) Stage 1 | CABL | 3335PU4096-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T05:37:43.3930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T13:39:23.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-31T19:15:18.9330000
T-00191-0049 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331HE4006-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-19T00:41:21.2870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T23:53:37.5930000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-19T00:10:18.5930000
T-00191-0050 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4152-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0051 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4102-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:51:01.1330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:42:34.1370000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-23T20:16:28.9770000
T-00191-0053 | LV Cable (Control) Stage 1 | CABL | 3331PU4147-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:38:05.3070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:53:01.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:31:29.7730000
T-00191-0054 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4120-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-25T13:25:31.6230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T06:19:49.9700000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-24T21:43:54.1330000
T-00191-0056 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4136-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-03T23:45:08.3230000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-02T21:56:16.6900000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-02T22:29:08.6600000
T-00191-0058 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335PU4098-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0060 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:19:32.6070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T04:13:49.2370000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-19T04:43:59.4500000
T-00191-0063 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4110-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:40:19.0970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T22:48:18.6970000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-27T23:10:20.0300000
T-00191-0064 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4040-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0070 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338GE4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0071 | LV Cable (Control) Stage 1 | CABL | 3334PU4082-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:38:27.1630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T23:41:04.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:31:46.4700000
T-00191-0072 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332SN4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-29T20:51:27.8770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-23T06:26:16.7130000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-23T20:17:01.9200000
T-00191-0073 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4136-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-05T06:44:13.7770000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-04T03:53:46.1570000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2021-02-05T02:50:41.9030000
T-00191-0074 | LV Cable (Control) Stage 1 | CABL | 3331HE4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:38:47.3970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:43:40.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:32:05.5870000
T-00191-0075 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4135-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-01T03:25:35.7470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-01-30T21:02:17.1370000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:42:31.6800000
T-00191-0076 | LV Cable (Control) Stage 1 | CABL | 3331PU4007-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:39:08.7330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T22:31:11.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:32:23.1300000
T-00191-0079 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4118-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-24T10:57:41.1270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T05:51:09.8370000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-24T06:45:01.6770000
T-00191-0080 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4140-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0082 | LV Cable (Control) Stage 1 | CABL | 3331PU4143-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:39:32.1230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:45:37.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-30T06:18:58.5330000
T-00191-0083 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4115-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:20:03.4300000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T06:49:33.2470000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:20:53.1570000
T-00191-0085 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4156-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0086 | LV Cable (Control) Stage 1 | CABL | 3331PU4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:40:29.0930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T20:16:44.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-21T21:09:07.1400000
T-00191-0087 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332FN4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T06:41:34.2300000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:02:14.6070000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-22T04:37:28.3370000
T-00191-0088 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331PU4004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:14:59.1430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-10T05:06:38.2470000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-11T03:56:12.6900000
T-00191-0089 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4110-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-12T04:49:32.6230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-11T22:58:07.0970000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-11T23:35:13.9670000
T-00191-0090 | LV Cable (Control) Stage 1 | CABL | 3333PU4035-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T05:41:01.0300000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-21T21:55:20.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-22T02:34:22.4330000
T-00191-0091 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333FD4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0092 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334PU4041-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-03T23:45:40.5100000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-02T21:23:03.2170000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-02T22:13:29.3870000
T-00191-0093 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4114-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:20:25.0030000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T06:55:00.0970000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:21:40.3030000
T-00191-0094 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4108-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:40:43.2770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T22:40:44.8500000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-27T23:10:52.1300000
T-00191-0096 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334PU4119-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:07:31.5700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T04:45:02.4670000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-19T06:33:35.9300000
T-00191-0098 | LV Cable (Control) Stage 1 | CABL | 3335PU4095-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T05:41:23.9100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T13:45:05.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-31T19:15:57.6400000
T-00191-0099 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4111-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:20:46.2500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T20:04:35.0500000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:22:15.4730000
T-00191-0100 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331SN4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-09T04:07:37.5770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-07T22:43:25.1370000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-08T02:43:10.2600000
T-00191-0101 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4030-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T05:36:26.5200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-21T02:03:42.0970000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-21T05:17:15.2070000
T-00191-0102 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333SN4004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0103 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4034-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:21:34.3970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-29T20:13:19.7600000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-30T06:10:42.2200000
T-00191-0104 | LV Cable (Control) Stage 1 | CABL | 3331PU4145-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:41:47.3930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:49:11.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:34:41.3900000
T-00191-0106 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4012-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:21:04.3170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:14:30.0700000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-28T06:13:18.8430000
T-00191-0108 | LV Cable (Control) Stage 1 | CABL | 3331PU4146-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:42:09.8630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T23:50:53.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:35:13.4130000
T-00191-0110 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333CO4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0114 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334AG4012-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0115 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334PU4043-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-02-03T23:46:09.1570000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-02T21:25:02.8470000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-02T22:14:39.8230000
T-00191-0117 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:21:07.4670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T04:08:06.6370000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-19T04:44:26.1600000
T-00191-0119 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4102-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 20C+E 1.5mm2 PVC/PVC
T-00191-0120 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4117-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:21:29.4530000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T06:38:43.3470000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:22:58.4500000
T-00191-0121 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333DY4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0124 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4101-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:52:39.8530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:16:49.6900000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-29T20:46:49.9770000
T-00191-0125 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4105-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T22:17:47.2800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-01T05:04:59.5530000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-01T20:44:47.3570000
T-00191-0126 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335PU4099-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0128 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4010-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:12:37.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T02:37:16.5130000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-19T04:05:18.0830000
T-00191-0129 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4103-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:53:05.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T05:51:24.1930000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-23T20:17:22.2200000
T-00191-0130 | LV Cable (Control) Stage 1 | CABL | 3331PU4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:25:17.7500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T20:24:46.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-21T21:09:57.6770000
T-00191-0131 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4032-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T12:44:19.5930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T04:06:51.8530000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-30T06:06:34.0970000
T-00191-0132 | LV Cable (Control) Stage 1 | CABL | 3333PU4141-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:25:43.1270000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T14:05:16.1300000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:19:36.8370000
T-00191-0133 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4114-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T06:23:10.9100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T06:06:25.9470000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-03T06:12:36.7670000
T-00191-0134 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331PU4009-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T10:46:15.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T06:16:20.4870000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-19T06:29:12.4900000
T-00191-0137 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TH4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-05T06:49:22.5930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-04T05:12:45.2670000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-05T04:28:26.8370000
T-00191-0138 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TH4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-05T06:48:55.5030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-04T05:10:51.1500000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-05T04:24:53.7600000
T-00191-0139 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338BT4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0140 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4028-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T03:25:43.2630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T06:03:30.7900000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-23T06:57:48.1700000
T-00191-0142 | LV Cable (Control) Stage 1 | CABL | 3331FN4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:26:04.5430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-22T00:10:30.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:35:43.4700000
T-00191-0144 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4117-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-24T10:58:03.3170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T05:24:00.9430000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-24T06:38:37.4530000
T-00191-0147 | E1.Txxx LV Cable (Control) Stage 1 | CABL | 3331TH4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:26:26.0170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T07:05:14.0170000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-31T07:06:06.9330000
T-00191-0149 | E1.Txxx LV Cable (Control) Stage 1 | CABL | 3331PU4158-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:26:49.4000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T06:42:14.7730000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-31T07:05:37.3170000
T-00191-0150 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333HE4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0152 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4104-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T20:53:29.5670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-23T06:04:26.1730000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-23T20:17:42.5300000
T-00191-0153 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338GE4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0154 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333FD4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0155 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4151-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0158 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4013-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:21:29.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:53:41.1800000 | 6C+E 1.5mm2 PVC/PVC | 2021-03-28T06:13:42.3470000
T-00191-0160 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4157-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0162 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4118-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-19T06:21:56.6230000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-15T06:29:58.7100000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-16T20:23:32.8430000
T-00191-0163 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4025-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-01T03:26:19.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:23:17.5630000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:45:57.2870000
T-00191-0164 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4107-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:41:10.7400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T22:37:06.7330000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-27T23:11:16.5600000
T-00191-0165 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4141-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0168 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4113-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T06:32:53.0630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T06:03:43.8770000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-03T06:10:32.3630000
T-00191-0169 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338BT4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0170 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AG4112-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T06:33:20.0470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T05:55:38.1700000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-03T06:11:12.5230000
T-00191-0171 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4121-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T03:26:46.1370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T19:59:54.9230000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-31T02:47:05.7670000
T-00191-0172 | LV Cable (Control) Stage 1 | CABL | 3334PU4088-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T05:47:14.0400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T22:49:00.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:39:13.5170000
T-00191-0174 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4138-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-03T23:46:36.5570000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-02T22:00:46.3370000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-02T22:29:38.8170000
T-00191-0176 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4153-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0180 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4021-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:23:38.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T21:38:43.5670000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-27T22:21:08.1730000
T-00191-0182 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DIT0527-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-04T02:33:43.8630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T03:53:12.2100000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:36:49.6570000
T-00191-0186 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0441-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:07:09.5430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T23:52:53.1630000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T03:56:59.7630000
T-00191-0188 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4073-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:35:53.1200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:42:00.4500000
T-00191-0189 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DIT0126-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-03T22:56:54.3770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-03T06:26:00.6670000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T22:34:22.5330000
T-00191-0190 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334OP4084-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 12C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0191 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH0564-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:55:35.5700000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T22:15:42.0770000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T22:16:32.6270000
T-00191-0192 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0019-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:15:24.5270000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-13T04:54:21.4630000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T07:05:49.2370000
T-00191-0194 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0536-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T12:44:49.7400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:51:08.8100000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:07:10.5330000
T-00191-0196 | LV Cable (Control) Stage 1 | CABL | 3335OP4093-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T05:48:16.8170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-23T15:11:17.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:50:22.2970000
T-00191-0197 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS0588-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0198 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335AV0854-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T20:53:51.6400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-25T02:29:55.1200000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-25T03:03:28.3470000
T-00191-0200 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4035-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-19T06:22:29.1830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-19T04:19:25.9130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:44:46.0930000
T-00191-0201 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TS2457-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T21:33:55.0400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:17:31.4230000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T03:47:32.3400000
T-00191-0202 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4034-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:41:58.6470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:16:26.2100000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:12:22.6700000
T-00191-0203 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1021-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:57:32.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:38:04.5930000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:44:12.8170000
T-00191-0204 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0451-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:07:48.6000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T04:38:07.2600000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T04:49:56.6030000
T-00191-0206 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TS2458-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T21:34:25.8000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:18:43.1930000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T03:47:52.0270000
T-00191-0209 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4059-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0210 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4052-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0211 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0216-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0213 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4072-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 24C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0214 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338U1151-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0215 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DIT0033-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:23:19.8570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:05:42.6130000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:19:53.7200000
T-00191-0218 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0863-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0219 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0417-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T06:03:14.2170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-28T03:02:37.8900000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:02:29.9830000
T-00191-0220 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0525-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:41:34.0500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T07:05:48.0470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T20:48:10.2370000
T-00191-0221 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS0619-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0222 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0067-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:49:20.7070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-08T23:53:43.0270000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T04:45:59.8800000
T-00191-0223 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0578-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0224 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0323-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0225 | LV Cable (Control) Stage 1 | CABL | 3335OP4092-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T06:04:46.0000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-23T15:18:04.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:50:58.9130000
T-00191-0226 | LV Cable (Control) Stage 1 | CABL | 3331FV0009-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:51:00.2070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:05:12.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:19:58.4930000
T-00191-0229 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1038-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-29T17:57:58.1770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-29T02:00:57.3800000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-29T06:29:30.1270000
T-00191-0230 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0135-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0231 | LV Cable (Control) Stage 1 | CABL | 3331MB4011-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T05:51:51.8230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-21T22:42:06.0000000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-22T02:39:40.2200000
T-00191-0232 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4049-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-02T02:47:24.6000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-31T23:38:16.5330000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:39:43.8770000
T-00191-0233 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4025-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:22:56.1630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-15T00:08:24.4330000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:24:24.7800000
T-00191-0234 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1109-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-02-17T22:36:11.0830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-17T21:21:18.3370000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-17T21:46:06.3770000
T-00191-0235 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4033-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-08T20:03:25.4000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-08T04:30:21.7170000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T05:38:17.7030000
T-00191-0236 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0142-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:54:50.9930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T06:24:50.3270000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-19T07:22:37.4470000
T-00191-0237 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4236-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:42:27.3400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T00:59:47.1500000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-13T06:22:54.4770000
T-00191-0238 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0068-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:16:06.9970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T04:50:34.0070000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T07:06:31.8270000
T-00191-0239 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS0584-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0240 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1044-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:24:01.1270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:10:47.4670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T06:15:39.3100000
T-00191-0241 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4077-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0242 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4026-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:55:25.3970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T01:15:12.7870000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:09:42.3830000
T-00191-0243 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS0585-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0245 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-22T16:05:30.2870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T01:05:06.2330000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T03:55:47.4230000
T-00191-0246 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0131-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0247 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0051-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:07:38.5670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T00:16:32.0700000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T00:59:46.7900000
T-00191-0249 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0437-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:27:56.5570000 | Vendor Cable | 2021-04-26T06:42:43.9570000
T-00191-0250 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4067-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T03:14:33.8170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-02T23:33:11.0300000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:41:33.5470000
T-00191-0252 | LV Cable (Control) Stage 1 | CABL | 3331OP4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T05:52:18.8400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-23T12:48:50.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:51:40.4500000
T-00191-0253 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS1108-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0254 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0848-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:16:29.8230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T20:04:59.1370000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T03:59:10.2170000
T-00191-0255 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4048-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:24:26.3700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T21:25:58.6130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T03:09:17.6700000
T-00191-0257 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4036-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-19T06:23:28.5330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-14T22:48:12.9570000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:25:08.7830000
T-00191-0259 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0612-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-03T22:55:38.9430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-03T06:28:16.1770000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T22:17:01.3570000
T-00191-0260 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0352-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-01T06:20:29.8130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-28T22:29:56.0530000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:18:13.4070000
T-00191-0261 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4026-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-29T20:54:19.1030000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-24T10:46:15.0000000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:06:57.7070000
T-00191-0262 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338U1150-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0263 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0839-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0264 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4054-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:24:53.9270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T05:09:13.0330000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T06:10:55.8930000
T-00191-0266 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334OP4084-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 12C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0267 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1010-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-16T22:57:31.7630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:46:00.9500000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:02:52.6430000
T-00191-0269 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4084-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:56:29.7670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T05:24:50.7930000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:14:29.3670000
T-00191-0270 | LV Cable (Control) Stage 1 | CABL | 3331MB4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:20:58.4930000
T-00191-0271 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0865-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0272 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS7823-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0273 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1037-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0275 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4062-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:22:19.9170000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:43:31.1430000
T-00191-0278 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH0833-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0280 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338XE4101-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0281 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4032-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 20C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0282 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0842-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:54:56.6030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-05T05:35:19.8370000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-07T00:13:07.6270000
T-00191-0283 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4022-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:25:18.9070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-18T06:58:24.1370000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:45:12.6400000
T-00191-0285 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331U0021-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0286 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1025-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0287 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DIT0545-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:40:41.4170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T07:19:08.4200000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:27:27.4770000
T-00191-0288 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0503-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:18:23.9600000 | Vendor Cable | 2021-04-26T06:43:54.4300000
T-00191-0289 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0602-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-29T05:28:57.1100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T20:18:10.2570000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-29T00:45:06.0930000
T-00191-0290 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4038-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Closed | 2021-01-19T06:25:40.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-15T00:34:34.4470000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:26:03.7730000
T-00191-0291 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH0776-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-28T16:12:04.1970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-28T00:58:04.7800000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T01:29:50.0770000
T-00191-0292 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0052-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:08:45.9530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T00:25:18.8200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T01:00:03.1370000
T-00191-0293 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1046-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:24:50.0500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:08:51.3830000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T06:16:07.2530000
T-00191-0295 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0595-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0297 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1051-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0298 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4070-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0299 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL0551-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:59:16.7770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T03:12:27.5570000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T22:17:02.8900000
T-00191-0302 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4202-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-22T02:24:06.2570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T05:07:29.1770000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-21T07:31:42.9530000
T-00191-0303 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0104-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T00:54:20.6000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:38:01.7470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T05:15:32.9070000
T-00191-0304 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334OP4082-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:48:42.7500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-01T00:08:30.4270000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:23:34.1030000
T-00191-0306 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1074-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0307 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0482-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-05T07:11:48.6230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-04T02:16:08.7770000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-05T04:26:42.2400000
T-00191-0308 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0825-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0309 | LV Cable (Control) Stage 1 | CABL | 3331FV0082-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:52:46.6900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T14:12:02.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:20:35.3270000
T-00191-0310 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334OP4083-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2021-04-07T04:34:45.6730000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:54:40.1570000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-06T07:40:34.4430000
T-00191-0311 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4089-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:37:21.1870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:48:39.2500000
T-00191-0312 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334UI0693-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0313 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0481-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-05T07:12:19.7800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-04T02:13:53.0870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-05T04:27:13.5130000
T-00191-0314 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0577-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0315 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0070-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-03T23:47:05.4030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T21:47:38.9430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:17:37.3070000
T-00191-0316 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0196-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-28T16:25:12.8570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T06:52:15.8900000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T07:08:30.5570000
T-00191-0317 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4046-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-15T21:48:28.1470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-15T06:04:48.6470000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T06:48:33.1530000
T-00191-0318 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0428-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T04:57:54.5500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:26:20.9200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:48:22.9370000
T-00191-0319 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DE0056-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-22T15:40:45.4570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-21T06:13:49.8870000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:32:18.0770000
T-00191-0320 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DE0126-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0321 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DE0033-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:41:09.5200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T05:38:51.1030000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:21:26.4600000
T-00191-0323 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1042-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:25:35.6670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:15:23.5330000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T06:16:39.1830000
T-00191-0324 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1024-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0325 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4031-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-29T17:58:34.3930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-29T02:09:53.7670000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-29T06:29:50.5970000
T-00191-0326 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4056-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0328 | LV Cable (Control) Stage 1 | CABL | 3331FV0084-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:53:13.2100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:10:41.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:21:09.0830000
T-00191-0329 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4026-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-19T06:27:50.0070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-15T00:02:41.3600000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:26:33.9200000
T-00191-0330 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1071-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0331 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1045-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-28T16:25:58.3300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:13:44.9670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T06:17:11.0130000
T-00191-0333 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0700-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0334 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0845-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:17:01.4800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-11T06:39:17.6530000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-11T06:57:24.6400000
T-00191-0335 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4051-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0338 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4205-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-20T22:02:54.0170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-20T06:23:34.4300000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-20T06:25:04.7800000
T-00191-0341 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0491-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:31:17.5330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T06:07:32.6800000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:51:59.4930000
T-00191-0342 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0696-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0343 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335AV0868-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-18T23:02:36.4630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T18:05:03.0670000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:13:25.0000000
T-00191-0344 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0441-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-03T03:34:09.2370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:35:51.6630000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:53:52.6670000
T-00191-0345 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AIT1061-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-03T03:56:39.9170000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-02T23:56:16.4770000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:05:03.5170000
T-00191-0346 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4073-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 24C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0351 | LV Cable (Control) Stage 1 | CABL | 3331OP4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:55:01.3230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-02T15:39:53.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-02T19:59:48.3870000
T-00191-0352 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0120-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T04:42:06.1100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T06:53:49.3300000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:55:35.8600000
T-00191-0353 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1023-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:34:40.6830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:51:26.9270000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:53:24.4000000
T-00191-0355 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0701-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0356 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4053-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Completed |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-26T06:09:39.3030000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:45:44.0100000
T-00191-0358 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0697-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0360 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0307-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-03T06:13:54.2630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T03:54:32.7570000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T06:03:23.6030000
T-00191-0361 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH0551-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:00:32.6970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:54:47.2070000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:38:45.1470000
T-00191-0363 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0519-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:41:59.6630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T07:02:02.6030000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T20:59:06.7430000
T-00191-0364 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4015-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0365 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4057-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0366 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0418-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T05:27:46.6370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T22:24:40.7470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:49:07.4670000
T-00191-0367 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335OP4203-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-12T09:12:19.0070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-11T23:42:16.0100000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-12T00:07:46.0200000
T-00191-0369 | LV Cable (Control) Stage 1 | CABL | 3331FV0002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:17:53.0300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-11T06:30:38.5030000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-11T06:57:46.0370000
T-00191-0370 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1157-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0371 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0517-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:42:23.7630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:56:09.2570000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T20:59:55.5130000
T-00191-0372 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4028-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-07T05:02:15.0700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T03:56:37.2130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T04:10:43.5270000
T-00191-0374 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0024-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:18:25.2170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T20:17:40.1370000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T03:59:43.3330000
T-00191-0375 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4021-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-21T02:42:53.4130000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-19T05:36:33.7470000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T06:17:05.2470000
T-00191-0376 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0862-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0377 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DIT0074-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:41:34.3700000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:03:11.6200000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:21:56.4700000
T-00191-0378 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4046-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-03-08T20:02:17.2600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-08T04:53:00.2470000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:08:38.8170000
T-00191-0380 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0439-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-22T16:04:56.3200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T01:08:16.8500000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T03:56:37.2370000
T-00191-0381 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AIT1061-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-03T03:57:12.9970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-02T06:34:49.7370000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:06:15.1130000
T-00191-0383 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:18:49.1030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-11T05:43:06.4330000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-11T05:55:47.3800000
T-00191-0384 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1073-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:24:38.0470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T01:24:25.4230000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T04:00:00.3170000
T-00191-0386 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1035-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0387 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4022-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-05T06:44:46.4630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-05T00:38:41.6470000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:41:13.4470000
T-00191-0388 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0116-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:35:38.7870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:50:13.4330000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:56:35.7670000
T-00191-0389 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4034-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0391 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0066-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T05:56:25.4370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-08T22:46:01.9170000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T04:45:38.6700000
T-00191-0392 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0820-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0393 | LV Cable (Control) Stage 1 | CABL | 3331MB4010-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T05:58:52.1130000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-21T22:38:45.0000000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-22T02:40:10.4630000
T-00191-0394 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS1166-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0396 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DE0074-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:41:57.6470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:17:45.8230000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:22:33.8230000
T-00191-0397 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0122-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:52:06.1470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T16:02:11.8830000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T19:59:25.0600000
T-00191-0399 | LV Cable (Control) Stage 1 | CABL | 3331OP4007-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T05:59:22.9870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-23T12:47:26.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:52:11.6070000
T-00191-0400 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0687-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0401 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DIT0032-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:42:18.8870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:10:49.5530000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:23:05.2270000
T-00191-0402 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS1164-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0403 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0950-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0405 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335OP4205-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-15T11:19:24.4570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T04:58:44.0070000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T07:06:56.4270000
T-00191-0406 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:19:47.4230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-11T05:50:11.9030000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-11T05:56:09.9770000
T-00191-0408 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS1107-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0409 | LV Cable (Control) Stage 1 | CABL | 3335OP4091-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T05:59:48.1630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-23T15:30:39.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:52:44.0870000
T-00191-0410 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1033-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0412 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0672-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-27T08:42:45.8330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T05:10:01.7870000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-27T05:53:14.0730000
T-00191-0413 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0166-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-25T13:15:53.1700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T02:53:14.3700000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T21:33:39.3270000
T-00191-0415 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1092-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0416 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0416-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T05:28:24.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T22:22:39.0200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:49:30.4000000
T-00191-0417 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0861-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0418 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4088-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-02T03:01:57.2470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-01T02:00:03.7430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:44:34.5400000
T-00191-0419 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DE0527-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-03T04:00:41.6670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-03T00:13:07.8400000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:08:13.3900000
T-00191-0420 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4039-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-19T06:28:14.2570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-15T00:41:56.3270000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:27:59.7970000
T-00191-0421 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4237-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:42:53.9030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-12T23:43:31.3930000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-13T06:23:31.7630000
T-00191-0423 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0104-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-05T04:28:20.2500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-05T02:02:55.2800000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:24:44.5770000
T-00191-0424 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4017-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0425 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335MB4091-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:56:58.0500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T06:06:57.0300000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:15:45.9430000
T-00191-0426 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0155-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:20:07.4600000 | Vendor Cable | 2021-04-26T06:44:25.0670000
T-00191-0427 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0460-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:08:22.3070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T23:07:41.2930000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-18T01:32:06.9930000
T-00191-0428 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS7824-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0429 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4034-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:42:26.2600000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:13:01.9670000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:13:53.9670000
T-00191-0431 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4046-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-15T21:48:57.8770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-15T06:12:23.7030000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T06:48:03.9230000
T-00191-0432 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331U0064-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0433 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4029-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-10T20:07:52.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T04:42:31.1700000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-10T06:58:23.7500000
T-00191-0434 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0350-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-01T06:20:58.3430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-28T22:29:23.4500000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:17:50.1300000
T-00191-0437 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1075-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0438 | LV Cable (Control) Stage 1 | CABL | 3331OP4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:00:12.7870000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-23T12:35:31.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:53:04.8170000
T-00191-0439 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0866-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0440 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0057-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:10:59.9530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:33:49.9600000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:16:57.8030000
T-00191-0441 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL0564-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:25:08.8730000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T02:54:33.9700000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T03:46:30.0630000
T-00191-0442 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1012-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:11:49.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T00:31:12.3870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T01:00:20.4430000
T-00191-0443 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4066-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:50:23.9770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:06:01.7830000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:24:15.4970000
T-00191-0445 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4086-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T07:08:48.8270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T20:46:16.4470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T23:03:51.0970000
T-00191-0447 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0058-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:12:36.0970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:36:51.0970000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:17:17.9600000
T-00191-0448 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4076-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:55:53.4230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T06:43:43.2400000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:22:18.4230000
T-00191-0449 | LV Cable (Control) Stage 1 | CABL | 3331FV0003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:00:35.3630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:16:31.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:23:56.9830000
T-00191-0450 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0307-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:51:13.4430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T22:18:26.2470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:49:57.6870000
T-00191-0451 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS1165-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0452 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0683-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:49:10.0200000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-28T06:51:30.0600000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:28:45.9530000
T-00191-0453 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4021-C4 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:57:32.2670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T00:36:32.2830000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC,BLK | 2021-03-02T04:28:58.8630000
T-00191-0455 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0075-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-03T23:47:32.7570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T07:04:02.5570000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:18:27.4670000
T-00191-0456 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH0704-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-12T04:50:08.3570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-11T07:46:54.0630000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-11T07:49:36.8800000
T-00191-0457 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4013-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-12T09:17:25.0630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-12T02:37:25.4470000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-12T06:51:30.9470000
T-00191-0458 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0423-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-14T07:59:32.7800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T06:05:11.9600000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:24:57.5030000
T-00191-0459 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4040-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-25T13:35:31.1900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-24T04:08:28.0130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:10:45.0270000
T-00191-0460 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4047-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-19T06:28:37.4800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-18T06:44:06.1100000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:51:50.6700000
T-00191-0464 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0047-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-16T22:58:41.3400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:31:05.7970000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:03:32.0300000
T-00191-0465 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U1061-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:29:50.6700000 | Vendor Cable | 2021-04-26T06:44:56.8270000
T-00191-0466 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4021-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-21T02:45:10.4800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-19T06:27:48.1130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-20T21:13:10.2570000
T-00191-0468 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0050-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:13:43.1430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:26:35.3630000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:17:38.9500000
T-00191-0469 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4206-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-20T22:04:06.1500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-20T06:15:45.1500000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-20T06:26:11.3700000
T-00191-0470 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0196-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T02:06:01.1130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T23:52:01.4770000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:05:21.6230000
T-00191-0471 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0841-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-07T20:56:05.6030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-05T05:34:24.8430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-07T00:13:30.4400000
T-00191-0472 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4081-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:56:55.3270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T01:21:55.4970000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:29:56.1830000
T-00191-0474 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4033-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-04T02:34:20.8470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T05:52:30.6730000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:04:04.7830000
T-00191-0475 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0867-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0476 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4011-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-07T05:04:01.3430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-06T23:52:05.6700000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T00:08:56.9030000
T-00191-0477 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334ZS0824-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0479 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0471-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-05T06:45:16.4900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-03T07:07:59.9700000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:32:03.3470000
T-00191-0480 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331AV0085-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-19T06:30:24.4530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-18T07:09:04.3670000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:52:12.6770000
T-00191-0481 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4205-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T03:25:06.2170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-20T06:43:25.7170000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-20T22:51:52.7570000
T-00191-0482 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333MB4071-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-04 - Marshalling boxes Molybdenum Concentrate Handling | CS0A - Process Control - Network and DCS panels | Completed |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-26T05:52:26.4300000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:46:15.7230000
T-00191-0483 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332A0577/80-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 12C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0484 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1024-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0486 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1040-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T05:25:52.4300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T06:17:20.2870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T07:18:11.5600000
T-00191-0487 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4043-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:09:54.7970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:39:35.4570000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T20:08:27.0230000
T-00191-0489 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0142-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-24T10:57:10.8130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-24T02:50:15.4430000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T07:28:07.1070000
T-00191-0490 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334U0694-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T06:31:24.1930000 | Vendor Cable | 2021-04-26T06:45:20.2570000
T-00191-0491 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0076-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-03T23:48:04.8200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T22:06:11.6430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:30:08.8430000
T-00191-0492 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0491-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:47:52.8600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:16:47.1670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:55:14.2430000
T-00191-0493 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1036-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:43:09.0400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:53:31.1700000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-26T06:49:34.9330000
T-00191-0494 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0631-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-10T20:22:14.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T07:16:42.7630000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-10T19:16:39.4630000
T-00191-0496 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4028-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-29T17:59:01.9870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-29T02:05:55.4130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-29T06:30:16.2630000
T-00191-0497 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0462-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:10:22.3500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:44:03.5270000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:57:26.0630000
T-00191-0499 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4050-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-19T06:30:51.8770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-18T06:53:50.9730000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:52:36.6570000
T-00191-0502 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4061-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0503 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4024-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T02:24:03.8270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:11:18.5800000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T02:07:30.1730000
T-00191-0504 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4078-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:57:30.6730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T06:48:06.8770000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:28:34.6300000
T-00191-0506 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4085-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-11T06:49:56.9970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-11T05:07:03.0900000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-11T06:11:45.7300000
T-00191-0507 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4042-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:11:07.1200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:35:25.2070000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T20:08:49.9530000
T-00191-0509 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0604-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-10T20:22:37.8570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T07:12:42.5430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-10T19:17:21.0600000
T-00191-0510 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZS0622-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0511 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0951-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0512 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0078-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:16:38.4130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T07:02:48.9070000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T19:14:20.0970000
T-00191-0513 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4071-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Completed |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-26T06:12:17.1600000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:40:23.1070000
T-00191-0514 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0048-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-16T22:59:13.1230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:36:26.0630000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:04:14.8800000
T-00191-0515 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DE0032-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:42:39.0270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:12:45.9030000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:23:58.1870000
T-00191-0516 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4061-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-02-15T03:54:49.4370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-13T22:37:33.9370000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-14T01:53:32.4470000
T-00191-0517 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4068-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-09T04:08:03.4370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-07T22:40:51.8630000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-08T02:44:21.2070000
T-00191-0518 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1032-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0519 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335OP4204-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-01-21T02:45:45.5100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-13T05:06:33.3670000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T07:08:03.1770000
T-00191-0520 | LV Cable (Control) Stage 1 | CABL | 3331OP4006-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:01:02.3630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-23T12:41:44.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:53:28.6370000
T-00191-0521 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0584-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0522 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332A0577/80-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0523 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332AV0585-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0524 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332UA0106-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:52:57.8900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T05:43:15.1000000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:12:47.5670000
T-00191-0525 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS1020-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-20T22:58:22.2770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:31:42.6670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:37:14.2430000
T-00191-0526 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0187-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-04T02:08:20.1730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-02T00:19:11.4670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:04:52.4270000
T-00191-0527 | LV Cable (Control) Stage 1 | CABL | 3331FV0007-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:01:33.8530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:19:03.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:24:22.8870000
T-00191-0530 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0534-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T12:45:13.6770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:47:43.8730000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:07:37.8370000
T-00191-0531 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1050-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0532 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3335ZS0846-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-10T06:02:03.3670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-09T22:02:41.2400000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T23:58:01.2970000
T-00191-0533 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1072-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:25:37.7370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T06:35:11.3970000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:36:11.7670000
T-00191-0534 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4081-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0536 | LV Cable (Control) Stage 1 | CABL | 3331FV0008-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:02:25.0300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:21:54.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:24:47.3330000
T-00191-0537 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334OP4081-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Closed | 2021-03-01T06:51:39.4870000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-01T00:30:20.7430000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:31:12.1500000
T-00191-0538 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0114-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T10:53:44.0100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:49:02.8870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:56:55.3430000
T-00191-0540 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0254-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T13:18:11.3270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T22:46:20.8430000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T00:27:33.7400000
T-00191-0541 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0450-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:11:36.6070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T04:36:17.2570000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T04:50:42.9800000
T-00191-0543 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334MB4075-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:57:56.7530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T06:45:50.8900000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:19:27.6700000
T-00191-0544 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4207-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-13T07:43:16.0030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T07:02:51.0730000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-13T07:03:49.7130000
T-00191-0545 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4064-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-20T01:44:06.8470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-19T04:24:09.8130000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:53:11.8470000
T-00191-0547 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0473-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-02-05T06:45:44.0730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-03T06:58:56.7470000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:39:31.9370000
T-00191-0549 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0606-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-10T20:23:01.4800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-10T07:10:48.0300000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-10T19:20:08.4330000
T-00191-0550 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4057-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0551 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0537-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T12:45:34.0470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:55:13.9030000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:08:00.8830000
T-00191-0552 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4085-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-24T03:17:58.2570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-23T06:30:47.7330000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-23T07:11:17.0130000
T-00191-0555 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0054-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:15:46.7430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:30:32.2870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:19:05.1970000
T-00191-0556 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4051-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-25T21:53:11.4630000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-25T07:01:49.0870000 | 20C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-25T07:22:54.1030000
T-00191-0558 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332DE0545-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:43:00.7270000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T07:31:29.8570000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:46:28.2830000
T-00191-0559 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TS2459-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T21:35:00.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:19:48.5830000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T03:48:22.0170000
T-00191-0560 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0256-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T13:18:45.1570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T22:52:05.0400000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T00:27:59.5730000
T-00191-0561 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0487-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0563 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0461-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:12:04.9930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T23:04:54.2730000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-18T01:32:31.0800000
T-00191-0564 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4060-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:08:52.4000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-20T06:30:49.1870000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T07:13:23.8800000
T-00191-0566 | LV Cable (Control) Stage 1 | CABL | 3331OP4004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:02:49.1830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-23T16:49:04.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:53:59.3270000
T-00191-0567 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331U0091-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00191-0568 | LV Cable (Control) Stage 1 | CABL | 3331FV0081-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:03:15.5770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:24:09.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:25:06.4830000
T-00191-0569 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4025-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-29T20:54:41.6730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-24T11:00:20.0000000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:06:36.2000000
T-00191-0570 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0546-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:03:52.6470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T01:04:34.5130000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:08:29.5400000
T-00191-0571 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331ZS0025-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-12T09:12:55.7070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-12T04:02:24.4670000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-12T06:47:54.6400000
T-00191-0572 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4021-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-20T01:47:17.7900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-19T05:16:03.6870000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T06:17:25.7770000
T-00191-0574 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331DIT0056-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-22T15:41:18.0170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-21T05:57:21.0170000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:30:17.9500000
T-00191-0575 | LV Cable (Control) Stage 1 | CABL | 3331FV0005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:05:07.1630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T15:26:27.0000000 | 8C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-30T19:25:25.3330000
T-00191-0577 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0433-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-07T05:27:09.2130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-06T22:24:04.7170000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:48:46.5330000
T-00191-0578 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332U0166-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:55:22.6170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T06:28:33.4200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-19T07:23:18.5300000
T-00191-0580 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4206-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-20T22:03:29.3770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-20T06:01:22.4000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-20T06:25:41.6570000
T-00191-0581 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4065-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:46:36.9870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:09:09.2800000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:24:55.0770000
T-00191-0582 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4087-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:17:06.2930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-02T04:47:02.1300000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:02:34.3100000
T-00191-0584 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C12 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:07:49.5100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T02:12:17.0000000 | 25C+E 1.5mm2 PVC/PVC,BLK | 2020-12-17T07:42:13.3470000
T-00191-0585 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C4 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:13:39.8600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T04:21:40.0000000 | 25C+E 1.5mm2 PVC/PVC,BLK | 2020-12-18T07:04:05.6870000
T-00191-0586 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C11 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:32:33.2070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T00:06:52.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-18T00:31:11.8270000
T-00191-0587 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C10 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:33:01.5700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T00:00:03.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-18T00:31:31.2470000
T-00191-0588 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:14:50.2270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T04:22:43.0000000 | 25C+E 1.5mm2 PVC/PVC,BLK | 2020-12-18T07:04:30.2000000
T-00191-0589 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C8 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:15:12.7270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T04:23:13.0000000 | 25C+E 1.5mm2 PVC/PVC,BLK | 2020-12-18T07:04:49.7770000
T-00191-0590 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C9 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:15:04.7800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T01:37:54.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-17T07:44:28.1770000
T-00191-0592 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:15:38.5570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T04:23:48.0000000 | 25C+E 1.5mm2 PVC/PVC,BLK | 2020-12-18T07:05:12.2070000
T-00191-0593 | LV Cable (Control) Stage 1 | CABL | 3338OP4001-C5 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:17:39.3670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T01:27:06.0000000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2020-12-17T07:45:19.5570000
T-00191-0594 | LV Cable (Control) Stage 1 | CABL | 3333FD4001-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:05:40.9070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T00:40:39.9270000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:01:06.0430000
T-00191-0595 | LV Cable (Control) Stage 1 | CABL | 3331PU4154-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:06:19.3530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T21:51:50.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:40:34.0700000
T-00191-0596 | LV Cable (Control) Stage 1 | CABL | 3332PU4030-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T06:06:50.8830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-12-30T02:28:12.7870000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:51:33.7270000
T-00191-0597 | LV Cable (Control) Stage 1 | CABL | 3332PU4120-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T06:07:13.4600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-12-30T02:16:30.8270000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:59:05.1370000
T-00191-0598 | LV Cable (Control) Stage 1 | CABL | 3331PU4003-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:07:45.8300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T12:45:02.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-31T19:16:27.9130000
T-00191-0599 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332TH4003-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0600 | LV Cable (Control) Stage 1 | CABL | 3331PU4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:08:07.0930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T12:48:44.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-30T19:26:12.3570000
T-00191-0602 | LV Cable (Control) Stage 1 | CABL | 3333PU4153-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:09:09.0530000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T01:43:20.1270000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:04:35.7500000
T-00191-0603 | LV Cable (Control) Stage 1 | CABL | 3334PU4083-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:09:31.2470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-30T12:37:38.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:26:34.6000000
T-00191-0604 | LV Cable (Control) Stage 1 | CABL | 3332PU4112-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:09:52.7730000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T01:29:57.7670000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:57:51.0400000
T-00191-0605 | LV Cable (Control) Stage 1 | CABL | 3332ML4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T06:10:15.4970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-12-30T01:21:14.2470000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:24:09.6170000
T-00191-0606 | LV Cable (Control) Stage 1 | CABL | 3338OP4002-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-19T19:19:50.8970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T20:38:48.0000000 | 10C+E 1.5mm2 PVC/PVC | 2020-12-18T20:55:54.4030000
T-00191-0607 | LV Cable (Control) Stage 1 | CABL | 3333PU4103-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T06:27:13.7430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T01:13:36.4230000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:01:54.1270000
T-00191-0608 | LV Cable (Control) Stage 1 | CABL | 3335PU4091-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-01-10T06:10:46.8300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T11:19:27.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-30T19:26:55.9730000
T-00191-0609 | LV Cable (Control) Stage 1 | CABL | 3332PU4121-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-10T06:11:12.0800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-12-30T01:01:49.8370000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:59:20.9800000
T-00191-0610 | LV Cable (Control) Stage 1 | CABL | 3334PU4050-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2021-01-10T06:11:39.5370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-12-30T00:50:42.1600000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:05:04.7330000
T-00191-0612 | LV Cable (Control) Stage 1 | CABL | 3332PU4117-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:12:07.3070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T04:16:29.9200000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:58:32.1870000
T-00191-0613 | LV Cable (Control) Stage 1 | CABL | 3331AG4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:12:34.4730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-21T22:14:25.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:40:51.8900000
T-00191-0614 | LV Cable (Control) Stage 1 | CABL | 3332PU4022-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-01-10T06:13:03.8970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-12-30T04:22:18.7270000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:29:30.2870000
T-00191-0615 | LV Cable (Control) Stage 1 | CABL | 3332FN4002-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:13:26.8500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T04:28:39.3530000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:23:49.8000000
T-00191-0616 | LV Cable (Control) Stage 1 | CABL | 3332PU4138-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-01-10T06:13:51.7130000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-12-30T04:34:45.5500000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:00:21.8530000
T-00191-0617 | LV Cable (Control) Stage 1 | CABL | 3334PU4088-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:14:15.9470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-30T13:11:51.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:27:22.1500000
T-00191-0618 | LV Cable (Control) Stage 1 | CABL | 3332PU4111-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:14:39.7300000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T04:42:36.6900000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:57:33.8800000
T-00191-0619 | LV Cable (Control) Stage 1 | CABL | 3334PU4084-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:15:06.6430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-30T13:15:29.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:27:41.4870000
T-00191-0620 | LV Cable (Control) Stage 1 | CABL | 3332PU4010-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-10T06:15:31.6300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2020-12-30T04:49:54.0230000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:24:35.6970000
T-00191-0621 | LV Cable (Control) Stage 1 | CABL | 3331AG4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:15:55.1100000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-21T22:16:31.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-22T02:41:19.2870000
T-00191-0622 | LV Cable (Control) Stage 1 | CABL | 3331PU4007-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:16:19.0700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T13:19:41.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:28:02.0770000
T-00191-0623 | LV Cable (Control) Stage 1 | CABL | 3332PU4026-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-01-10T06:16:41.8700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-12-30T05:01:02.3570000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:29:56.1130000
T-00191-0624 | LV Cable (Control) Stage 1 | CABL | 3338OP4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-19T19:20:16.0400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T20:42:14.0000000 | 10C+E 1.5mm2 PVC/PVC | 2020-12-18T21:31:10.2300000
T-00191-0625 | LV Cable (Control) Stage 1 | CABL | 3335PU4090-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-01-10T06:17:06.1570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T13:22:47.0000000 | 6C+E 1.5mm2 PVC/PVC | 2020-12-30T19:28:16.4100000
T-00191-0627 | LV Cable (Control) Stage 1 | CABL | 3332PU4014-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-01-10T06:17:29.9200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2020-12-30T05:13:15.5270000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:29:10.7930000
T-00191-0628 | LV Cable (Control) Stage 1 | CABL | 3332PU4115-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:17:52.9100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T05:20:08.2970000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:58:13.2930000
T-00191-0629 | LV Cable (Control) Stage 1 | CABL | 3332PU4135-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-01-10T06:18:15.5500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-12-30T05:27:16.0170000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:59:41.0300000
T-00191-0630 | LV Cable (Control) Stage 1 | CABL | 3332FN4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:18:39.0970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T05:33:17.2030000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:19:27.3800000
T-00191-0631 | LV Cable (Control) Stage 1 | CABL | 3333PU4152-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:18:58.9200000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T05:40:06.3230000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:02:40.7900000
T-00191-0632 | LV Cable (Control) Stage 1 | CABL | 3338OP4002-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-19T19:21:08.5430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T20:47:21.0000000 | 10C+E 1.5mm2 PVC/PVC | 2020-12-18T20:57:57.7970000
T-00191-0634 | LV Cable (Control) Stage 1 | CABL | 3333PU4102-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T06:19:50.7930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T05:46:21.5530000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:01:28.6400000
T-00191-0635 | LV Cable (Control) Stage 1 | CABL | 3334PU4082-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:21:08.4830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-30T12:58:15.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:28:48.2570000
T-00191-0636 | LV Cable (Control) Stage 1 | CABL | 3332PU4118-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-10T06:22:04.9070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T05:56:44.1700000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T06:58:47.6170000
T-00191-0637 | LV Cable (Control) Stage 1 | CABL | 3331PU4004-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:22:36.8430000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-30T13:02:16.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:29:03.4900000
T-00191-0638 | LV Cable (Control) Stage 1 | CABL | 3333PU4140-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:22:59.5470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T06:07:06.2300000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:02:16.6170000
T-00191-0639 | LV Cable (Control) Stage 1 | CABL | 3333DY4001-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-01-10T06:23:22.5470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2020-12-30T06:12:46.8900000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T07:00:41.8570000
T-00191-0640 | LV Cable (Control) Stage 1 | CABL | 3334PU4086-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:24:08.4930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-30T13:06:05.0000000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2020-12-30T19:29:19.4230000
T-00191-0642 | LV Cable (Control) Stage 1 | CABL | 3331MB4001-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:24:39.5170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-23T17:10:30.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:54:29.6130000
T-00191-0643 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4055-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-02-05T06:47:08.3970000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-02-03T06:46:00.9430000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:51:16.6970000
T-00191-0644 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4010-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:27:46.6070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-02T12:34:25.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-02T20:00:09.6430000
T-00191-0645 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4009-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:28:13.1070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-02T12:50:16.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-02T20:00:28.5030000
T-00191-0646 | LV Cable (Control) Stage 1 | CABL | 3331MB4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:28:34.1370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-23T17:05:35.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-24T18:54:54.6700000
T-00191-0647 | LV Cable (Control) Stage 1 | CABL | 3331OP4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2020-12-18T07:37:47.5800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-18T04:47:08.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-18T05:34:24.0000000
T-00191-0648 | LV Cable (Control) Stage 1 | CABL | 3331MB4001-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:29:00.3630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-23T17:18:56.0000000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T19:10:44.4500000
T-00191-0652 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338OP4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2021-02-20T20:36:51.2800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-19T22:34:57.6800000 | 4C+E 1.5mm2 PVC/PVC | 2021-02-19T22:43:08.8570000
T-00191-0654 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332FN4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:30:23.0000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T23:02:04.9030000 | 6C+E 1.5mm2 PVC/PVC | 2021-04-19T04:00:44.6400000
T-00191-0655 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4032-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-05T06:47:45.3070000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-04T21:19:06.6730000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2021-02-05T02:39:57.0370000
T-00191-0656 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4140-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0657 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332PU4114-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-02-05T06:48:13.8500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-04T20:40:01.0130000 | 15C+E 1.5mm2 PVC/PVC,BLK | 2021-02-05T02:50:12.7470000
T-00191-0659 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331FN4006-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T23:19:38.8930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:14:40.3630000 | 6C+E 1.5mm2 PVC/PVC | 2021-02-16T07:15:30.9200000
T-00191-0660 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331PU4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:29:25.0100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-09T04:42:20.5000000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-09T04:44:42.9230000
T-00191-0661 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PU4141-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 6C+E 1.5mm2 PVC/PVC
T-00191-0662 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4012-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:29:54.3130000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-09T04:47:34.0630000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T06:58:47.8270000
T-00191-0663 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338TF4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0664 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331PSH0084-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:34:52.2030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T06:11:40.6470000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T06:29:34.2170000
T-00191-0665 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4202-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-10T06:30:20.3870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-04T15:27:49.4470000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-04T19:52:25.6300000
T-00191-0666 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332MB4060-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-24T03:21:46.2030000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T02:29:05.3170000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:51:47.2830000
T-00191-0667 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS1106-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T07:44:16.2170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-20T06:31:29.7770000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T07:04:27.1570000
T-00191-0668 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4016-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0669 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0515-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:45:01.9300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:52:13.3830000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T21:00:34.2000000
T-00191-0670 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZS0415-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-01T06:12:02.7370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-28T03:06:36.9700000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:05:36.4430000
T-00191-0672 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338TF4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0673 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331PU4011-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:21:36.2970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-05T06:01:08.9800000 | 6C+E 1.5mm2 PVC/PVC | 2021-01-06T21:01:53.9670000
T-00191-0674 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4027-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-29T20:55:09.9200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-24T11:13:24.0000000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:07:52.5670000
T-00191-0675 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4006-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0676 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH1199-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0677 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSL1192B-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:55:42.5900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T12:19:04.0000000 | 2C+E | 2021-01-24T21:08:13.2900000
T-00191-0678 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4004-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0679 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSL1192D-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:56:04.7930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T13:55:01.0000000 | 2C+E | 2021-01-24T21:08:35.1570000
T-00191-0680 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH1198B-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0681 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH1195-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:44:01.2830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T23:54:53.3870000 | 2C+E | 2021-03-27T05:13:20.7430000
T-00191-0684 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSL1197-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0685 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSH1192B-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:56:27.2900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T13:58:20.0000000 | 2C+E | 2021-01-24T21:09:00.0770000
T-00191-0686 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL1195-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:44:35.6700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T23:56:35.0370000 | 2C+E | 2021-03-27T05:13:49.6100000
T-00191-0687 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH1197-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0688 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338DB4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0689 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSH1192A-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:56:49.9470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T14:02:39.0000000 | 2C+E | 2021-01-24T21:09:26.1470000
T-00191-0690 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL1196-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-11T05:40:30.3900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-11T02:09:14.3370000 | 2C+E | 2021-04-11T03:40:11.2270000
T-00191-0691 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH1193-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T06:45:02.9130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T05:04:09.9170000 | 2C+E | 2021-04-11T06:06:22.0030000
T-00191-0692 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4003-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0693 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSH1192D-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:57:13.2330000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T14:07:22.0000000 | 2C+E | 2021-01-24T21:10:24.2600000
T-00191-0694 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSL1198B-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0695 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338MC4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-04 - MCC | CSED - Switch Room & MCCs | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 10C+E 1.5mm2 PVC/PVC
T-00191-0696 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4029-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-29T20:57:47.1070000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-24T11:15:55.0000000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:11:36.1230000
T-00191-0697 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331MB4002-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-26T04:19:27.1970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-25T07:01:15.8970000 | 24C+E,1.5mm²,PVC/PVC/SWA/PVC,BLK | 2021-04-25T07:28:02.3400000
T-00191-0698 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4002-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0699 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSH1198A-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0700 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0701 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338BR4001-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-30T21:49:19.1070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-30T00:49:46.2030000 | 10C+E,1.5mm2,PVC/PVC | 2021-01-30T06:47:35.1670000
T-00191-0702 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331OP4205-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:40:19.4230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T00:53:31.5200000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T00:55:35.6230000
T-00191-0704 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338GE4001-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0705 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSH1192C-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:58:51.6770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T14:19:10.0000000 | 2C+E | 2021-01-24T21:12:02.5930000
T-00191-0706 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH1196-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-12T05:27:06.6230000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-11T07:04:34.1200000 | 2C+E | 2021-04-11T20:25:46.6700000
T-00191-0707 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSL1192C-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:59:32.6600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T14:37:52.0000000 | 2C+E | 2021-01-24T21:12:27.1500000
T-00191-0708 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332OP4235-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:43:43.7500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T02:31:55.6870000 | 4C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-13T06:24:00.0570000
T-00191-0709 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL1193-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-11T06:45:35.0670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T04:57:56.8530000 | 2C+E | 2021-04-11T06:07:27.3230000
T-00191-0710 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3338AC4005-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0711 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSL1199-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0712 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3331LSL1192A-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-29T20:59:55.1630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-24T14:41:15.0000000 | 2C+E | 2021-01-24T21:12:46.9100000
T-00191-0713 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334LSL1198A-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2C+E
T-00191-0773 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0495-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-08T19:59:16.5100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-08T03:52:01.8430000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:17:58.0630000
T-00191-0774 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0205-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T05:53:02.4870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T04:02:09.9530000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:38:10.4070000
T-00191-0775 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0316-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:31:50.7200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T11:18:27.2130000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:19:08.5930000
T-00191-0776 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0145-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:00:30.7570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T05:52:59.1670000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-22T23:55:18.9800000
T-00191-0777 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0205-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T05:54:10.2170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T04:04:17.7470000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:39:55.5300000
T-00191-0778 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0203-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:00:21.7670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:48:43.3270000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:40:24.7000000
T-00191-0779 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0204-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:01:49.3670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:42:25.0600000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:41:33.3170000
T-00191-0780 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0172-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:01:02.7900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T05:26:25.1330000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:01:16.2630000
T-00191-0781 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0316-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:29:51.1370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T11:21:11.0800000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:19:58.6770000
T-00191-0782 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0321-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:32:23.6570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T12:18:31.7400000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:20:25.0300000
T-00191-0783 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0203-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:01:03.0630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:51:08.1630000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:42:05.5670000
T-00191-0784 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0495-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-08T19:59:55.3570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-08T03:55:14.6030000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:18:26.9030000
T-00191-0785 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0500-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-08T20:00:30.8070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-08T03:49:02.1370000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:18:51.7000000
T-00191-0786 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0202-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:03:17.7670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:54:07.6000000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:42:36.8400000
T-00191-0787 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0144-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:01:28.6600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T04:40:25.7600000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:16:39.7170000
T-00191-0788 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0145-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:01:56.7100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T04:52:48.8130000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:17:19.5070000
T-00191-0789 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0321-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:33:09.2830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T12:21:21.7770000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:20:49.3970000
T-00191-0790 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0171-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:02:32.0370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T05:01:56.5630000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:19:03.8300000
T-00191-0791 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0171-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:03:38.1900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T05:14:14.9600000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:19:45.3370000
T-00191-0792 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0305-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:33:39.8330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T10:37:04.3500000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:21:43.1130000
T-00191-0793 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0500-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-08T20:01:07.2000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-08T03:47:05.7830000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:19:23.0430000
T-00191-0794 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0170-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:04:03.9200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T04:56:22.6600000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:20:17.3900000
T-00191-0795 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0170-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:04:27.0170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T05:00:38.1930000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:22:43.6600000
T-00191-0796 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0202-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:03:49.1670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:57:38.6970000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:43:02.2970000
T-00191-0797 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0305-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:34:19.3870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T10:40:15.8630000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:22:21.8600000
T-00191-0798 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0204-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-05T06:02:29.6870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-04T03:46:05.5200000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:43:26.4930000
T-00191-0799 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0144-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:04:49.6670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-21T06:57:52.1300000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T00:23:02.7800000
T-00191-0800 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0311-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:34:53.3300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T10:49:40.9830000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:22:52.4870000
T-00191-0801 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSO0172-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:56:07.5130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:39:00.0030000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T02:07:51.9700000
T-00191-0802 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332ZSC0311-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-04T02:35:34.4030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-02T11:15:19.0030000 | 2C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:26:45.1830000
T-00191-0803 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334FV2108-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-26T09:33:46.7800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T01:34:39.1800000 | 4C+E,1.5mm2,PVC/PVC,BLK | 2021-01-24T01:36:49.2570000
T-00191-0804 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSL-102-MGL-W2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:04:59.1070000 |  |  | 0.25 | 2021-04-12T07:39:23.0870000 | VENDOR CABLE | 2021-04-12T07:43:13.7430000
T-00191-0805 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSH-101-MGP-W3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:05:24.3470000 |  |  | 0.25 | 2021-04-12T07:29:14.5200000 | VENDOR CABLE | 2021-04-12T07:43:40.4800000
T-00191-0806 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSH-101-MGW-W6 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:05:52.3200000 |  |  | 0.25 | 2021-04-12T07:30:16.0800000 | VENDOR CABLE | 2021-04-12T07:44:00.1100000
T-00191-0807 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSL-101-MGP-W4 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:06:13.8470000 |  |  | 0.25 | 2021-04-12T07:36:39.6500000 | VENDOR CABLE | 2021-04-12T07:44:20.0630000
T-00191-0808 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSH-102-MGL-W1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:06:38.7770000 |  |  | 0.25 | 2021-04-12T07:33:20.6170000 | VENDOR CABLE | 2021-04-12T07:44:44.7330000
T-00191-0809 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSL-102-MGW-W10 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:07:04.6730000 |  |  | 0.25 | 2021-04-12T07:38:54.4830000 | VENDOR CABLE | 2021-04-12T07:45:08.6500000
T-00191-0810 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSH-102-MGW-W9 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:07:30.1370000 |  |  | 0.25 | 2021-04-12T07:33:21.2800000 | VENDOR CABLE | 2021-04-12T07:45:36.0600000
T-00191-0811 | E1.T067 LV Cable (Control) Stage 1 | CABL | ZSL-101-MGW-W7 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T22:07:55.7230000 |  |  | 0.25 | 2021-04-12T07:36:16.7930000 | VENDOR CABLE | 2021-04-12T07:45:57.1970000
T-00191-0812 | E1.T067 LV Cable (Control) Stage 1 | CABL | PS-101-MGG-W12 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-13T20:16:46.6230000 |  |  | 0.25 | 2021-04-13T07:31:50.7600000 | VENDOR CABLE | 2021-04-13T20:10:04.0770000
T-00191-0813 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-GT-2165-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 4C 0.34mm2 Cu PVC/SCR/PVC
T-00191-0814 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-XS-2126-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00191-0815 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-OP-4203-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 40C+E,0.75mm²,PVC/PVC
T-00191-0816 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-XS-2127-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00191-0817 | E1.T067 LV Cable (Control) Stage 1 | CABL | 7ZS02-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00191-0818 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-LSH-2101A-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,0.75mm²,PVC/PVC
T-00191-0819 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-PS-2160-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00191-0820 | E1.T067 LV Cable (Control) Stage 1 | CABL | 7ZS01-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00191-0821 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-LSH-2101B-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C+E,0.75mm²,PVC/PVC
T-00191-0822 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-XS-2132-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PUR/PUR
T-00191-0823 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-XS-2177-J1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00191-0824 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333-LSH-2108-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  |  |  | 0.25 |  | 5C 0.25mm2 Cu PVC/PVC
T-00191-0825 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3334HE4008-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.25 |  | 4C+E,1.5mm2,PVC/PVC,BLK
T-00191-0826 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSL1194-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:25:16.8370000 |  |  | 0.25 | 2021-04-17T03:51:56.2630000 | 3332-PU-4022 | 2021-04-17T03:59:57.9430000
T-00191-0827 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3332LSH1194-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:26:07.1630000 |  |  | 0.25 | 2021-04-17T03:58:55.4900000 | 2C+E | 2021-04-17T04:00:39.1570000
T-00191-0828 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4210-C3 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0829 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSH2232-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0830 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSH2232-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0831 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSH2220-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0832 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333MT2230-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0833 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSL2219-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0834 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSH2220-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0835 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333PSH2218-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0836 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4210-C5 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0837 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333XV2214-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0838 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZSC2233-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0839 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4210-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0840 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4210-C4 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0841 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333OP4210-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 8C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0842 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333SSL2227-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0843 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333ZSC2234-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0844 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333SSL2213-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0845 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333SSL2213-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0846 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333SSL2227-C1 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00191-0847 | E1.T067 LV Cable (Control) Stage 1 | CABL | 3333LSL2219-C2 | CCBL - Control Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 2C+E,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0012 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FD4002-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0017 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333DY4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0018 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4038-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-23T00:34:56.9400000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T02:51:10.3470000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:49:50.7330000
T-00192-0027 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FD4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0033 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333VS4021-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-15T11:22:11.5400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-12T20:43:16.8900000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-13T04:03:25.1500000
T-00192-0041 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331VS4004-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-21T05:28:11.5900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T02:31:32.5700000 | 2PR,I/OAS,0.5mm2,PVC/PVC,BLK | 2021-02-21T05:02:35.8130000
T-00192-0043 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4110-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T03:42:36.1030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-17T21:23:33.6230000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-17T23:04:33.9270000
T-00192-0051 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4141-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0055 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338PF4002-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-25T13:31:35.0930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T21:13:41.7230000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-24T22:04:09.8070000
T-00192-0059 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0138B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:50:52.8430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:48:56.9270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:03:58.5170000
T-00192-0060 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0579-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T02:30:52.2970000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T07:07:11.2230000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T07:25:07.1230000
T-00192-0061 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0824-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0062 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0716-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0063 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4081-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T07:00:58.7730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T01:52:09.2030000 | 12PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:31:39.9470000
T-00192-0064 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT0063-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:24:05.7100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T10:42:17.7830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-03T20:35:14.8500000
T-00192-0065 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335MB4091-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:58:07.7930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T06:12:23.5370000 | 8PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:16:10.6470000
T-00192-0066 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1080-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0067 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0354-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T07:12:32.6900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:15:21.9130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T20:09:09.9970000
T-00192-0068 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0690-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0069 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LIT0870-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0070 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0329-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-02T02:48:10.2800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T06:11:03.4970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:40:14.5530000
T-00192-0071 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0527-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-27T04:20:46.8230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T00:02:16.2770000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T03:55:01.2800000
T-00192-0072 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0555-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:46:27.4900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T22:00:30.9300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T03:46:56.7230000
T-00192-0073 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LI0821A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0074 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0596-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0075 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4033-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-08T20:04:47.4700000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-08T04:07:46.9200000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:09:09.2500000
T-00192-0076 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1140-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0077 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335AIT0854-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T21:05:23.5530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T05:51:24.0870000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:13:16.2770000
T-00192-0078 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0565A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0079 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0718-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0080 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PIT0031-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-12T09:13:25.1400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-12T02:30:39.5430000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-12T06:49:57.9930000
T-00192-0081 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0436-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:13:55.7630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T05:31:46.7230000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:10:55.2070000
T-00192-0082 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0216-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0083 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0790-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:44:04.1200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T06:51:20.7170000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:53:31.7870000
T-00192-0084 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0306-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:51:58.9130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T20:09:53.4700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:56:43.7670000
T-00192-0085 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LCV2365-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-04T21:50:10.4900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-02T05:00:06.6570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-04T02:12:55.1970000
T-00192-0086 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT2147-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-11T13:55:30.0130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-10T12:59:38.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T04:48:36.9700000
T-00192-0087 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333VS4022-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0088 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335MB4093-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 12PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0089 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1047-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:35:28.9100000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T05:44:34.4670000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:12:44.0670000
T-00192-0090 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0155-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0091 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0310-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:52:56.7300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T05:42:26.6000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:20:28.9430000
T-00192-0092 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0093 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0728-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0094 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0348-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-03T22:57:43.5600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T06:43:01.0570000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T22:19:54.6530000
T-00192-0095 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4060-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:03:43.9470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:14:47.6970000 | 12C+E,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:40:08.2900000
T-00192-0096 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4076-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0097 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0185A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:26:34.7570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T22:54:44.0930000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:10:43.7230000
T-00192-0098 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0494A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-04T02:34:53.9270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T05:19:22.9600000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:02:10.8670000
T-00192-0099 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1124-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:37:31.5500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-16T06:29:21.5270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:58:34.6530000
T-00192-0100 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0715-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0101 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0131-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0102 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0126-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-04T06:18:32.1570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-03T05:37:53.8430000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-04T02:08:40.6400000
T-00192-0103 | LV Cable (Instrument) Stage 1 | CABL | 3331MB4010-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-15T11:24:53.3970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-21T22:46:33.0000000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-22T02:41:35.6870000
T-00192-0104 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0106-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:27:53.7570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T21:53:39.3000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T23:27:17.6700000
T-00192-0105 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332OP4205-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-15T03:52:24.1070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-13T20:50:54.1700000 | 8PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-14T01:52:00.4870000
T-00192-0106 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00192-0107 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0187-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-03T22:28:20.5400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-03T21:46:13.8730000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T22:18:05.3670000
T-00192-0108 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0457-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-14T07:59:56.3730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:08:10.5830000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T04:10:57.0730000
T-00192-0109 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0717-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0110 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335TIT0810-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0111 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0767-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-25T22:02:07.5370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T07:04:03.0030000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-25T07:26:16.8830000
T-00192-0112 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0304A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:53:42.1000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T05:18:49.8700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:22:13.0470000
T-00192-0113 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0480A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:14:48.2200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T04:45:13.9470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T04:51:22.2670000
T-00192-0114 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0652A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:30:37.6230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:08:31.7370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T06:23:34.4100000
T-00192-0116 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1056-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0117 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1127-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0118 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0186-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:56:35.8230000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-27T22:45:05.5470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T23:14:13.7000000
T-00192-0119 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0452-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:06:02.5270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T07:12:51.2300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-23T07:48:40.5600000
T-00192-0120 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335FY0855-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-22T09:22:59.5030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-21T22:28:58.8530000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T22:41:22.1770000
T-00192-0121 | LV Cable (Instrument) Stage 1 | CABL | 3331MB4002-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-15T11:25:34.6400000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-26T11:01:08.0000000 | 16PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:22:59.5670000
T-00192-0122 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0654-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:41:30.1170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T07:06:36.9470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T07:07:57.5800000
T-00192-0123 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0872-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0124 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4086-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:43:11.9530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:21:51.6770000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:18:21.7630000
T-00192-0125 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4026-J3 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T06:59:27.4730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T01:51:34.1500000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:15:28.2600000
T-00192-0126 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0486-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-23T00:38:00.2630000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T05:18:27.9530000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:13:33.5170000
T-00192-0127 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DE0126-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Vendor Cable
T-00192-0128 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0494-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:50:45.2330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T22:49:16.9200000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T23:11:47.4870000
T-00192-0129 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1048-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0130 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0324-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0131 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0790-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:44:33.7870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T06:55:57.5030000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:54:02.8800000
T-00192-0132 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1042-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0133 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1137-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0135 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0111-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T11:47:36.7500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:03:21.2800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:13:47.5700000
T-00192-0136 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0148-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0137 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0464-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:15:15.1670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:06:32.6270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:13:40.5200000
T-00192-0138 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0791-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:47:04.3230000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T07:00:30.9270000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:54:27.1570000
T-00192-0139 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LIT0580-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0140 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0761-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0141 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0141B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:51:18.6100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:06:18.7970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:05:28.2970000
T-00192-0142 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0582-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:51:49.8470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T05:43:41.2370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:35:29.3270000
T-00192-0143 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0414-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:22:01.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T21:13:47.8930000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:01:47.4930000
T-00192-0144 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0145 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0719-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0146 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0194-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:27:05.5470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:11:32.2170000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:24:39.4470000
T-00192-0148 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0149 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1102-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0150 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0825-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0151 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4022-J3 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-05T06:52:07.3700000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-04T20:30:48.6970000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:42:38.2200000
T-00192-0152 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0831-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0153 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335FIT0864-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-18T23:03:35.1370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T18:09:40.0300000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:14:11.6570000
T-00192-0154 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0250-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:11:31.8500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:42:46.4300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T00:21:26.1870000
T-00192-0155 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0164-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T23:00:07.8830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-16T05:15:19.8270000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:05:07.6500000
T-00192-0156 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0315B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:54:41.0270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T21:13:18.7630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:00:09.9170000
T-00192-0157 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0731-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0158 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4037-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-09T06:32:08.1530000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-07T22:27:51.3630000 | 16PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-08T04:49:14.5000000
T-00192-0159 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0323-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0160 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0508-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T03:48:32.4230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:28:39.1170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:57:47.2530000
T-00192-0161 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0711-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0162 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0503-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0163 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0419-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:22:40.3330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T21:01:43.1070000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:04:31.9670000
T-00192-0164 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0146-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:26:18.6600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T00:48:32.4370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T03:09:41.8330000
T-00192-0165 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335FIT0851-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Closed | 2021-01-29T21:05:54.9430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-25T02:49:21.8700000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-25T03:03:51.8700000
T-00192-0166 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0301-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:42:13.8570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T20:27:40.4570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:55:54.6670000
T-00192-0167 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0457-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-14T08:00:19.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:02:33.5930000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T04:11:40.1670000
T-00192-0168 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0804-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0169 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0156-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:52:37.8830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:50:48.8370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:06:17.8330000
T-00192-0171 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0190B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:27:34.5100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T23:56:07.7770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:26:00.1530000
T-00192-0172 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4105-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0173 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0769-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T07:17:45.4630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T07:21:25.7370000
T-00192-0174 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0580-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0175 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0148-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0176 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0348-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-02T02:50:56.0070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T06:25:33.4330000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:41:10.6530000
T-00192-0177 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0714-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0178 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DE0033-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:43:25.2300000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T05:48:22.1400000 | Vendor Cable | 2021-04-24T07:24:31.5370000
T-00192-0179 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0496-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:53:58.7270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T22:57:50.6630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T23:12:42.7900000
T-00192-0180 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0758-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0181 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DIT0527-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-04T02:52:19.7670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T03:56:27.1270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:37:13.4970000
T-00192-0182 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0141A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:53:04.3530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:25:07.4170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:06:33.4930000
T-00192-0183 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0133-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:53:31.8370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:59:28.3330000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:08:40.3200000
T-00192-0184 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0315-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:43:05.5830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:07:35.0570000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:21:06.4170000
T-00192-0185 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1041-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0187 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0138-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:54:01.4500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T23:38:14.3200000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:09:37.6070000
T-00192-0188 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0685-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0189 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335AIT0868-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-18T23:04:16.4800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:58:30.2570000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:14:48.0070000
T-00192-0190 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0729-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0191 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0111A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T11:48:09.1170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:06:05.1900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:15:31.8830000
T-00192-0192 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0317-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:43:49.3730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:38:39.1100000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:55:28.5100000
T-00192-0193 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1055-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:09:48.8800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T07:15:44.1770000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-23T07:49:35.1430000
T-00192-0194 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0304B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:56:01.2100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:09:42.4630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:22:36.9530000
T-00192-0195 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0310A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:45:56.4630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T20:41:35.8270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:58:48.4200000
T-00192-0196 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0185B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:28:02.2000000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T23:43:13.4430000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:11:27.2470000
T-00192-0197 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0166-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:38:35.4330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T22:18:34.2630000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T23:36:48.4600000
T-00192-0198 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0324-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0199 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0869-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0200 | LV Cable (Instrument) Stage 1 | CABL | 3334FIT2113-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:31:30.8970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-26T10:03:43.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:23:44.4800000
T-00192-0201 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0726-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0203 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PIT0902-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Closed | 2021-02-11T13:53:44.3800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-10T20:14:56.6800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T04:45:03.5730000
T-00192-0204 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4021-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:58:45.4670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T00:35:08.9300000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:29:19.5000000
T-00192-0206 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0576-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:38:28.2570000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-18T06:46:16.7000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-18T22:32:58.9270000
T-00192-0207 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1040-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0208 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PDIT1163-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0209 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AIT0085-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-21T02:43:28.8530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-17T00:12:35.7900000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-17T03:50:35.0770000
T-00192-0210 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0191-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:28:50.8170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T23:46:13.7130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T05:25:14.8370000
T-00192-0211 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PIT0860-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-18T23:05:17.6270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T18:14:52.9270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:15:16.6370000
T-00192-0212 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331FIT0074-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-04T02:36:16.8100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T05:44:41.2770000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:27:59.9570000
T-00192-0213 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0106-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T21:13:38.0770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T02:28:13.5000000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-19T04:05:43.4300000
T-00192-0214 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1138-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0215 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1043-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0216 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0488-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0217 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PIT0848-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-21T02:50:02.6900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-16T07:01:04.1670000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-16T20:28:25.6730000
T-00192-0218 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0437-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0219 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0499B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:54:23.8870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T17:14:47.1400000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T21:12:05.8330000
T-00192-0220 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PIT0590-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0221 | LV Cable (Instrument) Stage 1 | CABL | 3335MB4092-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:33:21.4300000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-26T12:20:33.0000000 | 16PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:29:22.8530000
T-00192-0222 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0555A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0223 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0156-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:54:33.0200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:09:16.0570000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:11:21.3670000
T-00192-0224 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1044-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0225 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FIT0593-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0226 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4106-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0227 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4082-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-20T22:44:26.0470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-20T06:02:48.3370000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T06:04:27.6430000
T-00192-0228 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0652B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:31:15.5330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:16:08.0670000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T06:24:31.3370000
T-00192-0229 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0169A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:54:58.0600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:14:44.2030000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:11:41.9470000
T-00192-0230 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1075-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0231 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0213-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0232 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0532-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0233 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0200A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:29:23.7870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:41:24.0500000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T03:44:02.0130000
T-00192-0234 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0843-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0235 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1073-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0236 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0718-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0237 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0196-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-07T04:50:11.5530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-06T22:57:25.7930000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-06T23:41:44.7270000
T-00192-0238 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0177-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0239 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0160-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T23:00:39.5270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-16T05:02:21.7400000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:05:41.4630000
T-00192-0240 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332OP4221-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0241 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1052-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T07:24:33.1970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-27T07:24:58.3570000
T-00192-0242 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331FIT0087-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Closed | 2021-04-24T21:25:57.5000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-24T07:20:08.3330000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:28:37.8470000
T-00192-0243 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0413-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:23:09.0600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T06:47:10.7830000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:38:11.5300000
T-00192-0244 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0470A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:19:22.3270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T01:21:42.4900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T04:09:39.0570000
T-00192-0245 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0246 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0414A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:23:42.9330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T21:18:48.9670000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:00:31.9530000
T-00192-0247 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332ZIT2340-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-04T21:50:41.4270000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-02T05:03:43.2700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-04T02:13:27.8630000
T-00192-0248 | LV Cable (Instrument) Stage 1 | CABL | 3331MB4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-10T06:33:55.0330000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-26T12:16:34.0000000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:27:12.3830000
T-00192-0249 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0210-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0250 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0141-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T23:01:14.8970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-16T04:39:14.5830000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:06:04.8870000
T-00192-0251 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0731-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0252 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0600-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:45:02.1400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T06:53:25.2870000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-26T19:14:15.1230000
T-00192-0253 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DIT0032-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-25T05:58:19.8900000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-23T20:39:57.0530000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-24T18:41:33.2130000
T-00192-0254 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0480-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:23:39.4630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:15:40.4070000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:22:03.8130000
T-00192-0255 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0161-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:55:28.7300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T22:52:10.2870000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:13:01.2730000
T-00192-0256 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT0790-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0257 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0182-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:29:55.8300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T22:45:23.2570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T23:56:24.7330000
T-00192-0258 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00192-0259 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0710-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0260 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DE0056-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-02-22T15:41:53.6170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-21T06:00:24.2500000 | Vendor Cable | 2021-02-21T06:31:50.5970000
T-00192-0261 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0443-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:22:35.3100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:03:21.2130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:25:19.7970000
T-00192-0262 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DE0545-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:43:50.9430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T07:36:25.6930000 | Vendor Cable | 2021-04-24T07:46:04.8970000
T-00192-0263 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0490-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:50:19.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T17:33:14.5930000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T22:18:38.3100000
T-00192-0264 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1135-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0266 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4026-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T07:00:00.3100000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T01:38:20.7870000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:11:45.1200000
T-00192-0267 | LV Cable (Instrument) Stage 1 | CABL | 3334FIT2117-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:34:18.4370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-26T09:43:29.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:29:50.8530000
T-00192-0268 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LI0840A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T09:13:49.5970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T22:43:17.3000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T23:24:46.6470000
T-00192-0269 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0320A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:47:37.0000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T21:40:36.5600000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:02:29.6030000
T-00192-0270 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4028-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-30T13:22:52.8030000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-30T05:23:41.8170000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:11:32.2270000
T-00192-0271 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0720-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0272 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT0034-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:53:29.0730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:10:23.0330000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:38:16.4300000
T-00192-0273 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1079-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0274 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0712-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0275 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PDIT0852-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T21:12:05.0670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T06:01:56.4730000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:13:35.8970000
T-00192-0276 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1071-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0277 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0317-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:41:43.8800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:49:17.6800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:57:44.8000000
T-00192-0278 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LIT0840-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-12T09:14:18.4370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T22:40:59.2500000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T23:25:12.9930000
T-00192-0279 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0842-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0280 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0832-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0281 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0282 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DE0032-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:44:13.6830000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T05:36:22.4600000 | Vendor Cable | 2021-04-24T07:24:58.9730000
T-00192-0283 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1066-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:24:12.7670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T20:42:16.3230000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:49:32.8430000
T-00192-0284 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PDIT7829-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0285 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335FIT0849-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T11:26:37.5370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-12T20:08:51.0530000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-13T04:01:29.7700000
T-00192-0286 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332OC4001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0287 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT0022-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-10T06:35:02.6730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-03T10:33:00.1100000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-03T20:35:34.7200000
T-00192-0288 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1046-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-24T03:01:44.6630000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-23T06:46:41.9000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-23T07:07:28.4800000
T-00192-0289 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1029-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0290 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0200-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:32:10.5570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:36:16.5630000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T03:44:24.6370000
T-00192-0291 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0544-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:04:19.1170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:44:03.8570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:08:57.7270000
T-00192-0292 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT2237-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:51:54.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T06:43:15.8200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T21:02:07.6900000
T-00192-0293 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LIT0856-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-02-21T00:03:46.6730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:41:50.9500000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:45:47.5100000
T-00192-0294 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0191-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:33:07.5970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:12:28.7030000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:24:03.3600000
T-00192-0295 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0581-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:50:14.0570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T05:34:57.4630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T03:48:40.6600000
T-00192-0296 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0722-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0297 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338CA0004-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00192-0298 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0435-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-03T03:49:21.8530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:22:38.9030000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:58:50.2870000
T-00192-0299 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0468-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:24:05.3530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:43:25.7030000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:57:47.7570000
T-00192-0300 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4034-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:43:43.7770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:32:22.8470000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:18:55.2570000
T-00192-0301 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0658-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-24T02:06:24.1530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T05:46:09.7070000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-23T06:58:32.5070000
T-00192-0302 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0165-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:56:23.7230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:42:24.4200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:13:47.3970000
T-00192-0303 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4022-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-12T09:17:59.3370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-12T02:40:20.2030000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-12T06:51:56.8100000
T-00192-0304 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0194A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:38:37.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:18:48.2600000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:26:44.5500000
T-00192-0305 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0722-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0306 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0165-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:56:56.6500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:17:57.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:14:16.1030000
T-00192-0307 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0456-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-03T03:50:09.3170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:22:06.1130000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T00:59:38.2470000
T-00192-0308 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0133-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:57:20.9070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:40:30.0530000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:14:43.1600000
T-00192-0310 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0791-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:50:37.9570000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T07:05:04.9970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:54:54.7770000
T-00192-0311 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0186-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-28T04:54:56.1170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T22:41:57.7300000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T23:13:10.7370000
T-00192-0312 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0732-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0313 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0164B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:58:09.2030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T22:39:34.3570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:15:05.3170000
T-00192-0314 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0315 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LY0840-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-02-05T06:58:56.1470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-03T06:54:34.1830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:45:58.8470000
T-00192-0316 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0466-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:25:25.6000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T05:56:14.0800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:14:01.2600000
T-00192-0318 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0113-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-15T00:06:28.0300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-13T23:53:15.0170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-14T00:59:29.0430000
T-00192-0319 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0876-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0320 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1136-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T07:32:06.9830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-27T07:25:44.0270000
T-00192-0321 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0462-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:32:44.9270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T07:31:26.3300000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-18T22:26:26.5930000
T-00192-0322 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0575-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0323 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0499A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:55:25.0800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T17:15:32.7630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T22:20:15.4800000
T-00192-0324 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1049-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0325 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DE0074-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:44:34.0830000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:24:57.5500000 | Vendor Cable | 2021-04-24T07:25:22.0100000
T-00192-0326 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0656-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:42:11.9670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:47:19.1800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T07:06:57.3670000
T-00192-0327 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0176-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T06:59:45.4730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T06:53:03.5970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:26:09.8330000
T-00192-0328 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0132-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:00:14.1800000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T22:05:42.7800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:15:29.7400000
T-00192-0329 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0180-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-04-20T03:43:06.7470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-19T04:53:46.7130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:29:47.7670000
T-00192-0330 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1005-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:45:24.6030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:57:28.1200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-26T06:49:01.2400000
T-00192-0331 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0658-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Completed |  | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-26T06:41:44.6430000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:47:10.5470000
T-00192-0332 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0463-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:29:06.0670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T05:20:45.9570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:14:21.0500000
T-00192-0333 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4028-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-24T03:24:07.2930000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T03:23:16.3400000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:52:34.4630000
T-00192-0334 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4060-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0335 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4046-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-15T21:50:00.3800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-15T06:16:29.3130000 | 12PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T06:49:43.3970000
T-00192-0336 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0480B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:29:30.2600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T04:59:59.3770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T05:05:37.3830000
T-00192-0337 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LI0740A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0339 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0312-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:42:30.7530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:01:42.6770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:57:12.2970000
T-00192-0340 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0521-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-02-28T04:51:37.3600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T00:15:46.9670000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T03:55:29.1170000
T-00192-0341 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4071-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0342 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0490-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:55:48.0500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T17:20:43.1230000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T22:20:43.6330000
T-00192-0343 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0712-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0344 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0345 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0585-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:41:09.2900000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:18:12.5170000 | 2PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:41:14.6530000
T-00192-0346 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1152-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0348 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4085-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-30T13:23:19.0830000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-29T20:40:17.3170000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:12:02.7730000
T-00192-0349 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0702-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0350 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0453-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:24:29.7500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-20T04:52:59.3370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:14:11.2470000
T-00192-0351 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0770-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:51:12.7400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T06:40:59.0370000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:55:13.1530000
T-00192-0352 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0752-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0353 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0466-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:29:52.7400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:13:32.3870000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:22:24.2830000
T-00192-0354 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4026-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-01T07:00:27.6770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-28T01:26:50.8030000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:12:12.7570000
T-00192-0355 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0306-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:43:20.7770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T20:04:49.3330000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:45:57.1170000
T-00192-0356 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0714-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0357 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0169B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:00:44.4100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:18:10.6730000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:15:56.7000000
T-00192-0358 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0349A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-20T07:30:17.1570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:29:22.2970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-17T20:09:34.0730000
T-00192-0359 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0470-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-22T06:38:23.9470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-22T04:54:58.5470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T05:55:29.3870000
T-00192-0360 | LV Cable (Instrument) Stage 1 | CABL | 3334FIT2115-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-10T06:35:30.2970000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-26T09:43:52.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:30:09.1100000
T-00192-0361 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0453-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:24:51.8500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-20T04:48:11.1600000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:15:01.7200000
T-00192-0362 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1053-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0363 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0494B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-03-01T06:21:26.5970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T23:42:09.0770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T06:09:05.5630000
T-00192-0364 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LI0693A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0365 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0721-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0366 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0662-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:42:59.6930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:20:35.4000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T06:24:56.4670000
T-00192-0367 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT1061-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-03T03:58:03.1300000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-02T23:52:52.9470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:07:03.0430000
T-00192-0368 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1167B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:38:55.5830000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-19T04:54:29.9270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:38:15.0300000
T-00192-0369 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0468-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:34:33.4700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T06:04:31.7270000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-16T06:14:39.8900000
T-00192-0370 | LV Cable (Instrument) Stage 1 | CABL | 3331LCV2147-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-10T06:36:30.3500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T12:51:27.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-31T19:17:21.8370000
T-00192-0371 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4035-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-01T03:27:21.4630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-30T21:30:45.6870000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-31T02:47:43.4270000
T-00192-0372 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0710-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0373 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0182-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:39:14.8570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T22:39:54.4930000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T23:45:10.4230000
T-00192-0374 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4070-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0375 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PIT0903-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-02-15T00:05:46.0070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-13T17:04:27.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-13T19:53:28.3230000
T-00192-0376 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0723-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0377 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PIT0083-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-04T02:36:58.1170000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T22:12:44.1200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:31:30.2370000
T-00192-0378 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0565-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:48:14.6670000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-19T21:57:04.7170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T03:49:06.3700000
T-00192-0380 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LI0022A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:27:32.9200000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-09T04:37:04.3470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T04:44:04.1030000
T-00192-0381 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0768-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-25T22:02:53.8900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-25T07:03:05.9770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-25T07:26:48.4070000
T-00192-0382 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335FIT0855-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-02-20T23:57:42.3930000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-20T22:45:30.6230000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:48:59.4200000
T-00192-0383 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0194B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:39:44.4030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:22:40.0900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:27:29.2600000
T-00192-0384 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0823-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0385 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331FIT0056-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:33:28.6630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T16:48:36.6930000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:19:29.1730000
T-00192-0386 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0195-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:45:43.2730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-27T23:49:35.4830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T05:25:44.7870000
T-00192-0387 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY1029-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0388 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0445-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:23:04.3670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:09:30.9800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:25:49.1570000
T-00192-0389 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0349-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-02T02:51:32.2230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-01T06:15:27.9370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:41:41.8870000
T-00192-0390 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DIT0126-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-03T06:14:29.1430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-03T01:10:29.2970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T06:04:17.7400000
T-00192-0391 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0770-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Closed | 2021-01-21T02:52:47.5170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-18T06:45:48.6970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-19T04:55:41.3670000
T-00192-0392 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0250-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:12:06.1470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:37:28.8300000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T00:21:00.9170000
T-00192-0393 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0320B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:48:00.4070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T22:15:07.8370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T22:50:14.3670000
T-00192-0394 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1105-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0395 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AIT0021-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0397 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0190-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:46:08.2830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:52:38.7430000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:27:40.5570000
T-00192-0398 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0110-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T11:48:40.0200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-21T06:20:28.5930000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-21T06:34:15.9870000
T-00192-0399 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0496-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-28T04:56:14.3670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-27T22:53:02.0730000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-27T23:13:40.2530000
T-00192-0401 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1078-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0402 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DIT0074-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-25T05:58:50.6370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-23T21:43:25.8970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-24T18:41:59.4370000
T-00192-0403 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4034-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:44:12.0570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:43:23.3530000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:19:36.4170000
T-00192-0404 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1074-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0405 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0108-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-15T00:07:00.6270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-13T22:54:34.9630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-14T00:59:44.8130000
T-00192-0406 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4022-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-05T07:01:47.9370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-04T20:35:24.7770000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:43:03.8030000
T-00192-0407 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333MB4071-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-04 - Marshalling boxes Molybdenum Concentrate Handling | CS0A - Process Control - Network and DCS panels | Completed |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-26T05:58:21.4000000 | 12PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:46:36.9270000
T-00192-0408 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PIT0877-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0409 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0445-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:23:26.8370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T00:40:31.9070000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:26:09.6730000
T-00192-0410 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0175-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:26:38.4570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T00:55:34.0300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T03:10:20.3500000
T-00192-0411 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1126-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0412 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT0821-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0413 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0161-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:02:20.4600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T22:45:05.5170000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:16:17.7500000
T-00192-0414 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0449B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:40:49.7170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:55:15.3100000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T03:40:33.6670000
T-00192-0415 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0652A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:34:03.4570000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T05:59:02.3370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T06:02:08.8770000
T-00192-0416 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4075-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0417 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1141-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0418 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0713-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0419 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0315A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T05:55:21.6830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T21:08:35.3400000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:59:36.5270000
T-00192-0420 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4033-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-08T20:05:33.8200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-08T04:17:51.5270000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-08T06:16:44.7070000
T-00192-0421 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0456-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-03T03:50:54.1100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:26:42.0700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:00:13.8030000
T-00192-0422 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0449-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:23:52.0970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T04:56:34.6370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:26:33.3630000
T-00192-0423 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LIT0850-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0424 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0173-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:26:59.6100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T00:52:25.7800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-28T03:10:41.2130000
T-00192-0425 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0138A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:02:47.0270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:54:17.7700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:16:37.9900000
T-00192-0426 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT0693-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0427 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0312-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:43:59.4470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T07:05:26.2130000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:55:06.5930000
T-00192-0428 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0447-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:24:21.3600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:22:43.4830000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:27:56.4830000
T-00192-0429 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0830-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0430 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY1026-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0431 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332OP4206-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-02-15T03:52:58.5470000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-02-13T20:49:33.4770000 | 8PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-14T01:52:21.8970000
T-00192-0432 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0584-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:39:34.6370000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:16:49.7470000 | 2PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:41:48.5300000
T-00192-0433 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332ZIT2240-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-04T02:53:58.0430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-02T05:08:00.2330000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-04T02:13:58.6230000
T-00192-0434 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4084-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T21:59:33.8730000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-01T05:42:34.6500000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T05:14:55.1470000
T-00192-0435 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY1105-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0436 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT0039-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T10:47:23.5300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T06:47:20.3470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-19T06:48:43.8430000
T-00192-0437 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0213-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0438 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0135-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0439 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0004-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0440 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0200B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:46:37.4730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:46:25.2870000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T03:51:55.8600000
T-00192-0441 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0458-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T06:46:05.0170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T06:48:12.4200000
T-00192-0442 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT0442-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:24:47.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T05:00:30.2830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:28:31.0670000
T-00192-0443 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1050-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:39:52.4000000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T06:32:37.5200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T07:10:59.0770000
T-00192-0444 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1154-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0445 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1076-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0446 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DIT0056-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:44:57.6370000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T06:30:15.2700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:25:46.1770000
T-00192-0447 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0841-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0448 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PDIT0853-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-29T21:12:34.9830000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T06:08:14.9900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T21:13:58.9770000
T-00192-0449 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0362-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-25T21:47:26.8500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-25T07:02:10.9100000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-25T07:19:02.4070000
T-00192-0450 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0840-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0451 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0005-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0452 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0210-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0453 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0010-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0454 | LV Cable (Instrument) Stage 1 | CABL | 3334FIT2119-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:28:05.8800000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-26T10:06:26.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:30:30.6070000
T-00192-0455 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0108-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-12T09:14:45.3800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-11T20:09:24.2730000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T21:38:40.8070000
T-00192-0456 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0436A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:41:15.4730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-20T05:38:09.1770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:11:19.6770000
T-00192-0457 | LV Cable (Instrument) Stage 1 | CABL | 3334FIT2111-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:28:35.4430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-26T10:09:28.0000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2020-12-26T20:28:55.3370000
T-00192-0458 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0160B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:03:09.3070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:41:29.0370000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:19:22.4930000
T-00192-0459 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0662-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:43:42.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T07:02:28.4300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T07:07:26.3170000
T-00192-0460 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PT2337-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-22T07:08:03.7270000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T03:09:47.1770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:42:41.8400000
T-00192-0461 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0488-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0462 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0169-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-16T23:01:43.9370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-16T05:28:23.8930000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-16T07:06:24.4400000
T-00192-0463 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1057-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0464 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0465 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0466 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331OP4202-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-01-15T11:29:13.9400000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-04T15:40:39.4770000 | 8PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-04T19:52:55.9870000
T-00192-0467 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0142-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:39:07.4730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T22:11:03.6100000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T23:35:42.2900000
T-00192-0468 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0691-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Started |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0469 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0160A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:03:38.6430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T20:25:48.1130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:20:00.4700000
T-00192-0470 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0759-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0471 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0301-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:44:50.5230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T20:14:06.1170000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:43:56.6900000
T-00192-0472 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1072-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0473 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0441-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-06T23:47:21.5870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T00:48:32.0470000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-06T07:35:21.1670000
T-00192-0474 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0435-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Closed | 2021-04-03T03:51:32.9470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-02T01:31:00.7800000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T01:00:48.5970000
T-00192-0475 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LI0790A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0476 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335LI0870A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0477 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0113-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Closed | 2021-02-22T12:12:39.8830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-21T22:30:39.1570000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-22T00:20:13.1270000
T-00192-0478 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LIT7821-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0479 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0177-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0480 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00192-0481 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0725-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0482 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1167A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:42:04.5370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-19T04:54:56.2600000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:38:37.6900000
T-00192-0483 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0491-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-03T22:59:29.4800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T06:20:34.0230000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-03T22:25:19.8500000
T-00192-0484 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0132-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:04:10.4670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T21:39:03.6400000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:20:23.0930000
T-00192-0485 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1153-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0486 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PIT0073-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-04T02:37:31.6770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-02T07:10:30.6200000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-02T22:28:32.4100000
T-00192-0487 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0413-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T02:24:39.2470000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-01T06:36:31.1170000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:59:33.4070000
T-00192-0488 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4021-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-04T22:00:06.6500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-02T00:33:44.7930000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-02T04:29:43.6030000
T-00192-0489 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0716-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0490 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0164A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-05T07:04:35.4900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-03T22:34:05.3470000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-05T02:20:42.1500000
T-00192-0491 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT0691-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0492 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0652B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-07T22:34:39.5500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-07T06:03:21.0130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-07T06:24:00.6800000
T-00192-0493 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4082-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-20T22:42:32.4970000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-20T06:03:09.2900000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T06:05:11.2330000
T-00192-0494 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1158-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0495 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0307-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-07T04:50:56.4270000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-06T23:07:10.4470000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-06T23:47:54.6330000
T-00192-0496 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0577-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0497 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DIT0545-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-24T22:45:19.5200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T07:28:47.2930000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-24T07:29:21.9000000
T-00192-0498 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0320-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:45:38.8330000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:30:20.2530000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:58:15.9270000
T-00192-0499 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0304-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T21:46:23.3200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T06:08:34.0200000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T06:19:37.3070000
T-00192-0501 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4030-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-02T03:03:38.1200000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-01T01:51:25.2200000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-02T00:45:46.7570000
T-00192-0502 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0185-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:47:15.8630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T22:49:24.1200000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:01:47.7700000
T-00192-0503 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0545-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:04:47.9130000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T00:40:23.2470000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-30T06:09:18.7670000
T-00192-0504 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FY0720-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0505 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AIT0091-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0507 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332DE0527-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-04-03T04:01:59.5800000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-03T00:09:48.4630000 | Vendor Cable | 2021-04-03T01:08:52.6370000
T-00192-0508 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AIT0064-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0510 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0449A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-15T21:45:34.7230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T01:56:45.5700000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-15T03:37:49.7100000
T-00192-0511 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PT2104-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:30:00.6770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-07T22:18:54.7900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-08T00:07:53.9800000
T-00192-0512 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332MB4031-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-01T03:28:00.3070000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-30T21:47:45.6970000 | 8PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-31T02:48:06.6000000
T-00192-0513 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4086-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-25T13:44:41.2630000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-24T04:08:57.9500000 | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-24T22:20:06.2430000
T-00192-0514 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0499-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-04-10T08:08:23.8030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-10T06:04:03.1400000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-10T06:45:40.0230000
T-00192-0515 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LIT0179-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:28:43.3700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-20T02:45:21.2400000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T23:28:02.8030000
T-00192-0516 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LCV2242-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-04T06:19:44.8130000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-02T04:56:36.6300000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-04T02:09:12.0870000
T-00192-0517 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PIT0833-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0518 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1045-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Completed |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-26T07:21:04.4630000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-27T07:26:17.5900000
T-00192-0519 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0458A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Completed |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-26T07:10:35.7100000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-26T07:15:03.0400000
T-00192-0520 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LI0580A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0521 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LIT0615-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0522 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1104-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0523 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331DIT0033-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0U-01 - Density Instruments | CS0U - Density Instruments | Closed | 2021-03-25T05:59:34.1870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-23T21:39:03.5830000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-24T18:42:27.6700000
T-00192-0524 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FIT1077-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0525 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331FIT0004-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T22:55:44.9730000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-20T22:26:28.4000000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-20T22:36:55.9170000
T-00192-0526 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332CA0006-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0527 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00192-0528 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0486-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Closed | 2021-04-24T03:02:09.4130000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-20T05:13:30.6970000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-20T06:13:53.0530000
T-00192-0529 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LIT1110-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-05T05:31:46.0570000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-05T02:08:01.3000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-05T04:43:51.8630000
T-00192-0530 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PIT0055-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-18T23:34:15.8770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-18T17:22:57.7970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-18T19:19:55.0470000
T-00192-0531 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT0195-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:56:44.8900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-01T00:29:58.3900000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T04:32:08.4230000
T-00192-0532 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LI0106A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T22:07:41.7700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-19T21:45:49.2130000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-19T21:48:00.3330000
T-00192-0533 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0310B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-03-07T06:46:37.9370000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-03-06T21:05:35.8970000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-06T21:59:12.2230000
T-00192-0534 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334MB4087-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 24PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0535 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334AIT0694-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0536 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0672-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-27T08:45:50.7600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T05:06:31.1100000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-27T05:53:39.2830000
T-00192-0537 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AIT0104-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T00:55:25.3070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:05:42.8300000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-28T05:15:59.2430000
T-00192-0538 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LY0190A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-03-01T05:58:19.8030000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T23:51:12.4330000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-03-01T00:25:15.5630000
T-00192-0539 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1051-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0540 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1100-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0541 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LI0063A-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T11:31:04.1470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-09T04:25:05.6530000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-09T04:43:45.9270000
T-00192-0542 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FIT1026-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0543 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FY0447-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-14T20:25:11.0900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T00:35:41.3770000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-14T07:30:43.4230000
T-00192-0544 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332OP4230-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-20T23:37:32.0570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-20T22:30:47.5070000 | Cat 6/LAN | 2021-02-20T22:37:30.2970000
T-00192-0546 | E1.Txxx LV Cable (Instrument) Stage 1 | CABL | 3334VS4028-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:31:43.2330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T14:10:52.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:18:07.2070000
T-00192-0547 | E1.Txxx LV Cable (Instrument) Stage 1 | CABL | 3331VS4003-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T11:32:26.7630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T14:13:09.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:19:17.2270000
T-00192-0548 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4017-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T07:08:47.6100000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T06:00:14.1530000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:32:23.6570000
T-00192-0549 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334VS4026-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:42:40.7670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T16:07:12.2770000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-23T20:18:10.2030000
T-00192-0550 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4011-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:46:14.6200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T06:52:19.3800000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-26T06:52:50.2470000
T-00192-0551 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334VS4027-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:43:11.3670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T16:10:55.0630000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-23T20:18:50.2670000
T-00192-0552 | E1.Txxx LV Cable (Instrument) Stage 1 | CABL | 3334VS4029-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T11:32:55.7070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T14:15:15.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:19:51.9430000
T-00192-0553 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4005-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T05:25:09.7730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T07:14:09.7100000 | 2Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-11T20:27:18.1530000
T-00192-0554 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4012-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T04:25:36.5870000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T06:38:42.0830000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:32:58.2200000
T-00192-0555 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4015-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-15T12:11:40.5430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-12T20:38:34.6000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-13T04:02:30.5700000
T-00192-0556 | E1.Txxx LV Cable (Instrument) Stage 1 | CABL | 3334VS4030-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T12:12:50.3870000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T14:17:25.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:27:30.8400000
T-00192-0557 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333VS4036-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-04-22T07:13:28.5670000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:19:38.4570000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:47:13.7130000
T-00192-0558 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4031-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-01-15T12:13:17.0800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-01-12T20:39:48.5830000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-13T04:02:58.9670000
T-00192-0559 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4016-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T04:26:12.7770000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T06:16:48.6200000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:33:41.5270000
T-00192-0563 | LV Cable (Instrument) Stage 1 | CABL | 3331VS4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T12:13:46.0400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2020-12-31T14:19:25.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:27:47.7930000
T-00192-0570 | LV Cable (Instrument) Stage 1 | CABL | 3331VS4002-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:11:09.9030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T14:21:22.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:28:13.9770000
T-00192-0571 | LV Cable (Instrument) Stage 1 | CABL | 3334VS4033-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Closed | 2021-01-15T12:14:12.6570000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2020-12-31T14:23:32.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:26:09.7900000
T-00192-0572 | LV Cable (Instrument) Stage 1 | CABL | 3331VS4041-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:14:54.9770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-31T13:50:37.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2020-12-31T19:26:55.2030000
T-00192-0574 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4007-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-12T05:25:38.7000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T07:42:53.3470000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-11T20:26:44.8270000
T-00192-0575 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4008-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-12T05:26:05.4200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T23:02:33.1230000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-11T23:36:03.0300000
T-00192-0576 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4010-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-22T04:26:46.5430000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T06:47:01.3930000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:37:26.7430000
T-00192-0577 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4140-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0578 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4102-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0579 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4034-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-12T05:26:31.4300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-11T23:09:15.0170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-11T23:36:38.7570000
T-00192-0580 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338PF4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Closed | 2021-02-25T13:32:02.5070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-24T15:50:02.0000000 | 2C+E,4mm2,PVC/SWA/PVC,0.6/1 kV | 2021-02-24T22:06:24.2030000
T-00192-0581 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333VS4037-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Closed | 2021-04-22T22:05:09.7930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:43:24.9600000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:47:56.7870000
T-00192-0582 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4014-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T04:27:17.4800000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T05:52:25.7070000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:37:54.4230000
T-00192-0583 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4009-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:46:38.4270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-27T05:14:13.8570000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-27T05:54:01.1870000
T-00192-0584 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4013-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T04:27:49.4170000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T06:26:55.5000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:38:21.6700000
T-00192-0585 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4006-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-19T00:43:34.3600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T23:58:12.6230000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-02-19T00:09:41.1830000
T-00192-0586 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4040-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-24T03:02:38.8470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T03:05:40.3700000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:50:30.4500000
T-00192-0587 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4032-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T04:28:18.7930000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-21T05:51:50.0170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-21T07:39:29.1530000
T-00192-0588 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4035-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T13:19:18.3500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T01:11:38.4130000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-02-22T01:44:20.6070000
T-00192-0589 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333VS4023-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-24T02:57:40.2500000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-22T02:29:44.5170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:49:00.2870000
T-00192-0590 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332VS4039-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-24T03:03:07.9370000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-22T02:58:06.4670000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-22T04:50:58.7900000
T-00192-0591 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PIT1167C-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-24T03:03:31.3430000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-19T04:55:26.0570000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-19T06:38:57.6830000
T-00192-0592 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331FIT0032-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-11T13:59:22.0330000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-11T04:08:21.3530000 | 2PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-02-11T04:56:43.9330000
T-00192-0593 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT0740-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0594 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331ZIT2146-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:16:37.5230000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:46:09.2500000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-05T00:51:10.2100000
T-00192-0603 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2252-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0604 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2251-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0605 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2232-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0606 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338GE4001-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK
T-00192-0607 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2231-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0608 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1351-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0609 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3432-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0610 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3431-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0611 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3572-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0612 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1361-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0613 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1552-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0614 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3551-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0615 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3571-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0616 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2351-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0617 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LL2101-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:17:29.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T04:30:54.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:20:44.5570000
T-00192-0618 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1442-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0619 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3541-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0620 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3462-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0621 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS121-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | KS1-35*B
T-00192-0622 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FV2107-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T12:17:54.2530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T18:07:47.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-01T19:57:27.9470000
T-00192-0623 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1461-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0624 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LSL2103-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T00:43:59.8300000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T17:46:24.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T20:20:15.3000000
T-00192-0625 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1462-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0626 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS221-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | KS1-25*B
T-00192-0627 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2332-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0628 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3472-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0630 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3442-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0631 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3452-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0632 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338XE4101-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK
T-00192-0633 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338XE4101-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK
T-00192-0634 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1541-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0635 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331ZL2146-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:19:37.8600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T02:50:09.9130000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:21:24.0930000
T-00192-0636 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331ZH2146-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:20:35.2670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T02:42:32.2900000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:21:59.5600000
T-00192-0637 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338TE4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Closed | 2021-01-29T21:13:02.6000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-28T00:47:04.3170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-28T05:38:00.1270000
T-00192-0638 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT2101-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T05:18:26.6070000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-24T05:14:27.5900000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-24T05:16:34.5800000
T-00192-0639 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1452-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0640 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1362-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0641 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1272-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0642 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FV2108-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T12:20:57.5430000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T17:55:03.0000000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-01T20:07:45.8070000
T-00192-0643 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2242-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0644 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LL2102-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:21:57.7370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T04:19:56.7700000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:22:27.8670000
T-00192-0645 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3461-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0646 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3552-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0647 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1241-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0649 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334FS2106-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-24T02:55:04.2500000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-23T18:05:52.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-23T20:20:36.3200000
T-00192-0650 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3441-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0652 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1371-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0653 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2222-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0655 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1262-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0656 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1441-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0657 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1252-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0658 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1551-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0659 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3542-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0661 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3531-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0662 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3451-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0663 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3471-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0664 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1352-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0665 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1542-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0666 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3481-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0667 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3561-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0668 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2241-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0669 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3562-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0670 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3361-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0671 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338GE4001-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-06 - Switch room General | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK
T-00192-0672 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1451-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0673 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3582-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0674 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2352-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0675 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3272-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0676 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3532-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0678 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1372-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0679 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3261-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0680 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2331-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0681 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3581-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0682 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1261-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0683 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1251-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0684 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1271-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0685 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3482-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0686 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1342-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0687 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3271-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0688 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PS2148-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:23:04.3530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T04:25:49.6070000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-01-03T05:23:14.0030000
T-00192-0689 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3362-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0690 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT2109-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T12:23:29.6030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T18:03:41.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-01T20:08:06.9000000
T-00192-0691 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1242-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0692 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS351-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | KS1-25*B
T-00192-0694 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LIT2121-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-01-15T12:23:54.3000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-01T17:59:41.0000000 | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-01-01T20:08:26.3470000
T-00192-0695 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331LT2103-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:25:07.2600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-04T22:53:38.9200000 | 2PR,I/OAS,0.5mm2,PVC/PVC,BLK | 2021-01-05T00:44:16.0270000
T-00192-0696 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS2221-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0697 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS3262-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M025
T-00192-0698 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3338DCS1341-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | AKB337-M035
T-00192-0699 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4040-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK
T-00192-0700 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4010-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-22T11:49:16.1470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T01:11:14.2170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-02-22T04:00:23.5870000
T-00192-0702 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PU4096-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T12:25:30.4370000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-09T20:26:57.4270000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-09T21:50:08.1930000
T-00192-0703 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AG4102-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T03:28:32.8970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-31T20:34:54.9700000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-31T23:41:24.1700000
T-00192-0704 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FN4002-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-22T23:34:44.1530000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T22:51:34.3200000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-19T04:01:10.3170000
T-00192-0705 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4035-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0706 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4138-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-06T23:50:01.6900000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:51:23.5200000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-06T07:41:40.9330000
T-00192-0707 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4050-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0708 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4012-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:27:21.6770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T05:21:07.7070000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-03-28T06:17:36.1770000
T-00192-0709 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4117-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:29:33.6570000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T03:50:43.2930000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-18T22:29:52.5970000
T-00192-0710 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4026-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:47:10.9400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T23:08:19.2700000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-17T04:10:30.9270000
T-00192-0711 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4013-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-28T16:27:44.2270000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-28T06:03:57.3700000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-03-28T06:18:04.4130000
T-00192-0712 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AG4002-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T12:26:17.6930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-03T01:25:23.3870000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:23:34.9030000
T-00192-0713 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4088-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:08:36.2130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T03:46:40.5930000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-10T07:00:40.2500000
T-00192-0714 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4118-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:30:22.7670000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-18T03:53:35.1630000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-18T22:30:11.8170000
T-00192-0715 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PU4095-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-01-15T12:26:42.4470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-09T20:10:31.6100000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-09T21:50:40.1970000
T-00192-0716 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333DY4001-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0717 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FD4002-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0718 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4120-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-27T08:46:59.8300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-26T05:50:04.7730000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-26T06:48:29.3900000
T-00192-0719 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335PU4097-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Closed | 2021-02-20T23:56:09.2000000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-20T19:50:37.8570000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-02-20T20:46:35.8300000
T-00192-0720 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4152-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0721 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4103-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0722 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4022-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-15T21:46:09.9970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-15T02:10:06.4170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-15T03:46:41.9430000
T-00192-0723 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4136-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-06T23:49:30.3130000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:44:16.8570000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-06T07:42:42.6330000
T-00192-0724 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4083-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:08:59.5770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T03:59:00.7930000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-10T07:01:05.1030000
T-00192-0725 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4111-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-23T00:30:51.0830000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-16T05:19:31.9470000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-16T06:20:57.5630000
T-00192-0726 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331AG4001-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-15T12:27:42.9670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-03T01:26:31.5970000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-03T05:23:59.0200000
T-00192-0727 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4014-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-01T03:29:01.3800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-01-30T20:41:35.0300000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-31T02:49:08.8300000
T-00192-0728 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4086-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:09:20.7130000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T03:41:18.1230000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-10T07:03:42.7730000
T-00192-0729 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AG4105-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:13:33.8300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:39:30.8170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-29T20:47:32.6130000
T-00192-0730 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4030-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-21T03:26:38.3770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-21T01:27:38.6130000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-21T01:49:01.5730000
T-00192-0731 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AG4103-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:14:03.7100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:32:02.4170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-29T20:54:50.9900000
T-00192-0732 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4141-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0733 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FD4001-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0734 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4112-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Closed | 2021-04-15T21:47:53.4600000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-15T07:29:58.7170000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-15T07:45:47.5930000
T-00192-0735 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4084-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:09:45.5600000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T03:36:13.3670000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-10T07:05:17.6500000
T-00192-0736 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4003-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:28:11.6530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-10T05:22:18.1800000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-11T03:53:57.5070000
T-00192-0737 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4158-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T19:56:24.4470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-08T06:48:07.3770000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-08T07:04:43.8630000
T-00192-0738 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332FN4001-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Submitted |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-04-15T07:18:49.9970000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0739 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4004-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-01-15T12:28:34.1130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-01-10T05:14:26.3370000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-11T03:54:39.8170000
T-00192-0740 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4135-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Closed | 2021-04-06T23:49:01.6470000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-06T06:29:54.8770000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-04-06T07:42:59.2730000
T-00192-0741 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334PU4082-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:10:06.6170000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T03:52:45.9230000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-10T07:05:40.6500000
T-00192-0742 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4034-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:22:16.4700000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-03-29T20:10:29.9430000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-03-30T06:11:04.7570000
T-00192-0743 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AG4104-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:14:30.5100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:35:49.6830000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-29T20:55:41.4700000
T-00192-0744 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4102-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0745 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4114-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0746 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4001-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-01-29T21:14:54.8630000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-01-28T02:27:08.2470000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-28T05:38:48.9570000
T-00192-0747 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4153-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0749 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4110-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-01T06:16:11.7230000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-28T02:15:18.7470000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-02-28T06:08:25.1300000
T-00192-0750 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4121-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-01T03:29:28.2430000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-30T20:06:57.9830000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-31T02:50:52.3830000
T-00192-0751 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332AG4101-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-01-29T21:15:18.3200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-01-29T05:21:37.6830000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-01-29T20:57:52.0270000
T-00192-0752 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PU4140-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0753 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4115-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0754 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4009-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-03-19T10:46:44.0370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-19T05:25:44.3100000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-03-19T05:48:34.6370000
T-00192-0755 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4032-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-03-30T13:23:48.5000000 | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 | 2021-03-30T04:09:19.8200000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-30T06:09:38.9830000
T-00192-0756 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332PU4028-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T02:06:55.2970000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-23T06:11:15.1470000 | 2PR,I/OAS,1.5mm2,PVC/PVC,BLK | 2021-04-23T06:59:31.4000000
T-00192-0757 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3334LS2104-J1 | ICBL - Instrument Cable |  |  | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  | Pr1/
T-00192-0758 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3331PU4158-T2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-08T19:56:48.5900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-08T06:52:36.4130000 | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-03-08T07:05:08.1400000
T-00192-0759 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0185AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:46:34.0730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:48:24.6500000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:33:02.5600000
T-00192-0760 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0190BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:47:15.6100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T07:05:18.9270000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:43:38.8500000
T-00192-0761 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0164BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:03:07.3200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T01:16:55.1430000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:40:15.9070000
T-00192-0762 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0169BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:03:45.2100000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T00:37:55.9100000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:40:50.8770000
T-00192-0763 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0160AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:04:20.8170000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T02:41:00.6430000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:46:49.3030000
T-00192-0764 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0160BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:04:58.2730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T02:49:44.1670000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:51:13.8100000
T-00192-0765 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0164AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:05:25.8070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T00:46:10.8030000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:41:20.9530000
T-00192-0766 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0169AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:06:06.0730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T00:28:31.6430000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:47:44.1400000
T-00192-0767 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0164AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-18T22:44:58.1930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-18T01:29:57.0070000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-18T01:45:18.1870000
T-00192-0768 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0194BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:47:47.6200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:35:21.7870000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:33:54.7870000
T-00192-0769 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0190BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:48:23.6600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T07:09:14.4430000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:35:25.9370000
T-00192-0770 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0194AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:49:14.7200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:25:45.8400000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:39:13.0900000
T-00192-0771 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0164BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:06:36.2670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T02:34:22.5970000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:49:07.1570000
T-00192-0772 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0169BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:07:08.7070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T00:21:09.8370000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:49:30.0570000
T-00192-0773 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0138AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:07:39.2700000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:32:11.3330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:11:09.5370000
T-00192-0774 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0160BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:08:11.3400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T03:40:56.8700000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:12:00.5530000
T-00192-0775 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0169AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:08:38.7400000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T00:03:29.4400000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T02:50:27.7570000
T-00192-0776 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0190AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:49:46.3200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:58:01.1770000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:39:58.7070000
T-00192-0777 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0141AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:09:10.7070000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:00:51.0400000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:12:51.7270000
T-00192-0778 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0160AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:09:43.7370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T02:56:01.9230000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T03:16:43.3500000
T-00192-0779 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0138BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:10:41.3730000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:50:16.9270000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:13:16.9800000
T-00192-0780 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0138BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:11:14.9670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T05:02:21.6300000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:15:19.6000000
T-00192-0781 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0194BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:50:20.7670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:30:17.7730000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:41:48.0400000
T-00192-0782 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0141AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:11:55.1300000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T03:52:31.1830000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:16:14.4130000
T-00192-0783 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0185AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:50:48.9200000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:45:39.3270000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:42:13.7800000
T-00192-0784 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0185BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:51:15.2930000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:54:27.6670000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:44:06.0830000
T-00192-0785 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0185BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:51:41.4770000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T06:51:00.0530000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:44:54.9500000
T-00192-0786 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0190AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:52:08.6670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T07:02:03.6530000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:45:17.2270000
T-00192-0787 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0141BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:12:28.8370000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:12:03.3330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:16:47.8600000
T-00192-0788 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0141BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:14:12.8600000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:18:43.5500000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:18:02.6170000
T-00192-0789 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0138AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Closed | 2021-02-17T22:17:37.5530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-17T04:42:11.5430000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-17T19:21:04.8870000
T-00192-0790 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0194AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:52:37.9870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:18:29.9070000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:45:41.1600000
T-00192-0791 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0200BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:53:03.3670000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:50:12.4170000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:46:02.1200000
T-00192-0792 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0320BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T13:47:47.6030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:49:36.7970000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:04:06.6370000
T-00192-0793 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0499AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:53:09.7730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:23:41.2370000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:25:23.1070000
T-00192-0794 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0310BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:06:27.1130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:43:13.8400000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:18:48.6200000
T-00192-0795 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0304BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:07:08.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:13:33.1770000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:19:22.5130000
T-00192-0796 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0315AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:07:50.0730000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:57:37.5030000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:06:57.9630000
T-00192-0797 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0200AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:53:27.2900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:45:37.2530000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:46:26.3200000
T-00192-0798 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0315AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:29:07.8970000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:53:47.1900000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:04:35.9730000
T-00192-0799 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0499AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:53:41.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:18:43.6270000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:25:45.8300000
T-00192-0800 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0494AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:54:06.3570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:50:06.7570000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:05:02.1430000
T-00192-0801 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0499BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-23T02:54:52.8170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:30:11.0330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:48:17.6270000
T-00192-0802 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0304AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:29:47.2000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:59:43.6330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:19:50.1430000
T-00192-0803 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0499BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:54:34.6600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:00:05.7470000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:23:59.3700000
T-00192-0804 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0494BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:55:06.1000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:25:14.0330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:24:26.6970000
T-00192-0805 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0494BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:55:31.0100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:12:33.6700000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:24:51.7770000
T-00192-0806 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0200BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:53:59.1830000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:55:19.7300000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:47:19.4230000
T-00192-0807 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0310AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:30:16.9530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:18:03.3330000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:20:17.0100000
T-00192-0808 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0315BB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:30:48.5830000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:09:06.6070000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:20:50.6900000
T-00192-0809 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0310BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:31:17.9500000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:37:44.1130000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:21:30.5970000
T-00192-0810 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0494AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Closed | 2021-02-22T16:55:58.5300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:05:40.0670000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:07:26.5570000
T-00192-0811 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0320AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T14:31:42.2570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:40:32.3470000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:05:27.4500000
T-00192-0812 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0304BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:00:50.8870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:09:05.2600000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:22:08.6370000
T-00192-0813 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0320BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:17:29.4770000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T03:44:04.7000000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:05:51.5570000
T-00192-0814 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0315BA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:18:02.4900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:02:45.8570000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:07:48.7170000
T-00192-0815 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0320AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:18:40.5630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T02:55:21.1530000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T04:06:26.2730000
T-00192-0816 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0310AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:19:07.1870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T04:14:15.9200000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:23:10.5000000
T-00192-0817 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0304AB-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Closed | 2021-02-22T15:19:33.7400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-02-22T05:04:09.7870000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T05:23:33.1270000
T-00192-0818 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332XY0200AA-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Closed | 2021-02-23T02:54:30.0900000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-02-22T20:41:04.8100000 | 1PR,OAS,0.5mm²,PVC/PVC | 2021-02-22T23:47:53.6200000
T-00192-0819 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3335MB4091-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-24T03:25:15.8870000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-22T04:44:34.8770000 | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC | 2021-04-22T04:53:55.7370000
T-00192-0820 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | LT-101-MGW-W14 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:27:14.2530000 |  |  | 0.25 | 2021-04-17T03:06:08.4270000 | VENDOR CABLE | 2021-04-17T04:01:03.0500000
T-00192-0821 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | TE-101-MGA-W15 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:28:00.2670000 |  |  | 0.25 | 2021-04-17T04:55:41.3730000 | VENDOR CABLE | 2021-04-17T04:59:31.4730000
T-00192-0822 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | TE-101-MGG-W13 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-20T01:28:43.9670000 |  |  | 0.25 | 2021-04-17T03:24:14.2270000 | VENDOR CABLE | 2021-04-17T04:01:26.5670000
T-00192-0823 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | TE-103-MGA-W16 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Completed |  |  |  | 0.25 | 2021-04-26T07:34:38.7570000 | VENDOR CABLE | 2021-04-27T06:58:35.3030000
T-00192-0824 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332-ME-4012-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:46:50.0670000 |  |  | 0.25 | 2021-04-13T07:21:52.9570000 |  | 2021-04-13T07:40:16.2100000
T-00192-0825 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332-ME-4013-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:46:31.8730000 |  |  | 0.25 | 2021-04-13T07:23:38.0670000 |  | 2021-04-13T07:40:41.1200000
T-00192-0826 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332-ME-4014-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T07:47:29.2670000 |  |  | 0.25 | 2021-04-13T07:25:03.0770000 |  | 2021-04-13T07:41:01.8670000
T-00192-0827 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332-ME-4015-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T23:44:31.3300000 |  |  | 0.25 | 2021-04-13T07:26:22.3030000 |  | 2021-04-13T23:03:36.0530000
T-00192-0828 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332-ME-4016-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-13T23:44:58.7730000 |  |  | 0.25 | 2021-04-13T07:27:57.0800000 |  | 2021-04-13T23:04:09.2300000
T-00192-0830 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-SE-2107-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0831 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2180-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0832 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | JB01-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 6C+E,0.75mm²,PVC/PVC
T-00192-0833 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2111-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0834 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-LT-2102-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0835 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2194-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0836 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2199A | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0837 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | ALMB01-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 6C+E,0.5mm²,PVC/PVC
T-00192-0838 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2196-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0839 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-MB-4072-LT-C1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 1Pr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr
T-00192-0840 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2175-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0841 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | JB03-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 11C+E,0.75mm²,PVC/PVC
T-00192-0842 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2198-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0843 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2174-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0844 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-MB-4072-CNTR-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 14C+E,0.75mm²,PVC/PVC
T-00192-0845 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2179-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0846 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2178-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0847 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-LC-2192-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 12C 0.34mm2 Cu PVC/PVC
T-00192-0848 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2173-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0849 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2195-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0850 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2199B-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0851 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2158-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0852 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XS-2191-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 8C 0.34mm2 Cu PVC/PVC
T-00192-0853 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-SE-2106-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0854 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-XY-2197-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 2C+E,0.75mm²,PVC/PVC
T-00192-0855 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2176-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0856 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2185-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 3C 0.25mm2 Cu PVC/PVC
T-00192-0857 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TE2207-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1TR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0858 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PIT2214-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0859 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333MT2230-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0861 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TT2237-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0862 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LIT0661-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.25 |  | VENDOR CABLE WLT1119
T-00192-0863 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TE2208-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1TR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0864 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TT2232-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0865 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333LIT0671-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.25 |  | VENDOR CABLE WLT1103
T-00192-0866 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FIT2209-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0867 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TIT2211-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0868 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TIT2208-J | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0869 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333OP4210-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0870 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333OP4210-J3 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0871 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TIT2215-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0872 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333HS0705-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.25 |  | VENDOR CABLE WHZ0705
T-00192-0873 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333FE2209-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | VENDOR CABLE
T-00192-0874 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TE2216-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1TR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0875 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333PIT2205-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0876 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TE2215-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1TR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0877 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333OP4210-J2 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 4PR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0878 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TE2211-T1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1TR,I/OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0879 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TIT2216-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0880 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333TIT2207-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.25 |  | 1PR,OAS,1.5mm²,PVC/PVC/SWA/PVC
T-00192-0881 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3333-PE-2193-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 4C 0.34mm2 Cu PVC/PVC
T-00192-0882 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LT2236-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.25
T-00192-0883 | I1.T004 LV Cable (Instrument) Stage 1 | CABL | 3332LT2336-J1 | ICBL - Instrument Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.25
T-00193-0002 | E1.Txxx LV Cable (Triad) Stage 1 | CABL | 3331MB4010-J2 | TCBL - Triad Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-04-24T22:45:46.8670000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-04-24T01:20:50.2300000 | 3TR,OAS,1.5mm2,PVC/SWA/PVC,BLK | 2021-04-24T07:26:18.1030000
T-00193-0003 | E1.Txxx LV Cable (Triad) Stage 1 | CABL | 3331MB4012-J2 | TCBL - Triad Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-15T12:30:02.4500000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-09T05:10:36.0000000 | 6TR,OAS,1.5mm2,PVC/SWA/PVC,BLK | 2021-01-09T06:59:14.8330000
T-00193-0004 | E1.Txxx LV Cable (Triad) Stage 1 | CABL | 3331MB4012-J1 | TCBL - Triad Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Closed | 2021-01-15T12:30:24.4430000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-01-09T05:27:33.9130000 | 6TR,OAS,1.5mm2,PVC/SWA/PVC,BLK | 2021-01-09T06:59:39.1730000
T-00193-0005 | E1.Txxx LV Cable (Triad) Stage 1 | CABL | 3331PU4007-T1 | TCBL - Triad Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-16T22:56:55.9830000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-16T06:53:08.2270000 | 6Tr 0.5mm2 Cu PVC/SCR/PVC - Overall Scr | 2021-02-16T07:01:59.8070000
T-00194-0001 | HV Transformer Stage 1 | ELEC | 3338-TF-4002 | TF - TRANSFORMER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T14:18:48.8800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T07:57:53.8030000 |  | 2020-12-17T10:04:45.4830000
T-00194-0002 | HV Transformer Stage 1 | ELEC | 3338-TF-4001 | TF - TRANSFORMER | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T15:45:02.4300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T08:00:16.5300000 |  | 2020-12-17T10:05:03.6330000
T-00195-0001 | Trenching & UG Conduit Stage 1 | CABL | Route No 1 | UGC - Underground Conduit | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS00-01 - NTSF dam wall | CS00 - Tie-in (System) | Closed | 2020-11-17T22:54:25.0000000 |  |  | 0.25 |  | Type: HPD / Quantity Power: 3 ¦ Quantity Control/Fiber: 2 | 2020-11-16T22:41:40.0000000
T-00195-0002 | Trenching & UG Conduit Stage 1 | CABL | Route No 2 | UGC - Underground Conduit | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS00-01 - NTSF dam wall | CS00 - Tie-in (System) | Closed | 2020-11-17T22:06:36.0000000 |  |  | 0.25 |  | Type: HPD / Quantity Power: 2 ¦ Quantity Control/Fiber: 1 | 2020-11-16T22:41:58.0000000
T-00195-0003 | Trenching & UG Conduit Stage 1 | CABL | Route No 3 | UGC - Underground Conduit | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS00-01 - NTSF dam wall | CS00 - Tie-in (System) | Closed | 2020-11-17T22:54:50.0000000 |  |  | 0.25 |  | Type: HPD / Quantity Power: 2 ¦ Quantity Control/Fiber: 1 | 2020-11-16T22:42:39.0000000
T-00195-0004 | Trenching & UG Conduit Stage 1 | CABL | Route No 4 | UGC - Underground Conduit | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS00-01 - NTSF dam wall | CS00 - Tie-in (System) | Closed | 2020-11-17T22:55:05.0000000 |  |  | 0.25 |  | Type: HPD / Quantity Power: 2 ¦ Quantity Control/Fiber: 1 | 2020-11-16T22:43:20.0000000
T-00197-0002 | HV Cable Stage 1 | CABL | 3338TF4002-P1 | HVCBL - High Voltage Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T15:46:32.2930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-16T01:26:56.9030000 | 3C, 120 mm2, XLPE/SCR/SWA/PVC, 19/33kV | 2020-12-17T10:05:21.3070000
T-00197-0003 | HV Cable Stage 1 | CABL | 3338TF4001-P1 | HVCBL - High Voltage Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-17T15:47:19.1530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-15T06:52:22.1830000 | 3C, 120 mm2, XLPE/SCR/SWA/PVC, 19/33kV | 2020-12-17T10:06:05.4700000
T-00197-0004 | HV Cable Stage 1 | CABL | 3338RU4001-P1 | HVCBL - High Voltage Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-21T03:00:58.5130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T23:16:48.8500000 | 3C, 120 mm2, XLPE/SCR/SWA/PVC, 19/33kV | 2020-12-19T03:56:54.4530000
T-00199-0001 | Fibre & Comms Stage 1 | CABL | FIBRE-4001 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS29-02 - Permanent Building | CS29 - Bio sewage Treatment | Closed | 2020-12-18T07:16:33.1670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-17T22:08:14.7370000 | 24C Fibre Optic single Mode | 2020-12-18T00:31:51.5570000
T-00199-0003 | Fibre & Comms Stage 1 | CABL | FIBRE-4000 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2020-12-18T07:18:48.3570000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2020-12-17T22:00:31.1370000 | 24C Fibre Optic single Mode | 2020-12-18T04:09:40.6230000
T-00199-0008 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16251C-05 / FO03-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0009 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1661-KVM / KVMSW-03 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0010 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16252C-27 / FO02-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0011 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1601CPU-R BUS2 / SWT16252B-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0012 | E1.Txxx Fibre & Comms Stage 1 | CABL | TSECLIENT2 / SWT16250C-15 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0013 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1661B / SWT16252B-11 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0014 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1650A / SWT16252A-09 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0015 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1649B / SWT16252B-08 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0016 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1649C / SWT16252C-08 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0017 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1603CPU-R BUS1 / SWT16252A-06 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0018 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1664-KVM / KVMSW-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0019 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16252C-28 / FO02-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0020 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1603CPU-L BUS2 / SWT16252B-05 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0021 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1661C / SWT16252C-11 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0022 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1602CPU-L BUS1 / SWT16252A-03 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0023 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1660B / SWT16252B-10 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0024 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1603CPU-R BUS2 / SWT16252B-06 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0025 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1650-KVM / KVMSW-05 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0026 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1650C / SWT16252C-09 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0027 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1660-KVM / KVMSW-04 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0028 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1648-KVM / KVMSW-07 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0029 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1664A / SWT16252A-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0030 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16252A-28 / FO01-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0031 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1602CPU-R BUS2 / SWT16252B-04 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0032 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1660C / SWT16252C-10 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0033 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1661A / SWT16252A-11 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0034 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1662-KVM / KVMSW-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0035 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1601CPU-L BUS1 / SWT16252A-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0036 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1649-KVM / KVMSW-06 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLACK
T-00199-0037 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1649A / SWT16252A-08 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0038 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1650B / SWT16252B-09 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0039 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1662A / SWT16252A-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0040 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1602CPU-L BUS2 / SWT16252B-03 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0041 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1603CPU-L BUS1 / SWT16252A-05 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0042 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1664C / SWT16252C-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0043 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1660A / SWT16252A-10 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0044 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1648C / SWT16252C-07 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0045 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1648A / SWT16252A-07 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0046 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16252C-26 / FO02-03 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0047 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1662B / SWT16252B-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0048 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1601CPU-L BUS2 / SWT16252B-01 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0049 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1601CPU-R BUS1 / SWT16252A-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0050 | E1.Txxx Fibre & Comms Stage 1 | CABL | TSECLIENT1 / SWT16251C-14 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0051 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16252B-28 / FO01-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0052 | E1.Txxx Fibre & Comms Stage 1 | CABL | SWT16250C-05 / FO04-02 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | SM FO
T-00199-0053 | E1.Txxx Fibre & Comms Stage 1 | CABL | FCS1602CPU-R BUS1 / SWT16252A-04 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/RED
T-00199-0054 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1664B / SWT16252B-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0055 | E1.Txxx Fibre & Comms Stage 1 | CABL | STN1648B / SWT16252B-07 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/YELLOW
T-00199-0056 | E1.Txxx Fibre & Comms Stage 1 | CABL | HIS1662C / SWT16252C-12 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | CAT 6/BLUE
T-00199-0057 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3334OP4201-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-10T20:11:07.0030000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-10T19:59:24.9570000 | Cat 6/LAN | 2021-03-10T20:02:48.6730000
T-00199-0060 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338OP4001-C13 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2021-02-21T01:49:36.4170000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-02-21T00:48:56.4570000 | RS485, 1 Pr | 2021-02-21T00:56:38.2000000
T-00199-0061 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3334CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0062 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00199-0064 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3333OP4202-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0065 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0066 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331OP4201-J2 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:48:40.1130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:26:25.7300000 | Cat 6/LAN | 2021-02-20T22:35:54.6670000
T-00199-0067 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0068 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OP4234-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-20T07:42:52.1600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T03:56:22.1570000 | Cat 6/LAN | 2021-04-17T04:10:50.3670000
T-00199-0069 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OP4221-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0070 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0071 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00199-0072 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0073 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OC4001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0074 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338CA0004-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00199-0075 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3334CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0076 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3333OP4203-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0077 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0002-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0078 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3333OP4201-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0079 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OP4233-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T07:43:20.1530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T03:55:02.2630000 | Cat 6/LAN | 2021-04-17T04:11:10.3100000
T-00199-0081 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0004-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0082 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0005-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0083 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0084 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3333CA0001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0085 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN/Underground
T-00199-0086 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331OP4201-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T23:48:00.8000000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T22:23:43.5370000 | Cat 6/LAN | 2021-02-20T22:36:17.0970000
T-00199-0087 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332CA0006-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0088 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3334CA0003-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0090 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3331OP4205-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T07:43:44.1930000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:35:38.5500000 | Cat 6/LAN | 2021-04-16T07:39:31.6730000
T-00199-0091 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OP4235-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-20T07:47:34.9870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:37:20.5000000 | Cat 6/LAN | 2021-04-16T07:39:51.4400000
T-00199-0092 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338XE4001-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-19T10:47:50.5770000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-18T22:32:01.1230000 | Cat 6/LAN | 2021-03-19T04:30:31.3830000
T-00199-0093 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338XE4008-J1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Closed | 2021-03-19T10:48:12.4470000 | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 | 2021-03-18T22:34:58.1600000 | Cat 6/LAN | 2021-03-19T04:30:58.2230000
T-00199-0094 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3338XE4013-j1 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25 |  | Cat 6/LAN
T-00199-0095 | E1.Txxx Fibre & Comms Stage 1 | CABL | 3332OP4230-J2 | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Started |  |  |  | 0.25 |  | Single Mode Optic Fibre
T-00199-0096 | E1.Txxx Fibre & Comms Stage 1 | CABL | 23PLC08-ETH | Fibre - Fibre & Comm Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.25 |  | 4C 0.2mm2 Cu PVC/PVC
T-00200-0001 | E1.T051 Switchroom Inspection Stage 1 | ELEC | 3338-SS-4001 | SS - Substation | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-23T00:11:44.7100000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 1 | 2020-12-22T02:23:58.8870000 |  | 2020-12-22T02:41:52.6330000
T-00201-0001 | E.T005 Cable Conduit Stage 1 | CABL | 3338TF4002-P1 | HVCBL - High Voltage Cable | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Closed | 2020-12-18T07:34:28.7370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2020-12-18T04:28:43.1670000 | 3C, 120 mm2, XLPE/SCR/SWA/PVC, 19/33kV | 2020-12-18T07:11:57.8270000
T-00203-0001 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4015 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0002 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4028 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:29:47.8630000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-24T23:15:40.7800000 |  | 2021-04-24T23:19:27.6300000
T-00203-0003 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4005 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00203-0004 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4035 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00203-0005 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4008 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00203-0006 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3331-VS-4003 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-25T05:28:25.5370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-20T05:22:59.3930000 |  | 2021-04-25T02:52:42.9630000
T-00203-0007 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4012 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0008 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4021 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0009 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4017 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0010 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4032 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0011 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4010 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0012 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4007 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00203-0013 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3331-VS-4041 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5
T-00203-0014 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4040 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0015 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3331-VS-4004 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T05:49:47.7500000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.5 | 2021-03-23T22:50:33.4270000 |  | 2021-03-24T18:35:14.1330000
T-00203-0016 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4037 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0017 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4024 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0018 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4023 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0019 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4029 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T02:11:31.8800000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-23T21:01:41.5400000 |  | 2021-04-23T23:03:49.1500000
T-00203-0020 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4026 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:30:10.1070000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-24T22:11:03.8300000 |  | 2021-04-24T23:05:04.5800000
T-00203-0021 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4033 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0022 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4030 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T03:26:57.8700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-23T21:13:53.1800000 |  | 2021-04-23T22:58:05.0770000
T-00203-0023 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4022 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0024 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4018 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0025 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4019 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0026 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3331-VS-4001 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-20T07:48:07.8430000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-13T05:20:27.5200000 |  | 2021-04-18T03:30:49.1400000
T-00203-0027 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4038 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0028 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4013 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0029 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4025 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0030 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4014 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0031 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3334-VS-4027 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:30:34.7700000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.5 | 2021-04-24T22:16:25.2230000 |  | 2021-04-24T23:03:24.2530000
T-00203-0032 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4036 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0033 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4031 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0034 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4034 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.5
T-00203-0035 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3331-VS-4002 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-25T05:28:50.0170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.5 | 2021-04-20T05:20:16.1400000 |  | 2021-04-25T02:52:09.4770000
T-00203-0036 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4016 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0037 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4009 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00203-0038 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3333-VS-4020 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.5
T-00203-0039 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4006 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00203-0040 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4039 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.5
T-00203-0041 | E2.T049 Variable Speed Drive Settings Stage 2 | ELEC | 3332-VS-4011 | VS - VSD |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.5
T-00205-0001 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4112 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0002 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4102 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0003 | M3.T004 Agitator Stage 3 | MECH | 3331-AG-4002 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00205-0004 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4110 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0005 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4105 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0006 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4111 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0007 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4117 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0008 | M3.T004 Agitator Stage 3 | MECH | 3333-AG-4006 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00205-0009 | M3.T004 Agitator Stage 3 | MECH | 3334-AG-4012 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00205-0010 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4107 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0011 | M3.T004 Agitator Stage 3 | MECH | 3331-AG-4001 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00205-0012 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4004 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0013 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4109 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0014 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4103 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0015 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4104 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0016 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4101 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0017 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4005 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00205-0018 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4118 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0019 | M3.T004 Agitator Stage 3 | MECH | 3334-AG-4013 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00205-0020 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4114 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0021 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4113 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00205-0022 | M3.T004 Agitator Stage 3 | MECH | 3332-AG-4108 | AG - AGITATOR | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00206-0001 | M3.T005 Air Blower Stage 3 | MECH | 3334-BL-4001 | BL - BLOWER | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00207-0001 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4155 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T20:01:45.8530000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-19T06:59:19.3770000 |  | 2021-02-19T06:59:34.3270000
T-00207-0002 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4014 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Closed | 2021-04-05T21:42:22.2870000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T00:17:40.5000000 |  | 2021-04-05T06:57:25.9170000
T-00207-0003 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4090 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-20T04:03:08.6030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T03:50:51.9230000 |  | 2021-02-20T03:50:57.9970000
T-00207-0004 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4086 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:37:21.7900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-07T18:32:56.0770000 |  | 2021-03-07T18:33:02.2370000
T-00207-0005 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4032 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0006 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4159 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0007 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4044 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0009 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4121 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T18:14:04.9470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T17:48:53.5570000 |  | 2021-03-08T17:49:01.5000000
T-00207-0010 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4071 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0011 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4035 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0012 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4084 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:38:26.6470000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-07T18:33:19.0130000 |  | 2021-03-07T18:33:24.9800000
T-00207-0013 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4026 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:46:29.5900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T07:37:57.9400000 |  | 2021-04-21T07:38:04.5970000
T-00207-0014 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4010 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Closed | 2021-03-08T15:05:28.3630000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-08T14:10:11.2530000 |  | 2021-03-08T14:10:21.6100000
T-00207-0015 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4117 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0016 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4123 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0017 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4082 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:38:40.9670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-07T18:33:43.3330000 |  | 2021-03-07T18:33:49.5500000
T-00207-0018 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4091 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-20T04:02:30.8770000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T03:51:51.1670000 |  | 2021-02-20T03:51:57.8630000
T-00207-0019 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4030 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-12T22:55:35.2870000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-12T22:47:23.0400000 |  | 2021-03-12T22:47:28.8170000
T-00207-0020 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4005 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T04:01:07.0930000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-20T03:46:33.3970000 |  | 2021-02-20T03:46:40.7200000
T-00207-0021 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4096 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T20:02:52.1000000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-19T06:57:06.2670000 |  | 2021-02-19T06:57:13.2300000
T-00207-0022 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4110 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-17T20:59:37.7500000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-17T07:08:35.6300000 |  | 2021-04-17T07:08:42.4130000
T-00207-0023 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4070 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0024 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4106 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0025 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4153 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0026 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4076 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0027 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4127 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0028 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4122 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0029 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4112 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0030 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4130 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0031 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4126 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0032 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4060 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0033 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4120 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-03-09T16:06:43.9470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-03-09T15:01:30.4270000 |  | 2021-03-09T16:04:29.3270000
T-00207-0034 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4007 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-11T19:26:46.6130000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-11T04:10:15.2630000 |  | 2021-03-11T04:10:26.7570000
T-00207-0035 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4152 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0036 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4136 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0038 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4052 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0039 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4157 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0040 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4081 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0041 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4124 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0042 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4061 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0043 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4004 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-26T08:58:12.8970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-23T01:37:59.2430000 |  | 2021-02-23T01:38:11.8430000
T-00207-0044 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4024 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:47:51.5170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T04:57:00.1470000 |  | 2021-04-21T04:57:08.2800000
T-00207-0045 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4111 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0046 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4080 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0047 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4079 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0048 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4105 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0049 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4075 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0050 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4003 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-02-26T08:59:14.0900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-23T01:43:36.1930000 |  | 2021-02-23T01:43:44.3730000
T-00207-0051 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4041 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0052 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4051 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0053 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4160 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0054 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4129 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0055 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4083 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:38:56.1670000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-07T18:34:18.0930000 |  | 2021-03-07T18:34:23.8870000
T-00207-0056 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4099 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00207-0057 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4131 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0058 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4097 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00207-0059 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4128 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0060 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4115 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0061 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4135 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0062 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4158 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Closed | 2021-03-09T16:20:30.9400000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-09T16:15:34.5870000 |  | 2021-03-09T16:15:41.8600000
T-00207-0063 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4141 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0064 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4078 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0065 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4057 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00207-0066 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4050 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0068 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4154 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-04T21:46:27.2600000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-21T05:53:26.1670000 |  | 2021-02-21T05:53:33.6600000
T-00207-0069 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4103 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0070 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4088 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-03-07T18:39:14.7900000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-03-07T18:34:44.0130000 |  | 2021-03-07T18:34:49.5730000
T-00207-0071 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4043 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0072 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4125 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0073 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4053 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0074 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4095 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-02-19T20:03:45.9400000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-19T06:56:37.4230000 |  | 2021-02-19T06:56:45.4970000
T-00207-0075 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4077 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0076 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4072 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0077 | M1.T059 Pump Set Stage 1 | MECH | 3331-PU-4001 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-02-20T04:01:49.6770000 | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25 | 2021-02-20T03:45:17.0630000 |  | 2021-02-20T03:45:25.8730000
T-00207-0078 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4114 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0079 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4025 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-21T11:48:16.5030000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-21T07:34:10.5700000 |  | 2021-04-21T07:34:21.4800000
T-00207-0080 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4102 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0081 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4098 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00207-0082 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4022 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-18T03:32:29.2170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-18T03:18:32.8670000 |  | 2021-04-18T03:18:42.7170000
T-00207-0083 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4118 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0084 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-4138 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0085 | M1.T059 Pump Set Stage 1 | MECH | 3335-PU-4093 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-12T01:48:59.4500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-02-12T01:41:24.5230000 |  | 2021-02-12T01:42:34.9970000
T-00207-0086 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4140 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0087 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4156 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0088 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4059 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Past Due |  | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25
T-00207-0092 | M1.T059 Pump Set Stage 1 | MECH | 3334-PU-4119 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0095 | M1.T059 Pump Set Stage 1 | MECH | 3333-PU-4151 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Started |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00207-0098 | M1.T059 Pump Set Stage 1 | MECH | 3332-PU-1061 | PU - PUMP | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.25
T-00208-0001 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4155 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0002 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4014 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Started |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00208-0003 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4090 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0004 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4086 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0005 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4032 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0006 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4159 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0007 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4044 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0009 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4121 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00208-0010 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4071 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0011 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4035 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0012 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4084 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0013 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4026 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00208-0014 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4010 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00208-0015 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4117 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0016 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4123 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0017 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4082 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0018 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4091 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0019 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4030 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00208-0020 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4005 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0021 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4096 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0022 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4110 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00208-0023 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4070 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0024 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4106 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0025 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4153 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0026 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4076 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0027 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4127 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0028 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4122 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0029 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4112 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0030 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4130 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0031 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4126 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0032 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4060 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0033 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4120 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00208-0034 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4007 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0035 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4152 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0036 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4136 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0037 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4092 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0038 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4052 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0039 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4157 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0040 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4081 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0041 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4124 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0042 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4061 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0043 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4004 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0044 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4024 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00208-0045 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4111 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0046 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4080 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0047 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4079 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0048 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4105 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0049 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4075 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0050 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4003 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0051 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4041 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0052 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4051 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0053 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4160 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0054 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4129 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0055 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4083 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0056 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4099 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0057 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4131 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0058 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4097 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0059 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4128 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0060 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4115 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0061 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4135 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0062 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4158 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0063 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4141 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0064 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4078 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0065 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4057 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0066 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4050 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0067 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4094 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0068 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4154 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00208-0069 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4103 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0070 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4088 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0071 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4043 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0072 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4125 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0073 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4053 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0074 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4095 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0075 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4077 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0076 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4072 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0077 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4001 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00208-0078 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4114 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0079 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4025 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00208-0080 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4102 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0081 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4098 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0082 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4022 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00208-0083 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4118 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0084 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-4138 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0085 | M3.T059 Pump Set Stage 3 | MECH | 3335-PU-4093 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0086 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4140 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0087 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4156 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0088 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4059 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00208-0089 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4146 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0090 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4143 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0091 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4144 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0092 | M3.T059 Pump Set Stage 3 | MECH | 3334-PU-4119 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0093 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4148 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0094 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4145 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0095 | M3.T059 Pump Set Stage 3 | MECH | 3333-PU-4151 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00208-0097 | M3.T059 Pump Set Stage 3 | MECH | 3331-PU-4147 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00208-0098 | M3.T059 Pump Set Stage 3 | MECH | 3332-PU-1061 | PU - PUMP | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  |  |  | 0.25
T-00210-0099 | E2.T043A LV Motor Stage 2A | ELEC | 3332-FN-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0100 | E2.T043A LV Motor Stage 2A | ELEC | 3334-AG-4012-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0101 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4084-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00210-0102 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4114-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0103 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4141-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0104 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4005-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0105 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4140-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0106 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4007-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0107 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4104-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0108 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4026-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0109 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4044-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0110 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4105-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0111 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4103-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0112 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4035-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0113 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4110-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0115 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4146-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0116 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4111-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0117 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4118-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0118 | E2.T043A LV Motor Stage 2A | ELEC | 3333-AG-4006-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0119 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4098-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0121 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4088-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-25T05:31:02.5400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-25T03:21:15.4200000 |  | 2021-04-25T03:24:10.0230000
T-00210-0122 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:20:15.5670000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-15T07:22:04.0000000 |  | 2021-04-15T07:45:08.9670000
T-00210-0123 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4013-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0124 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FN-4006-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0125 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4090-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-01T22:18:31.4070000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-02-01T02:30:56.0670000 |  | 2021-02-01T20:45:23.7830000
T-00210-0126 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4095-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:48:43.3130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:39:02.2070000 |  | 2021-04-18T06:00:06.8830000
T-00210-0128 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4120-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0129 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4143-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0131 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4109-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0132 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4155-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00210-0133 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4050-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0134 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4122-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0135 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4028-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0136 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4158-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00210-0137 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4080-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0138 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4057-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0140 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4102-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0142 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4152-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0143 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4102-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0144 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4014-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0145 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4011-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T07:48:29.9600000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-13T20:50:42.0930000 |  | 2021-04-13T21:06:59.5530000
T-00210-0146 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4108-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0147 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4121-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0148 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4009-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-23T07:59:30.3030000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-23T07:06:37.2070000 |  | 2021-04-23T07:06:56.2870000
T-00210-0150 | E2.T043A LV Motor Stage 2A | ELEC | 3331-AG-4001-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-20T22:32:52.0400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-17T07:08:22.7500000 |  | 2021-04-17T07:15:02.7770000
T-00210-0151 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4094-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-22T09:14:05.3930000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-02-21T06:14:46.7300000 |  | 2021-02-21T06:38:48.4730000
T-00210-0152 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4117-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0153 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4117-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0154 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4043-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0155 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4135-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0156 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4147 M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0157 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4159-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0158 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4105-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0159 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4145-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0160 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0162 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4093-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-21T06:15:01.4400000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-02-21T05:45:55.3670000 |  | 2021-02-21T06:08:34.5770000
T-00210-0163 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4151-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0164 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4107-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0165 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4091-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-01T22:21:57.9330000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-02-01T02:45:48.7030000 |  | 2021-02-01T20:45:48.0630000
T-00210-0166 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4103-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0167 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4096-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:49:39.1170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-16T07:37:45.1100000 |  | 2021-04-18T06:02:40.0130000
T-00210-0168 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4113-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0169 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4157-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0170 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4111-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0171 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4138-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0172 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4156-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0173 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4106-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0174 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4126-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0176 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4030-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0177 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4076-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0178 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4097-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0179 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4024-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0180 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4115-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0181 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4078-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0182 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4144-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0183 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4112-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0184 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4082-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T05:55:46.1900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T05:38:46.2100000 |  | 2021-04-24T05:39:18.4100000
T-00210-0185 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4086-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T03:27:31.7670000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-23T20:46:25.3870000 |  | 2021-04-23T22:53:33.6230000
T-00210-0186 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4118-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0187 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4131-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0188 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4025-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0189 | E2.T043A LV Motor Stage 2A | ELEC | 3334-FD-4003-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T21:21:04.5400000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T06:12:31.0000000 |  | 2021-04-24T07:28:59.8400000
T-00210-0190 | E2.T043A LV Motor Stage 2A | ELEC | 3333-FN-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0191 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4128-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0192 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4072-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0193 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4148-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0194 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4005-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T07:48:59.5270000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-13T20:47:04.9670000 |  | 2021-04-13T21:01:52.1600000
T-00210-0195 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4034-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0196 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4154-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T07:44:53.4170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-18T00:54:58.6230000 |  | 2021-04-20T07:37:41.3370000
T-00210-0197 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4101-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0198 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4110-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0199 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4083-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T05:56:13.7170000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T03:39:55.3800000 |  | 2021-04-24T04:50:56.1330000
T-00210-0200 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4153-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0201 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4041-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0202 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4119-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0203 | E2.T043A LV Motor Stage 2A | ELEC | 3333-FD-4002-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0204 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4070-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0205 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4052-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0206 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FN-4005-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00210-0207 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4032-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0208 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4129-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0209 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4125-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0210 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4060-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0211 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4003-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:20:50.5130000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-15T07:18:40.0000000 |  | 2021-04-15T07:37:56.3570000
T-00210-0212 | E2.T043A LV Motor Stage 2A | ELEC | 3331-PU-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-14T20:25:39.2900000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-13T23:08:53.5030000 |  | 2021-04-13T23:44:02.1570000
T-00210-0213 | E2.T043A LV Motor Stage 2A | ELEC | 3332-FN-4002-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0215 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4022-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0216 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4136-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0217 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4124-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0218 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4130-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0219 | E2.T043A LV Motor Stage 2A | ELEC | 3333-FD-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0220 | E2.T043A LV Motor Stage 2A | ELEC | 3334-BL-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Rejected |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T06:30:17.0000000
T-00210-0221 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4099-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00210-0222 | E2.T043A LV Motor Stage 2A | ELEC | 3332-AG-4114-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00210-0223 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4079-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0224 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4112-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0225 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4012-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0226 | E2.T043A LV Motor Stage 2A | ELEC | 3333-PU-4040-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0227 | E2.T043A LV Motor Stage 2A | ELEC | 3331-AG-4002-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-21T07:44:30.9170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-21T06:09:15.0000000 |  | 2021-04-21T06:26:02.3230000
T-00210-0228 | E2.T043A LV Motor Stage 2A | ELEC | 3335-PU-4160-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0229 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4081-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0230 | E2.T043A LV Motor Stage 2A | ELEC | 3334-AG-4013-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T21:22:05.8100000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T06:05:26.0000000 |  | 2021-04-24T07:27:19.3600000
T-00210-0231 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4077-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0232 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4123-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0233 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4071-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0234 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4127-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0235 | E2.T043A LV Motor Stage 2A | ELEC | 3334-PU-4075-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00210-0236 | E2.T043A LV Motor Stage 2A | ELEC | 3332-PU-4010-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Started |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00210-0237 | E2.T043A LV Motor Stage 2A | ELEC | 3334-VI-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Rejected |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T07:14:49.0000000
T-00210-0238 | E2.T043A LV Motor Stage 2A | ELEC | 3334-AT-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T21:23:08.8000000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-24T06:26:36.0000000 |  | 2021-04-24T07:27:55.8700000
T-00210-0239 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0082 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:22:55.2070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T02:14:14.8900000 |  | 2021-03-27T02:59:35.5500000
T-00210-0240 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0009 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:23:33.7970000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:27:30.8770000 |  | 2021-03-27T03:00:19.3000000
T-00210-0241 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0007 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:24:05.6130000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:11:24.4070000 |  | 2021-03-27T03:00:45.0530000
T-00210-0242 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0005 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:25:00.9130000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:59:58.8700000 |  | 2021-03-27T03:01:21.2630000
T-00210-0243 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0002 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:25:44.5830000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:14:00.0400000 |  | 2021-03-27T03:01:50.8270000
T-00210-0244 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0008 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:26:14.4030000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T02:19:40.3470000 |  | 2021-03-27T03:02:39.5500000
T-00210-0245 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0084 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:27:03.8300000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:41:23.0400000 |  | 2021-03-27T03:03:09.5700000
T-00210-0246 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0003 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:27:39.6130000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T01:12:38.2200000 |  | 2021-03-27T03:03:32.9470000
T-00210-0247 | E2.T043A LV Motor Stage 2A | ELEC | 3331-FV-0081 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:28:12.9470000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T02:06:54.2170000 |  | 2021-03-27T03:03:56.8270000
T-00211-0099 | E2.T043B LV Motor Stage 2B | ELEC | 3332-FN-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0100 | E2.T043B LV Motor Stage 2B | ELEC | 3334-AG-4012-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0101 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4084-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0102 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4114-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0103 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4141-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0104 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4005-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0105 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4140-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0106 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4007-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0107 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4104-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0108 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4026-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0109 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4044-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0110 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4105-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0111 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4103-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0112 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4035-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0113 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4110-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0115 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4146-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0116 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4111-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0117 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4118-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0118 | E2.T043B LV Motor Stage 2B | ELEC | 3333-AG-4006-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0119 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4098-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0121 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4088-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T03:27:56.2570000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T01:35:01.6230000
T-00211-0122 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-20T03:40:11.6170000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-18T04:02:02.8970000
T-00211-0123 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4013-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0124 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FN-4006-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0125 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4090-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-23T02:44:20.0500000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-02-08T05:43:10.0730000 |  | 2021-02-22T04:03:09.4900000
T-00211-0126 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4095-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:50:10.4200000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-16T07:55:10.6900000
T-00211-0128 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4120-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0129 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4143-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0131 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4109-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0132 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4155-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Started |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0133 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4050-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0134 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4122-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0135 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4028-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0136 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4158-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25
T-00211-0137 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4080-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0138 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4057-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0140 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4102-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0142 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4152-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0143 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4102-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0144 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4014-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0145 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4011-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-13T07:48:00.4100000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-13T07:46:15.1300000
T-00211-0146 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4108-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0147 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4121-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0148 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4009-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Closed | 2021-04-24T02:04:00.4370000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-23T23:08:37.8370000
T-00211-0150 | E2.T043B LV Motor Stage 2B | ELEC | 3331-AG-4001-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:41:48.3130000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-12T04:34:05.8670000 |  | 2021-04-12T04:34:30.2800000
T-00211-0151 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4094-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-04-13T23:45:28.5870000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-04-13T00:55:03.3400000
T-00211-0152 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4117-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0153 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4117-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0154 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4043-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0155 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4135-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0156 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4147 M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0157 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4159-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0158 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4105-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0159 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4145-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0160 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0162 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4093-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-02-23T02:43:06.5900000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-02-20T06:24:58.5700000
T-00211-0163 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4151-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0164 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4107-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0165 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4091-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Closed | 2021-02-25T13:17:09.2800000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-02-08T05:47:43.3070000 |  | 2021-02-25T06:15:17.1870000
T-00211-0166 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4103-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0167 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4096-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Closed | 2021-04-20T07:50:51.4600000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-16T08:00:33.1900000
T-00211-0168 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4113-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0169 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4157-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0170 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4111-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0171 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4138-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0172 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4156-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0173 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4106-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0174 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4126-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0176 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4030-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0177 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4076-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0178 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4097-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0179 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4024-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0180 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4115-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0181 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4078-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0182 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4144-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0183 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4112-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0184 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4082-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0185 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4086-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T03:23:23.0230000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T01:32:22.3830000
T-00211-0186 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4118-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0187 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4131-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0188 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4025-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0189 | E2.T043B LV Motor Stage 2B | ELEC | 3334-FD-4003-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0190 | E2.T043B LV Motor Stage 2B | ELEC | 3333-FN-4004-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0191 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4128-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0192 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4072-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0193 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4148-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0194 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4005-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-13T07:48:21.3530000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-13T07:45:28.3330000
T-00211-0195 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4034-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0196 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4154-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Closed | 2021-03-25T05:50:29.3400000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-02-09T01:34:11.8270000 |  | 2021-03-24T18:36:45.3630000
T-00211-0197 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4101-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0198 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4110-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0199 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4083-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Closed | 2021-04-24T04:00:26.5300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 |  |  | 2021-04-24T03:30:51.5330000
T-00211-0200 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4153-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0201 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4041-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0202 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4119-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0203 | E2.T043B LV Motor Stage 2B | ELEC | 3333-FD-4002-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0204 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4070-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0205 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4052-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0206 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FN-4005-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00211-0207 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4032-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0208 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4129-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0209 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4125-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0210 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4060-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0211 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4003-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-15T21:21:27.3970000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 |  |  | 2021-04-15T06:38:20.7670000
T-00211-0212 | E2.T043B LV Motor Stage 2B | ELEC | 3331-PU-4001-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Submitted |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-14T01:10:41.9730000
T-00211-0213 | E2.T043B LV Motor Stage 2B | ELEC | 3332-FN-4002-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0215 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4022-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0216 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4136-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0217 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4124-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0218 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4130-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0219 | E2.T043B LV Motor Stage 2B | ELEC | 3333-FD-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0220 | E2.T043B LV Motor Stage 2B | ELEC | 3334-BL-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0221 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4099-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00211-0222 | E2.T043B LV Motor Stage 2B | ELEC | 3332-AG-4114-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00211-0223 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4079-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0224 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4112-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0225 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4012-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0226 | E2.T043B LV Motor Stage 2B | ELEC | 3333-PU-4040-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0227 | E2.T043B LV Motor Stage 2B | ELEC | 3331-AG-4002-M1 | MO - Motor | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-12T05:31:12.4430000 | 2021-03-24T00:00:00.0000000 | 2021-03-31T00:00:00.0000000 | 0.25 | 2021-04-12T04:44:03.9270000 |  | 2021-04-12T04:44:13.6800000
T-00211-0228 | E2.T043B LV Motor Stage 2B | ELEC | 3335-PU-4160-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0229 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4081-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0230 | E2.T043B LV Motor Stage 2B | ELEC | 3334-AG-4013-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0231 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4077-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0232 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4123-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0233 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4071-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0234 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4127-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0235 | E2.T043B LV Motor Stage 2B | ELEC | 3334-PU-4075-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00211-0236 | E2.T043B LV Motor Stage 2B | ELEC | 3332-PU-4010-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00211-0237 | E2.T043B LV Motor Stage 2B | ELEC | 3334-VI-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0238 | E2.T043B LV Motor Stage 2B | ELEC | 3334-AT-4001-M1 | MO - Motor |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25
T-00211-0239 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0082 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T22:29:31.7130000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:26:37.9600000
T-00211-0240 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0009 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T22:30:00.7800000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:27:22.9730000
T-00211-0241 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0007 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T22:30:34.2730000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:27:51.7470000
T-00211-0242 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0005 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:29:03.7700000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-27T00:11:10.9470000
T-00211-0243 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0002 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T22:31:08.2500000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:31:48.5600000
T-00211-0244 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0008 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T23:31:34.4930000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:28:44.6030000
T-00211-0245 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0084 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T23:32:02.2070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:29:38.8530000
T-00211-0246 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0003 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T23:32:24.7870000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:30:11.5470000
T-00211-0247 | E2.T043B LV Motor Stage 2B | ELEC | 3331-FV-0081 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-25T23:33:13.4070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-25T21:30:47.9630000
T-00212-0099 | E3.T043 LV Motor Stage 3 | ELEC | 3332-FN-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0100 | E3.T043 LV Motor Stage 3 | ELEC | 3334-AG-4012-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0101 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4084-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0102 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4114-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0103 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4141-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0104 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4005-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0105 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4140-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0106 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4007-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0107 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4104-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0108 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4026-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0109 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4044-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0110 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4105-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0111 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4103-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0112 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4035-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0113 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4110-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0115 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4146-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0116 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4111-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0117 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4118-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0118 | E3.T043 LV Motor Stage 3 | ELEC | 3333-AG-4006-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0119 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4098-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0121 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4088-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0122 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4004-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0123 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4013-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0124 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FN-4006-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0125 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4090-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0126 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4095-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0128 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4120-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0129 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4143-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0131 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4109-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0132 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4155-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0133 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4050-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0134 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4122-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0135 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4028-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0136 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4158-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Predecessors Pending |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0137 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4080-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0138 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4057-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0140 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4102-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0142 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4152-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0143 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4102-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0144 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4014-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0145 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4011-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0146 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4108-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0147 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4121-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0148 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4009-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0150 | E3.T043 LV Motor Stage 3 | ELEC | 3331-AG-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0151 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4094-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0152 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4117-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0153 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4117-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0154 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4043-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0155 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4135-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0156 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4147 M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0157 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4159-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0158 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4105-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0159 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4145-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0160 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4004-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0162 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4093-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0163 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4151-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0164 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4107-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0165 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4091-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0166 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4103-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0167 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4096-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0168 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4113-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0169 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4157-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0170 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4111-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0171 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4138-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0172 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4156-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0173 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4106-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0174 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4126-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0176 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4030-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0177 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4076-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0178 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4097-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0179 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4024-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0180 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4115-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0181 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4078-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0182 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4144-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0183 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4112-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0184 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4082-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0185 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4086-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0186 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4118-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0187 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4131-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0188 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4025-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0189 | E3.T043 LV Motor Stage 3 | ELEC | 3334-FD-4003-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0190 | E3.T043 LV Motor Stage 3 | ELEC | 3333-FN-4004-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0191 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4128-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0192 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4072-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0193 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4148-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0194 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4005-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0195 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4034-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0196 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4154-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0197 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4101-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0198 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4110-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0199 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4083-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Past Due |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0200 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4153-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0201 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4041-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0202 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4119-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0203 | E3.T043 LV Motor Stage 3 | ELEC | 3333-FD-4002-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0204 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4070-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0205 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4052-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0206 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FN-4005-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0207 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4032-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0208 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4129-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0209 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4125-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0210 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4060-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0211 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4003-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0212 | E3.T043 LV Motor Stage 3 | ELEC | 3331-PU-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0213 | E3.T043 LV Motor Stage 3 | ELEC | 3332-FN-4002-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0215 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4022-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0216 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4136-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0217 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4124-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0218 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4130-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0219 | E3.T043 LV Motor Stage 3 | ELEC | 3333-FD-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0220 | E3.T043 LV Motor Stage 3 | ELEC | 3334-BL-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0221 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4099-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0222 | E3.T043 LV Motor Stage 3 | ELEC | 3332-AG-4114-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00212-0223 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4079-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0224 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4112-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0225 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4012-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0226 | E3.T043 LV Motor Stage 3 | ELEC | 3333-PU-4040-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0227 | E3.T043 LV Motor Stage 3 | ELEC | 3331-AG-4002-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-04-06T00:00:00.0000000 | 2021-04-13T00:00:00.0000000 | 0.25
T-00212-0228 | E3.T043 LV Motor Stage 3 | ELEC | 3335-PU-4160-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Predecessors Pending |  | 2021-04-10T00:00:00.0000000 | 2021-04-17T00:00:00.0000000 | 0.25
T-00212-0229 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4081-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0230 | E3.T043 LV Motor Stage 3 | ELEC | 3334-AG-4013-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0231 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4077-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0232 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4123-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0233 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4071-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0234 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4127-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0235 | E3.T043 LV Motor Stage 3 | ELEC | 3334-PU-4075-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00212-0236 | E3.T043 LV Motor Stage 3 | ELEC | 3332-PU-4010-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Predecessors Pending |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00212-0237 | E3.T043 LV Motor Stage 3 | ELEC | 3334-VI-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0238 | E3.T043 LV Motor Stage 3 | ELEC | 3334-AT-4001-M1 | MO - Motor | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Predecessors Pending |  | 2021-04-09T00:00:00.0000000 | 2021-04-16T00:00:00.0000000 | 0.25
T-00212-0239 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0082 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0240 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0009 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0241 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0007 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0242 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0005 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0243 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0002 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0244 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0008 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0245 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0084 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0246 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0003 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00212-0247 | E3.T043 LV Motor Stage 3 | ELEC | 3331-FV-0081 | MOV - Motorised Valve | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00213-0001 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4001 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00213-0002 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4002 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00213-0003 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4003 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00213-0004 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4004 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00213-0005 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4005 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00213-0006 | E1.T002 Air Conditioning Stage 1 | ELEC | 3338-AC-4006 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00214-0001 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4001 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00214-0002 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4002 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00214-0003 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4003 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00214-0004 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4004 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00214-0005 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4005 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00214-0006 | E2.T003 Air Conditioning Stage 2 | ELEC | 3338-AC-4006 | AC - AIR CONDITIONING |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00215-0001 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4001 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00215-0002 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4002 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00215-0003 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4003 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00215-0004 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4004 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00215-0005 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4005 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00215-0006 | M1.T007 Air Conditioner Stage 1 | MECH | 3338-AC-4006 | AC - AIR CONDITIONING | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00216-0001 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4004 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T03:24:00.1530000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T02:53:05.3570000 |  | 2021-04-18T02:53:11.7800000
T-00216-0002 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4006 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Closed | 2021-04-20T00:52:32.8500000 | 2021-04-23T00:00:00.0000000 | 2021-04-30T00:00:00.0000000 | 0.25 | 2021-04-19T02:21:44.7130000 |  | 2021-04-19T02:21:54.8770000
T-00216-0004 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4001 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-04T22:37:27.6300000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T04:24:47.9400000 |  | 2021-04-03T04:25:00.3730000
T-00216-0005 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4003 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-18T01:35:47.0470000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-18T00:07:27.9870000 |  | 2021-04-18T00:07:39.4170000
T-00216-0006 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4002 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Closed | 2021-04-04T22:38:10.8530000 | 2021-04-02T00:00:00.0000000 | 2021-04-09T00:00:00.0000000 | 0.25 | 2021-04-03T04:24:13.4330000 |  | 2021-04-03T04:24:22.3170000
T-00216-0007 | M1.T047 Monorail & Hoist Stage 1 | MECH | 3332-HT-4005 | HT - HOIST | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Closed | 2021-04-24T09:24:45.3330000 | 2021-03-26T00:00:00.0000000 | 2021-04-02T00:00:00.0000000 | 0.25 | 2021-04-24T05:45:59.7470000 |  | 2021-04-24T05:46:25.4700000
T-00217-0001 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4004 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00217-0002 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4006 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Next Week |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00217-0004 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4001 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00217-0005 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4003 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00217-0006 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4002 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | This Week |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00217-0007 | M3.T047 Monorail & Hoist Stage 3 | MECH | 3332-HT-4005 | HT - HOIST | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Past Due |  | 2021-04-16T00:00:00.0000000 | 2021-04-23T00:00:00.0000000 | 0.25
T-00218-0001 | M3.T020 Crane Stage 3 | MECH | 3331-CN-4002 | CN - CRANE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-19T00:00:00.0000000 | 2021-03-26T00:00:00.0000000 | 0.25
T-00218-0002 | M3.T020 Crane Stage 3 | MECH | 3333-CN-4001 | CN - CRANE | S3.1.1 - Water Testing | S3.1 - Wet Commissioning | S3 - Stage 3 Wet Commissioning | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-05-07T00:00:00.0000000 | 2021-05-14T00:00:00.0000000 | 0.25
T-00219-0001 | E2.T071 Crane Energised Commissioning Stage 2 | ELEC | 3331-CN-4002 | CN - CRANE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Past Due |  | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25
T-00219-0002 | E2.T071 Crane Energised Commissioning Stage 2 | ELEC | 3333-CN-4001 | CN - CRANE |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Predecessors Pending |  | 2021-04-30T00:00:00.0000000 | 2021-05-07T00:00:00.0000000 | 0.25
T-00224-0001 | IA to OP Box Stage 1 | PIPE | 3335-OP-4573-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:13:01.9730000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T02:59:02.2370000 |  | 2021-03-15T02:59:07.7200000
T-00224-0002 | IA to OP Box Stage 1 | PIPE | 3334-OP-4084-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:29:35.4970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:00:07.6970000 |  | 2021-03-15T03:00:14.5530000
T-00224-0003 | IA to OP Box Stage 1 | PIPE | 3334-PK-4007-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:30:06.7200000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:00:37.7700000 |  | 2021-03-15T03:00:50.3470000
T-00224-0004 | IA to OP Box Stage 1 | PIPE | 3331-OP-4006-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:30:28.3030000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:01:14.1600000 |  | 2021-03-15T03:01:20.7370000
T-00224-0005 | IA to OP Box Stage 1 | PIPE | 3331-OP-4005-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:30:45.3970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:01:50.1700000 |  | 2021-03-15T03:01:59.7800000
T-00224-0006 | IA to OP Box Stage 1 | PIPE | 3331-OP-4003-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:31:16.0070000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:02:16.5600000 |  | 2021-03-15T03:02:22.9700000
T-00224-0007 | IA to OP Box Stage 1 | PIPE | 3331-OP-4002-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:31:39.9900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:02:38.5130000 |  | 2021-03-15T03:02:44.7770000
T-00224-0008 | IA to OP Box Stage 1 | PIPE | 3331-OP-4007-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:31:57.9270000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:03:00.9870000 |  | 2021-03-15T03:03:10.9130000
T-00224-0009 | IA to OP Box Stage 1 | PIPE | 3335-OP-4571-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:32:17.0370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:03:37.2400000 |  | 2021-03-15T03:03:46.3870000
T-00224-0010 | IA to OP Box Stage 1 | PIPE | 3335-OP-4574-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:32:46.9500000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:04:54.8500000 |  | 2021-03-15T03:05:07.3470000
T-00224-0011 | IA to OP Box Stage 1 | PIPE | 3335-OP-4093-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:33:06.0530000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:05:30.7700000 |  | 2021-03-15T03:05:38.1300000
T-00224-0012 | IA to OP Box Stage 1 | PIPE | 3334-OP-4561-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:33:44.3800000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:05:54.5870000 |  | 2021-03-15T03:06:00.3370000
T-00224-0013 | IA to OP Box Stage 1 | PIPE | 3331-OP-4010-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:34:04.3900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:06:16.3930000 |  | 2021-03-15T03:06:24.6730000
T-00224-0014 | IA to OP Box Stage 1 | PIPE | 3334-OP-4560-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:34:24.5970000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:06:39.8900000 |  | 2021-03-15T03:06:58.6900000
T-00224-0015 | IA to OP Box Stage 1 | PIPE | 3335-OP-4092-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:34:46.8370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:07:20.8730000 |  | 2021-03-15T03:08:09.7230000
T-00224-0016 | IA to OP Box Stage 1 | PIPE | 3335-OP-4572-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:35:06.4630000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:08:30.5800000 |  | 2021-03-15T03:08:38.0600000
T-00224-0017 | IA to OP Box Stage 1 | PIPE | 3331-OP-4001-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:35:38.9900000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:08:58.8670000 |  | 2021-03-15T03:09:05.6900000
T-00224-0018 | IA to OP Box Stage 1 | PIPE | 3335-OP-4091-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:35:59.2300000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:09:22.2200000 |  | 2021-03-15T03:09:28.6270000
T-00224-0019 | IA to OP Box Stage 1 | PIPE | 3331-OP-4008-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:36:18.8370000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:10:40.7400000 |  | 2021-03-15T03:10:47.4530000
T-00224-0020 | IA to OP Box Stage 1 | PIPE | 3331-OP-4009-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:36:40.6470000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:11:07.9800000 |  | 2021-03-15T03:13:28.6300000
T-00224-0021 | IA to OP Box Stage 1 | PIPE | 3334-OP-4562-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:37:12.9670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:14:10.7330000 |  | 2021-03-15T03:14:21.4370000
T-00224-0022 | IA to OP Box Stage 1 | PIPE | 3331-PU-4007-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:37:41.8700000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:15:04.2600000 |  | 2021-03-15T03:15:10.2870000
T-00224-0023 | IA to OP Box Stage 1 | PIPE | 3331-OP-4004-IA | Line - IA Line | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-03-15T03:37:59.6670000 | 2021-03-12T00:00:00.0000000 | 2021-03-19T00:00:00.0000000 | 0.25 | 2021-03-15T03:15:38.1170000 |  | 2021-03-15T03:15:49.7730000
T-00225-0001 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0082 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:29:31.4770000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:53:30.8370000 |  | 2021-03-27T05:03:22.2400000
T-00225-0002 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0009 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:30:01.3930000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:33:46.3670000 |  | 2021-03-27T05:03:47.6700000
T-00225-0003 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0007 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:30:25.4170000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:16:14.4230000 |  | 2021-03-27T05:04:11.7300000
T-00225-0004 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0005 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:30:49.4000000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:11:30.4730000 |  | 2021-03-27T05:04:33.0800000
T-00225-0005 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0002 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:31:09.4270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T03:54:00.4930000 |  | 2021-03-27T05:05:02.4870000
T-00225-0006 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0008 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:31:28.2070000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T06:19:29.2170000 |  | 2021-03-27T06:24:22.5970000
T-00225-0007 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0084 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:31:48.3270000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T05:08:51.8670000 |  | 2021-03-27T06:11:48.6270000
T-00225-0008 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0003 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:32:08.2130000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T03:57:41.2100000 |  | 2021-03-27T05:05:29.5370000
T-00225-0009 | I2.T024A Motorised Valve Stage 2A | INST | 3331-FV-0081 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:32:26.9670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 | 2021-03-27T04:45:39.1300000 |  | 2021-03-27T05:06:05.5430000
T-00226-0001 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0082 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:32:46.6900000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T04:48:40.5370000
T-00226-0002 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0009 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T02:59:52.3770000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T02:25:10.9030000
T-00226-0003 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0007 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T03:00:17.5730000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T02:34:23.7700000
T-00226-0004 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0005 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:33:05.4670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-27T02:49:48.4730000
T-00226-0005 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0002 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T03:02:09.9800000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T02:45:36.6370000
T-00226-0006 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0008 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:33:31.7300000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T22:29:16.4670000
T-00226-0007 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0084 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:33:54.4670000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T03:47:01.8430000
T-00226-0008 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0003 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-26T03:02:39.9900000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T01:43:22.4870000
T-00226-0009 | I2.T024B Motorised Valve Stage 2B | INST | 3331-FV-0081 | MOV - Motorised Valve |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-03-27T08:34:11.6870000 | 2021-03-14T00:00:00.0000000 | 2021-03-21T00:00:00.0000000 | 0.25 |  |  | 2021-03-26T04:33:19.9970000
T-00227-0001 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-ME-4013 | ME - FROTH CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-14T07:44:18.7870000 |  |  | 0.25 | 2021-04-14T03:52:02.0170000 |  | 2021-04-14T04:05:14.1130000
T-00227-0002 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-ME-4012 | ME - FROTH CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-14T07:44:46.2430000 |  |  | 0.25 | 2021-04-14T03:54:54.1730000 |  | 2021-04-14T04:05:32.8600000
T-00227-0003 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-ME-4014 | ME - FROTH CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-14T07:45:07.1470000 |  |  | 0.25 | 2021-04-14T03:53:17.0000000 |  | 2021-04-14T04:06:08.5470000
T-00227-0006 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-ME-4015 | ME - FROTH CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-14T07:45:29.5670000 |  |  | 0.25 | 2021-04-14T03:56:14.1370000 |  | 2021-04-14T04:06:31.5770000
T-00227-0007 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-ME-4016 | ME - FROTH CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Closed | 2021-04-14T07:45:50.8600000 |  |  | 0.25 | 2021-04-14T03:57:24.5470000 |  | 2021-04-14T04:07:18.9730000
T-00227-0009 | I1.T0xx CCTV & Camera Stage 1 | INST | 3334-CA-0002 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0010 | I1.T0xx CCTV & Camera Stage 1 | INST | 3338-CA-0003 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0011 | I1.T0xx CCTV & Camera Stage 1 | INST | 3338-CA-0002 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0012 | I1.T0xx CCTV & Camera Stage 1 | INST | 3331-CA-0002 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0013 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0005 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0014 | I1.T0xx CCTV & Camera Stage 1 | INST | 3338-CA-0004 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0015 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0002 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0016 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0006 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0017 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0003 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0018 | I1.T0xx CCTV & Camera Stage 1 | INST | 3331-CA-0003 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0019 | I1.T0xx CCTV & Camera Stage 1 | INST | 3334-CA-0001 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0020 | I1.T0xx CCTV & Camera Stage 1 | INST | 3331-CA-0001 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0021 | I1.T0xx CCTV & Camera Stage 1 | INST | 3334-CA-0003 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0022 | I1.T0xx CCTV & Camera Stage 1 | INST | 3333-CA-0001 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0023 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0001 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0024 | I1.T0xx CCTV & Camera Stage 1 | INST | 3332-CA-0004 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00227-0025 | I1.T0xx CCTV & Camera Stage 1 | INST | 3338-CA-0001 | CA - CAMERA | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.25
T-00228-0001 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-ME-4013 | ME - FROTH CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00228-0002 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-ME-4012 | ME - FROTH CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00228-0003 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-ME-4014 | ME - FROTH CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00228-0006 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-ME-4015 | ME - FROTH CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00228-0007 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-ME-4016 | ME - FROTH CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.25
T-00228-0009 | I2.T0xx CCTV & Camera Stage 2 | INST | 3334-CA-0002 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0010 | I2.T0xx CCTV & Camera Stage 2 | INST | 3338-CA-0003 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0011 | I2.T0xx CCTV & Camera Stage 2 | INST | 3338-CA-0002 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0012 | I2.T0xx CCTV & Camera Stage 2 | INST | 3331-CA-0002 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0013 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0005 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0014 | I2.T0xx CCTV & Camera Stage 2 | INST | 3338-CA-0004 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0015 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0002 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0016 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0006 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0017 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0003 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0018 | I2.T0xx CCTV & Camera Stage 2 | INST | 3331-CA-0003 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0019 | I2.T0xx CCTV & Camera Stage 2 | INST | 3334-CA-0001 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0020 | I2.T0xx CCTV & Camera Stage 2 | INST | 3331-CA-0001 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0021 | I2.T0xx CCTV & Camera Stage 2 | INST | 3334-CA-0003 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0022 | I2.T0xx CCTV & Camera Stage 2 | INST | 3333-CA-0001 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0023 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0001 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0024 | I2.T0xx CCTV & Camera Stage 2 | INST | 3332-CA-0004 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00228-0025 | I2.T0xx CCTV & Camera Stage 2 | INST | 3338-CA-0001 | CA - CAMERA |  | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Predecessors Pending |  |  |  | 0.25
T-00230-0001 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-09 - Copper concentrate Jib Crane | CS01 - Cu Concentrate Feed Tanks & Bypass | Started |  |  |  | 0.5
T-00230-0002 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-07 - GEHO Pump | CS01 - Cu Concentrate Feed Tanks & Bypass | Created |  |  |  | 0.5
T-00230-0003 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01A - Concentrate Storage Tank 2 (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:54:47.9930000
T-00230-0004 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03A - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART A) | CS01 - Cu Concentrate Feed Tanks & Bypass | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:58:08.4830000
T-00230-0005 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-05 - Blayney Feed & Bypass (C11) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-17T00:21:37.6200000 |  |  | 0.5 |  |  | 2021-04-16T22:19:02.0830000
T-00230-0006 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-08 - Concentrate Storage Area Sump | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-26T15:44:23.3430000 |  |  | 0.5 |  |  | 2021-04-26T05:36:22.4030000
T-00230-0007 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-01 - Copper Concentrate Thickener (Top) | CS25 - Copper Concentrate Thickener | Started |  |  |  | 0.5
T-00230-0008 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-02 - Copper Concentrate Thickener (Bottom) | CS25 - Copper Concentrate Thickener | Closed | 2021-04-26T15:45:33.5500000 |  |  | 0.5 |  |  | 2021-04-26T05:35:24.7870000
T-00230-0009 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-08 - Copper Concentrate Thickener Froth Hopper | CS25 - Copper Concentrate Thickener | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:56:46.7900000
T-00230-0010 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-09 - Copper Concentrate Thickener Area Sump | CS25 - Copper Concentrate Thickener | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:57:27.1800000
T-00230-0011 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS25-03 - Concentrate Thickener Screen & Metallurgical Sampler | CS25 - Copper Concentrate Thickener | Created |  |  |  | 0.5
T-00230-0012 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-01B - Concentrate Storage Tank 2 (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Closed | 2021-04-17T00:22:07.3270000 |  |  | 0.5 |  |  | 2021-04-16T22:20:54.8930000
T-00230-0013 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS01-03B - Concentrate Storage Tank 1 to Rougher Conditioning Tank 1 and Cu Concentrate Thickener (PART B) | CS01 - Cu Concentrate Feed Tanks & Bypass | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:58:50.8900000
T-00230-0014 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-01 - Intermediate Thickener | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00230-0015 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-07 - Regrind mill | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00230-0016 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-06 - Cleaner area sump | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00230-0017 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-02 - Rougher Conditioning Tanks 1 & 2 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0018 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-05 - Rougher Jameson Cell & ISA Samplers | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0019 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-08 - Rougher Scavenger Flotation Cells | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0020 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-10 - Rougher Scavenger Tailings Hopper & Cu Concentrate Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0021 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-12 - Rougher Area Sump 1 | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0022 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-21 - Rougher Area Sump 2 & NaHS Sump | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0023 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS03-04 - Intermediate & Moly Thickener Overflow Tank | CS03 - Intermediate Thickener and Regrind Mill | Created |  |  |  | 0.5
T-00230-0024 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS04-01 - First Cleaner Flotation Cells | CS04 - 1st Cleaner Flotation | Created |  |  |  | 0.5
T-00230-0025 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-03 - Second Cleaner Tailings Hopper | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00230-0026 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS05-08 - Second Cleaner Flotation Cells | CS05 - 2nd Cleaner Flotation | Created |  |  |  | 0.5
T-00230-0027 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS06-01 - Cleaner Flotation Cells | CS06 - Cleaner Scavenger Flotation | Created |  |  |  | 0.5
T-00230-0028 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-13 - Fourth Cleaner Jameson Cell, Fourth Cleaner Hopper & Third/Forth Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Created |  |  |  | 0.5
T-00230-0029 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS07-14 - Third Cleaner Jameson Cell & Third Cleaner Hopper | CS07 - 3rd & 4th Cleaner Jameson Cells | Started |  |  |  | 0.5
T-00230-0030 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0M-02 - Gland Seal Water Charging Pumps | CS0M - Gland Water | Created |  |  |  | 0.5
T-00230-0031 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-01 - Flotation Scrubber, Caustic Soda & Sodium Hypochlorite Tanks | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00230-0032 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-02 - Caustic Dosing and Distribution | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00230-0033 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS11-03 - Flotation Scrubber Vent Network | CS11 - Scrubber & Caustic Soda (Sodium hydroxide / NaOH) Tank | Created |  |  |  | 0.5
T-00230-0034 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS28-01 - OSA Building, Feed and Return Network | CS28 - OSA | Created |  |  |  | 0.5
T-00230-0035 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-01 - Rougher Conditioning Metallurgical Sampler | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0036 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS02-07 - Rougher Scavenger Cells ISA & Froth Cameras | CS02 - Rougher & Scavenger Cells | Created |  |  |  | 0.5
T-00230-0037 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-01 - Concentrate Dryer | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00230-0038 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-01 - Molybdenum Concentrate Thickener | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0039 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-07 - Filter Building Gantry Crane | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0040 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-09 - Molybdenum Filter Feed Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0041 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-10 - Molybdenum Filter, Pressing & Washing Water Tanks | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0042 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-11 - Concentrate Filter Recovery Tank | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0043 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS08-12 - Filter Area Sump, Molybdenum Thickener Sump & Filter Building Drains | CS08 - Molybdenum Thickener and Concentrate Filter | Created |  |  |  | 0.5
T-00230-0044 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS09-03 - Concentrate Dryer Scrubber | CS09 - Concentrate Dryer & Scrubber | Created |  |  |  | 0.5
T-00230-0045 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS27-01 - Concentrate Bagging Plant | CS27 - Bagging Plant | Created |  |  |  | 0.5
T-00230-0046 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-03 - Flocculant area sump | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.5
T-00230-0047 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS19-01 - Collector Storage, Makeup & Distribution | CS19 - Collector Storage, Makeup & Distribution | Created |  |  |  | 0.5
T-00230-0048 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS13-01 - Flocculant Plant and Distribution | CS13 - Flocculant Preparation & Distribution | Created |  |  |  | 0.5
T-00230-0049 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-01 - NaHS Distribution Network | CS14 - NaHS Preparation & Distribution | Created |  |  |  | 0.5
T-00230-0050 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS14-03 - NaHS Ring Main & Storage Tanks | CS14 - NaHS Preparation & Distribution | Created |  |  |  | 0.5
T-00230-0051 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS15-01 - Frother Tank and Distribution Network | CS15 - Frother Distribution | Created |  |  |  | 0.5
T-00230-0052 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-01 - Defoamer Tank & Ring Main | CS16 - Defoamer Distribution | Created |  |  |  | 0.5
T-00230-0053 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS16-02 - Defoamer Distribution Network | CS16 - Defoamer Distribution | Created |  |  |  | 0.5
T-00230-0054 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS17-01 - CO2 Plant and Distribution Network | CS17 - CO2 Storage & Distribution | Created |  |  |  | 0.5
T-00230-0055 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-01 - Process Control - Network and DCS panels | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0056 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEC-01 - Power Factor Correction / Harmonic Filters | CSEC - Power Factor Correction / Harmonic Filters | Created |  |  |  | 0.5
T-00230-0057 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-02 - VESDA and Fire System | CSED - Switch Room & MCCs | Created |  |  |  | 0.5
T-00230-0059 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-05 - Lighting and Small Power Molybdenum Floatation | CSEE - Lighting and General Purpose Outlets | Created |  |  |  | 0.5
T-00230-0060 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-06 - Lighting and Small Power Molybdenum Concentrate Handling | CSEE - Lighting and General Purpose Outlets | Created |  |  |  | 0.5
T-00230-0061 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-07 - Lighting and Small Power Reagents | CSEE - Lighting and General Purpose Outlets | Created |  |  |  | 0.5
T-00230-0062 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-09 - Lighting and Small Power Plant Infrastructure | CSEE - Lighting and General Purpose Outlets | Created |  |  |  | 0.5
T-00230-0063 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEF-02 - Turn Style & Site Access | CSEF - Permanent Buildings | Created |  |  |  | 0.5
T-00230-0065 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0S-01 - Structural Steel | CS0S - Structrual Steel | Created |  |  |  | 0.5
T-00230-0066 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0T-01 - H2S Analysers | CS0T - H2S Analysers | Created |  |  |  | 0.5
T-00230-0067 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-01 - RMU, Transformers and HV Feed | CSED - Switch Room & MCCs | Started |  |  |  | 0.5
T-00230-0068 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-03 - Battery Charger & UPS | CSED - Switch Room & MCCs | Created |  |  |  | 0.5
T-00230-0069 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-04 - MCC | CSED - Switch Room & MCCs | Created |  |  |  | 0.5
T-00230-0070 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-05 - Switch room Air-conditioning | CSED - Switch Room & MCCs | Created |  |  |  | 0.5
T-00230-0071 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSED-06 - Switch room General | CSED - Switch Room & MCCs | Created |  |  |  | 0.5
T-00230-0072 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-02 - Marshalling boxes Bulk Concentrate Handling | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0073 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-03 - Marshalling boxes Molybdenum Floatation | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0074 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-04 - Marshalling boxes Molybdenum Concentrate Handling | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0075 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-05 - Marshalling boxes Utilities | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0076 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0A-06 - Marshalling boxes Reagents | CS0A - Process Control - Network and DCS panels | Created |  |  |  | 0.5
T-00230-0077 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0U-01 - Density Instruments | CS0U - Density Instruments | Created |  |  |  | 0.5
T-00230-0078 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CSEE-10 - Lighting and Small Power Molybdenum Flotation 2 | CSEE - Lighting and General Purpose Outlets | Created |  |  |  | 0.5
T-00230-0079 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-02A - Instrument air header A | CS0B - Plant Air / Instrument Air | Closed | 2021-04-17T00:22:38.8930000 |  |  | 0.5 |  |  | 2021-04-16T22:17:25.9600000
T-00230-0080 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-01 - Air & Nitrogen Plant | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.5
T-00230-0081 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-03 - Flotation Instrument Air Header | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.5
T-00230-0082 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-19 - Plant Air to Maintenance Outlets | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.5
T-00230-0083 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-21 - Plant Air to Molybdenum Filter & Receiver | CS0B - Plant Air / Instrument Air | Created |  |  |  | 0.5
T-00230-0084 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-01 - Raw Water Feed | CS0C - Raw Water | Closed | 2021-04-17T00:23:17.5730000 |  |  | 0.5 |  |  | 2021-04-16T22:23:54.4770000
T-00230-0085 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-04 - Raw Water Pump & Header | CS0C - Raw Water | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:55:57.1070000
T-00230-0086 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-05 - Raw Water to Process Water Tank & Flocculant Area | CS0C - Raw Water | Completed |  |  |  | 0.5 |  |  | 2021-04-27T00:59:44.3230000
T-00230-0087 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-06 - Raw Water to NaHS Area | CS0C - Raw Water | Created |  |  |  | 0.5
T-00230-0088 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-10 - Raw Water to Reagents & Scrubber | CS0C - Raw Water | Created |  |  |  | 0.5
T-00230-0089 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-15 - Raw Water to Filter Building | CS0C - Raw Water | Created |  |  |  | 0.5
T-00230-0090 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-01 - Fire Water Ring Main & Distribution | CS0D - Fire Water | Started |  |  |  | 0.5
T-00230-0091 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0D-03 - Fire Water Skid | CS0D - Fire Water | Closed | 2021-04-20T01:29:13.8830000 |  |  | 0.5 |  |  | 2021-04-18T05:09:13.6500000
T-00230-0092 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-01 - Process Water Tank, Pumps and Header | CS0E - Process Water Distribution | Completed |  |  |  | 0.5 |  |  | 2021-04-27T01:01:01.6770000
T-00230-0094 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-03 - Process Water to Rougher Flotation Cells, First Cleaner & Rougher Conditioning Tanks | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0095 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-06 - Process Water to Intermediate & Molybdenum Thickener Area | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0096 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-05 - Process Water to Second Cleaner & Third/Forth Cleaner | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0097 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-10 - Process Water to Maintenance Outlets | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0098 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-11 - Anti-Scalant | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0099 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0E-12 - Containment Pond | CS0E - Process Water Distribution | Created |  |  |  | 0.5
T-00230-0101 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0I-01 - Potable Water Tank & Distribution | CS0I - Potable Water | Created |  |  |  | 0.5
T-00230-0102 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0L-01 - Eye Wash Stations & Safety Showers | CS0L - Emergency Showers / Eyewash & First Aid Stations | Created |  |  |  | 0.5
T-00230-0103 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS20-02 - Nitrogen Distribution Network | CS20 - Nitrogen Generation & Distribution | Created |  |  |  | 0.5
T-00230-0104 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS29-01 - Septic Tank | CS29 - Bio sewage Treatment | Created |  |  |  | 0.5
T-00230-0106 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0C-02 - Raw Water Tank | CS0C - Raw Water | Closed | 2021-04-20T01:29:40.9170000 |  |  | 0.5 |  |  | 2021-04-18T05:10:57.9730000
T-00230-0107 | I/O Subsystem Completion Stage 2 | INST |  |  | S2.1.2 - Complete Energization | S2.1 - Pre Commissioning | S2 - Stage 2 Pre Commissioning | CS0B-02B - Instrument air header B | CS0B - Plant Air / Instrument Air | Started |  |  |  | 0.5
T-00231-0001 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created
T-00231-0002 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created
T-00231-0003 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created
T-00231-0004 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created
T-00231-0005 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created
T-00231-0006 | Area Painting and Labelling Completion | PIPE |  |  | S1.1.1 - Installation | S1.1 - Construction | S1 - Stage 1 Construction Completion |  |  | Created